## Sheet1
Additional Data Point | Value | Year | Value Completed (Baseline) in M SAR | Value Completed (Actual) in M SAR | Value Completed (Forecast) in M SAR
Latest Approved Completion Date​ | Q2-28 | 2025 | 0
Forecast Completion Date​ | Q1-29 | 2026 | 1250 | 1250
Approved baseline completion date | Q3-27 | 2027 | 2000 | 1550 | 1550
No. of schedule iterations | 8 | 2028 | 3100 |  | 2200
Planned duration up to a specific phase as per approved Baseline programme | 120 | 2029 |  |  | 3100
Duration taken to complete works up to the specific phase | 145
Recovery Plan | Needs Improvement
Extent of all EOT (design stage) | 3
Extent of all EOT (const. stage) | 6
No. of unresolved issues | 7
No. of (Open) Inherent Risks | 15
No. of (Closed) Residual Risks | 35
Project-level risks (including low, medium, and high severity) | 65
Procedures for risk management | Satisfactory
Risks identified and corresponding impact on schedule | NIL
Extra Cost due to Unresolved Issues | 1700000