## Sheet1
DevCo | Additional Data Point | Value | Year | Value Completed (Baseline) in M SAR | Value Completed (Actual) in M SAR | Value Completed (Forecast) in M SAR | Risk Category | Number of Risk Items | Risk | Source | Potential Impact | Risk Rating | Risk Status | Current Measures | Assessment Criteria | Value | Rating | Additional Data Point | Value | Year | Budget Value (Baseline) in M SAR | Budget Value (Revised) in M SAR | Budget Value (Forecast) in M SAR | Assessment Criteria | Value | Rating | Data Point | Input Value | Number of Quality Audits | Month | Additional Data Point | Value | Baseline | Actual | Forecast | Incident Category | Number of Incidents (To-Date) | Number of Investigations in Progress | Number of Investigations Completed | Number of Investigations Pending Approval | Audits/Inspections | In Progress_audits | Completed_audits | Remaining Planned | Actions | In Progress_actions | Completed_actions | Pending Approval | Year | Value_training | Program | Pending (Ha) | Assessment Criteria | Value | Performance Signal | Performance Signal Score | Rating | Assessment Criteria | Data Point | Input Value | Additional Data Point | Value | Assessment Criteria | Value | Rating | Performance Signal Score | Performance Signal | Remarks 3 | Performance Signal Score | Value | Rating | Assessment Criteria | Input Value | Data Point | Weightage | Name of the KPI | Rating | Assessment Criteria | Value
diriyah | Latest Approved Completion Date​ | Q2-28 | 2025 | 0 |  |  | Risk 1 | 19 | Risk 1 | Contractor | Cost | High | Open | Measure 02 | DevCo Schedule Performance Index (SPI) | 0.9 | Satisfactory | Estimate to Completion Declared by DevCo | 3200000000 | 2023 | 400 | 400 | 400 | Budget Variance | 0.10714 | Satisfactory | PIF Approved Capex budget (Initial Business Plan) | 2800000000 | 2 | Jan | No. of Site Access Required | 180 | 186 | 129 | 50 | Fatalities | 0 | 0 | 0 | 0 | HSE Audit | 3 | 5 | 4 | HSE | 6 | 22 | 12 | Jan | 30 | Program 1 | 5 | % of CESMP mitigation measures which align with ESIA* | 0.5 | Construction Planning Maturity | 2.3 | Needs Improvement | % of CESMP mitigation measures which align with ESIA* | Environmental mitigation measures included in CESMP | 10 | Implementation Success Rate for Innovation Strategy | 50 | Is there an innovation Strategy or document that lists the key focus areas and initiatives across design, construction and operation and aligned with DevCo strategic plan? | 0.4 | Needs Improvement | 1.7 | Innovation & Technology Deployment | DevCo has maintained adherence to the Vision, with a few outstanding variance approvals pending. The DevCo has demonstrated poor consideration for construction methodology simplification during the design phase, however, is demonstrating effective use of BIM software for interdisciplinary coordination across most projects. | 2.4 | 0.4 | Needs Improvement | Similarity between Original/Approved and Latest CGI and Animation | 0.2 | Percentage similarity between Approved CGI and Latest CGI at same angle and scale | 20 | KPI 1 | Satisfactory | Availability of Technical Function Strategy | Yes, but very brief
diriyah | Forecast Completion Date​ | Q1-29 | 2026 | 1250 | 1250 |  | Risk 2 | 16 | Risk 2 | Source A | Impact O | Med | Ongoing | Measure 01 |  |  |  | Total Expenditure to Date | 100000000 | 2024 | 1000 | 1200 | 1200 |  |  |  | Forecast budget (EAC) | 3100000000 | 5 | Feb | No. of Site Access Provided | 120 | 16100 | 9600 | 6800 | Severe Impairment | 1 | 0 | 1 | 0 | Welfare Inspection | 2 | 4 | 4 | Welfare | 25 | 10 | 7 | Feb | 40 | Program 2 | 30 | [6 empty] | Environmental mitigation measures recommended in ESIA | 20 | Innovation Adoption Effectiveness Index (strategy & leadership alignment) | 1 | [10 empty] | 0.6 | Percentage similarity between Approved Animation and Latest Animation at same camera angle | 20 | KPI 2 | Good | Alignment of Technical Strategy with Organizational Strategy | Well-aligned
diriyah | Approved baseline completion date | Q3-27 | 2027 | 2000 | 1550 | 1550 | Risk 3 | 12 | Risk 3 | Source B | Impact P | High | Open | Measure 04 | % milestone achievement in accordance with the approved business plan | 0.7 | Satisfactory | Contingency budgeted at DevCo level | 20000000 | 2025 | 1500 | 1800 | 1800 | % of projects having Budget Variance | 0.75 | Needs Improvement | Number of Projects with Budget Variance | 15 | 3 | Mar | Packaging & Phasing Strategy | Good |  |  |  | Lost Time Incidents | 3 | 0 | 1 | 2 | [8 empty] | Mar | 38 | Program 3 | 10 | Has the Construction Execution Plan been updated to reflect the latest stage of construction? | Yes |  |  | Good | Has the Construction Execution Plan been updated to reflect the latest stage of construction? | Update of construction execution plan | Yes | Innovation Adoption Effectiveness Index (skilled human resources) | 3 | [7 empty] | Yes | Good | Does the Latest Material Palette & Finish Schedule support the look of the Approved CGI? | Yes | Material Palette & Finish Schedule | 15 | KPI 3 | Satisfactory | Severity of Key Challenges Faced in Strategy Execution Technically | Moderate
diriyah | No. of schedule iterations | 8 | 2028 | 3100 |  | 2200 | Risk 4 | 7 | Risk 4 | Source F | Impact T | Med | Closed | Measure 05 |  |  |  | Contingency utilized at DevCo level | 7500000 | 2026 | 2000 | 2200 | 2300 |  |  |  | Total number of projects | 20 | 1 | Apr | Execution & Site Logistics | Satisfactory |  |  |  | Recordable Incidents | 14 | 3 | 11 | 0 | [8 empty] | Apr | 35 |  |  | Has the construction sequence and method statement been reviewed and approved? | No |  |  | Needs Improvement | Has the construction sequence and method statement been reviewed and approved? | Review and approval of Construction sequence & method statement | No | Innovation Adoption Effectiveness Index (planning & governance) | 2 | [7 empty] | Yes | Good | Does the DevCo have Design & Technical Guidelines (including Look & Feel Design Guidelines)? | Yes | Design and Technical Guidelines | 10 | KPI 4 | Satisfactory | Availability of Technical KPIs | Yes, but very brief
diriyah | Planned duration up to a specific phase as per approved Baseline programme | 120 | 2029 |  |  | 3100 | Risk 5 | 5 | Risk 5 | PMC | Reputation | Low | Ongoing | Measure 06 | % of projects with approved change requests in design phase since inception with time impact of more than 1 month | 0.22222 | Good | Contingency Utilization Rate |  | 2027 | 2500 | 2750 | 2900 | % of projects with contingency utilization rate > 1 | 0.25 | Satisfactory | Number of projects with contingency utilization > 1 | 5 | 0 | May | Procurement Strategy | Good |  |  |  | Near Misses | 26 | 2 | 21 | 3 | [8 empty] | May | 0 |  |  | Is total land acquisition sufficient to achieve the area required for construction site logistics? | No |  |  | Needs Improvement | Is total land acquisition sufficient to achieve the area required for construction site logistics? | Planned Area provision for site offices, amenities, laydown areas, storage facilities, workforce accommodations | Average | Innovation Adoption Effectiveness Index (process management) | 4 | [7 empty] | No | Good | Do DevCo projects comply with DDTG? | No | Look & Feel Guideline | 10 | KPI 5 | Good | Progress of Achievement of KPIs for Technical Team | 0.8
diriyah | Duration taken to complete works up to the specific phase | 145 | [6 empty] | Risk 6 | Source C | Impact Q | Med | Open | Measure 07 |  |  |  | Value of Changes in Design Stage | 200000 | 2028 | 2800 | 3100 | 3200 | % of projects with Approved Change Requests (design/construction) having a cost impact greater than 2% | 0.6 | Needs Improvement | No. of projects with approved change request having a cost impact greater than 2% | 12 | 0 | Jun | Required area for land acquisition | [17 empty] | Jun | 0 | [8 empty] | Actual Area provision for site offices, amenities, laydown areas, storage facilities, workforce accommodations | No | Innovation Adoption Effectiveness Index (partnerships and collaboration) | 2 | [6 empty] | 3 | 0.14286 | Good | % variance from approved Built-Up Area (BUA) | 16 | Latest BUA | 25 | Others
diriyah | Recovery Plan | Needs Improvement | [6 empty] | Risk 7 | Source D | Impact R | Low | Closed | Measure 08 | % of projects with approved change requests in construction phase since inception with time impact of more than 4 months | 0.54545 | Satisfactory | Value of Changes in Construction Stage | 5000000 |  |  |  |  | % of projects with Approved Claims | 0.5 | Needs Improvement | No. of projects with approved claims | 10 | 0 | Jul | Mitigation of Project Execution Plan implementation challenges | [17 empty] | Jul | 0 |  |  | Have Traffic Simulations been completed in preparing the Site & Logistics Plan? | Yes |  |  | Good | Have Traffic Simulations been completed in preparing the Site & Logistics Plan? | Completion of Traffic Simulations | Yes | Innovation Adoption Effectiveness Index (resource management) | 0.6 | [10 empty] | 14 | Approved BUA |  |  | Good | Appropriateness of KPIs for Technical Team | Aligned with industry benchmarks
diriyah | Extent of all EOT (design stage) | 3 | [6 empty] | Risk 8 | Supplier | Time | High | Closed | Measure 09 |  |  |  | Number of Changes (Concept MP) | 0 |  |  |  |  | % of provisional sums of the latest PIF Approved Capex budget | 0.00068966 | Good | Total provisional sums | 2000000 | 0 | Aug | Occurred delays due to stakeholder objections | [17 empty] | Aug | 0 |  |  | Has the Project Execution Plan been updated and approved in the last 12 months? | Yes |  |  | Good | Has the Project Execution Plan been updated and approved in the last 12 months? | Date of latest approved Procurement Plan | 2025-03-25 | Implementation Success Rate for Smart City Strategy | 70 | [7 empty] | 0.041667 | Good | % variance in land use permit area | 2.5 | Latest Land Area |  |  | Good | Criticality of Vacant/Missing Positions in Organization | Minor
diriyah | Extent of all EOT (const. stage) | 6 | [6 empty] | Risk 9 | CAA | Impact M | High | Closed | Measure 10 | % of projects with approved schedule extension | 0.65 | Needs Improvement | Number of Changes (Detailed MP) | 3 | [7 empty] | Latest Approved budget | 2900000000 | 0 | Sep | Workforce Planning and Availability | Needs Improvement | [16 empty] | Sep | 0 |  |  | % of Stakeholder MOU** / LUPs*** not executed in accordance with critical lead time | 0.05 |  |  | Good | % of Stakeholder MOU** / LUPs*** not executed in accordance with critical lead time | Number of Stakeholder MOU or Land Use Permits not executed on time | 5 | Number of Smart City Use Cases | 10 | Is there a smart city Strategy or document that lists the key focus areas of smart city aligned with DevCo strategic plan? | 0.4 | Needs Improvement | [7 empty] | 2.4 | Approved Land Area |  |  | Good | Appropriateness of Qualifications in Recruitment of Vacant Technical Department Head Positions | Minor
diriyah | No. of unresolved issues | 7 | [6 empty] | Risk 10 | Source E | Impact S | Med | Ongoing | Measure 11 |  |  |  | Number of Changes (Concept Design) | 2 |  |  |  |  | % of variance of Allocated Provisional sums against the awarded amount | 2.5 | Needs Improvement | Actual Utilized Provisional Sums | 800000 | 0 | Oct | Resource Planning and Availability | Good | [16 empty] | Oct | 0 | [8 empty] | Total Stakeholder MOU or Land Use Permits required | 100 | Smart City Adoption Effectiveness Index (strategy & leadership alignment) | 2 | [7 empty] | 0.052632 | Good | % variance from approved population | 1000 | Latest Population |  |  | Good | Robustness of Policy/Guideline/Procedure Communication | Strong
diriyah | No. of (Open) Inherent Risks | 15 | [15 empty] | Number of Changes (Detailed Design) | 6 | [9 empty] | 0 | Nov | Workforce retention track record | [17 empty] | Nov | 0 |  |  | % of Workforce Hired against Workforce Estimates | 1.1 | Workforce Resource Availability | 3 | Good | % of Workforce Hired against Workforce Estimates | Forecast workforce requirements | 10000 | Smart City Adoption Effectiveness Index (infrastructure readiness) | 2 | [10 empty] | 950 | Approved Population |  |  | Satisfactory | Robustness of Policy/Guideline/Procedure Compliance Monitoring Framework | Moderate
diriyah | No. of (Closed) Residual Risks | 35 | [12 empty] | % of projects with Forecast completion date beyond the latest approved schedule | 0.23077 | Satisfactory | Number of Changes (Construction) | 8 | [9 empty] | 0 | Dec | Turnover rate track record | [17 empty] | Dec | 0 | [8 empty] | Actual workforce employed | 11000 | Smart City Adoption Effectiveness Index (planning & governance) | 3 | [6 empty] | 2.8 | 0.33333 | Satisfactory | % value of modularization compared to the total construction value | 0.01 | Value of Modularized Construction Cost |  |  | Satisfactory | Robustness of Board Reporting Framework | Moderate
diriyah | Project-level risks (including low, medium, and high severity) | 65 | [12 empty] | Is the Forecast Finish Date at a given data date based on the alignment and buy-in from project teams and other listed stakeholders? | Yes | Good | Total Awarded Cost | 15000000 | [11 empty] | Plant/equipment downtime track record | [21 empty] | % of Labor Camp Capacity against Workforce Estimates | 1 |  |  | Good | % of Labor Camp Capacity against Workforce Estimates | Forecast number of labor camps | 6 | Smart City Adoption Effectiveness Index (stakeholder alignment) | 1 | [10 empty] | 0.03 | Value of Total Construction Cost
diriyah | Procedures for risk management | Satisfactory | [12 empty] | Based on the risks identified and approved change requests, has the DevCo conducted a sensitivity assessment on the forecast completion at a given data date? | Yes, but inadequate | Satisfactory | Approved Variations and Claims | 5200000 | [11 empty] | Number of technical queries raised | [27 empty] | Actual number of labor camps | 6 | Smart City Adoption Effectiveness Index (realized benefits & performance) | 0.5 | [7 empty] | Yes | Good | Have all projects completed a Constructability Report/Document? | Yes | Date and Revision of Constructability Report
diriyah | Risks identified and corresponding impact on schedule | NIL | [12 empty] | Has DevCo allocated risk contingency for the identified risks? | Yes | Good | Uncommitted Cost | 300000000 | [11 empty] | Number of technical queries closed | [21 empty] | % of Material Supply Capacity against Material Demand Estimates | 1.3333 |  |  | Good | % of Material Supply Capacity against Material Demand Estimates | Forecast number of batching / crushing plants/ precast yards, etc. | 3 | [9 empty] | Yes | Good | Was design for Enabling Work Package considerd as part of the design process to ensure the readiness of the site for the main construction work? | Yes | Assessment of enabling works required
diriyah | Extra Cost due to Unresolved Issues | 1700000 | [12 empty] | Was there any deferment in the project completion date due to unidentified risks? | Yes, but less than 1 month | Satisfactory | Pending Variations | 0 | [11 empty] | Average time to complete shop drawing reviews | 480 | [26 empty] | Actual number of batching / crushing plants/ precast yards, etc. | 4 | [9 empty] | Yes | Good | Are documentation packages meeting the LOD requirements of the latest Design Stage Gate? | Yes | LOD Required
diriyah | [14 empty] | Was there any Cost Overrun because of identified risk? | No | Good | Anticipated Variations | 1 | [11 empty] | Number of shop drawing review conducted | [21 empty] | Did DevCo adhere to Technical Submittals Review Cycle Time (RCT)? | Yes | Adherence to Design | 3 | Good | Did DevCo adhere to Technical Submittals Review Cycle Time (RCT)? | Time taken for closure of technical queries | Yes |  |  | Is there an impact assessment report or identified process/ guidelines to evaluate the impact of the innovation / smart city technologies adoption on DevCo performance? | 0.6 | Satisfactory | [7 empty] | Yes | LOD Documented (drawing sample from Design Report)
diriyah | [14 empty] | Was there any Cost Overrun because of unidentified risk? | Yes, but less than 1% | Satisfactory | [13 empty] | Number of material / product substitution requests | [27 empty] | Technical Submittal Review Cycle Time (RCT) | Yes | [9 empty] | Yes | Good | Have all projects adopted digital delivery using BIM and/or GIS? | Yes | % of projects adopting digital delivery using BIM/GIS
diriyah | [14 empty] | Risk Control Rate of the identified risks at DevCo Level | 0.8125 | Good | [13 empty] | Average time to approve product sample & materials | [21 empty] | % of approved shop drawing reviews vs planned | 0.94648 |  |  | Good | % of approved shop drawing reviews vs planned | Total number of shop drawing review requests | 14760 | [8 empty] | 2.6 | Yes | Good | Is project delivery occurring in accordance with the latest approved design strategy? | Yes | Date of Latest Approved Design Strategy
diriyah | [30 empty] | Product & Material Approval Rate | [27 empty] | Total number of shop drawing reviews approved | 13970 | [9 empty] | 0.1 | Needs Improvement | % of projects with completed technical design/peer reviews and verifications/certifications as required for the latest Design Stage Gate | 0.1 | Number of projects with completed design reviews and verification register
diriyah | [14 empty] | Is the DevCo fully compliant with Risk Management Plan requirements? | No | Needs Improvement | [13 empty] | Number of as-built drawing review conducted | 485 | [20 empty] | % of approved product waivers vs product specified | 0.986 |  |  | Good | % of approved product waivers vs product specified | Total number of product sample & material approvals requested | 1000 |  |  | Is there evidence for innovation / smart city technologies successful implementation (in final design report, master plan or other)? | Yes | Good |  |  |  |  | 0.85 | Good | % of Corrective Actions closed | 40 | Total Corrective Actions
diriyah | [14 empty] | Is there a difference in the time impact forecast before and after the risk event has triggered? | Yes, but less than 2 weeks | Satisfactory | [13 empty] | Average time to approve As-built rejections / iterations | [27 empty] | Total number of product sample & materials approved | 986 | [12 empty] | 34 | Number of Closed Corrective Actions
diriyah | [14 empty] | Is there a difference in the Cost impact forecast before and after the risk event has triggered? | Yes, but less than 0.5% | Satisfactory | [13 empty] | As-Built Drawing Approval Rate | [21 empty] | % of Certified As-Built Drawing Packages vs Planned | 0.95 |  |  | Good | % of Certified As-Built Drawing Packages vs Planned | Number of As-Built review requests | 500 |  |  | Are there Pilot or R&D projects conducted? | 0.55 | Needs Improvement | 1 | Pilot and R&D Transition Rate |  |  | 14 | Satisfactory | Average Cycle time to close corrective actions | 14 | Days taken to Close Corrective Actions
diriyah | [30 empty] | Average time to complete MIRs and close out approvals | [27 empty] | Number of As-built reviews / approvals | 475 | [9 empty] | Yes | Good | Is the average cycle time to complete reviews and certifications in accordance with the Design Management Report? | Yes | Days taken to complete Design Reviews
diriyah | [30 empty] | Average time to complete WIRs and close out approvals | [21 empty] | MIR Inspection Rate | 0.98333 |  |  | Good | MIR Inspection Rate | Total number of MIRs requested | 120 | [9 empty] | Yes | Good | Has the DevCo engaged independent certification of major critical elements? | Yes | Level of review and verification required for Stage Gate
diriyah | [30 empty] | Number of NCRs open for between 30 and 60 days | 23 | [26 empty] | Total number of MIRs inspected | 118 | [8 empty] | 2 | No | Needs Improvement | Are all project designs integrated with Regional Infrastructure & Mobility Plans? | No | Regional Strategies
diriyah | [30 empty] | Number of NCRs open for more than 60 days | 5 | [20 empty] | MIR Acceptance and Approval Rate | 0.91667 |  |  | Good | MIR Acceptance and Approval Rate | Total number of MIRs approved / rejected | 110 |  |  | % of pilot / R&D Projects Transitioned into Full-Scale | 0.13043 | Needs Improvement |  |  |  |  | Yes | Good | Do all projects comply with environmental guidelines in accordance with ESIA? | Yes | Extent of compliance to environmental guidelines
diriyah | [30 empty] | Leadership engagement | [21 empty] | WIR Inspection Rate | 0.97143 |  |  | Good | WIR Inspection Rate | Total number of WIRs requested | 350 | [8 empty] | 2.2 | 0.15 | Satisfactory | % of projects with Code Compliance Violations | 0.15 | Total Number of Code Compliance Violations
diriyah | [30 empty] | Leadership engagement | Satisfactory | [26 empty] | Total number of WIRs inspected | 340 | [9 empty] | 1.0476 | Good | % of approved deviation waivers against compliant codes & standards | 21 | Total Waiver Applications Submitted
diriyah | [30 empty] | Total number of ITPs requested | 100 | [20 empty] | WIR Acceptance and Approval Rate | 0.95714 |  |  | Good | WIR Acceptance and Approval Rate | Total number of WIRs approved / rejected | 335 | [12 empty] | 22 | Total Waivers Approved
diriyah | [30 empty] | Total number of ITPs attended | 98 | [20 empty] | Does the frequency of Audits align with the QMP? | Yes | Quality Assurance / Quality Control (QA/QC) | 2.6 | Good | Does the frequency of Audits align with the QMP? | Required Audit frequency | Yes |  |  | Availability of Innovation unit / department with structured team | 0 | Needs Improvement | 1.5 | Organization Maturity Towards Innovation Adoption |  |  | Yes | Good | Have all required Stakeholder Submittals been issued? | Yes | Stakeholder Submittal Date
diriyah | [30 empty] | Total number of ITPs approved | 87 | [20 empty] | % closure of Non-Conformance Reports (NCR) | 0.96667 |  |  | Good | % closure of Non-Conformance Reports (NCR) | Total number of defects & NCRs | 150 | [9 empty] | 0.31746 | Needs Improvement | % of time critical Stakeholder Approvals Pending impacting Design Stage Gate completion | 0.2 | Number of Stakeholder Approvals Pending
diriyah | [30 empty] | Total number of ITPs completed | 85 | [26 empty] | Total number of closed defects & NCRs | 145 | [12 empty] | 0.63 | Total number of stakeholder approvals required
diriyah | [30 empty] | Total number Quality Reports completed | [21 empty] | Average NCRs closeout Cycle Time | 23 |  |  | Needs Improvement | Average NCRs closeout Cycle Time | Average time to close NCRs | 23 | [9 empty] | Yes | Good | Does the Stakeholder Engagement Plan include proactive communication process to ensure timley coordination and approvals? | Yes | Scheduled Design Stage Gate Completion
diriyah | [30 empty] | Completeness of Quality Management Plan | Needs Improvement | [20 empty] | % of procurement packages delivered within the planned lead times defined in the PMP | 0.86 | Procurement & Contracting Compliance | 2.8 | Good | % of procurement packages delivered within the planned lead times defined in the PMP | Planned Procurement Package Lead Time | 100 |  |  | Availability of Innovation and Technology Strategy / Process & Framework | 0.5 | Satisfactory |  |  |  |  | 0.19048 | Needs Improvement | % of Stakeholder Comments Closed | 21 | Total Stakeholder Comments
diriyah | [30 empty] | Required number of ITPs signed off throughout construction | [27 empty] | Actual Procurement Package Delivery Time | 86 | [12 empty] | 4 | Stakeholder Comments Closed
diriyah | [30 empty] | Total number of raised closed-out defects & NCRs | [21 empty] | % of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures | 0.875 |  |  | Good | % of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures | Total number of claims and variations | 800 | [8 empty] | 1 | 0 | Needs Improvement | % of projects achieving DevCo ESG Targets | 1 | Planned ESG Target
diriyah | [30 empty] | Forecasted Procurement Budget | [27 empty] | Total number of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures | 700 | [12 empty] | 0 | Actual ESG Target
diriyah | [30 empty] | Actual Procurement Budget | [21 empty] | % of packages procured with 100% complete, compliant and well-structured documentation | 0.6 |  |  | Satisfactory | % of packages procured with 100% complete, compliant and well-structured documentation | Total number of packages | 0.5 | [8 empty] | 1 | No | Needs Improvement | Does the DevCo ESG Target align with globally recognized Best Practice Targets? | No | Alignment with globally recognized Best Practice Targets
diriyah | [30 empty] | Vendor Database | [27 empty] | Total number of packages procured with 100% complete, compliant and well-structured documentation | 0.3
diriyah | [30 empty] | Vendor Shortlist | [21 empty] | % of awarded contracts where vendors appointed passed full due diligence checks | 1.2857 |  |  | Good | % of awarded contracts where vendors appointed passed full due diligence checks | No. of awarded contracts where vendors appointed passed full due-diligence checks | 0.9
diriyah | [30 empty] | Vendor Awarded | [27 empty] | Total number of awarded contracts | 0.7
diriyah | [30 empty] | Vendor KPIs | [21 empty] | Did the DevCo complete a Supply Chain Risk-Market Intelligence Assessment in the last quarter? | Yes |  |  | Good | Did the DevCo complete a Supply Chain Risk-Market Intelligence Assessment in the last quarter? | Supply Chain Risk-Market Intelligence Assessment | Yes
diriyah | [30 empty] | Vendor Performance Database | [21 empty] | % of procurement activities executed as planned in the Annual Procurement Plan | 0.69355 | Procurement & Contracting Execution Performance | 1.8 | Needs Improvement | % of procurement activities executed as planned in the Annual Procurement Plan | Total number of procurement activities | 186
diriyah | [30 empty] | Tender return date: Planned / Actual | [27 empty] | Number of procurement activities executed as planned | 129
diriyah | [30 empty] | Tender Review & award time: Planned / actual | [21 empty] | % of deviations in total awarded contract value with tender cost estimates | 0.091166 |  |  | Good | % of deviations in total awarded contract value with tender cost estimates | Value of Awarded Contract | 35.32
diriyah | [30 empty] | Pre-Tender Cost Estimate | [27 empty] | Tender Cost Estimate | 32.1
diriyah | [30 empty] | Tender Performance Index | [21 empty] | % of contracts with filed claims | 10 |  |  | Needs Improvement | % of contracts with filed claims | Number of contracts with filed claims | 10
diriyah | [30 empty] | Contract clauses | Satisfactory | [20 empty] | Are Payment Certificates and payments being processed in accordance with the Contract terms and conditions? | Yes |  |  | Good | Are Payment Certificates and payments being processed in accordance with the Contract terms and conditions? | Processing of payment certificates and payments | Yes
diriyah | [30 empty] | Procurement Management Plan | Good | [20 empty] | Are Vendor performance assessment occurring which capture financial instability, delays, repeated quality issues in real-time? | No |  |  | Needs Improvement | Are Vendor performance assessment occurring which capture financial instability, delays, repeated quality issues in real-time? | Alignment of sourcing strategies with project schedules and requirements | No
diriyah | [30 empty] | Scope / design maturity | Satisfactory | [20 empty] | Does the HSE Management Manual have adequate provision for identification and escalation of high risk activities? | Yes | HSE Compliance | 2.47 | Good | Does the HSE Management Manual have adequate provision for identification and escalation of high risk activities? | Escalation criteria for high risk activities | Yes
diriyah | [30 empty] | Compliance with local content regulations / policies | [21 empty] | Is the rate of review of the Safety Risk Register in accordance with the HSE Management Manual? | Yes |  |  | Good | Is the rate of review of the Safety Risk Register in accordance with the HSE Management Manual? | HSE Risk Register Review Rate | Yes
diriyah | [30 empty] | Dispute rate | [21 empty] | % of closed Safety Risk items | 0.83333 |  |  | Good | % of closed Safety Risk items | Total number of Safety Risk items | 0.9
diriyah | [30 empty] | Claims processing cycle time | [27 empty] | Total number of closed Safety Risk items | 0.75
diriyah | [30 empty] | No. of related CRs being requested during or after tendering phase due to identified scope gap | [21 empty] | Average cycle time to close Safety Risk items | 14 Days |  |  | Needs Improvement | Average cycle time to close Safety Risk items | Cycle time to close Safety Risk items | 14 Days
diriyah | [30 empty] | Vendor Performance Assessment | Good | [20 empty] | Average cycle time to close Safety Incident | 0.65 |  |  | Good | Average cycle time to close Safety Incident | Cycle time to close Safety Incident | 20
diriyah | [30 empty] | Tender pack quality | Satisfactory | [26 empty] | Total number of closed safety incidents | 13
diriyah | [30 empty] | % payment paid within contractual terms | 80 | [20 empty] | Is the emergency drill rate compliant with EEPP? | No |  |  | Needs Improvement | Is the emergency drill rate compliant with EEPP? | Planned number of Emergency Drills | 35
diriyah | [30 empty] | Planned Packages | [27 empty] | Actual number of Emergency Drills | 20
diriyah | [30 empty] | Awarded Packages | [27 empty] | Recommended time to complete Emergency drills | 5 Days
diriyah | [30 empty] | Trade Most at Risk | [27 empty] | Actual Time to complete Emergency drills | 10 Days
diriyah | [30 empty] | Highest Risk Work Site | [21 empty] | Fatality Rate (FR) | 0 |  |  | Good | Fatality Rate (FR) | No. of incidents resulting in fatality or severe impairment per 200,000 work hours | 0
diriyah | [30 empty] | Number of planned audits | [21 empty] | Lost Time Injury Frequency Rate (LTIFR) | 0 |  |  | Good | Lost Time Injury Frequency Rate (LTIFR) | No. of incidents resulting in lost time per 200,000 work hours | 0
diriyah | [30 empty] | Number of conducted audits | [21 empty] | Total Recordable Incident Rate (TRIR) | 0 |  |  | Good | Total Recordable Incident Rate (TRIR) | No. of recordable incidents per 200,000 work hours | 0
diriyah | [30 empty] | Number of Notifiable Incidents | 6 | [20 empty] | Near Miss Rate | 3 |  |  | Satisfactory | Near Miss Rate | No. of near misses recorded per 200,000 work hours | 3
diriyah | [30 empty] | Number of Infringement Notices | 2 | [20 empty] | Safety Observation Rate | 8 |  |  | Needs Improvement | Safety Observation Rate | No. of safety observation recorded per 200,000 work hours | 8
diriyah | [30 empty] | Total Safe Manhours | [21 empty] | Leadership Safety Walk Rate | 0.73 |  |  | Good | Leadership Safety Walk Rate | Total number of Safety Walks | 300
diriyah | [30 empty] | Total number of closed Corrective actions | [27 empty] | Total number of Safety Walks with Leadership | 219
diriyah | [30 empty] | Inspection Pass Rate | [21 empty] | % of Grievances Closed | 1 | Welfare Compliance | 2.4 | Good | % of Grievances Closed | Number of grievances closed | 5
diriyah | [30 empty] | No. of recurring incidents / safety observations outside control | [27 empty] | Total number of grievances | 5
diriyah | [30 empty] | Total Site Manhours | 180000000 | [20 empty] | Average Cycle Time to Close Grievances | Good |  |  | Needs Improvement | Average Cycle Time to Close Grievances | Cycle time to close grievances | Good
diriyah | [30 empty] | Welfare of labor camps | [21 empty] | % of Welfare Staff vs Total workforce | Good |  |  | Good | % of Welfare Staff vs Total workforce | Percentage of Welfare Staff against total staff | Good
diriyah | [30 empty] | Welfare of site facilities | [21 empty] | % closed welfare observations or red flag if 0 observations | 0.75 |  |  | Good | % closed welfare observations or red flag if 0 observations | Total number of Welfare Observations | 20
diriyah | [30 empty] | Labor accommodation inspection rate | [27 empty] | Total number of Closed Welfare Observations | 15
diriyah | [30 empty] | Regulation Compliance | [21 empty] | % of Welfare Non-compliances closed | 0.58 |  |  | Needs Improvement | % of Welfare Non-compliances closed | Total Welfare Non-compliances | 100
diriyah | [58 empty] | Total Closed Welfare Non-compliances | 58
diriyah | [52 empty] | Average Cycle Time to Close Welfare Non-compliances | 10 Days |  |  | Needs Improvement | Average Cycle Time to Close Welfare Non-compliances | Cycle time to close Welfare Non-Compliances | 10 Days
diriyah | [52 empty] | Is frequency of Labor Accommodation Inspection occurring in accordance with VMMP? | Yes |  |  | Good | Is frequency of Labor Accommodation Inspection occurring in accordance with VMMP? | Mitigation measures in the event of welfare audit observations & recommendations | Yes
qiddiya | Latest Approved Completion Date​ | Q1-29 | 2025 | 0 |  |  |  |  | Risk 1 | Contractor | Cost | Low | Open | Measure 02 | DevCo Schedule Performance Index (SPI) | 0.96 | Satisfactory | Estimate to Completion Declared by DevCo | 519000000 | 2023 | 400 | 420 | 400 | Budget Variance | -0.11111 | Good | PIF Approved Capex budget (Initial Business Plan) | 450000000 | 2 | Jan | No. of Site Access Required | 180 | 186 | 129 | 50 | Fatalities | 0 | 0 | 0 | 0 | HSE Audit | 3 | 5 | 4 | HSE | 6 | 22 | 12 | Jan | 30 | Program 1 | 20 | % of CESMP mitigation measures which align with ESIA* | 0.5 | Construction Planning Maturity | 2.1 | Needs Improvement | % of CESMP mitigation measures which align with ESIA* | Environmental mitigation measures included in CESMP | 0.1 | Implementation Success Rate for Innovation Strategy | 3 | Is there an innovation Strategy or document that lists the key focus areas and initiatives across design, construction and operation and aligned with DevCo strategic plan? | 0.4 | Needs Improvement | 1.7 | Innovation & Technology Deployment | DevCo has maintained adherence to the Vision, with a few outstanding variance approvals pending. The DevCo has demonstrated poor consideration for construction methodology simplification during the design phase, however, is demonstrating effective use of BIM software for interdisciplinary coordination across most projects. | 2.4 | 0.4 | Needs Improvement | Similarity between Original/Approved and Latest CGI and Animation | 0.2 | Percentage similarity between Approved CGI and Latest CGI at same angle and scale | 20 | KPI 1 | Satisfactory | Availability of Technical Function Strategy | Yes, but very brief
qiddiya | Forecast Completion Date​ | Q3-29 | 2026 | 1350 | 1350 |  |  |  | Risk 2 | Source A | Impact O | Med | Ongoing | Measure 01 |  |  |  | Total Expenditure to Date | 100000000 | 2024 | 420 | 440 | 420 |  |  |  | Forecast budget (EAC) | 500000000 | 5 | Feb | No. of Site Access Provided | 120 | 16100 | 9600 | 6800 | Severe Impairment | 1 | 0 | 1 | 0 | Welfare Inspection | 2 | 4 | 4 | Welfare | 25 | 10 | 7 | Feb | 40 | Program 2 | 90 | [6 empty] | Environmental mitigation measures recommended in ESIA | 0.2 | Innovation Adoption Effectiveness Index (strategy & leadership alignment) | 1 | [10 empty] | 0.6 | Percentage similarity between Approved Animation and Latest Animation at same camera angle | 20 | KPI 2 | Good | Alignment of Technical Strategy with Organizational Strategy | Well-aligned
qiddiya | Approved baseline completion date | Q2-27 | 2027 | 3200 | 1600 | 1600 | Risk 1 | 20 | Risk 3 | Source B | Impact P | High | Open | Measure 04 | % milestone achievement in accordance with the approved business plan | 0.9 | Good | Contingency budgeted at DevCo level | 2000000 | 2025 | 440 | 460 | 455 | % of projects having Budget Variance | 1 | Needs Improvement | Number of Projects with Budget Variance | 15 | 3 | Mar | Packaging & Phasing Strategy | Good |  |  |  | Lost Time Incidents | 3 | 0 | 1 | 2 | [8 empty] | Mar | 38 | Program 3 | 40 | Has the Construction Execution Plan been updated to reflect the latest stage of construction? | Yes |  |  | Good | Has the Construction Execution Plan been updated to reflect the latest stage of construction? | Update of construction execution plan | Yes | Innovation Adoption Effectiveness Index (skilled human resources) | 3 | [7 empty] | Yes | Good | Does the Latest Material Palette & Finish Schedule support the look of the Approved CGI? | Yes | Material Palette & Finish Schedule | 15 | KPI 3 | Satisfactory | Severity of Key Challenges Faced in Strategy Execution Technically | Moderate
qiddiya | No. of schedule iterations | 8 | 2028 | 4000 |  | 2300 | Risk 2 | 18 | Risk 4 | Source F | Impact T | High | Closed | Measure 05 |  |  |  | Contingency utilized at DevCo level | 2500000 | 2026 | 460 | 480 | 500 |  |  |  | Total number of projects | 15 | 1 | Apr | Execution & Site Logistics | Satisfactory |  |  |  | Recordable Incidents | 14 | 3 | 11 | 0 | [8 empty] | Apr | 35 |  |  | Has the construction sequence and method statement been reviewed and approved? | No |  |  | Needs Improvement | Has the construction sequence and method statement been reviewed and approved? | Review and approval of Construction sequence & method statement | No | Innovation Adoption Effectiveness Index (planning & governance) | 2 | [7 empty] | Yes | Good | Does the DevCo have Design & Technical Guidelines (including Look & Feel Design Guidelines)? | Yes | Design and Technical Guidelines | 10 | KPI 4 | Satisfactory | Availability of Technical KPIs | Yes, but very brief
qiddiya | Planned duration up to a specific phase as per approved Baseline programme | 145 | 2029 |  |  | 4000 | Risk 3 | 15 | Risk 5 | PMC | Reputation | Low | Ongoing | Measure 06 | % of projects with approved change requests in design phase since inception with time impact of more than 1 month | 0.16667 | Good | Contingency Utilization Rate | 200000 | 2027 | 480 | 500 | 520 | % of projects with contingency utilization rate > 1 | 0.8 | Needs Improvement | Number of projects with contingency utilization > 1 | 12 | 0 | May | Procurement Strategy | Good |  |  |  | Nears Misses | 26 | 2 | 21 | 3 | [8 empty] | May | 0 |  |  | Is total land acquisition sufficient to achieve the area required for construction site logistics? | No |  |  | Needs Improvement | Is total land acquisition sufficient to achieve the area required for construction site logistics? | Planned Area provision for site offices, amenities, laydown areas, storage facilities, workforce accommodations | Average | Innovation Adoption Effectiveness Index (process management) | 4 | [7 empty] | No | Good | Do DevCo projects comply with DDTG? | No | Look & Feel Guideline | 10 | KPI 5 | Good | Progress of Achievement of KPIs for Technical Team | 0.8
qiddiya | Duration taken to complete works up to the specific phase | 160 |  |  |  |  | Risk 4 | 4 | Risk 6 | Source C | Impact Q | Med | Open | Measure 07 |  |  |  | Value of Changes in Design Stage | 6000000 | 2028 | 500 | 520 | 535 | % of projects with Approved Change Requests (design/construction) having a cost impact greater than 2% | 0.8 | Needs Improvement | No. of projects with approved change request having a cost impact greater than 2% | 12 | 0 | Jun | Required area for land acquisition | [17 empty] | Jun | 0 | [8 empty] | Actual Area provision for site offices, amenities, laydown areas, storage facilities, workforce accommodations | No | Innovation Adoption Effectiveness Index (partnerships and collaboration) | 2 | [6 empty] | 3 | 0.14286 | Good | % variance from approved Built-Up Area (BUA) | 16 | Latest BUA | 25 | Others
qiddiya | Recovery Plan | Satisfactory |  |  |  |  | Risk 5 | 7 | Risk 7 | Source D | Impact R | Low | Closed | Measure 08 | % of projects with approved change requests in construction phase since inception with time impact of more than 4 months | 0.33333 | Satisfactory | Value of Changes in Construction Stage | 3000000 |  |  |  |  | % of projects with Approved Claims | 0.66667 | Needs Improvement | No. of projects with approved claims | 10 | 0 | Jul | Mitigation of Project Execution Plan implementation challenges | [17 empty] | Jul | 0 |  |  | Have Traffic Simulations been completed in preparing the Site & Logistics Plan? | Yes |  |  | Good | Have Traffic Simulations been completed in preparing the Site & Logistics Plan? | Completion of Traffic Simulations | Yes | Innovation Adoption Effectiveness Index (resource management) | 0.6 | [10 empty] | 14 | Approved BUA |  |  | Good | Appropriateness of KPIs for Technical Team | Aligned with industry benchmarks
qiddiya | Extent of all EOT (design stage) | 4 | [6 empty] | Risk 8 | Supplier | Time | High | Closed | Measure 09 |  |  |  | Number of Changes (Concept MP) | 0 |  |  |  |  | % of provisional sums of the latest PIF Approved Capex budget | 0.0032787 | Good | Total provisional sums | 2000000 | 0 | Aug | Occurred delays due to stakeholder objections | [17 empty] | Aug | 0 |  |  | Has the Project Execution Plan been updated and approved in the last 12 months? | No |  |  | Needs Improvement | Has the Project Execution Plan been updated and approved in the last 12 months? | Date of latest approved Procurement Plan | No | Implementation Success Rate for Smart City Strategy | 3 | [7 empty] | 0.041667 | Good | % variance in land use permit area | 2.5 | Latest Land Area |  |  | Good | Criticality of Vacant/Missing Positions in Organization | Minor
qiddiya | Extent of all EOT (const. stage) | 8 | [6 empty] | Risk 9 | CAA | Impact M | Low | Closed | Measure 10 | % of projects with approved schedule extension | 0.43333 | Needs Improvement | Number of Changes (Detailed MP) | 6 | [7 empty] | Latest Approved budget | 610000000 | 0 | Sep | Workforce Availability | Needs Improvement | [16 empty] | Sep | 0 |  |  | % of Stakeholder MOU** / LUPs*** not executed in accordance with critical lead time | 0.05 |  |  | Good | % of Stakeholder MOU** / LUPs*** not executed in accordance with critical lead time | Number of Stakeholder MOU or Land Use Permits not executed on time | 5 | Number of Smart City Use Cases | 10 | Is there a smart city Strategy or document that lists the key focus areas of smart city aligned with DevCo strategic plan? | 0.4 | Needs Improvement | [7 empty] | 2.4 | Approved Land Area |  |  | Good | Appropriateness of Qualifications in Recruitment of Vacant Technical Department Head Positions | Minor
qiddiya | No. of unresolved issues | 10 | [6 empty] | Risk 10 | Source E | Impact S | Med | Ongoing | Measure 11 |  |  |  | Number of Changes (Concept Design) | 3 |  |  |  |  | % of variance of Allocated Provisional sums against the awarded amount | 1.6667 | Needs Improvement | Actual Utilized Provisional Sums | 1200000 | 0 | Oct | Resource Availability | Good | [16 empty] | Oct | 0 | [8 empty] | Total Stakeholder MOU or Land Use Permits required | 100 | Smart City Adoption Effectiveness Index (strategy & leadership alignment) | 2 | [7 empty] | 0.052632 | Good | % variance from approved population | 1000 | Latest Population |  |  | Good | Robustness of Policy/Guideline/Procedure Communication | Strong
qiddiya | No. of (Open) Inherent Risks | 20 | [15 empty] | Number of Changes (Detailed Design) | 4 | [9 empty] | 0 | Nov | Workforce retention track record | [17 empty] | Nov | 0 |  |  | % of Workforce Hired against Workforce Estimates | 1 | Workforce Resource Availability | 3 | Good | % of Workforce Hired against Workforce Estimates | Forecast workforce requirements | 0.4 | Smart City Adoption Effectiveness Index (infrastructure readiness) | 2 | [10 empty] | 950 | Approved Population |  |  | Satisfactory | Robustness of Policy/Guideline/Procedure Compliance Monitoring Framework | Moderate
qiddiya | No. of (Closed) Residual Risks | 45 | [12 empty] | % of projects with Forecast completion date beyond the latest approved schedule | 0.46154 | Needs Improvement | Number of Changes (Construction) | 10 | [9 empty] | 0 | Dec | Turnover rate track record | [17 empty] | Dec | 0 | [8 empty] | Actual workforce employed | 0.4 | Smart City Adoption Effectiveness Index (planning & governance) | 3 | [6 empty] | 2.8 | 0.33333 | Satisfactory | % value of modularization compared to the total construction value | 0.01 | Value of Modularized Construction Cost |  |  | Satisfactory | Robustness of Board Reporting Framework | Moderate
qiddiya | Project-level risks (including low, medium, and high severity) | 80 | [12 empty] | Is the Forecast Finish Date at a given data date based on the alignment and buy-in from project teams and other listed stakeholders? | Yes | Good | Total Awarded Cost | 15000000 | [11 empty] | Plant/equipment downtime track record | [21 empty] | % of Labor Camp Capacity against Workforce Estimates | 1.125 |  |  | Good | % of Labor Camp Capacity against Workforce Estimates | Forecast number of labor camps | 0.8 | Smart City Adoption Effectiveness Index (stakeholder alignment) | 1 | [10 empty] | 0.03 | Value of Total Construction Cost
qiddiya | Procedures for risk management | Satisfactory | [12 empty] | Based on the risks identified and approved change requests, has the DevCo conducted a sensitivity assessment on the forecast completion at a given data date? | Yes, but inadequate | Satisfactory | Approved Variations and Claims | 10000000 | [11 empty] | Number of technical queries raised | [27 empty] | Actual number of labor camps | 0.9 | Smart City Adoption Effectiveness Index (realized benefits & performance) | 0.5 | [7 empty] | Yes | Good | Have all projects completed a Constructability Report/Document? | Yes | Date and Revision of Constructability Report
qiddiya | Risks identified and corresponding impact on schedule | NIL | [12 empty] | Has DevCo allocated risk contingency for the identified risks? | Yes | Good | Uncommitted Cost | 250000000 | [11 empty] | Number of technical queries closed | [21 empty] | % of Material Supply Capacity against Material Demand Estimates | 1.4 |  |  | Good | % of Material Supply Capacity against Material Demand Estimates | Forecast number of batching / crushing plants/ precast yards, etc. | 0.5 | [9 empty] | Yes | Good | Was design for Enabling Work Package considerd as part of the design process to ensure the readiness of the site for the main construction work? | Yes | Assessment of enabling works required
qiddiya | Extra Cost due to Unresolved Issues | 2000000 | [12 empty] | Was there any deferment in the project completion date due to unidentified risks? | Yes, but less than 1 month | Satisfactory | Pending Variations | 0 | [11 empty] | Average time to complete shop drawing reviews | [27 empty] | Actual number of batching / crushing plants/ precast yards, etc. | 0.7 | [9 empty] | Yes | Good | Are documentation packages meeting the LOD requirements of the latest Design Stage Gate? | Yes | LOD Required
qiddiya | [14 empty] | Was there any Cost Overrun because of identified risk? | No | Good | Anticipated Variations | 1 | [11 empty] | Number of shop drawing review conducted | 480 | [20 empty] | Did DevCo adhere to Technical Submittals Review Cycle Time (RCT)? | Yes | Adherence to Design | 3 | Good | Did DevCo adhere to Technical Submittals Review Cycle Time (RCT)? | Time taken for closure of technical queries | Yes |  |  | Is there an impact assessment report or identified process/ guidelines to evaluate the impact of the innovation / smart city technologies adoption on DevCo performance? | 0.6 | Satisfactory | [7 empty] | Yes | LOD Documented (drawing sample from Design Report)
qiddiya | [14 empty] | Was there any Cost Overrun because of unidentified risk? | Yes, but less than 1% | Satisfactory | [13 empty] | Number of material / product substitution requests | [27 empty] | Technical Submittal Review Cycle Time (RCT) | Yes | [9 empty] | Yes | Good | Have all projects adopted digital delivery using BIM and/or GIS? | Yes | % of projects adopting digital delivery using BIM/GIS
qiddiya | [14 empty] | Risk Control Rate of the identified risks at DevCo Level | 0.6 | Satisfactory | [13 empty] | Average time to approve product sample & materials | [21 empty] | % of approved shop drawing reviews vs planned | 0.99167 |  |  | Good | % of approved shop drawing reviews vs planned | Total number of shop drawing review requests | 480 | [8 empty] | 2.6 | Yes | Good | Is project delivery occurring in accordance with the latest approved design strategy? | Yes | Date of Latest Approved Design Strategy
qiddiya | [30 empty] | Product & Material Approval Rate | [27 empty] | Total number of shop drawing reviews approved | 476 | [9 empty] | 0.1 | Needs Improvement | % of projects with completed technical design/peer reviews and verifications/certifications as required for the latest Design Stage Gate | 0.1 | Number of projects with completed design reviews and verification register
qiddiya | [14 empty] | Is the DevCo fully compliant with Risk Management Plan requirements? | No | Needs Improvement | [13 empty] | Number of as-built drawing review conducted | 485 | [20 empty] | % of approved product waivers vs product specified | 2 |  |  | Good | % of approved product waivers vs product specified | Total number of product sample & material approvals requested | 0.3 |  |  | Is there evidence for innovation / smart city technologies successful implementation (in final design report, master plan or other)? | Yes | Good |  |  |  |  | 0.85 | Good | % of Corrective Actions closed | 40 | Total Corrective Actions
qiddiya | [14 empty] | Is there a difference in the time impact forecast before and after the risk event has triggered? | Yes, but less than 2 weeks | Satisfactory | [13 empty] | Average time to approve As-built rejections / iterations | [27 empty] | Total number of product sample & materials approved | 0.6 | [12 empty] | 34 | Number of Closed Corrective Actions
qiddiya | [14 empty] | Is there a difference in the Cost impact forecast before and after the risk event has triggered? | Yes, but less than 0.5% | Satisfactory | [13 empty] | As-Built Drawing Approval Rate | [21 empty] | % of Certified As-Built Drawing Packages vs Planned | 0.95 |  |  | Good | % of Certified As-Built Drawing Packages vs Planned | Number of As-Built review requests | 500 |  |  | Are there Pilot or R&D projects conducted? | 0.55 | Needs Improvement | 1 | Pilot and R&D Transition Rate |  |  | 14 | Satisfactory | Average Cycle time to close corrective actions | 14 | Days taken to Close Corrective Actions
qiddiya | [30 empty] | Average time to complete MIRs and close out approvals | [27 empty] | Number of As-built reviews / approvals | 475 | [9 empty] | Yes | Good | Is the average cycle time to complete reviews and certifications in accordance with the Design Management Report? | Yes | Days taken to complete Design Reviews
qiddiya | [30 empty] | Average time to complete WIRs and close out approvals | [21 empty] | MIR Inspection Rate | 0.98333 |  |  | Good | MIR Inspection Rate | Total number of MIRs requested | 120 | [9 empty] | Yes | Good | Has the DevCo engaged independent certification of major critical elements? | Yes | Level of review and verification required for Stage Gate
qiddiya | [30 empty] | Number of NCRs open for between 30 and 60 days | 23 | [26 empty] | Total number of MIRs inspected | 118 | [8 empty] | 2 | No | Needs Improvement | Are all project designs integrated with Regional Infrastructure & Mobility Plans? | No | Regional Strategies
qiddiya | [30 empty] | Number of NCRs open for more than 60 days | 5 | [20 empty] | MIR Acceptance and Approval Rate | 0.91667 |  |  | Good | MIR Acceptance and Approval Rate | Total number of MIRs approved | 110 |  |  | % of pilot / R&D Projects Transitioned into Full-Scale | 0.13043 | Needs Improvement |  |  |  |  | Yes | Good | Do all projects comply with environmental guidelines in accordance with ESIA? | Yes | Extent of compliance to environmental guidelines
qiddiya | [30 empty] | Leadership engagement | Satisfactory | [20 empty] | WIR Inspection Rate | 0.97143 |  |  | Good | WIR Inspection Rate | Total number of WIRs requested | 350 | [8 empty] | 2.2 | 0.15 | Satisfactory | % of projects with Code Compliance Violations | 0.15 | Total Number of Code Compliance Violations
qiddiya | [30 empty] | Total number of ITPs requested | 100 | [26 empty] | Total number of WIRs inspected | 340 | [9 empty] | 1.0476 | Good | % of approved deviation waivers against compliant codes & standards | 21 | Total Waiver Applications Submitted
qiddiya | [30 empty] | Total number of ITPs attended | 98 | [20 empty] | WIR Acceptance and Approval Rate | 0.95714 |  |  | Good | WIR Acceptance and Approval Rate | Total number of WIRs approved | 335 | [12 empty] | 22 | Total Waivers Approved
qiddiya | [30 empty] | Total number of ITPs approved | 87 | [20 empty] | Does the frequency of Audits align with the QMP? | Yes | Quality Assurance / Quality Control (QA/QC) | 2.6 | Good | Does the frequency of Audits align with the QMP? | Required Audit frequency | Yes |  |  | Availability of Innovation unit / department with structured team | 0 | Needs Improvement | 1.5 | Organization Maturity Towards Innovation Adoption |  |  | Yes | Good | Have all required Stakeholder Submittals been issued? | Yes | Stakeholder Submittal Date
qiddiya | [30 empty] | Total number of ITPs completed | 85 | [20 empty] | % closure of Non-Conformance Reports (NCR) | 0.96667 |  |  | Good | % closure of Non-Conformance Reports (NCR) | Total number of defects & NCRs | 150 | [9 empty] | 0.31746 | Needs Improvement | % of time critical Stakeholder Approvals Pending impacting Design Stage Gate completion | 0.2 | Number of Stakeholder Approvals Pending
qiddiya | [30 empty] | Total number Quality Reports required | [27 empty] | Total number of closed defects & NCRs | 145 | [12 empty] | 0.63 | Total number of stakeholder approvals required
qiddiya | [30 empty] | Total number Quality Reports completed | [21 empty] | Average NCRs closeout Cycle Time | 5 Weeks |  |  | Needs Improvement | Average NCRs closeout Cycle Time | Average time to close NCRs | 5 Weeks | [9 empty] | Yes | Good | Does the Stakeholder Engagement Plan include proactive communication process to ensure timley coordination and approvals? | Yes | Scheduled Design Stage Gate Completion
qiddiya | [30 empty] | Completeness of Quality Management Plan | Needs Improvement | [20 empty] | % of procurement packages delivered within the planned lead times defined in the PMP | 2 | Procurement & Contracting Compliance | 2.8 | Good | % of procurement packages delivered within the planned lead times defined in the PMP | Planned Procurement Package Lead Time | 5 |  |  | Availability of Innovation and Technology Strategy / Process & Framework | 0.5 | Satisfactory |  |  |  |  | 0.19048 | Needs Improvement | % of Stakeholder Comments Closed | 21 | Total Stakeholder Comments
qiddiya | [30 empty] | Required number of ITPs signed off throughout construction | [27 empty] | Actual Procurement Package Delivery Time | 10 | [12 empty] | 4 | Stakeholder Comments Closed
qiddiya | [30 empty] | Total number of raised closed-out defects & NCRs | [21 empty] | % of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures | 0.875 |  |  | Good | % of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures | Total number of claims and variations | 800 | [8 empty] | 1 | 0 | Needs Improvement | % of projects achieving DevCo ESG Targets | 1 | Planned ESG Target
qiddiya | [30 empty] | Forecasted Procurement Budget | [27 empty] | Total number of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures | 700 | [12 empty] | 0 | Actual ESG Target
qiddiya | [30 empty] | Actual Procurement Budget | [21 empty] | % of packages procured with 100% complete, compliant and well-structured documentation | 0.6 |  |  | Satisfactory | % of packages procured with 100% complete, compliant and well-structured documentation | Total number of packages | 0.5 | [8 empty] | 1 | No | Needs Improvement | Does the DevCo ESG Target align with globally recognized Best Practice Targets? | No | Alignment with globally recognized Best Practice Targets
qiddiya | [30 empty] | Vendor Database | [27 empty] | Total number of packages procured with 100% complete, compliant and well-structured documentation | 0.3
qiddiya | [30 empty] | Vendor Shortlist | [21 empty] | % of awarded contracts where vendors appointed passed full due diligence checks | 1.2857 |  |  | Good | % of awarded contracts where vendors appointed passed full due diligence checks | No. of awarded contracts where vendors appointed passed full due-diligence checks | 0.9
qiddiya | [30 empty] | Vendor Awarded | [27 empty] | Total number of awarded contracts | 0.7
qiddiya | [30 empty] | Vendor KPIs | [21 empty] | Did the DevCo complete a Supply Chain Risk-Market Intelligence Assessment in the last quarter? | Yes |  |  | Good | Did the DevCo complete a Supply Chain Risk-Market Intelligence Assessment in the last quarter? | Supply Chain Risk-Market Intelligence Assessment | Yes
qiddiya | [30 empty] | Vendor Performance Database | [21 empty] | % of procurement activities executed as planned in the Annual Procurement Plan | 0.66667 | Procurement & Contracting Execution Performance |  | Needs Improvement | % of procurement activities executed as planned in the Annual Procurement Plan | Total number of procurement activities | 129
qiddiya | [30 empty] | Tender return date: Planned / Actual | [27 empty] | Number of procurement activities executed as planned | 86
qiddiya | [30 empty] | Tender Review & award time: Planned / actual | [21 empty] | % of deviations in total awarded contract value with tender cost estimates | 0.4 |  |  | Good | % of deviations in total awarded contract value with tender cost estimates | Value of Awarded Contract | 0.1
qiddiya | [30 empty] | Pre-Tender Cost Estimate | [27 empty] | Tender Cost Estimate | 0.06
qiddiya | [30 empty] | Tender Performance Index | [21 empty] | % of contracts with filed claims | 0.3 |  |  | Satisfactory | % of contracts with filed claims | Number of contracts with filed claims | 0.3
qiddiya | [30 empty] | Contract clauses | Satisfactory | [20 empty] | Are Payment Certificates and payments being processed in accordance with the Contract terms and conditions? | 80 |  |  |  | Are Payment Certificates and payments being processed in accordance with the Contract terms and conditions? | Processing of payment certificates and payments | 80
qiddiya | [30 empty] | Procurement Management Plan | Good | [20 empty] | Are Vendor performance assessment occurring which capture financial instability, delays, repeated quality issues in real-time? | No |  |  | Needs Improvement | Are Vendor performance assessment occurring which capture financial instability, delays, repeated quality issues in real-time? | Alignment of sourcing strategies with project schedules and requirements | No
qiddiya | [30 empty] | Scope / design maturity | Satisfactory | [20 empty] | Does the HSE Management Manual have adequate provision for identification and escalation of high risk activities? | Yes | HSE Compliance | 1.87 | Good | Does the HSE Management Manual have adequate provision for identification and escalation of high risk activities? | Escalation criteria for high risk activities | Yes
qiddiya | [30 empty] | Compliance with local content regulations / policies | [21 empty] | Is the rate of review of the Safety Risk Register in accordance with the HSE Management Manual? | Yes |  |  | Good | Is the rate of review of the Safety Risk Register in accordance with the HSE Management Manual? | HSE Risk Register Review Rate | Yes
qiddiya | [30 empty] | Dispute rate | [21 empty] | % of closed Safety Risk items | 0.83333 |  |  | Good | % of closed Safety Risk items | Total number of Safety Risk items | 0.9
qiddiya | [30 empty] | Claims processing cycle time | [27 empty] | Total number of closed Safety Risk items | 0.75
qiddiya | [30 empty] | No. of related CRs being requested during or after tendering phase due to identified scope gap | [21 empty] | Average cycle time to close Safety Risk items | 14 Days |  |  | Needs Improvement | Average cycle time to close Safety Risk items | Cycle time to close Safety Risk items | 14 Days
qiddiya | [30 empty] | Vendor Performance Assessment | Good | [20 empty] | Average cycle time to close Safety Incident | 0.65 |  |  | Good | Average cycle time to close Safety Incident | Cycle time to close Safety Incident | 20
qiddiya | [30 empty] | Tender pack quality | Satisfactory | [26 empty] | Total number of closed safety incidents | 13
qiddiya | [30 empty] | Total packages | [21 empty] | Is the emergency drill rate compliant with EEPP? | No |  |  | Needs Improvement | Is the emergency drill rate compliant with EEPP? | Planned number of Emergency Drills | 35
qiddiya | [30 empty] | Planned Packages | [27 empty] | Actual number of Emergency Drills | 20
qiddiya | [30 empty] | Awarded Packages | [27 empty] | Recommended time to complete Emergency drills | 5 Days
qiddiya | [30 empty] | Trade Most at Risk | [27 empty] | Actual Time to complete Emergency drills | 10 Days
qiddiya | [30 empty] | Highest Risk Work Site | [21 empty] | Fatality Rate (FR) | 5 |  |  | Needs Improvement | Fatality Rate (FR) | No. of incidents resulting in fatality or severe impairment per 200,000 work hours | 5
qiddiya | [30 empty] | Number of planned audits | [21 empty] | Lost Time Injury Frequency Rate (LTIFR) | 10 |  |  | Needs Improvement | Lost Time Injury Frequency Rate (LTIFR) | No. of incidents resulting in lost time per 200,000 work hours | 10
qiddiya | [30 empty] | Number of conducted audits | [21 empty] | Total Recordable Incident Rate (TRIR) | 30 |  |  | Needs Improvement | Total Recordable Incident Rate (TRIR) | No. of recordable incidents per 200,000 work hours | 30
qiddiya | [30 empty] | Number of Notifiable Incidents | 6 | [20 empty] | Near Miss Rate | 60 |  |  | Good | Near Miss Rate | No. of near misses recorded per 200,000 work hours | 60
qiddiya | [30 empty] | Number of Infringement Notices | 2 | [20 empty] | Safety Observation Rate | 80 |  |  | Satisfactory | Safety Observation Rate | No. of safety observation recorded per 200,000 work hours | 80
qiddiya | [30 empty] | Total Safe Manhours | 2 | [20 empty] | Leadership Safety Walk Rate | 0.6 |  |  | Satisfactory | Leadership Safety Walk Rate | Total number of Safety Walks | 50
qiddiya | [30 empty] | Total number of closed Corrective actions | 1 | [26 empty] | Total number of Safety Walks with Leadership | 30
qiddiya | [30 empty] | Inspection Pass Rate | [21 empty] | % of Grievances Closed | 1 | Welfare Compliance | 2.4 | Good | % of Grievances Closed | Number of grievances closed | 5
qiddiya | [30 empty] | No. of recurring incidents / safety observations outside control | [27 empty] | Total number of grievances | 5
qiddiya | [30 empty] | Total Site Manhours | 180000000 | [20 empty] | Average Cycle Time to Close Grievances | Good |  |  | Needs Improvement | Average Cycle Time to Close Grievances | Cycle time to close grievances | Good
qiddiya | [30 empty] | Welfare of labor camps | [21 empty] | % of Welfare Staff vs Total workforce | Good |  |  | Good | % of Welfare Staff vs Total workforce | Percentage of Welfare Staff against total staff | Good
qiddiya | [30 empty] | Welfare of site facilities | [21 empty] | % closed welfare observations or red flag if 0 observations | 0.75 |  |  | Good | % closed welfare observations or red flag if 0 observations | Total number of Welfare Observations | 20
qiddiya | [30 empty] | Labor accommodation inspection rate | [27 empty] | Total number of Closed Welfare Observations | 15
qiddiya | [30 empty] | Regulation Compliance | [21 empty] | % of Welfare Non-compliances closed | 0.58 |  |  | Needs Improvement | % of Welfare Non-compliances closed | Total Welfare Non-compliances | 100
qiddiya | [58 empty] | Total Closed Welfare Non-compliances | 58
qiddiya | [52 empty] | Average Cycle Time to Close Welfare Non-compliances | 10 Days |  |  | Needs Improvement | Average Cycle Time to Close Welfare Non-compliances | Cycle time to close Welfare Non-Compliances | 10 Days
qiddiya | [52 empty] | Is frequency of Labor Accommodation Inspection occurring in accordance with VMMP? | Yes |  |  | Good | Is frequency of Labor Accommodation Inspection occurring in accordance with VMMP? | Mitigation measures in the event of welfare audit observations & recommendations | Yes