## Main
0.268 | 0.2 | 0.2 | 0.2 | 0.6 | 0.2 | 0.2 | MEINHARDT | Administrator: | Admin
0.732
LOGIN
User
Setting
Assessment Summary
UPDATE
Create Lead
Create Sec
PROJECT LIGHTHOUSE
ASSESSMENT GUIDE
DIRIYAH
STRICTLY CONFIDENTIAL
þ Assessment In Progress
þ To Be Assessed
þ To Be Reviewed
þ In Review
þ Assessment Completed
Design
& Technical
(D&T)
Development
& Construction
(D&C)
Cost Estimation
& Optimization
(CE&O)
Innovation
& Technology
(I&T)
Strategy
& Operations
(S&O)
þ Assessment In Progress
þ To Be Assessed
þ To Be Reviewed
þ In Review
þ Assessment Completed
þ Assessment In Progress
þ To Be Assessed
þ To Be Reviewed
þ In Review
þ Assessment Completed
þ Assessment In Progress
þ To Be Assessed
þ To Be Reviewed
þ In Review
þ Assessment Completed
þ Assessment In Progress
þ To Be Assessed
þ To Be Reviewed
þ In Review
þ Assessment Completed
þ Assessment In Progress
þ To Be Assessed
þ To Be Reviewed
þ In Review
þ Assessment Completed
Planning
& Monitoring
(P&M)
DevCo Assessment Input (P&M)
DevCo Assessment Analysis (P&M)
DevCo Assessment Input (D&T)
DevCo Assessment Analysis (D&T)
DevCo Assessment Input (D&C)
DevCo Assessment Analysis (D&C)
DevCo Assessment Input (CE&O)
DevCo Assessment Analysis (CE&O)
DevCo Assessment Input (I&T)
DevCo Assessment Analysis (I&T)
DevCo Assessment Input (S&O)
DevCo Assessment Analysis (S&O)
Interview Question
(P&M)
Interview Question
(D&T)
Interview Question
(D&C)
Interview Question
(CE&O)
Interview Question
(I&T)
Interview Question
(S&O)
Additional Data Points (P&M)
Additional Data Points (D&T)
Additional Data Points (D&C)
Additional Data Points (CE&O)
Additional Data Points (I&T)
Additional Data Points (S&O)
Log
Instructions
Glossary & Definitions
Document List
Q1 2025
Period of Assessment

## Instructions
PIF Project Lighthouse
Instructions
SN | Page | Role | Instructions
1 | Document List |  | This page lists all the documents submitted by the DevCo, which consist the location of the documents and the file names.
2 | DevCo Assessment Input |  | This page is used for the input of data points required for the assessment criteria
3 | DevCo Assessment Input | Assessor | Enter the assessment value for each data point in " INPUT VALUE" column. Note: 1) For non-quantitative AC, use the drop-down box to select the right option 2) The drop down box would have options across all the Assessment critera (AC) and hence you may see drop down values, which are not relevant to the specific AC. Please toggle to the Assessment Analysis page to identify the relevant options to input.
4 | DevCo Assessment Input | Assessor | Input the Document Request Number (for e.g., DR-017) under the "DATA SOURCE" column. Please refer to the Document List for the Document Request (DR) number
5 | DevCo Assessment Input | Assessor | Please note down any remarks in the Assessor Remarks column
6 | DevCo Assessment Input | Reviewer | Please review the findings with the Data Analyst/Assessor and update the "INPUT VALUE" column (if required). For any changes to the "INPUT VALUE" input or to make any additional remarks, please update the "REVIEWER REMARKS" column
7 | DevCo Assessment Analysis | All | A score of 'Good', 'Satisfactory', and 'Critical' will be automatically generated based on each Assessment Criteria's value
8 | DevCo Assessment Analysis | All | Please note down remarks, if any
9 | Interview Questions (IQs) |  | This page is used for the discussions with DevCos
10 | Interview Question | All | Predefined interview questions will be populated here and additional questions can be added as needed.
11 | Interview Question | All | Please note down the conversation/interview date in the "DATE OF INTERVIEW" column
12 | Interview Question | All | Please note down DevCo answers to the interview questions in " RESPONSE" Column
13 | Interview Question | All | Please note down any further queries in "FOLLOW UP QUESTIONS " for easy tracking
14 | Additional Data Points (ADPs) |  | This page is used for the input of additional data points which are not required for the assessment criteria but are needed for the dashboard
15 | Additional Data Points | Data Analyst / Assessor | Please populate the "VALUE" column for each Additional Data Points
Go to Main Page

## Glossary&Definitions
PIF Project Lighthouse
Glossary&Definitions
SN | Section | Term | Description
1 | Cost Estimation & Optimization | Actual Cost (AC) | Actual Cost is the total cost incurred for work completed on a project at a given point in time. It includes all direct and indirect costs spent on labor, materials, equipment, and other expenses.
2 | Cost Estimation & Optimization | Aggregated Budget Variance | Cumulative difference between total budgeted figures and actual results across multiple categories or projects, highlighting overall financial performance deviations within a specific period
3 | Planning & Monitoring | Aggregated SPI | Indication of overall schedule performance at DevCo level
4 | Development & Construction | Annual Procurement Plan / Strategy | The Procurement Plan is required to be reviewed and updated by the DevCo as a minimum annually and submitted to PIF for approval in accordance with the requirements of the Project Execution Plan.
5 | General | Authority | Each development stage requires approval. The Authority is the relevant party responsible for the approval at the relevant stage (e.g. CEO, Founding Board etc.)
6 | Design & Technical | BUA | Built Up Area (BUA) is the total area being developed or constructed. It is the Gross Floor Area (GFA) plus Parking plus any Service Area.
7 | Cost Estimation & Optimization | Budget Variance (BV) | Extent of variance in budget
8 | Cost Estimation & Optimization | Budget At Completion (BAC) | The Budget at Completion (BAC) represents the total budgeted cost for all the work planned for a project
9 | Cost Estimation & Optimization | Estimate To Complete (ETC) | The estimated cost required to complete the remaining work of a project
10 | Cost Estimation & Optimization | Estimate At Completion (EAC) | Total forecasted cost of the project based on the ongoing
11 | General | Business Plan | Documentation developed by PIF informing the Vision and key objectives of the project
12 | General | Change Management Log | A document summarising the status of all proposed and approved Variations
13 | General | Change Management Procedure | Procedural document stipulating the requirements to be met when administering any amendment to a Contract or Project.
14 | Cost Estimate & Optimization | Contingency Utilization Rate (CUR) | Percentage of a project’s allocated contingency fund that has been used to address unforeseen costs or risks, reflecting the efficiency of contingency planning and management.
15 | Development & Construction | Contract Management Policy | A policy outlining award and management of contracts between DevCo and Vendors.
16 | Cost Estimate & Optimization | Cost Estimate and Optimization (CE&O) | Technical function which covers cost benchmarks for development of budgets, and cost optimization levers
17 | Cost Estimate & Optimization | Cost Report | A document provided on an interim basis to inform of the current financial status of a Project
18 | Design & Technical | Design and Technical (D&T) | Technical Function which covers all design-related topics of a project including architecture, engineering, masterplanning, infrastructure and environment & sustainability
19 | Development & Construction | Development and Construction (D&C) | Technical function which covers construction project execution plans, contract management and procurement, and construction quality and Health, Safety and Environment (HSE) topics
20 | Planning & Monitoring | Earned Value (EV) | Value of the work that is completed at a given time, measured against the budgeted cost.
21 | Planning & Monitoring | Extension of Time (EOT) | Extension of Time is a contractual provision in construction allowing the project completion date to be extended due to unforeseen delays beyond the contractor’s control, ensuring fairness and mitigating penalties.
22 | Design & Technical | Gross Floor Area (GFA) | Gross Floor Area (GFA) is the total floor area of a building including any underground saleable or leasable area but excluding parking and underground technical/service areas. The GFA is calculated based on the distance from external wall to external wall.
23 | Innovation & Technology | Innovation and Technology (I&T) | Technical function which covers incorporation of high-impact advanced technologies and methodologies across the entire project life cycle, and implementation of smart city use cases.
24 | Development & Construction | Inspection Test Plan (ITP) | A document which specifies the manatory Inspection, Witness and Hold Points throughout construction that must be verified by a suitably qualified person before works are authorised to proceed.
25 | General | Key Performance Indicator (KPI) | Key quantifiable indicators of progress toward an intended result
26 | Development & Construction | Non-Conformance Report (NCR) | Non-Conformance Report is a quality management document that identifies, tracks, and records deviations from specified standards, facilitating process improvement and quality control.
27 | Cost Estimate & Optimization | Planned Budget (PB) | It represents how much is expected to be spent at a given point in time from the Approved Over All Budget (BAC)
28 | Planning & Monitoring | Planned Value (PV) | The amount of work that was planned to be completed at a given time as per the approved Schedule.
29 | Planning & Monitoring | Planning and Monitoring (P&M) | Technical Function which covers schedule development and monitoring, and risk management
30 | Development & Construction | Procurement Strategy | Methodical approach for determining the contractural relationship and agreements between DevCo and Vendors
31 | Development & Construction | Procurement Procedures Manual | A manual which details every aspect of the tendering and overall procurement activities.
32 | Development & Construction | Project Execution Plan (PEP) | Project Execution Plan prepared initially by PIF as part of the Business Plan Stage, which is then passed to the DevCo to lead, review and update from Masterplan Stage onwards
33 | Development & Construction | Request For Information (RFI) | A formal communication tool for requesing information
34 | Development & Construction | Rework Cost | Indication of the rework done due to quality, design etc issues
35 | Planning & Monitoring | Schedule Performance Index (SPI) | Indication of project schedule performance
36 | Cost Estimate & Optimization | Soft Cost | Soft costs are indirect, non-physical expenses in a construction project that are not directly tied to labor, materials, or physical construction work.
37 | General | Stage | The description of the Project Stage as per Development Company and PIF terminology.
38 | Strategy & Operations | Strategy & Organization | Technical Function which covers topics around strategy development and execution, people and tools.
39 | Design & Technical | Value Engineering | Process to derive greater value within a Project seeking improvement in time and/ or cost outcomes
40 | Development & Construction | Vendor Database | A database of Vendors, including pre-qualified Vendors, Vendor appraisal and performance assessment and a list of blacklisted Vendors.
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
Go to Main Page

## DocumentList
PIF Project Lighthouse
DocumentList
SN | Document Request ID (Sharepoint) | Document Request | DevCo or Project Level | Document Number | File Name | Date Received | Remarks
1 | Cost Data | Cost Data Template | DevCo
2 | DR-001 | Baseline and Updated Master schedule (including cost linked Milestone summary for earned value, planned value analysis, and Schedule Updates) | DevCo | DR-001-01 | Project Mapping WBS1&2 Mapping and Dec-24 Cost Report Rev.3 | 2025-07-02 16:31
3 |  |  |  | DR-001-02 | IMS-P1-UP-241228-R1C (STEP 1) - Update Final Cost Loaded | 2025-07-02 16:31
4 |  |  |  | DR-001-03 | Zallal P3 Updated Schedule DD 17-Jan-15 | 2025-07-02 16:31
5 |  |  |  | DR-001-04 | 106, Al Zallal - Planned VS Actual 24-Jan-25 | 2025-07-02 16:31
6 |  |  |  | DR-001-05 | 106, Al Zallal, PBL Rev. 2.2, DD 24-Jan-25, Sub`d 23-Jan-25 | 2025-07-02 16:31
7 |  |  |  | DR-001-06 | Change Log-AL Zallal | 2025-07-02 16:31
8 |  |  |  | DR-001-07 | IMS_Dec'24_DD. AUG22_Baseline Cost Loaded | 2025-07-02 16:31
9 |  |  |  | DR-001-08 | Project Mapping WBS1&2 Mapping and Dec-24 Cost Report Rev.3 | 2025-07-02 16:31
10 |  |  |  | DR-001-09 | Reconciliation of Mapped Scope for Cost Loading | 2025-07-02 16:31
11 |  |  |  | DR-001-10 | 00. LH_2025_05_22_Diriyah_Document_Review_PM-with DevCo response | 2025-07-02 16:31
12 | DR-002 | Program Management Plan | DevCo | DR-002-01 | 15th April - Updated DGCL DoA 7 | 2025-07-02 16:31
13 |  |  |  | DR-002-02 | Completion, Handover & Opening (Policy and Process Manual) | 2025-05-07 21:29
14 |  |  |  | DR-002-03 | Development Managment Policy Process Manual_ | 2025-05-07 21:29
15 |  |  |  | DR-002-04 | GCEO Signed Sub-DOA V2 7 | 2025-05-07 21:29
16 |  |  |  | DR-002-05 | 2025.03.20 Periodic Schedule Update - Two Step Approach | 2025-05-07 21:29
17 |  |  |  | DR-002-06 | SW-SWD-550-0000-MAC-GDL-PC-000042 - Integrated Master Schedule Update | 2025-05-07 21:29
18 |  |  |  | DR-002-07 | SW-SWD-550-0000-MAC-PLN-PC-000003 - Schedule Management Plan | 2025-05-07 21:29
19 |  |  |  | DR-002-08 | SW-SWD-550-0000-MAC-PRO-PC-000025 - Integrated Master Schedule Update | 2025-05-07 21:29
20 | DR-003 | Latest Approved Monthly Progress Report | DevCo | DR-003-01 | DevCo President Commercial Update - Dec -2024 | 2025-05-07 21:29
21 |  |  |  | DR-003-02 | 241226-DC-PMO-GCEO Programme Update - DI DII HD&WH WS | 2025-05-07 21:29
22 |  |  |  | DR-003-03 | 241226-DC-PMO-GCEO Report DI DII HD&WH WS - Dec-24 | 2025-05-07 21:29
23 |  |  |  | DR-003-04 | DevCo President Commercial Update - Dec -2024 | 2025-05-07 21:29
24 | DR-004 | Change request register (covering latest approved schedule extension requests) | DevCo
25 | DR-005 | Latest approved risk mapping / risk register (including mitigation plans) documented at DevCo level and the list of Stakeholders | DevCo | DR-005-01 | 00-000-000-0000-MAC-REG-RK-000002(17) DC Portfolio Risk Register_Mar25 (1) | 2025-05-07 21:29
26 |  |  |  | DR-005-02 | 00-000-000-0000-MAC-REG-RK-000003(16) DC Portfolio Issue Register_Mar25 | 2025-05-07 21:29
27 |  |  |  | DR-005-03 | Risk Management Dashboard_New | 2025-05-07 21:29
28 |  |  |  | DR-005-04 | SW-SWD-550-0000-MAC-PRE-RK-000002(11) Principal Risk and Issue Mtg Presentation_Feb25_Final (1) | 2025-05-07 21:29
29 |  |  |  | DR-005-05 | SW-SWD-550-0000-MAC-ROM-RK-000002(08) DC Principal Risk Meeting Minutes_Feb25 | 2025-05-07 21:29
30 | DR-006 | Lookahead Schedules / Short-term execution plans (e.g., 4-week or 6-week lookahead) | DevCo | DR-006-01 | DC - DevCo Risk Management Procedure (Rev 00) signed | 2025-05-07 21:29
31 | DR-007 | Sample of project level approved risk register | Project
32 | DR-008 | Risk Management Plan | DevCo
33 | DR-009 | Latest Updated Cost report | DevCo
34 | DR-010 | Program Tracker | DevCo
35 | DR-011 | Original Approved and Latest version of CGI & Animation (Material Palette & Finish Schedule) | Project
36 | DR-012 | Original Approved and Latest version of the Drawings | DevCo
37 | DR-013 | DevCo Design & Technical Guidelines (including, but not limited to, Look & Feel Design Guidelines) | DevCo | DR-013-01 | 123DG_GUIDELINES_Part III_RWK.PDF | 2025-05-07 21:29
38 |  |  |  | DR-013-02 | 240117 [1] DII Residential Design Guidelines.PDF | 2025-05-07 21:29
39 |  |  |  | DR-013-03 | FLS Guidelines | 2025-05-07 21:29
40 |  |  |  | DR-013-04 | MEP Guidelines | 2025-05-07 21:29
41 |  |  |  | DR-013-05 | Structural Guidelines | 2025-05-07 21:29
42 | DR-014 | Design Report / Return Brief Report (including approved and latest Asset Area Schedule & Population) | Project
43 | DR-015 | Latest Stage Gate Cost Plan | Project
44 | DR-016 | Report including constructability feasibility and construction methodology | Project
45 | DR-017 | Digital Information Management Plan | DevCo | DR-017-01 | 20231022 Spatial Data GIS Requirements | 2025-05-07 21:29
46 |  |  |  | DR-017-02 | SW-SWD-550-0000-DGD-STD-BM-000001 Employer Information Requirements. | 2025-05-07 21:29
47 |  |  |  | DR-017-03 | SW-SWD-550-0000-DGD-STD-BM-000002 Appendix 01 - Asset Information Requirements | 2025-05-07 21:29
48 |  |  |  | DR-017-04 | SW-SWD-550-0000-DGD-STD-BM-000003 Appendix 01.1-Asset Information Data Structure & Classification. | 2025-05-07 21:29
49 |  |  |  | DR-017-05 | SW-SWD-550-0000-DGD-STD-BM-000004 Appendix 01.2 -Asset Classification&Information Mapping | 2025-05-07 21:29
50 | DR-018 | Latest Project Execution Plan (including Design Strategy, Packaging Strategy and Phasing Strategy) | DevCo | DR-018-01 | DG2 High Level Delivery Strategy_Final r15MAR25_FK | 2025-05-07 21:29
51 | DR-019 | Design Master Schedule | DevCo
52 | DR-020 | Procedures and Governance for design approvals and change management | DevCo | DR-020-01 | Change Approval Map | 2025-05-07 21:29
53 | DR-021 | Design Basis Report and Stage Gate Design Report (including Design Management Report, Design Reviews & Verifications Register) | Project
54 | DR-022 | Infrastructure and Engineering report (including Water, Energy, Waste, Infrastructure & Mobility Plans) | DevCo
55 | DR-023 | Environmental and Social Impact Assessment | DevCo | DR-023-01 | 1. Enviromental Permit GAMEP - DGI - Arabic | 2025-05-07 21:29
56 |  |  |  | DR-023-02 | 2. Environmental permit GAMEP- DGI - Translation | 2025-05-07 21:29
57 |  |  |  | DR-023-03 | 3. Extension letter - Translation | 2025-05-07 21:29
58 |  |  |  | DR-023-04 | 140920-Enviromental Permit GAMEP | 2025-05-07 21:29
59 |  |  |  | DR-023-05 | OG_GN_NCEC_44-8902_بشأن عدم الحاجة لتجديد التصاريح البيئية | 2025-05-07 21:29
60 |  |  |  | DR-023-06 | Diriyah Gate EIA report - 20feb20 | 2025-05-07 21:29
61 |  |  |  | DR-023-07 | Appendix A | 2025-05-07 21:29
62 |  |  |  | DR-023-08 | Appendix B | 2025-05-07 21:29
63 |  |  |  | DR-023-09 | Appendix C | 2025-05-07 21:29
64 |  |  |  | DR-023-10 | Appendix D | 2025-05-07 21:29
65 |  |  |  | DR-023-11 | DG002-KEO-CM-TCR-0000049_OACEMP_rev06 | 2025-05-07 21:29
66 |  |  |  | DR-023-12 | appendix_a_diriyah_gate_development_bujairi_samhan_wh_epc | 2025-05-07 21:29
67 |  |  |  | DR-023-13 | appendix_a_diriyah_gate_development_epc | 2025-05-07 21:29
68 |  |  |  | DR-023-14 | appendix_B_current_contracts_information_08122024 | 2025-05-07 21:29
69 |  |  |  | DR-023-15 | Appendix_C_unpaved_road_chemical_treatment_08122024 | 2025-05-07 21:29
70 |  |  |  | DR-023-16 | Appendix_D_waste_signage_08032024 | 2025-05-07 21:29
71 |  |  |  | DR-023-17 | appendix_E_soil_sampling_and_analysis_procedure_08122024 | 2025-05-07 21:29
72 |  |  |  | DR-023-18 | incident_reporting_forms_investigation_08122024 | 2025-05-07 21:29
73 |  |  |  | DR-023-19 | incident_reporting_forms_notification_24-hr_08122024 | 2025-05-07 21:29
74 |  |  |  | DR-023-20 | mwan_approved_waste_licensed_parties | 2025-05-07 21:29
75 |  |  |  | DR-023-21 | ncec_approved_waste_licensed_parties | 2025-05-07 21:29
76 |  |  |  | DR-023-22 | appendix_H_legal_register_08122024 | 2025-05-07 21:29
77 |  |  |  | DR-023-23 | Appendix_I_waste_management_manifest_arabic | 2025-05-07 21:29
78 |  |  |  | DR-023-24 | Appendix_I_waste_management_manifest_english | 2025-05-07 21:29
79 |  |  |  | DR-023-25 | appendix_J_contractor's_cemp_specific_structure_08122024 | 2025-05-07 21:29
80 |  |  |  | DR-023-26 | appendix_K_CEMP_Compliance_checklist 08122024 | 2025-05-07 21:29
81 |  |  |  | DR-023-27 | appendix_L_demobilization_audit_checklist_08122024 | 2025-05-07 21:29
82 |  |  |  | DR-023-28 | appendix_M_non_conformance_report | 2025-05-07 21:29
83 |  |  |  | DR-023-29 | appendix_N_Pre_Construction-mobilization_audit_checklist_08122024 | 2025-05-07 21:29
84 |  |  |  | DR-023-30 | appendix_O_Air_Quality_Management_checklist_08032024 | 2025-05-07 21:29
85 |  |  |  | DR-023-32 | DG220-JCB-DE-TCR-000081-EIA-Rev03 | 2025-05-07 21:29
86 |  |  |  | DR-023-33 | DG220-JCB-DE-TCR-000063-02-Hydrology Study | 2025-05-07 21:29
87 |  |  |  | DR-023-34 | DG220-JCB-DE-TCR-000064-03 EPEP | 2025-05-07 21:29
88 |  |  |  | DR-023-35 | DG220-JCB-DE-TCR-000095-01_Traffic Noise Modelling Assessment | 2025-05-07 21:29
89 |  |  |  | DR-023-36 | DG220-JCB-DE-TCR-000085-03 Baseline Report | 2025-05-07 21:29
90 |  |  |  | DR-023-37 | DG220-JCB-DE-TCR-000096-02_Traffic ADM | 2025-05-07 21:29
91 |  |  |  | DR-023-38 | Visual Directory | 2025-05-07 21:29
92 |  |  |  | DR-023-39 | DG220-JCB-DE-TCR-000091-02_OCEMP | 2025-05-07 21:29
93 |  |  |  | DR-023-40 | DGII SW-MPL-008-0000-KEO-PLN-EN-000001 | 2025-05-07 21:29
94 |  |  |  | DR-023-41 | DG220-JCB-DE-TCR-000091-02_OCEMP | 2025-05-07 21:29
95 |  |  |  | DR-023-42 | 1. Environmental Permit NCEC - Wadi Safar - Arabic | 2025-05-07 21:29
96 |  |  |  | DR-023-43 | 2. Environmental Permit NCEC - Wadi Safar - Translation | 2025-05-07 21:29
97 |  |  |  | DR-023-44 | 3. Extension letter - Translated | 2025-05-07 21:29
98 |  |  |  | DR-023-45 | Volume 1 | 2025-05-07 21:29
99 |  |  |  | DR-023-46 | Volume 2 | 2025-05-07 21:29
100 |  |  |  | DR-023-47 | Appendix A - GAMEP License | 2025-05-07 21:29
101 |  |  |  | DR-023-48 | Appendix B - Legal and Statutory Requirements from General Authority of Meteorology and Environmental Protection (GAMEP) | 2025-05-07 21:29
102 |  |  |  | DR-023-49 | Appendix C - Ambient Air Quality and Noise Monitoring Report, LEAF Global, January 2020 | 2025-05-07 21:29
103 |  |  |  | DR-023-50 | Appendix D - Geotechnical Investigation Report (Extract), SAFCO, April 2020 | 2025-05-07 21:29
104 |  |  |  | DR-023-51 | Appendix E – Flood Study Report, Jacobs, August 2020 | 2025-05-07 21:29
105 |  |  |  | DR-023-52 | Appendix F – Preliminary Slope Assessment, BuroHappold, January 2020 | 2025-05-07 21:29
106 |  |  |  | DR-023-53 | Appendix G – Outline Environmental Construction Management Plan (O-CEMP) | 2025-05-07 21:29
107 |  |  |  | DR-023-54 | WS-000-000-0000-KEO-PLN-EN-000001OCEMP - Rev01 | 2025-05-07 21:29
108 |  |  |  | DR-023-55 | OG_GN_NCEC_44-8902_بشأن عدم الحاجة لتجديد التصاريح البيئية | 2025-05-07 21:29
109 |  |  |  | DR-023-56 | WS Env. Permit_200007170458 | 2025-05-07 21:29
110 |  |  |  | DR-023-57 | SW-SWD-551-0000-SET-GDL-EV-000004-Ver 01 - NTM Facility Bulletin-Revised_AK_KK_HJ (1) | 2025-05-07 21:29
111 |  |  |  | DR-023-58 | تعميم بشأن معالجة مخالفات رمي مخلفات البناء والحفريات في مدينة الرياض | 2025-05-07 21:29
112 |  |  |  | DR-023-59 | appendix_c_current_contracts_information_20230921 | 2025-05-07 21:29
113 |  |  |  | DR-023-60 | Appendix_d_unpaved_road_chemical_treatment_20230921 | 2025-05-07 21:29
114 |  |  |  | DR-023-61 | Appendix_e_waste_signage_20240330 | 2025-05-07 21:29
115 |  |  |  | DR-023-62 | appendix_f_soil_sampling_and_analysis_procedure_20230921 | 2025-05-07 21:29
116 |  |  |  | DR-023-63 | incident_reporting_forms_investigation_20230921 | 2025-05-07 21:29
117 |  |  |  | DR-023-64 | incident_reporting_forms_notification_24-hr_20230921 | 2025-05-07 21:29
118 |  |  |  | DR-023-65 | mwan_approved_waste_licensed_parties | 2025-05-07 21:29
119 |  |  |  | DR-023-66 | ncec_approved_waste_licensed_parties | 2025-05-07 21:29
120 |  |  |  | DR-023-67 | appendix_i_legal_register_20230921 | 2025-05-07 21:29
121 |  |  |  | DR-023-68 | DC Waste Manifest_Arabic | 2025-05-07 21:29
122 |  |  |  | DR-023-69 | DC Waste Manifest_English | 2025-05-07 21:29
123 |  |  |  | DR-023-70 | appendix_k_contractor's_cemp_specific_structure_20230921 | 2025-05-07 21:29
124 |  |  |  | DR-023-71 | Weekly Environment Inspection Report_Rev02 | 2025-05-07 21:29
125 |  |  |  | DR-023-72 | Pre_Mobilization_Environmental_Checklist_Rev06 Aug 24 | 2025-05-07 21:29
126 |  |  |  | DR-023-73 | DC_TEBS - Methodology Guideline_July 2024 | 2025-05-07 21:29
127 |  |  |  | DR-023-74 | Appendix_o_demobilization_audit_checklist_20230921 | 2025-05-07 21:29
128 |  |  |  | DR-023-75 | NCR - Non-Conformance Report | 2025-05-07 21:29
129 |  |  |  | DR-023-76 | Air Quality Management Checklist | 2025-05-07 21:29
130 |  |  |  | DR-023-77 | Monthly Environmental Report Rev 02 | 2025-05-07 21:29
131 |  |  |  | DR-023-78 | Quarterly CEMP Compliance Review Checklist | 2025-05-07 21:29
132 |  |  |  | DR-023-79 | KPIs and Scoring Criteria | 2025-05-07 21:29
133 |  |  |  | DR-023-80 | 1. DC_Environment Requirements_Contractors_Nov. 2023 | 2025-05-07 21:29
134 |  |  |  | DR-023-81 | 2. DC_Environment Requirements_CSC_Nov. 2023 | 2025-05-07 21:29
135 |  |  |  | DR-023-82 | 3. DC_Environment Requirements_PMC_Nov. 2023 | 2025-05-07 21:29
136 |  |  |  | DR-023-83 | DG-DSQ-000-0000-SSA-SCH-PC-000001(03) | 2025-05-07 21:29
137 |  |  |  | DR-023-84 | Oberoi Hotel CEMP | 2025-05-07 21:29
138 |  |  |  | DR-023-85 | DG-BUJ-106-0000-NSM-PLN-EN-000002 Rev.02 | 2025-05-07 21:29
139 |  |  |  | DR-023-86 | appendix_a_diriyah_gate_development_bujairi_samhan_wh_epc | 2025-05-07 21:29
140 |  |  |  | DR-023-87 | Appendix_d_unpaved_road_chemical_treatment_20230921 | 2025-05-07 21:29
141 |  |  |  | DR-023-88 | Appendix_D_waste_signage_08032024 | 2025-05-07 21:29
142 |  |  |  | DR-023-89 | appendix_g_soil_sampling_and_analysis_procedure_20230921 | 2025-05-07 21:29
143 |  |  |  | DR-023-90 | incident_reporting_forms_investigation_20230921 | 2025-05-07 21:29
144 |  |  |  | DR-023-91 | incident_reporting_forms_notification_24-hr_20230921 | 2025-05-07 21:29
145 |  |  |  | DR-023-92 | ZAB SIGNED AGREEMENT | 2025-05-07 21:29
146 |  |  |  | DR-023-93 | appendix_t_legal_register_20230921 | 2025-05-07 21:29
147 |  |  |  | DR-023-94 | Appendix_j_waste_management_manifest_arabic | 2025-05-07 21:29
148 |  |  |  | DR-023-95 | Appendix_j_waste_management_manifest_english | 2025-05-07 21:29
149 |  |  |  | DR-023-96 | appendix_l_contractor's_cemp_specific_structure_20230921 | 2025-05-07 21:29
150 |  |  |  | DR-023-97 | CEMP COMPLIANCE CHECKLIST | 2025-05-07 21:29
151 |  |  |  | DR-023-98 | appendix_M_demobilization_audit_checklist_20230921 | 2025-05-07 21:29
152 |  |  |  | DR-023-99 | appendix_N_non_conformance_report_20230921 | 2025-05-07 21:29
153 |  |  |  | DR-023-100 | appendix_N_Pre_Construction-mobilization_audit_checklist_08122024 | 2025-05-07 21:29
154 |  |  |  | DR-023-101 | Air Quality Management Checklist for Earthwork Activities - Template | 2025-05-07 21:29
155 |  |  |  | DR-023-102 | 02A. Schedule Narrative- Zallal P3 | 2025-05-07 21:29
156 |  |  |  | DR-023-103 | 02B. Baseline Schedule Zallal Package-3, Rev-04 (6-june-24) | 2025-05-07 21:29
157 |  |  |  | DR-023-104 | Overall Logistic Plan | 2025-05-07 21:29
158 |  |  |  | DR-023-105 | APPENDIX P – ENVIRONMENTAL TRAINING MATRIX | 2025-05-07 21:29
159 |  |  |  | DR-023-106 | DG-BUJ-106-0000-NSM-MTS-CE-000016 Rev.03 | 2025-05-07 21:29
160 |  |  |  | DR-023-107 | DG-BUJ-106-0000-NSM-MTS-CE-000024 Rev.02 | 2025-05-07 21:29
161 |  |  |  | DR-023-108 | DG-BUJ-106-0000-NSM-MTS-CE-000025 Rev.02 | 2025-05-07 21:29
162 |  |  |  | DR-023-109 | DG-BUJ-106-0000-NSM-MTS-CE-000026 | 2025-05-07 21:29
163 |  |  |  | DR-023-110 | DG-BUJ-106-0000-NSM-MTS-CE-000027 Rev.01 | 2025-05-07 21:29
164 |  |  |  | DR-023-111 | DG-BUJ-106-0000-NSM-ORG-AD-000001 Rev.02 | 2025-05-07 21:29
165 |  |  |  | DR-023-112 | Daily Checklist | 2025-05-07 21:29
166 |  |  |  | DR-023-113 | 1. MAINTENANCE RECORD WORK SHOP SEPTEMBER 2024 | 2025-05-07 21:29
167 |  |  |  | DR-023-114 | Spill Kits Checklist | 2025-05-07 21:29
168 |  |  |  | DR-023-115 | LIST OF CHEMICAL REPORT 322823 | 2025-05-07 21:29
169 |  |  |  | DR-023-116 | Drinking Water Checklist | 2025-05-07 21:29
170 |  |  |  | DR-023-117 | Waste Management Checklist | 2025-05-07 21:29
171 | DR-024 | Environmental Compliance Report | DevCo
172 | DR-025 | Register of Authority Engagement, Approvals and Waivers | DevCo
173 | DR-026 | Stakeholder Management Plan (including Stakeholder Management Tracker) | DevCo
174 | DR-027 | Baseline ESG Strategy and Latest Annual ESG Report | DevCo
175 | DR-028 | Construction Environmental and Social Management Plan (including Environmental Permit Register) | Project
176 | DR-029 | Construction Execution Plan | Project
177 | DR-030 | Site and Logistics Plan (including traffic simulations) | Project
178 | DR-031 | Interface Management Plan (including Stakeholder Management Plan*, Communication Plan & Contractor Staging Plan and Commissioning, Handover & Close-out Plan) | DevCo
179 | DR-032 | Workforce Planning Strategy | DevCo | DR-032 | IMS_Report-Dec'24-R2 | 2025-05-07 21:29
180 | DR-033 | Construction Progress Report (including workforce numbers) | Project
181 | DR-034 | Register of Technical Queries | Project
182 | DR-035 | Register of Shop Drawing Reviews | Project
183 | DR-036 | Register of Material & Product Approval / Product Substitution or Change Requests | Project
184 | DR-037 | Register of As-Built Drawings | Project
185 | DR-038 | Register of Material Inspection Requests | Project
186 | DR-039 | Register of Work Inspection Requests | Project
187 | DR-040 | Quality Management Manual (QMP) | DevCo
188 | DR-041 | Latest Monthly Quality Report, including defects and NCR data | DevCo
189 | DR-042 | Inspection Test Plan (ITP) | Project
190 | DR-043 | Sample of project specific Project Quality Plan (PQP) | Project
191 | DR-044 | Latest Quality Audit Report | Project
192 | DR-045 | Procurement Management Plan (including annual procurement lookahead and pre-qualified vendor database) | DevCo | DR-045-01 | DR-045a Procurement Executive Dashboard | 2025-05-07 21:29
193 |  |  |  | DR-045-02 | DR-045b-PQQ & Shortlist Process Map | 2025-05-07 21:29
194 | DR-046 | Sample of Tender Award Report | Project
195 | DR-047 | Procurement and Contracting Risk Register | DevCo
196 | DR-048 | List of Appointed Vendors (including due-diligence checks) | DevCo | DR-048-01 | PSPR Extract Appendices | 2025-05-07 21:29
197 |  |  |  | DR-048-02 | PSPR Extract | 2025-05-07 21:29
198 | DR-049 | Supply Chain Risk Assessment | DevCo | DR-049 | Portfolio Risk and Issue Register Procurement-Extract | 2025-05-07 21:29
199 | DR-050 | Current Procurement Schedule | DevCo | DR-050 | DR-050 12 Month Forecast | 2025-05-07 21:29
200 | DR-051 | Sample of Signed Agreement / Awarded Contract | Project
201 | DR-052 | Sample of Supplier and Contractor Performance Report | DevCo | DR-052-01 | Jacobs Performance | 2025-05-07 21:29
202 |  |  |  | DR-052-02 | Salini Performance | 2025-05-07 21:29
203 | DR-053 | Contract Execution Register (including Letter of Award and Letter of Commencement) | DevCo | DR-053 | LOA_Contract_New_Tracker_Extract | 2025-05-07 21:29
204 | DR-054 | Claims Register | DevCo | DR-054 | Claims Register Extract Sample | 2025-05-07 21:29
205 | DR-055 | Post Tender Clarification (PTC) Register | DevCo | DR-055-01 | DR-055a Tender Report PTC excerpt - PTC log | 2025-05-07 21:29
206 |  |  |  | DR-055-02 | DR-055b Tender Report PTC excerpt log signed | 2025-05-07 21:29
207 | DR-056 | Payment Register | DevCo | DR-056 | Payments Tracker 31.12.2024 | 2025-05-07 21:29
208 | DR-057 | HSE Management Manual | DevCo | DR-057-01 | DD-SWD-SW-SWD-000-000-DGD-MAN-HS-000001 (05)_DGCL Construction Occupational Health and Safety Manual | 2025-05-07 21:29
209 |  |  |  | DR-057-02 | DG-DSQ-000-0000-SSA-PLN-HS-000001(04) (3) Approved SSA HSE Plan | 2025-05-07 21:29
210 |  |  |  | DR-057-03 | Oberoi Hotel - HSE Management Plan - WS-WSH-685-0000-USC-PLN-HS-000001 | 2025-05-07 21:29
211 |  |  |  | DR-057-04 | DG-BUJ-106-0000-NSM-PLN-HS-000015 Rev.01 | 2025-05-07 21:29
212 |  |  |  | DR-057-05 | DG-BUJ-106-0000-NSM-PLN-HS-000019 Rev.01 | 2025-05-07 21:29
213 | DR-058 | HIRAC Methodology & Safety Risk Register | DevCo | DR-058-01 | DG-BUJ-106-0000-NSM-RPT-HS-000045 - Zallal | 2025-05-07 21:29
214 |  |  |  | DR-058-02 | DG-DSQ-000-0000-SSA-PLN-HS-000001(04) (3) Approved SSA HSE Plan | 2025-05-07 21:29
215 | DR-059 | Emergency Evacuation & Preparedness Plan | Project
216 | DR-060 | Latest Monthly HSE Report | DevCo | DR-060-01 | DG-DSQ-000-0000-SSA-RPT-HS-000001(07) | 2025-05-07 21:29
217 |  |  |  | DR-060-02 | Zallal Monthly OH&S Trend Analysis Report January 2025 | 2025-05-07 21:29
218 |  |  |  | DR-060-03 | Zallal-OHS Monthly KPIs-Jan- 2025 | 2025-05-07 21:29
219 | DR-061 | Latest HSE Audit Report | DevCo | DR-061-01 | Monthly PCI - Oberoi Hotel - April 2025 | 2025-05-07 21:29
220 |  |  |  | DR-061-02 | PCI - AGA-P3-6-7 Apr 2025 Score (signed) - DSQ | 2025-05-07 21:29
221 |  |  |  | DR-061-03 | PCI -Jan 2025 | 2025-05-07 21:29
222 |  |  |  | DR-061-04 | PCI SCAR Report Jan 2025 | 2025-05-07 21:29
223 |  |  |  | DR-061-05 | Zallal-PCI Jan 2025-Signed | 2025-05-07 21:29
224 | DR-062 | Latest Monthly Welfare Monitoring Report | DevCo | DR-062-01 | DG-DSQ-316-0000-AEC-RPT-HS-001081 (00) | 2025-05-07 21:29
225 |  |  |  | DR-062-02 | Zallal Mixed Use- Monthly Welfare Facilities and Transportation Focus Inspection - 19-10-2024 | 2025-05-07 21:29
226 |  |  |  | DR-062-03 | Camp Inspection Report-Oberoi Hotel -April 2025 | 2025-05-07 21:29
227 |  |  |  | DR-062-04 | Focus Inspection Checklist - Drinking & Ablution Water-12022025 | 2025-05-07 21:29
228 |  |  |  | DR-062-05 | Welfare Focused Inspection - Oberoi Hotel - April 2025 | 2025-05-07 21:29
229 | DR-063 | Welfare Management Manual (including Vendor Management & Monitoring Program) | DevCo | DR-063-01 | 04- Contractors Workers’ Quality of Life and Accommodations Procedures- 2024 - DSQ | 2025-05-07 21:29
230 |  |  |  | DR-063-02 | DG-BUJ-106-0000-NSM-PLN-HS-000021 Rev.02 - Zallal | 2025-05-07 21:29
231 | DR-064 | Latest Welfare Audit Report | DevCo | DR-064-01 | Accommodation Camp Audit Inspection Report-14 Oct 2024 - Zallal | 2025-05-07 21:29
232 |  |  |  | DR-064-02 | Alpha - Accommodation Camp Audit Inspection Report April 2025 | 2025-05-07 21:29
233 |  |  |  | DR-064-03 | Azzam - Accommodation Camp Audit Inspection Report April 2025 | 2025-05-07 21:29
234 |  |  |  | DR-064-04 | Salboukh - Accommodation Camp Audit Inspection Report April 2025 | 2025-05-07 21:29
235 |  |  |  | DR-064-05 | Camp Inspection Report-Oberoi Hotel -April 2025 | 2025-05-07 21:29
236 |  |  |  | DR-064-06 | Focus Inspection Checklist - Drinking & Ablution Water-12022025 | 2025-05-07 21:29
237 | DR-065 | Quarterly/annual progress reports for preceding three years (including approved budget, contingency utilization and change requests / claims) | DevCo | DR-065 | Cost Data Template_Diriyah (Dec24) | 2025-05-07 21:29
238 | DR-066 | Provisional Sums Status | DevCo
239 | DR-067 | Innovation Strategy | DevCo | DR-067-01 | 250430_DevCo's innovation strategic approach_vs | 2025-05-07 21:29
240 | DR-068 | Smart City Strategy | DevCo | DR-068 | Smart Diriyah overarching strategy (Executive summary) v2 | 2025-05-07 21:29
241 | DR-069 | Innovation/ smart city impact assessment Report | DevCo
242 | DR-070 | Sample of final master plan showing innovation/ Smart city considerations | Project
243 | DR-071 | Register of Innovation & Technology pilots and R&D projects along with progress tracker | DevCo
244 | DR-072 | Technical functions' strategy and initiatives | DevCo | DR-072-01 | 20250318_Business plan BoD deck_vDevco.pdf | 2025-05-07 21:29
245 |  |  |  | DR-072-02 | 241027_DevCo_onboarding_v35 (without video) | 2025-05-07 21:29
246 |  |  |  | DR-072-03 | DevCo development capacity_v29 (for PIF) | 2025-05-07 21:29
247 | DR-073 | Latest report which includes the progress of technical strategy initiatives | DevCo | DR-073 | 250503_Portfolio wide projects | 2025-05-07 21:29
248 | DR-074 | List of technical functions’ KPIs (including baseline and targets) | DevCo | DR-074 | Performance Management Handbook v37.1 | 2025-05-07 21:29
249 | DR-075 | Latest report which includes the progress of achievement of technical functions’ KPIs | DevCo | DR-075 | E-Annual plan components and details v1 | 2025-05-07 21:29
250 | DR-076 | Approved and as-is org structure, including staffed/unstaffed positions, roles & responsibilities | DevCo | DR-076-01 | Busness Development | 2025-05-07 21:29
251 |  |  |  | DR-076-02 | Commercial Leasing | 2025-05-07 21:29
252 |  |  |  | DR-076-03 | Commercial | 2025-05-07 21:29
253 |  |  |  | DR-076-04 | Design | 2025-05-07 21:29
254 |  |  |  | DR-076-05 | DevCo Organization Chart | 2025-05-07 21:29
255 |  |  |  | DR-076-06 | Development DG1 | 2025-05-07 21:29
256 |  |  |  | DR-076-07 | Development DG2 | 2025-05-07 21:29
257 |  |  |  | DR-076-08 | Development WS | 2025-05-07 21:29
258 |  |  |  | DR-076-09 | Materplanning | 2025-05-07 21:29
259 |  |  |  | DR-076-10 | OHSS Str 29.4.25 | 2025-05-07 21:29
260 |  |  |  | DR-076-11 | Projects | 2025-05-07 21:29
261 |  |  |  | DR-076-12 | Retail Leasing | 2025-05-07 21:29
262 |  |  |  | DR-076-13 | Sales | 2025-05-07 21:29
263 | DR-077 | Strategic DevCo technical workforce planning report, including capacity and competency planning | DevCo | DR-077 | DevCo Workforce | 2025-05-07 21:29
264 | DR-078 | Register of Approved technical-related policies and procedures | DevCo
265 | DR-079 | Register of technical platforms | DevCo
Go to P&M
Go to D&T
Go to D&C
Go to CE&O
Go to I&T
Go to S&O
Go to Main Page
Add Document
Delete Document

## DevCoAssessmentInput(P&M)
PIF Project Lighthouse
DevCoAssessmentInput(P&M)
Assessment Criteria | Data Point | Input Value | Data Source | Assessor Remarks | Assessment Time Stamp | Reviewer Remarks | Review Time Stamp | Formula
DevCo Schedule Performance Index (SPI) | Planned Value (PV) | 55.49 | DR-002-01 | Values in Billion SAR ( From the P6 file provided excluding DG-ii) |  |  |  | Earned Value (EV) / Planned Value (PV) | 1 | 3
| Earned Value (EV) | 36.6 | DR-002-01 | Values in Billion SAR ( From the P6 file provided excluding DG-ii) | [5 empty] | 4
% milestone achievement in accordance with the approved business plan | No. of planned milestones | 1050 | DR-002-01 | From the P6 file provided. (excludes DG-ii) |  |  |  | No. of milestones achieved on time/ No. of planned milestones | 2 | 6
| No. of milestones achieved on time | 945 | DR-002-01 | From the P6 file provided. (excludes DG-ii) | [5 empty] | 7
% of projects with approved change requests in design phase since inception with time impact of more than 1 month | Total number of projects in design phase | 118 |  | From the P6 file provided as on Dec 2024 cut off date. |  |  |  | Number of projects with approved change requests in design phase since inception with time impact of more than 1 month / Total number of projects in design phase | 3 | 11
| Number of projects with approved change requests in design phase since inception with time impact of more than 1 month | 4 |  | From DR-54 , Claims Register. EOTs resulting due to design changes are considered. | [5 empty] | 12
% of projects with approved change requests in construction phase since inception with time impact of more than 4 months | Total number of projects in construction phase | 69 |  | From the P6 file provided as on Dec 2024 cut off date and the GCEO report |  |  |  | Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months / Total number of projects in construction phase | 4 | 14
| Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months | 13 |  | From DR-54 , Claims Register.EOTs resulting due to Construction changes are considered | [5 empty] | 15
% of projects with approved schedule extension | No. of Approved EOTs | 32 |  | From DR-54 , Claims Register |  |  |  | (Number of Projects with Approved Schedule Extension)/Total Number of Projects) | 5 | 17
| No. of projects with schedule extension (design stage) | 6 |  | From DR-54 , Claims Register. EOTs resulting due to design changes are considered. | [5 empty] | 18
| No. of projects with schedule extension (construction stage) | 8 |  | From DR-54 , Claims Register.EOTs resulting due to Construction changes are considered | [5 empty] | 19
% of projects with Forecast completion date beyond the latest approved schedule | Number of projects with forecast completion date beyond the latest approved schedule | 86 |  | From the P6 file provided and the GCEO report |  |  |  | Number of projects with forecast completion date beyond the latest approved schedule / [Total number of projects in design phase + Total number of projects in construction phase] | 6 | 20
Is the Forecast Finish Date at a given data date based on the alignment and buy-in from project teams and other listed stakeholders? | Total list of stakeholders and their commitment to the forecast finish date (Text) | Yes, but inadequate |  | Based on workshops with the DevCo, it is understood that the submitted progress reports have undergone multiple levels of scrutiny and approval in line with their RACI, and the assessments have been carried out accordingly |  |  |  | "Satisfactory Score" if key project stakeholders (engineering, procurement, construction, client teams) were formally briefed, discussed on the forecast date includ any foreseen risks but no formal sign off doc on the forecast finish date is available | 7 | 21
Based on the risks identified and approved change requests, has the DevCo conducted a sensitivity assessment on the forecast completion at a given data date? | Identified risks with probability and impact ratings and Historical Project Performance (SPI, past variances, Productivity Trends) | Yes, but inadequate |  | Devco has provided a risk register with risks identified but doesn’t mention the portfolios. And Change request register not provided. |  |  |  | "Satisfactory" if new activities as per the risks identified and discussions with stakeholders are added in the revised programme but do not have logical relationships and there is no comparison of the critical path analysis before and after date change | 8 | 22
Has DevCo allocated risk contingency for the identified risks? | Risk severity and Risk mapping | Yes, but inadequate |  | contigency in P6 file cannot be validated in reference to the risk register. The risk register does not explicitly mention the schedule impact in days/months. against the identified risks. |  |  |  | Satisfactory Score if - Contingency allocated but not aligning with the risk severity as per the heat map | 9 | 24
Was there any deferment in the project completion date due to unidentified risks? | Source of the unidentified risk | Data Not Available |  | contigency in P6 file cannot be validated in reference to the risk register. The risk register does not explicitly mention the schedule impact in days/months. against the identified risks. |  |  |  | Satisfactory Score if - the deferment was less than 1 month | 10 | 25
Was there any Cost Overrun because of identified risk? | % of cost overrun from the latest approved budget due to identified risk | Yes, but less than 5% | DR-003-01 | Values under additional risk and BOD budget (TDC) in the commercial updated report are considered for this evaluation |  |  |  | Satisfactory Score if - the cost overrun was less than 5% | 11 | 26
Was there any Cost Overrun because of unidentified risk? | % of cost overrun from the latest approved budget due to unidentified risk | Data Not Available |  | The risk register and other related documents does not speak about the unidentified risk. |  |  |  | Satisfactory Score if - the cost overrun was less than 1% | 12 | 27
Risk Control Rate of the identified risks at DevCo Level | Number of controlled risks | 123 | [5 empty] | Number of Controlled Risks / Total number of identified risks | 13 | 32
| Total number of identified risks | 123 | [7 empty] | 33
Is the DevCo fully compliant with Risk Management Plan requirements? | Risk Manager or Risk Committee overseeing risk governance | Yes, but inadequate | [5 empty] | Satisfactory Score if - the risks were identified, mitigations planned but not communicated to all the relevant stakeholders. And the risk register is updated | 14 | 34
Is there a difference in the time impact forecast before and after the risk event has triggered? | Difference between anticipated and actual effects on time and cost, after the risk event triggered | Data Not Available |  | As there is no information on the programme tracker, this criteria cannot be assessed |  |  |  | Satisfactory Score if - the time impact is less than 2 weeks for Design phase completion and less than 1 month of Construction Phase Completion | 15 | 35
Is there a difference in the Cost impact forecast before and after the risk event has triggered? | Reasons on the difference between anticipated and actual effects on time and cost | Data Not Available |  | As there is no information on the programme tracker, this criteria cannot be assessed |  |  |  | Satisfactory Score if - the cost impact is less than 0.5% of the identified risk costing | 16 | 36
Go to Main Page
Go to Document
Go to Analysis
Note on A6: PM-AC-001
Note on B6: PM-DP-003
Note on B7: PM-DP-004
Note on A8: PM-AC-002
Note on B8: PM-DP-006
Note on B9: PM-DP-007
Note on A10: PM-AC-003
Note on B10: PM-DP-011
Note on B11: PM-DP-012
Note on A12: PM-AC-004
Note on B12: PM-DP-014
Note on B13: PM-DP-015
Note on A14: PM-AC-005
Note on B14: PM-DP-017
Note on B15: PM-DP-018
Note on B16: PM-DP-019
Note on A17: PM-AC-006
Note on B17: PM-DP-020
Note on A18: PM-AC-007
Note on B18: PM-DP-021
Note on A19: PM-AC-008
Note on B19: PM-DP-022
Note on A20: PM-AC-009
Note on B20: PM-DP-024
Note on A21: PM-AC-010
Note on B21: PM-DP-025
Note on A22: PM-AC-011
Note on B22: PM-DP-026
Note on A23: PM-AC-012
Note on B23: PM-DP-027
Note on A24: PM-AC-013
Note on B24: PM-DP-032
Note on B25: PM-DP-033
Note on A26: PM-AC-014
Note on B26: PM-DP-034
Note on A27: PM-AC-015
Note on B27: PM-DP-035
Note on A28: PM-AC-016
Note on B28: PM-DP-036

## DevCoAssessmentAnalysis(P&M)
PIF Project Lighthouse
DevCoAssessmentAnalysis(P&M)
Assessment Criteria | Data Point | Value | Rating | Score | Assessment Criteria Weightage | Assessment Guideline/Formula | Good | Satisfactory | Needs Improvement | Remarks 1 | Performance Signal | Performance Signal Score | Performance Signals Weightage | Remarks 2 | Key Topic | Key Topic Score | Remarks 3
DevCo Schedule Performance Index (SPI) | Planned Value (PV) (No.) | 0.65958 | Needs Improvement | 33% | 70% | Earned Value (EV) / Planned Value (PV) | >1 | 0.85-1 | <0.85 | Evaluation from the P6 file provided (excludes DG-ii). In the event that PIF does not receive DGii data from the Devco, the value in Column C can be revised by proportionately reducing it by 38%, which corresponds to DGii’s weightage in the overall approved TDC | Schedule Adherence | 53% | 50% |  | Overall Progress | 65% |  | 1 | 3
| Earned Value (EV) (No.) | [17 empty] | 4
% milestone achievement in accordance with the approved business plan | No. of planned milestones (No.) | 90% | Good | 100% | 30% | No. of milestones achieved on time/ No. of planned milestones | >70% | 50-70% | <50% | Remarks same as above | [7 empty] | 2 | 6
| No. of milestones achieved on time (No.) | [17 empty] | 7
% of projects with approved change requests in design phase since inception with time impact of more than 1 month | Total number of projects in design phase (No.) | 3.39% | Good | 100% | 40% | Number of projects with approved change requests in design phase since inception with time impact of more than 1 month / Total number of projects in design phase | <30% | 30-70% | >70% | Response from Devco against the request for Change Request Register. However, considering the data from the DR-054 i.e Claim register , assessment is done. | Schedule Extension | 100% | 30% |  |  |  |  | 3 | 11
| Number of projects with approved change requests in design phase since inception with time impact of more than 1 month (No.) | [17 empty] | 12
% of projects with approved change requests in construction phase since inception with time impact of more than 4 months | Total number of projects in construction phase (No.) | 18.84% | Good | 100% | 40% | Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months / Total number of projects in construction phase | <30% | 30-70% | >70% | Remarks same as above | [7 empty] | 4 | 14
| Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months (No.) | [17 empty] | 15
% of projects with approved schedule extension | No. of Approved EOTs (No.) | 17.11% | Good | 100% | 20% | (Number of Projects with Approved Schedule Extension)/Total Number of Projects) | <20% | 20-40% | >40% | Response from Devco against the request forProgramme Tracker.However, considering the data from the DR-054 i.e Claim register , assessment is done. | [7 empty] | 5 | 17
| No. of projects with schedule extension (design stage) (No.) | [17 empty] | 18
| No. of projects with schedule extension (construction stage) (No.) | [17 empty] | 19
% of projects with Forecast completion date beyond the latest approved schedule | Number of projects with forecast completion date beyond the latest approved schedule (No.) | 45.99% | Needs Improvement | 33% | 60% | Number of projects with forecast completion date beyond the latest approved schedule / [Total number of projects in design phase + Total number of projects in construction phase] | <20% | 20-40% | >40% | Evaluation from the P6 file provided and the GCEO report. | Schedule Achievability | 46% | 20% |  |  |  |  | 6 | 20
Is the Forecast Finish Date at a given data date based on the alignment and buy-in from project teams and other listed stakeholders? | Total list of stakeholders and their commitment to the forecast finish date (Text) | Yes, but inadequate | Satisfactory | 66% | 20% | "Satisfactory Score" if key project stakeholders (engineering, procurement, construction, client teams) were formally briefed, discussed on the forecast date includ any foreseen risks but no formal sign off doc on the forecast finish date is available | Yes | Yes, but inadequate | No | [8 empty] | 7 | 21
Based on the risks identified and approved change requests, has the DevCo conducted a sensitivity assessment on the forecast completion at a given data date? | Identified risks with probability and impact ratings and Historical Project Performance (SPI, past variances, Productivity Trends) (Text) | Yes, but inadequate | Satisfactory | 66% | 20% | "Satisfactory" if new activities as per the risks identified and discussions with stakeholders are added in the revised programme but do not have logical relationships and there is no comparison of the critical path analysis before and after date change | Yes | Yes, but inadequate | No | Devco has submitted a risk register with risks identified and treatment strategies but the risks are not linked to portfolio/projects/districts and also a schedule impact in terms of days/weeks/months are not provided. Considering the status of the risks(closed/open) and the GCEO report the scoring for the criteria is provided. | [7 empty] | 8 | 22
Has DevCo allocated risk contingency for the identified risks? | Risk severity and Risk mapping (Text) | Yes, but inadequate | Satisfactory | 66% | 20% | Satisfactory Score if - Contingency allocated but not aligning with the risk severity as per the heat map | Yes | Yes, but inadequate | No | Remarks same as above | Risk Governance | 49% | 60% |  | Risk Performance | 55% |  | 9 | 24
Was there any deferment in the project completion date due to unidentified risks? | Source of the unidentified risk (Text) | Data Not Available | Needs Improvement | 33% | 30% | Satisfactory Score if - the deferment was less than 1 month | No | Yes, but less than 1 month | Yes | The updated risk register provided does not mention about any unidentified risks. | [7 empty] | 10 | 25
Was there any Cost Overrun because of identified risk? | % of cost overrun from the latest approved budget due to identified risk (Text) | Yes, but less than 5% | Satisfactory | 66% | 30% | Satisfactory Score if - the cost overrun was less than 5% | No | Yes, but less than 5% | Yes | Assessment done based on the Commerical Report | [7 empty] | 11 | 26
Was there any Cost Overrun because of unidentified risk? | % of cost overrun from the latest approved budget due to unidentified risk (Text) | Data Not Available | Needs Improvement | 33% | 20% | Satisfactory Score if - the cost overrun was less than 1% | No | Yes, but less than 1% | Yes | The updated risk register provided does not mention about any unidentified risks. | [7 empty] | 12 | 27
Risk Control Rate of the identified risks at DevCo Level | Number of controlled risks (No.) | 100% | Good | 100% | 40% | Number of Controlled Risks / Total number of identified risks | >70% | 40-70% | <40% |  | Realized Risk Status | 66% | 40% |  |  |  |  | 13 | 32
| Total number of identified risks (No.) | [17 empty] | 33
Is the DevCo fully compliant with Risk Management Plan requirements? | Risk Manager or Risk Committee overseeing risk governance (Text) | Yes, but inadequate | Satisfactory | 66% | 20% | Satisfactory Score if - the risks were identified, mitigations planned but not communicated to all the relevant stakeholders. And the risk register is updated | Yes | Yes, but inadequate | No | Scoring is satifactory because the Devco has not provided any details on the cost impact for the identified risks. | [7 empty] | 14 | 34
Is there a difference in the time impact forecast before and after the risk event has triggered? | Difference between anticipated and actual effects on time and cost, after the risk event triggered (Text) | Data Not Available | Needs Improvement | 33% | 20% | Satisfactory Score if - the time impact is less than 2 weeks for Design phase completion and less than 1 month of Construction Phase Completion | No | Yes, but less than 2 weeks | Yes | The assessment is primarily based on the completeness of the risk register and its impact on the schedule, which is currently unavailable. However, since the baseline and forecast completion dates are aligned, the scoring may be reconsidered. | [7 empty] | 15 | 35
Is there a difference in the Cost impact forecast before and after the risk event has triggered? | Reasons on the difference between anticipated and actual effects on time and cost (Text) | Data Not Available | Needs Improvement | 33% | 20% | Satisfactory Score if - the cost impact is less than 0.5% of the identified risk costing | No | Yes, but less than 0.5% | Yes | IMS including DG ii is required to understand if there was any risk event having a schedule impact. | [7 empty] | 16 | 36
Go to Main Page
Go to Document
Go to Input
Note on A6: PM-AC-001
Note on B6: PM-DP-003
Note on B7: PM-DP-004
Note on A8: PM-AC-002
Note on B8: PM-DP-006
Note on B9: PM-DP-007
Note on A10: PM-AC-003
Note on B10: PM-DP-011
Note on B11: PM-DP-012
Note on A12: PM-AC-004
Note on B12: PM-DP-014
Note on B13: PM-DP-015
Note on A14: PM-AC-005
Note on B14: PM-DP-017
Note on B15: PM-DP-018
Note on B16: PM-DP-019
Note on A17: PM-AC-006
Note on B17: PM-DP-020
Note on A18: PM-AC-007
Note on B18: PM-DP-021
Note on A19: PM-AC-008
Note on B19: PM-DP-022
Note on A20: PM-AC-009
Note on B20: PM-DP-024
Note on A21: PM-AC-010
Note on B21: PM-DP-025
Note on A22: PM-AC-011
Note on B22: PM-DP-026
Note on A23: PM-AC-012
Note on B23: PM-DP-027
Note on A24: PM-AC-013
Note on B24: PM-DP-032
Note on B25: PM-DP-033
Note on A26: PM-AC-014
Note on B26: PM-DP-034
Note on A27: PM-AC-015
Note on B27: PM-DP-035
Note on A28: PM-AC-016
Note on B28: PM-DP-036

## InterviewQuestion(P&M)
PIF Project Lighthouse
InterviewQuestion(P&M)
SN | Question | Date of Interview | Response | Internal Comment | Follow Up Question
1 | In case the project is behind schedule, is there a recovery program to address the delay? | 2025-05-09 16:05
2 | What factors led to approve the change(s) in the completion date (design/construction/stakeholder approvals)? | 2025-05-09 16:05
3 | Using a sample project, please show how an in-depth analysis was conducted to ensure how realistic the remaining duration of the project planned/ forecasted was, critical path defined, considering resource availability, project constraints, and risk factors in order to avoid likelihood of schedule slippages & cost overruns. | 2025-05-09 16:05
4 | Did the approved schedule consider the risks identified during the Risk Assessment stage? | 2025-05-09 18:10
5 | What percentage of projects have an approved risk register? | 2025-05-09 16:05
6 | What percentage of risk associated costs is a part of total budget? | 2025-05-09 16:05
7 | After the risk event triggered, was there a difference between the anticipated and actual effects on time and cost? If so, what were the reasons and what is the plan to reduce the further overrun. | 2025-05-09 16:05
Go to Main Page

## AddDataPoint(P&M)
PIF Project Lighthouse
AddDataPoint(P&M) | [5 empty] | Schedule Chart |  |  |  | Top 10 Risks | [5 empty] | Top 5 Risk Categories |  | Project Overview
SN | Data Source | Additional Data Point | Input Value | Scorecard Visualization |  | Year | Value Completed (Baseline) in M SAR | Value Completed (Actual) in M SAR | Value Completed (Forecast) in M SAR | Risk | Source | Potential Impact | Risk Rating | Risk Status | Current Measures | Risk Category | Number of Risk Items | ProjectID | ForecastCompletionYear | ProjectType | ProjectStage | Criticality | DelayInSchedule | CostOverrun | Priority | ProjectValue
1 |  | Latest Approved Completion Date​ | 31/05/2029 | Used for Dashboard | 1 | 2025 |  |  |  | Risk 1 | [5 empty] | Risk 1 |  | Project A | Completed | Residential | Design | Priority | Yes | No | Yes | 1.5
2 |  | Forecast Completion Date​ | 2029-01-06 | Used for Dashboard | 2 | 2026 |  |  |  | Risk 2 | [5 empty] | Risk 2 |  | Project B | 2027 | Commercial | Construction | Standard | No | Yes | No | 1
3 |  | Approved baseline completion date | 31/05/2029 | Used for Dashboard | 5 | 2027 |  |  |  | Risk 3 | [5 empty] | Risk 3 |  | Project C | Completed | Mixed Use | Initiation | Priority | No | No | No | 2
4 |  | Planned duration up to a specific phase as per approved Baseline programme |  | Used for Dashboard | 8 | 2028 |  |  |  | Risk 4 | [5 empty] | Risk 4 |  | Project D | 2030 | Residential | Construction | Standard | Yes | Yes | Yes | 1.5
5 |  | Duration taken to complete works up to the specific phase |  | Used for Dashboard | 9 | 2029 |  |  |  | Risk 5 | [5 empty] | Risk 5 |  | Project E | 2028 | Hospitality | Design | Priority | No | No | No | 3
6 |  | Recovery Plan | Not Available | Used for Dashboard | 10 |  |  |  |  | Risk 6
7 |  | Extent of all EOT (design stage) | Not Available | Used for Dashboard | 13 |  |  |  |  | Risk 7
8 |  | Extent of all EOT (const. stage) | Not Available | Used for Dashboard | 16 |  |  |  |  | Risk 8
9 |  | Schedule Chart (Value Completed Baseline, Value Completed Actual, Value Completed Forecast) (No.) |  | Used for Dashboard (Manual) | 23 |  |  |  |  | Risk 9
10 |  | No. of unresolved issues |  | Used for Dashboard | 28 |  |  |  |  | Risk 10
11 |  | No. of (Open) Inherent Risks | 51 | Used for Dashboard | 29
12 |  | No. of (Closed) Residual Risks | 65 | Used for Dashboard | 30
13 |  | Project-level risks (including low, medium, and high severity) | available | Used for Dashboard | 31
14 |  | Extra Cost due to Unresolved Issues | Not Available | Used for Dashboard | 37
15 |  | Top 10 Risks (Risk, Source, Potential Impact, Risk Rating, RIsk Status, Current Measures) (Text) |  | Used for Dashboard (Manual) | 38
16 |  | Top 5 Risk Categories (RIsk Category, Number of RIsk Items) (Text) |  | Used for Dashboard (Manual) | 39
Note on C6: PM-DP-001
Note on C7: PM-DP-002
Note on C8: PM-DP-005
Note on C9: PM-DP-008
Note on C10: PM-DP-009
Note on C11: PM-DP-010
Note on C12: PM-DP-013
Note on C13: PM-DP-016
Note on C14: PM-DP-023
Note on C15: PM-DP-028
Note on C16: PM-DP-029
Note on C17: PM-DP-030
Note on C18: PM-DP-031
Note on C19: PM-DP-037
Note on C20: PM-DP-038
Note on C21: PM-DP-039
Go to Main Page

## DevCoAssessmentInput(D&T)
PIF Project Lighthouse
DevCoAssessmentInput(D&T)
Assessment Criteria | Data Point | Input Value | Data Source | Assessor Remarks | Assessment Time Stamp | Reviewer Remarks | Review Time Stamp | Formula
Similarity between original/approved and latest CGI | Percentage similarity between Approved CGI and Latest CGI at same angle and scale | 90% | DR-011-01 | The sample projects show high level of similarity between the different design stage has been maintained. |  |  |  | Percentage similarity between Approved CGI and Latest CGI at same angle and scale | 1 | 1
Availability of animation with a close match at same angle | Availability of Approved Animation and Latest Animation with a close match, at the same camera angle (Text) | Partially Applied | DR-011-48 |  |  |  |  | Animation is available with a close match at same angle | 2 | 2
Does the Latest Material Palette & Finish Schedule support the look of the Approved CGI? | Material Palette & Finish Schedule | 70% | DR-011-01 | The sample projects show high level of similarity between the different design stage has been maintained. However, tracking for the changes is not provided. |  |  |  | Material Palette & Finish Schedule matched Approved CGI | 3 | 3
Does the DevCo have Design & Technical Guidelines (including Look & Feel Design Guidelines)? | Design and Technical Guidelines | Yes | DR-013-01 |  |  |  |  | The Design and Technical Guidelines exist | 4 | 4
Do DevCo projects comply with DDTG? | Look & Feel Guideline | Yes | DR-012-01 |  |  |  |  | Material Palette & Finish Schedule aligns with Look & Feel Guideline | 5 | 5
% variance from approved Built-Up Area (BUA) or Gross Floor Area (GFA) | Latest BUA | 9352242 | DR-012-01 |  |  |  |  | (Latest BUA/GFA - Approved BUA/GFA) / Approved BUA/GFA | 6 | 6
| Approved BUA | 9085728 | DR-012-01 | [6 empty] | 7
% variance in land use permit area | Latest Land Area | 68302884 | DR-012-01 |  |  |  |  | (Latest Land Area - Approved Land Area) / Approved Land Area | 7 | 8
| Approved Land Area | 72152766 | DR-012-01 | [6 empty] | 9
% variance from approved population | Latest Population | 85346 | DR-012-01 |  |  |  |  | (Latest Population - Approved Population) / Approved Population | 8 | 10
| Approved Population | 88091 | DR-012-01 | [6 empty] | 11
Have all DevCos completed a Constructability assessment for complex/iconic projects? | Constructability Report (Text) | Partially Applied | DR-014-08 |  |  |  |  | Constructability assessment exists | 9 | 12
Was design for Enabling Work Package considerd as part of the design process to ensure the readiness of the site for the main construction work? | Assessment of enabling works required | Partially Applied | DR-015-01 |  |  |  |  | Consideration of design for enabling work package | 10 | 13
Are documentation packages meeting the LOD requirements of the latest Design Stage Gate? | LOD Required | 350 | DR-017-01 |  |  |  |  | LOD Documented matches LOD Required | 11 | 14
| LOD Documented (drawing sample from Design Report) | 350 | DR-017-01 | [6 empty] | 15
Have all projects adopted digital delivery using BIM and/or GIS? | Projects adopting digital delivery using BIM/GIS (Text) | Yes | DR-017-01 |  |  |  |  | BIM Documentation exists | 12 | 16
Is project delivery occurring in accordance with the latest approved design strategy? | Approved Design Strategy (Text) | No | [5 empty] | Review Latest Approved Design Strategy and compare with the Stage Gate Design Report | 13 | 17
% of projects with completed technical design/peer reviews and verifications/certifications as required for the latest Design Stage Gate | % of projects with completed design reviews and verification register (%) | 80% | DR-020-01 |  |  |  |  | Check the Design Review & Verification Register, assess if correct number of Design Reviews have occurred in accordance with the Design Management Report | 14 | 18
Availability of robust design management plan and appropriate design review trackers/registers | Design Management Plan and Design Review Trackers/Registers (Text) | Yes | DR-020-01 |  |  |  |  | Does DevCo have robust design management plan and appropriate design review trackers/registers | 15 | 19
Is the average cycle time to complete reviews and certifications in accordance with the Design Management Report? | Days taken to complete Design Reviews | Partially Applied | [5 empty] | Average number of days between Design Review Submittals and Completion of the Design Reviews compared to the number of days required to complete the Design Reviews in accordance with the Design Management Report | 16 | 20
Has the DevCo engaged independent certification of major critical elements? | Level of review and verification required for Stage Gate | No | [5 empty] | Independent Certification exists | 17 | 21
Are the master DevCo designs integrated with Regional Infrastructure & Mobility Plans? | Regional Strategies | Yes | DR-012-01 |  |  |  |  | The Infrastructure and Engineering Report references the Regional Infrastructure & Mobility Plans and demonstrates adoption of Regional Strategies | 18 | 22
Do all projects comply with environmental guidelines in accordance with ESIA? | Extent of compliance to environmental guidelines | Partially Applied | DR-023-01 |  |  |  |  | Key Environmental Risks and Site Environmental Factors are covered in the Environmental Compliance Report | 19 | 23
% of projects with Code Compliance Violations | % of Code Compliance Violations (%) | 10% | [5 empty] | Total Number of Code Compliance Violations taken from the Code Compliance Assessment Report or from any other relevant documents | 20 | 24
Availability of proper Register of Authority Engagement, Approvals and Waivers | Register of Authority Engagement, Approvals and Waivers (Text) | Yes | DR-026-01 |  |  |  |  | Does DevCo have proper Register of Authority Engagement, Approvals and Waivers in place | 21 | 25
Have all required Stakeholder Submittals been issued as planned? | Stakeholder Submittal Date | Partially Applied | DR-026-01 |  |  |  |  | Stakeholder Submittal Dates are in accordance with the Stakeholder Management Plan, or planned submission date, to ensure approvals can be achieved in line with Stage Gate completion requirements | 22 | 26
Availability of robust Stakeholder Management Plan in place | Stakeholder Management Plan (Text) | Yes | DR-026-01 |  |  |  |  | Does DevCo have robust Stakeholder Management Plan in place | 23 | 27
Does the Stakeholder Engagement Plan include proactive communication process to ensure timely coordination and approvals? | Scheduled Design Stage Gate Completion | Yes | DR-026-01 |  |  |  |  | Proactive communication in Stakeholder Engagement Plan | 24 | 28
Availability of proper tracking and closure procedure for stakeholder comments | Stakeholder Comments Tracking and Closure Procedure (Text) | Partially Applied | [5 empty] | Does DevCo has proper tracking and closure procedure for stakeholder comments | 25 | 29
% of projects achieving DevCo ESG Targets | Planned ESG Target | Data Not Available | [5 empty] | Actual ESG Achievement / Planned ESG Target | 26 | 30
| Actual ESG Target | Data Not Available | [7 empty] | 31
Does the DevCo ESG Target align with globally recognized Best Practice Targets? | Alignment with globally recognized Best Practice Targets | Yes | DR-027 |  |  |  |  | Alignment with globally recognized Best Practice Targets | 27 | 32
Go to Main Page
Go to Document
Go to Analysis
Note on A6: DT-AC-001
Note on B6: DT-DP-001
Note on A7: DT-AC-002
Note on B7: DT-DP-002
Note on A8: DT-AC-003
Note on B8: DT-DP-003
Note on A9: DT-AC-004
Note on B9: DT-DP-004
Note on A10: DT-AC-005
Note on B10: DT-DP-005
Note on A11: DT-AC-006
Note on B11: DT-DP-006
Note on B12: DT-DP-007
Note on A13: DT-AC-007
Note on B13: DT-DP-008
Note on B14: DT-DP-009
Note on A15: DT-AC-008
Note on B15: DT-DP-010
Note on B16: DT-DP-011
Note on A17: DT-AC-009
Note on B17: DT-DP-012
Note on A18: DT-AC-010
Note on B18: DT-DP-013
Note on A19: DT-AC-011
Note on B19: DT-DP-014
Note on B20: DT-DP-015
Note on A21: DT-AC-012
Note on B21: DT-DP-016
Note on A22: DT-AC-013
Note on B22: DT-DP-017
Note on A23: DT-AC-014
Note on B23: DT-DP-018
Note on A24: DT-AC-015
Note on B24: DT-DP-019
Note on A25: DT-AC-016
Note on B25: DT-DP-020
Note on A26: DT-AC-017
Note on B26: DT-DP-021
Note on A27: DT-AC-018
Note on B27: DT-DP-022
Note on A28: DT-AC-019
Note on B28: DT-DP-023
Note on A29: DT-AC-020
Note on B29: DT-DP-024
Note on A30: DT-AC-021
Note on B30: DT-DP-025
Note on A31: DT-AC-022
Note on B31: DT-DP-026
Note on A32: DT-AC-023
Note on B32: DT-DP-027
Note on A33: DT-AC-024
Note on B33: DT-DP-028
Note on A34: DT-AC-025
Note on B34: DT-DP-029
Note on A35: DT-AC-026
Note on B35: DT-DP-030
Note on B36: DT-DP-031
Note on A37: DT-AC-027
Note on B37: DT-DP-032

## DevCoAssessmentAnalysis(D&T)
PIF Project Lighthouse
DevCoAssessmentAnalysis(D&T)
Assessment Criteria | Data Point | Value | Rating | Score | Assessment Criteria Weightage | Assessment Guideline /Formula | Good | Satisfactory | Needs Improvement | Remarks 1 | Performance Signal | Performance Signal Score | Performance Signals Weightage | Remarks 2 | Key Topic | Key Topic Score | Remarks 3
Similarity between original/approved and latest CGI and availability of animation with a close match at same angle | Percentage similarity between Approved CGI and Latest CGI at same angle and scale (%) | 90% | Good | 100% | 27% | Percentage similarity between Approved CGI and Latest CGI at same angle and scale | >70% | 50-70% | <50% |  | CGI and Animation Compliance | 92% | 50% |  | Vision Adherence | 96% |  | 1 | 1
Similarity between original/approved and latest CGI and availability of animation with a close match at same angle | Availability of Approved Animation and Latest Animation with a close match, at the same camera angle (Text) | Partially Applied | Satisfactory | 66% | 3% | Animation is available with a close match at same angle | Yes | Partially Applied | No | [8 empty] | 2 | 2
Material Palette & Finish Schedule | Material Palette & Finish Schedule (%) | 70% | Satisfactory | 66% | 20% | Material Palette & Finish Schedule matched Approved CGI | >70% | 50-70% | <50% | [8 empty] | 3 | 3
Does the DevCo have Design & Technical Guidelines (including Look & Feel Design Guidelines)? | Design and Technical Guidelines (Text) | Yes | Good | 100% | 20% | The Design and Technical Guidelines exist | Yes | Partially Applied | No | [8 empty] | 4 | 4
Do DevCo projects comply with DDTG? | Look & Feel Guideline (Text) | Yes | Good | 100% | 30% | Material Palette & Finish Schedule aligns with Look & Feel Guideline | >70% | 50-70% | <50% | [8 empty] | 5 | 5
% variance from approved Built-Up Area (BUA) | Latest BUA or GFA (No.) | 2.933% | Good | 100% | 30% | (Latest BUA/GFA - Approved BUA/GFA) / Approved BUA/GFA | <15% | 15-30% | >30% |  | Development Program Variance | 100% | 50% |  |  |  |  | 6 | 6
| Approved BUA or GFA (No.) | [17 empty] | 7
% variance in land use permit area | Latest Land Area (No.) | -5.336% | Good | 100% | 30% | (Latest Land Area - Approved Land Area) / Approved Land Area | <15% | 15-30% | >30% | [8 empty] | 7 | 8
| Approved Land Area (No.) | [17 empty] | 9
Approved Population | Latest Population (No.) | -3.116% | Good | 100% | 40% | (Latest Population - Approved Population) / Approved Population | <30% | 30-40% | >40% | [8 empty] | 8 | 10
| Approved Population (No.) | [17 empty] | 11
Have all DevCos completed a Constructability assessment for complex/iconic projects? | Constructability Report (Text) | Partially Applied | Satisfactory | 66% | 25% | Constructability assessment exists | Yes | Partially Applied | No |  | Construction Design Maturity | 83% | 100% |  | Design for Constructability | 83% |  | 9 | 12
Was design for Enabling Work Package considerd as part of the design process to ensure the readiness of the site for the main construction work? | Assessment of enabling works required (Text) | Partially Applied | Satisfactory | 66% | 25% | Consideration of design for enabling work package | Yes | Partially Applied | No | [8 empty] | 10 | 13
Are documentation packages meeting the LOD requirements of the latest Design Stage Gate? | LOD Required (Text) | Yes | Good | 100% | 25% | LOD Documented matches LOD Required | Yes | Partially Applied | No | [8 empty] | 11 | 14
| LOD Documented (drawing sample from Design Report) (Text) | [17 empty] | 15
Have all projects adopted digital delivery using BIM and/or GIS? | Projects adopting digital delivery using BIM/GIS (Text) | Yes | Good | 100% | 25% | BIM Documentation exists | Yes | Partially Applied | No | [8 empty] | 12 | 16
Is project delivery occurring in accordance with the latest approved design strategy? | Approved Design Strategy (Text) | No | Needs Improvement | 33% | 10% | Review Latest Approved Design Strategy and compare with the Stage Gate Design Report | Yes | Partially Applied | No |  | Design Management Maturity | 69% | 100% |  | Design Management | 69% |  | 13 | 17
% of projects with completed technical design/peer reviews and verifications/certifications as required for the latest Design Stage Gate | % of projects with completed design reviews and verification register (%) | 80% | Good | 100% | 20% | Check the Design Review & Verification Register, assess if correct number of Design Reviews have occurred in accordance with the Design Management Report | >70% | 50-70% | <50% | [8 empty] | 14 | 18
Availability of robust design management plan and appropriate design review trackers/registers | Design Management Plan and Design Review Trackers/Registers (Text) | Yes | Good | 100% | 30% | Does DevCo have robust design management plan and appropriate design review trackers/registers | Yes | Partially Applied | No | [8 empty] | 15 | 19
Is the average cycle time to complete reviews and certifications in accordance with the Design Management Report? | Days taken to complete Design Reviews (Text) | Partially Applied | Satisfactory | 66% | 10% | Average number of days between Design Review Submittals and Completion of the Design Reviews compared to the number of days required to complete the Design Reviews in accordance with the Design Management Report | Yes | Partially Applied | No | [8 empty] | 16 | 20
Has the DevCo engaged independent certification of major critical elements? | Level of review and verification required for Stage Gate (Text) | No | Needs Improvement | 33% | 30% | Independent Certification exists | Yes | Partially Applied | No | [8 empty] | 17 | 21
Are the master DevCo designs integrated with Regional Infrastructure & Mobility Plans? | Regional Strategies (Text) | Yes | Good | 100% | 50% | The Infrastructure and Engineering Report references the Regional Infrastructure & Mobility Plans and demonstrates adoption of Regional Strategies | Yes | Partially Applied | No |  | Environmental Compliance Status | 83% | 40% |  | Regulatory Compliance | 84% |  | 18 | 22
Do all projects comply with environmental guidelines in accordance with ESIA? | Extent of compliance to environmental guidelines (Text) | Partially Applied | Satisfactory | 66% | 50% | Key Environmental Risks and Site Environmental Factors are covered in the Environmental Compliance Report | Yes | Partially Applied | No | [8 empty] | 19 | 23
% of projects with Code Compliance Violations | % of Code Compliance Violations (%) | 10% | Satisfactory | 66% | 10% | Total Number of Code Compliance Violations taken from the Code Compliance Assessment Report or from any other relevant documents | <10% | 10-30% | >30% |  | Authority Compliance Status | 86% | 60% |  |  |  |  | 20 | 24
Availability of proper Register of Authority Engagement, Approvals and Waivers | Register of Authority Engagement, Approvals and Waivers (Text) | Yes | Good | 100% | 20% | Does DevCo have proper Register of Authority Engagement, Approvals and Waivers in place | Yes | Partially Applied | No | [8 empty] | 21 | 25
Have all required Stakeholder Submittals been issued as planned? | Stakeholder Submittal Date (Text) | Partially Applied | Satisfactory | 66% | 15% | Stakeholder Submittal Dates are in accordance with the Stakeholder Management Plan, or planned submission date, to ensure approvals can be achieved in line with Stage Gate completion requirements | Yes | Partially Applied | No | [8 empty] | 22 | 26
Availability of robust Stakeholder Management Plan in place | Stakeholder Management Plan (Text) | Yes | Good | 100% | 25% | Does DevCo have robust Stakeholder Management Plan in place | Yes | Partially Applied | No | [8 empty] | 23 | 27
Does the Stakeholder Engagement Plan include proactive communication process to ensure timely coordination and approvals? | Scheduled Design Stage Gate Completion (Text) | Yes | Good | 100% | 15% | Proactive communication in Stakeholder Engagement Plan | Yes | Partially Applied | No | [8 empty] | 24 | 28
Availability of proper tracking and closure procedure for stakeholder comments | Stakeholder Comments Tracking and Closure Procedure (Text) | Partially Applied | Satisfactory | 66% | 15% | Does DevCo has proper tracking and closure procedure for stakeholder comments | Yes | Partially Applied | No | [8 empty] | 25 | 29
% of projects achieving DevCo ESG Targets | Planned ESG Target (No.) | Data Not Available | Needs Improvement | 33% | 100% | Actual ESG Achievement / Planned ESG Target | >70% | 50-70% | <50% |  | DevCo ESG Target Achievement | 33% | 80% |  | ESG Target Realization | 46% |  | 26 | 30
| Actual ESG Target (No.) | [17 empty] | 31
Does the DevCo ESG Target align with globally recognized Best Practice Targets? | Alignment with globally recognized Best Practice Targets (Text) | Yes | Good | 100% | 100% | Alignment with globally recognized Best Practice Targets | Yes | Partially Applied | No |  | Global ESG Target Alignment | 100% | 20% |  |  |  |  | 27 | 32
Go to Main Page
Go to Document
Go to Input
Note on A6: DT-AC-001
Note on B6: DT-DP-001
Note on A7: DT-AC-002
Note on B7: DT-DP-002
Note on A8: DT-AC-003
Note on B8: DT-DP-003
Note on A9: DT-AC-004
Note on B9: DT-DP-004
Note on A10: DT-AC-005
Note on B10: DT-DP-005
Note on A11: DT-AC-006
Note on B11: DT-DP-006
Note on B12: DT-DP-007
Note on A13: DT-AC-007
Note on B13: DT-DP-008
Note on B14: DT-DP-009
Note on A15: DT-AC-008
Note on B15: DT-DP-010
Note on B16: DT-DP-011
Note on A17: DT-AC-009
Note on B17: DT-DP-012
Note on A18: DT-AC-010
Note on B18: DT-DP-013
Note on A19: DT-AC-011
Note on B19: DT-DP-014
Note on B20: DT-DP-015
Note on A21: DT-AC-012
Note on B21: DT-DP-016
Note on A22: DT-AC-013
Note on B22: DT-DP-017
Note on A23: DT-AC-014
Note on B23: DT-DP-018
Note on A24: DT-AC-015
Note on B24: DT-DP-019
Note on A25: DT-AC-016
Note on B25: DT-DP-020
Note on A26: DT-AC-017
Note on B26: DT-DP-021
Note on A27: DT-AC-018
Note on B27: DT-DP-022
Note on A28: DT-AC-019
Note on B28: DT-DP-023
Note on A29: DT-AC-020
Note on B29: DT-DP-024
Note on A30: DT-AC-021
Note on B30: DT-DP-025
Note on A31: DT-AC-022
Note on B31: DT-DP-026
Note on A32: DT-AC-023
Note on B32: DT-DP-027
Note on A33: DT-AC-024
Note on B33: DT-DP-028
Note on A34: DT-AC-025
Note on B34: DT-DP-029
Note on A35: DT-AC-026
Note on B35: DT-DP-030
Note on B36: DT-DP-031
Note on A37: DT-AC-027
Note on B37: DT-DP-032

## InterviewQuestion(D&T)
PIF Project Lighthouse
InterviewQuestion(D&T)
SN | Question | Date of Interview | Response | Internal Comment | Follow Up Question
1 | How was the supply chain assessment done for materials & finishes required to achieve the Vision at point of incorporation? | 2025-05-09 16:05
2 | What were the reasons for any changes from original approved designs to latest design, and at which stage were these changes approved? | 2025-05-09 16:05
3 | Have the project designs aligned with DevCo Design & Technical Guidelines? Have there been any challenges adhering to the Vision? Provide an example how this has been resolved. | 2025-05-09 16:05
4 | Has the variance to the Development Program been submitted for approval? | 2025-05-09 16:05
5 | What were the reasons for the variance between the current business plan and latest development program? Were these submitted for approval? | 2025-05-09 16:05
6 | What is the impact, if any, on the business plan with these changes? Are there mitigation measures in place? | 2025-05-09 16:05
7 | Are there any outstanding FB directions and resolutions relating to design and development program? If so, please provide. | 2025-05-09 16:05
8 | Was the Vision assessed for construction viability at point of incorporation? | 2025-05-09 16:05
9 | How was designing for constructability incorporated in the design process? | 2025-05-09 16:05
10 | Have enabling works been considered to ensure the site is ready for development? | 2025-05-09 16:05
11 | Do all projects adopt digital delivery using BIM/GIS? If not, how are they managing coordination? | 2025-05-09 16:05
12 | What challenges has the DevCo faced in achieving the Design Strategy, how have these been overcome and has the PEP been updated and approved to reflect the changes. Provide example | 2025-05-09 16:05
13 | Has the DevCo had any difficulty engaging independent/peer design reviews for critical design packages. What method is used for design verification & certification? | 2025-05-09 16:05
14 | How has the design accommodated the regional guidelines and requirements (e.g. infrastructure, mobility, environment)? | 2025-05-09 16:05
15 | What are the environmental risks identified and how have they been mitigated? | 2025-05-09 16:05
16 | Are there any deviations from KSA or local codes and guidelines, justified by international/industry best practices? | 2025-05-09 16:05
17 | Has engagement commenced with all required stakeholders and what is the rate of closure of conditions and requirements? | 2025-05-09 16:05
18 | What are the challenges in meeting the targets? | 2025-05-09 16:05
Go to Main Page

## AddDataPoint(D&T)
PIF Project Lighthouse
AddDataPoint(D&T)
No. | Data Source | Additional Data Point | Input Value | Scorecard Visualization
Go to Main Page

## DevCoAssessmentInput(D&C)
PIF Project Lighthouse
DevCoAssessmentInput(D&C)
Assessment Criteria | Data Point | Input Value | Data Source | Assessor Remarks | Assessment Time Stamp | Reviewer Remarks | Review Time Stamp | Formula
% of CESMP mitigation measures which align with ESIA* | Environmental mitigation measures included in CESMP (No.) | 9 | DR-023-11 | Overarching CEMP includes 9 of the 11 mitigation categories included in the EMP. Public Realm & Public Safety are not included in the CEMP, however all other typical environmntal considerations are included eg Air, Noise, Vibration, Waste etc |  |  |  | Environmental mitigation measures included in CESMP / Environmental mitigation measures recommended in ESIA | 1 | 1
| Environmental mitigation measures recommended in ESIA (No.) | 11 | DR-023-06 | Comprehensive & Detailed EIA provided for Diriyah Gate | [5 empty] | 2
Does each project have Environmental Permits in place? | Authority Issued Environmental Permit for Constrution Works (Text) | Yes | DR-028 | Environmental Permits were supplied for each sample project |  |  |  | Review of projects with Environmental Permits in place? | 2 | 3
Can the DevCo demondstrate oversight or verification of Contractors compliance with Environmental Permit conditions? | Environmental Audit Report or Environmental Compliance Report (Text) | Yes | DR-023-123 | Regular environmentl auditing and reporting was demontrated in the sample projects provided |  |  |  | Review of projects with Environmental Audit Report or Environmental Compliance Reports? | 3 | 4
Has the Construction Execution Plan been updated to reflect the latest stage of construction? | Update of construction execution plan (Text) | Yes | DR-029 | Much of the construction execution planning was evident in the Site & Logisitcs Plans and there was evidence of these plans being regularly updated, reviewd and signed of by authorizing parties. A project management or execution plan for each vendor consultant or contractor was shared for Al-Zalall Bujairi for ther respective fields. |  |  |  | Update of construction execution plan | 4 | 5
Has the construction sequence and method statement been reviewed and approved? | Review and approval of Construction sequence & method statement (Text) | Partially Applied | DR-043-06 | Lists of proposed Method Statements are provided, however yet to see evidence of construction sequence or method statement documents being reviewed and approved. |  |  |  | Review and approval of construction sequence and method statement | 5 | 6
Has adequate planning been carried out to identify required area and location for worksite provisions including construction yards etc? | Development Site Logistics Map (Text) | Yes |  | Overarching planning was demonstrated for each masterplan, and are updated to reflect changes in the masterplan. These are communicated to the contractors through tender specifications. The Contractors then produce project specific logistics plans which are regularly reviewed, updated and signed off by authorizing parties. |  |  |  | Sufficent work site with lay down areas | 6 | 7
Have Traffic Simulations been completed in preparing the Site & Logistics Plan? | Completion of Traffic Simulations (Text) | Yes | DR-018-01 | Assessed against whats been supplied , it appears to be in line with the documentation |  |  |  | Completion of traffic simulations | 7 | 8
The contractor & PMC able to demonstrate Project Execution Planning occuring in the last 12 months including Packaging & Phasing, Site & Logistics Planning & Procurement Strategy Planning | Masterplan Delivery Strategy (Text) | Yes | [5 empty] | Precinct wide planning was completed for each of the Masterplans which form the basis of the tender specification for each project.by the contractor ,but reported to the DevCo in a detail monthly construction Progress report | 8 | 9
% of Stakeholder MOU** / LUPs*** not executed in accordance with critical lead time | Number of Stakeholder MOU or Land Use Permits not executed on time (No.) | 24 | DR-018-01 |  |  |  |  | Number of Stakeholder MOU or Land Use Permits not executed on time/ Total number of Stakeholder MOU or Land Use Permits required | 9 | 13
| Total Stakeholder MOU or Land Use Permits required (No.) | 63 | DR-018-01 | [6 empty] | 14
Does the DevCo adequately plan, track & monitor stakeholder applications? | Stakeholder Dashboard (Text) | Yes | [5 empty] | Review of stakeholder dashboard | 10 | 15
% of Workforce Hired against Workforce Estimates | Forecast workforce requirements (No.) | 15300 | DR-032-01 | Budgeted Manhours - All Districts & Infrastructure |  |  |  | Actual workforce employed / forecast workforce requirements | 11 | 17
| Actual workforce employed (No.) | 14400 | DR-032-01 | All District & Infrastructure - Resource statistics | [5 empty] | 18
Does the DevCo have an active governance role in assessing Labor Camp capacity to meet worforce demand? | Contractors Worker Camp Policy (Text) | <quarterly | [5 empty] | As part of the tender selection criteria the DevCo visits and inspects the contractors worker compound, they also undertake regular inspections throughout construction. | 12 | 21
% of Material Supply Capacity against Material Demand Estimates | Forecast number of batching / crushing plants/ precast yards, etc. (No.) | 45000 | DR-032 | Assessed against concrete batching plant requirements forecasted in the IMS report. Generally, based on the number of operating batching plants, concrete demand can be met. A projected shortfall for 2 months may occur based on the current peak demand projections. |  |  |  | Actual number of batching plants / forecast number of batching plants | 13 | 22
| Actual number of batching / crushing plants/ precast yards, etc. (No.) | 39300 | DR-32-01 | Assessed against concrete batching plant requirements forecasted in the IMS report. Generally, based on the number of operating batching plants, concrete demand can be met. A projected shortfall for 2 months may occur based on the current peak demand projections. | [5 empty] | 23
Average Technical Submittal closeout Cycle Time | Average Technical Submittal closeout Cycle Time (No.) | 20 | [5 empty] | Summation of closeout cycle time / number of projects | 14 | 24
% of approved shop drawing reviews vs planned | Total number of shop drawing review requests (No.) | 14760 | DR-35-01 |  |  |  |  | Total number of shop drawing reviews approved / Total number of shop drawing review requests | 15 | 25
| Total number of shop drawing reviews approved (No.) | 13970 | DR-35-01 | [6 empty] | 26
% of approved product waivers vs product specified | Total number of product sample & material approvals requested (No.) | 1342 | DR-35-01 |  |  |  |  | Total number of product sample & materials approved / Total number of product sample & material approvals requested | 16 | 27
| Total number of product sample & materials approved (No.) | 1319 | DR-036 | [6 empty] | 28
% of Certified As-Built Drawing Packages vs Planned | Number of As-Built Drawing review requests (No.) | 4827 | DR-035 |  |  |  |  | Number of As-built reviews / approvals / Number of As-Built review requests | 17 | 29
| Number of As-Built Drawings reviews approved (No.) | 4825 | DR-035 | [6 empty] | 30
MIR Inspection Rate | Total number of MIRs requested (No.) | 296 | [5 empty] | Number of MIR Inspected / Total number of MIRs requested | 18 | 31
| Total number of MIRs inspected (No.) | 293 | [7 empty] | 32
MIR Acceptance and Approval Rate | Total number of MIRs approved (No.) | 290 | [5 empty] | Number of Approved MIR / Total number of MIRs requested | 19 | 33
WIR Inspection Rate | Total number of WIRs requested (No.) | 5430 | DR-34-01 |  |  |  |  | Number of WIR Inspected / Total number of WIRs requested | 20 | 34
| Total number of WIRs inspected (No.) | 4985 | DR_034-01 | [6 empty] | 35
WIR Acceptance and Approval Rate | Total number of WIRs approved (No.) | 4616 | DR-043 |  |  |  |  | Number of Approved WIR / Total number of WIRs requested | 21 | 36
Does the frequency of Audits align with the QMP? | Required Audit frequency (Text) | [6 empty] | Alignment of audit frequency | 22 | 37
Has the DevCo verified the Contractor's ISO Certification | Copy of Contractor's ISO certification or most recent ISO Audit (Text) | Yes |  | Complies to iso 9001: 2015 QMS system standards 90% of the schedule Audits completed |  |  |  | Review of contractors audit | 23 | 38
% closure of Non-Conformance Reports (NCR) | Total number of defects & NCRs (No.) | 96 | DR-041 | NCR LOG: AL ZALLAL |  |  |  | Number of Non-Conformance Reports Closed / Total Number of Non-Conformance Reports | 24 | 39
| Total number of closed defects & NCRs (No.) | 90 | [7 empty] | 40
Average NCRs closeout Cycle Time | Average time to close NCRs (No.) | 105 | DR-041 | Ncr to be closed out 2 weeks from receiving the report |  |  |  | Sum (NCR Closeout cycle time)/Total number of Non-Conformance Reports | 25 | 41
Does the DevCo have an active Procurement Management Plan/Policy? | Procurement Approach (Text) | Partially Applied |  | No evidence of a single Procurement Policy was viewed, there is some detail in the Development Management Policy and Process Manual (March 23) Sections PRO-025 to PRO-028 describe some procurement procedures. In addition each Masterplan / PEPs include some detail of procurement approach and packaging strategy |  |  |  | Review of DevCoProcurement Management Plan/Policy | 26 | 49
| Date of latest approved Procurement Plan (Text) | [8 empty] | 50
Average no. days for claims to be closed out | Claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures (No.) | 100 |  | The assessment is done based on the data available in DR-54(raw data tab) filtering those claims that are resolved between the range 0-88 days |  |  |  | Average number of days based on guidelines from FIDIC silver book | 27 | 51
Is the DevCo actively conducting tender award assessments and it is well documented? | Tender award assessment documentation (Text) | Partially Applied |  | Samples of tender evaluation reports were provided and are of sound quality |  |  |  | Review of Tendar Award Assessment | 28 | 52
Is the DevCo undertaking due diligence of the vendors appointed? | Due diligence tender evaluation documents (Text) | Partially Applied |  | Samples of PSPR show detailed analysis and due-dilligence undertaken |  |  |  | Review of Due Diligence Evaluation | 29 | 53
Did the DevCo complete a Supply Chain Risk-Market Intelligence Assessment in the last quarter? | Supply Chain Risk-Market Intelligence Assessment (Text) | Partially Applied | DR-049 | Supply Chain Risk appears to be an ongoing item flagged in the risk register, factors noted include: Shipping delays due to regional conflicts Parallel giga projects competing for resources impacting cost of materials and causing delays |  |  |  | Completion of supply chain risk-market intelligence assessment | 30 | 54
% of procurement activities executed as planned in the Annual Procurement Plan | Total number of procurement activities (No.) | 48 | DR-045a | Procurement Executive Dashboard April-2025 taken from Presidents Commercial Update Report |  |  |  | Number of procurement activities executed as planned / Total number of procurement activities | 31 | 55
| Number of procurement activities executed as planned (No.) | 14 | DR-045a | [6 empty] | 56
% of deviations in total awarded contract value with approved TDC | Value of Awarded Contract (No.) | 50.15 | DR-003-01 | The values are obtained from President Commercial Update Cost report (Key Contract Packages section) DR-003 |  |  |  | (Value of Contract Awarded - Tender Cost Estimate) / Value of Award Contract | 32 | 57
| Tender Cost Estimate (No.) | [8 empty] | 58
% of contracts with pending claims | % of contracts with filed claims (%) | 32.5% |  | President update shows 13 of top 40 contracts (33%) with pending claims (Dec 24) |  |  |  | % of contracts with filed claims | 33 | 62
% of Payment Certificates and payments being processed within the contractual payment terms? | % payment paid within contractual terms (%) | 98.7% |  | Payment Register, 1.3% took longer than the payment term specified on the register, this has not been verified against the actual contractural terms |  |  |  | Processing of payment certificates and payments | 34 | 64
Are Vendor performance assessment occurring which capture financial instability, delays, repeated quality issues in real-time? | Alignment of sourcing strategies with project schedules and requirements (Text) | Partially Applied |  | No evidence provided to demonstrate ongoing or real time reviews are occuring. |  |  |  | Vendor performance assessment | 35 | 66
Does the HSE Management Manual have adequate provision for identification and escalation of high risk activities? | Escalation criteria for high risk activities (Text) | Yes | DR-057-01 DR-057-02 DR-057-03 DR-057-05 DR-057-06_01 | Diriyah Gate Company Construction Occupational Health and Safety Manual- Document number: DD-SWD-000-000-DGD-MAN-HS-000001 Rev 05 March 2023. Section 3.2 Definitions- Identifies and defines "Acceptable Risk" . Section 5.3.6- Contractor and Supply Chain outlines requirements for a project risk register. Diriyah Gate Company Limited- DD-SWD-SW-SWD-000-SSA-PLN-HS-000001 (04). Unable to verify that evidence was available for a process for the identification and escalation of high risk activities. Salini Saudi Arabia- Project HSE Plan-Diriyah Square Structural Works to the Above Ground assists-DSQ Package 03,06,07- DG-DSQ-000-0000-SSA-PLN-HS-000001(04) Unable to verify within Project HSE Plan that evidence was available for a process the escalation of high risk activities. UCC Saudi Company- Project Name: Oberoi Hotel and Branded Residences-Project Number: US0033- WS-UCC-HSE-0001 unable to verify within the HSE Management Plan that there is an adequate provision for the escalation of identified high risks. Request copy of USC-IMS-HSE-6003E Hazard Identification and Risk Assessment. Al-Zallal Mixed Used OH&S Plan Rv01- Unable to verify a process for the escalation of identified high risk activities. Noted that they have defined "acceptable risk". Unable to verify that any of the sample HSE Management Manuals provided have a documented process to define the organizations acceptable risk level and managements actions to be taken, if the accessed risk is higher than that level. |  |  |  | Provision for identification and escalation of high risk activities | 36 | 68
Has the DevCo provided a NCR Safety Register? | NCR safety register (Text) | No | [5 empty] | Review of NCR safety register | 37 | 69
Is the rate of review of the Safety Risk Register in accordance with the HSE Management Manual? | HSE Risk Register Review Rate (Text) | Yes | DR-057-02 and DR-058-02 are the same document. Additional evidence is required. DR-057-06_01 DR-058-04 | Diriyah Gate Company Limited- DD-SWD-SW-SWD-000-00001 (04). Has identified a review frequency rate of annually. Diriyah Company-DevCo OHS Risk Register- All Construction Activities- DD-SWD-SW-SWD-000-000-DGD-PNP-HS-000001 Rev.1 Dated 25 March 2025. Salini Saudi Arabia- DG-DSQ-000-0000-SSA-PLN-HS-000001 (04), Dated 25 Aug 2024 - In section 5.2.1 states that the project HSE risk register will be reviewed as required. Oberoi Hotel -WS-WSH-685-0000-HSE-PLN-HS-00001- Plan does specify that that a formal review will be undertaken monthly. Al-Zallal Mixed Used OH&S Plan- DG-BUJ-106-0000-NSM-PLN. Able to verify a required review rate of the safety risk register. Zallal Mixed Used- Project Risk Register DG-BUJ-106-0000-NSM-RPT-HS-000045 Rev 0 dated 08 May 2024. |  |  |  | Review rate of safety risk register | 38 | 70
% of closed Safety Risk items | Total number of Safety Risk items (No.) | 2823 | DR-060-01 DR-060-02 DR-060-03 | Salini Monthly HSE Report April 2025- 830 HSE observations recorded. Closed 556 HSE observations, Open 185 HSE observations, Overdue 101 HSE observations. GP HSE observations 89. DGCL (Hill International)-Monthly OH&S Trend Analysis Report January 2025. This report records the OHS KPI's for this week, year to date and project to date. Section 2.6 states the ratio of SOR closure (Open: Closed) 0:193. OH&S Monthly KPI's (Leading and Lagging indicators) is an extract of the DGCL (Hill International) January 2025 report. Infra DI,DII, SWL & PR OHS Monthly Performance Report 1-30 April 2025 2,823 Safety Observations Recorded. With a close out rate of 92.81%. |  |  |  | Total number of closed Safety Risk items / Total number of safety risk items | 39 | 71
| Total number of closed Safety Risk items (No.) | 2620 | DR-060-01 DR-060-02 DR-060-03 (extract from DR-060-02 | 67% of the 830 HSE observations recorded were closed based on the information provided in the Salini Monthly HSE Report April 2025. This percentage does not include the 101 identified overdue actions. DGCL Monthlies Trend Analysis Report January 2025- 100% close out rate. Infra DI,DII, SWL & PR OHS Monthly Performance Report 1-30 April 2025 2823 safety observations recorded with 203 overdue. 2620 safety Observation were closed out. | [5 empty] | 72
Average cycle time to close Safety Risk items | Cycle time to close Safety Risk items (in days) (No.) | 30 | DR-060-01 DR-060-02 DR-060-03 (extract from DR-060-02) | Unable to determine based on evidence supplied the exact average time to close out safety risk items. Further evidence is required. Access to Salini Saudi Arabia Monthly HSE Observation Tracker required. Access to Al-Zallal Mixed Used HSE Monthly tracker. DevCo safety NCR register to be made available (verbal confirmation during dedicated HSE meeting). |  |  |  | To input final number Sum (Cycle time to close safety risk items) / Total number of closed safety risk items | 40 | 73
Has the DevCo provided a a Safety Incident Register? | Safety incident register (Text) | No | [5 empty] | Review of safety incident register | 41 | 74
Average cycle time to close Safety Incident | Cycle time to close Safety Incident (in days) (No.) | 30 | DR-058 | Unable to determine based on evidence supplied the exact average time to close out safety incidents. Further evidence is required. Access to incident register is required. |  |  |  | To input final number. Sum (Cycle time to close safety incident) / Total number of closed safety incidents | 42 | 75
Is the emergency drill rate compliant with EEPP? | Planned number of Emergency Drills (No.) | 5 | DR-057-04 DR-060-01 DR-060-02 Awaiting documents for DR-059 | Zallal Mixed Use- Emergency Management Framework Project ID-322822- Document number- DG-BUJ-106-0000-NSM-PLN-HS-000015 Rev.1. Evidence available in section 1.2 Frequency and main participant that two major emergency drills shall be conducted annually. Salini Saudi Arabia- Project: DSQ-AGA- Structural Works to the Above Ground Assets. DG-DSQ-000-0000-SSA-RPT-HS-000001(07)-Monthly HSE Report April 2025. Three planned emergency drills. Diriyah Company Emergency Management Framework Rev:04 2025- DD-SWD-SW-SWD-000-000-DGD-PNP-HS-000010 page 31 states minimum number of planned emergency drills. |  |  |  | Compliance of emergency drill rate | 43 | 76
| Actual number of Emergency Drills (No.) | 11 | DR-060-02 Awaiting documents for DR-059 | Salini Saudi Arabia- Project: DSQ-AGA- Structural Works to the Above Ground Assets. Document Reference: DG-DSQ-000-0000-SSA-RPT-HS-000001(07)-Monthly HSE Report April 2025. Two drills undertaken on the 19 March 2025 and 22 April 2025. | [5 empty] | 77
| Recommended time to complete Emergency drills (No.) | Data Not Available | DR-057-04 Awaiting documents for DR-059 | Unable to verify with the supplied documentation. | [5 empty] | 78
| Actual Time to complete Emergency drills (No.) | Data Not Available | DR-057-04 Awaiting documents for DR-059 | 3 Emergency Drills were provided as evidence which took 39 minutes, 26 minutes and 27 minutes respectively. These included Package C- Final Medical Rescue Drill Report 26 Feb 2025 Drill Number: DC/FEMCO/05. Emergency Evacuation Drill Report- Excavation of CP A B- Drill Number :03 conducted on the 27/04/2025. Emergency Drill Report Form- Car Park Project Feb 2025. | [5 empty] | 79
Fatality Rate (FR) | No. of incidents resulting in fatality or severe impairment per 200,000 work hours (No.) | 0 | DR-061 | DGCL Monthly OH&S Trend Analysis Report January 2025- Monthly KPI's Section 3.1- Zero recorded fatalities. Infra DI,DII, SWL & PR OHS Monthly Performance Report 1-30 April 2025 Salini Saudi Arabia Monthly HSE Report April 2025- Zero fatalities recorded. |  |  |  | No. of incidents resulting in fatality or severe impairment per 200,000 work hours | 44 | 82
Lost Time Injury Frequency Rate (LTIFR) | No. of incidents resulting in lost time per 200,000 work hours (No.) | 0 | DR-061 | DGCL Monthly OH&S Trend Analysis Report January 2025- Monthly KPI's Section 3.2- Zero recorded LTIs. Infra DI,DII, SWL & PR OHS Monthly Performance Report 1-30 April 2025 Salini Saudi Arabia Monthly HSE Report April 2025- Zero LTIs recorded. |  |  |  | No. of incidents resulting in lost time per 200,000 work hours | 45 | 83
Total Recordable Incident Rate (TRIR) | No. of recordable incidents per 200,000 work hours (No.) | 0 | DR-061 | DGCL Monthly OH&S Trend Analysis Report January 2025- Monthly KPI's Section 3.1- Zero recorded Total Recordable Incident Rate (TRIR) Infra DI,DII, SWL & PR OHS Monthly Performance Report 1-30 April 2025 Salini Saudi Arabia Monthly HSE Report April 2025- Zero Total Recordable Incident Rate (TRIR) recorded. |  |  |  | No. of recordable incidents per 200,000 work hours | 46 | 84
Near Miss Rate | No. of near misses recorded per 200,000 work hours (No.) | 0.73 | DR-061 | DGCL Monthly OH&S Trend Analysis Report January 2025- Monthly KPI's Section 3.6 Near Miss- Zero recorded for the month of January 2025. Twenty-one Near Miss events have been recorded on the project to date. Infra DI,DII, SWL & PR OHS Monthly Performance Report 1-30 April 2025 Salini Saudi Arabia Monthly HSE Report April 2025- one Near Miss have been recorded for the month of April 2025 and Four have been recorded for the project to date. |  |  |  | No. of near misses recorded per 200,000 work hours | 47 | 85
Safety Observation Rate | No. of safety observation recorded per 200,000 work hours (No.) | 346 | DR-061 | Salini Saudi Arabia- Monthly HSE April 2025- 830 HSE Observations were recorded for a total of 469,224 hours worked for the month. 5,289 Observations have been recorded between 24th October 2024 to April 2025 (Unable to determine safety observation rate for this period). Infra DI,DII, SWL & PR OHS Monthly Performance Report 1-30 April 2025 DGCL- Al-Zallal Mixed Used- Monthly OHS January 2025- 193 observations were recorded. |  |  |  | No. of safety observation recorded per 200,000 work hours | 48 | 86
Is there evidence of Leadership Safety Walks occuring? | Total number of Safety Walks with Leadership (No.) | Yes | DR-060-02 | DGCL Monthly OH&S Trend Analysis Report January 2025- States in section 3- Monthly OH&S KPIs-Section 2.6- 219 OH&S Safety Leadership Site Walkthroughs were conducted for the month. |  |  |  | Total number of Safety Walks with Leadership / Total number of Safety Walks | 49 | 88
Is the DevCo tracking & monitoring Grievances? | Total number of grievances (No.) | Yes | DR-062-01 | DSQ P-2 Daily HSE Report- Focus Inspection Welfare Facilities- DG-DSQ-316-0000-AEC-RPT-HS-001081 dated 14/12/2024- 24 welfare related observations were recorded. No evidence of the number of grievances was available. Further evidence is required . Welfare facilities/camp hazard observation register. |  |  |  | Review of Welfare Monitoring documentation | 50 | 90
Has the DevCo demonstrated active management in closing out Grievances? | Cycle time to close grievances (No.) | No | DR-062 | Unable to verify the average time to close out identified welfare grievances. Further evidence is required . Welfare facilities/camp hazard observation register. |  |  |  | Review of Welfare Monitoring documentation | 51 | 91
Does the DevCo set targets and monitor the minimum number of HSE & Welfare staff vs the total workforce? | DevCo staffing register (Text) | No | [5 empty] | Review of Welfare Monitoring documentation | 52 | 94
Does the DevCo track and monitor closeout of welfare observations? | Total number of Closed Welfare Observations (No.) | Yes | DR-062 | Too small a sample size to adequately determine a number of the assessment criteria and data points. |  |  |  | Review of Welfare Monitoring documentation | 53 | 96
Has the DevCo demonstrated closeout of Welfare Non-compliances is occuring? | Total Closed Welfare Non-compliances (No.) | No | DR-064 | Unable to verify the total number of closed out welfare non-compliances |  |  |  | Review of Welfare Monitoring documentation | 54 | 97
Is frequency of Labor Accommodation Inspection occurring in accordance with VMMP? | Mitigation measures in the event of welfare audit observations & recommendations (Text) | No | DR-064 | Unable to verify what mitigation measures have been accepted and closed out. Further evidence is required. Welfare facilities/camp hazard observation register required. 04- Contractors Workers Quality of Life and Accommadation Procedures 2024- DSQ for available at the time of review. |  |  |  | Labor accommodation inspection frequency | 55 | 98
Go to Main Page
Go to Document
Go to Analysis
Note on A6: DC-AC-001
Note on B6: DC-DP-001
Note on B7: DC-DP-002
Note on A8: DC-AC-002
Note on B8: DC-DP-003
Note on A9: DC-AC-003
Note on B9: DC-DP-004
Note on A10: DC-AC-004
Note on B10: DC-DP-005
Note on A11: DC-AC-005
Note on B11: DC-DP-006
Note on A12: DC-AC-006
Note on B12: DC-DP-007
Note on A13: DC-AC-007
Note on B13: DC-DP-008
Note on A14: DC-AC-008
Note on B14: DC-DP-009
Note on A15: DC-AC-009
Note on B15: DC-DP-013
Note on B16: DC-DP-014
Note on A17: DC-AC-010
Note on B17: DC-DP-015
Note on A18: DC-AC-011
Note on B18: DC-DP-017
Note on B19: DC-DP-018
Note on A20: DC-AC-012
Note on B20: DC-DP-021
Note on A21: DC-AC-013
Note on B21: DC-DP-022
Note on B22: DC-DP-023
Note on A23: DC-AC-014
Note on B23: DC-DP-024
Note on A24: DC-AC-015
Note on B24: DC-DP-025
Note on B25: DC-DP-026
Note on A26: DC-AC-016
Note on B26: DC-DP-027
Note on B27: DC-DP-028
Note on A28: DC-AC-017
Note on B28: DC-DP-029
Note on B29: DC-DP-030
Note on A30: DC-AC-018
Note on B30: DC-DP-031
Note on B31: DC-DP-032
Note on A32: DC-AC-019
Note on B32: DC-DP-033
Note on A33: DC-AC-020
Note on B33: DC-DP-034
Note on B34: DC-DP-035
Note on A35: DC-AC-021
Note on B35: DC-DP-036
Note on A36: DC-AC-022
Note on B36: DC-DP-037
Note on A37: DC-AC-023
Note on B37: DC-DP-038
Note on A38: DC-AC-024
Note on B38: DC-DP-039
Note on B39: DC-DP-040
Note on A40: DC-AC-025
Note on B40: DC-DP-041
Note on A41: DC-AC-026
Note on B41: DC-DP-049
Note on B42: DC-DP-050
Note on A43: DC-AC-027
Note on B43: DC-DP-051
Note on A44: DC-AC-028
Note on B44: DC-DP-052
Note on A45: DC-AC-029
Note on B45: DC-DP-053
Note on A46: DC-AC-030
Note on B46: DC-DP-054
Note on A47: DC-AC-031
Note on B47: DC-DP-055
Note on B48: DC-DP-056
Note on A49: DC-AC-032
Note on B49: DC-DP-057
Note on B50: DC-DP-058
Note on A51: DC-AC-033
Note on B51: DC-DP-062
Note on A52: DC-AC-034
Note on B52: DC-DP-064
Note on A53: DC-AC-035
Note on B53: DC-DP-066
Note on A54: DC-AC-036
Note on B54: DC-DP-068
Note on A55: DC-AC-037
Note on B55: DC-DP-069
Note on A56: DC-AC-038
Note on B56: DC-DP-070
Note on A57: DC-AC-039
Note on B57: DC-DP-071
Note on B58: DC-DP-072
Note on A59: DC-AC-040
Note on B59: DC-DP-073
Note on A60: DC-AC-041
Note on B60: DC-DP-074
Note on A61: DC-AC-042
Note on B61: DC-DP-075
Note on A62: DC-AC-043
Note on B62: DC-DP-076
Note on B63: DC-DP-077
Note on B64: DC-DP-078
Note on B65: DC-DP-079
Note on A66: DC-AC-044
Note on B66: DC-DP-082
Note on A67: DC-AC-045
Note on B67: DC-DP-083
Note on A68: DC-AC-046
Note on B68: DC-DP-084
Note on A69: DC-AC-047
Note on B69: DC-DP-085
Note on A70: DC-AC-048
Note on B70: DC-DP-086
Note on A71: DC-AC-049
Note on B71: DC-DP-088
Note on A72: DC-AC-050
Note on B72: DC-DP-090
Note on A73: DC-AC-051
Note on B73: DC-DP-091
Note on A74: DC-AC-052
Note on B74: DC-DP-094
Note on A75: DC-AC-053
Note on B75: DC-DP-096
Note on A76: DC-AC-054
Note on B76: DC-DP-097
Note on A77: DC-AC-055
Note on B77: DC-DP-098

## DevCoAssessmentAnalysis(D&C)
PIF Project Lighthouse
DevCoAssessmentAnalysis(D&C)
Assessment Criteria | Data Point | Value | Rating | Score | Assessment Criteria Weightage | Assessment Guideline/Formula | Good | Satisfactory | Needs Improvement | Remarks 1 | Performance Signal | Performance Signal Score | Performance Signals Weightage | Remarks 2 | Key Topic | Key Topic Score | Remarks 3
% of CESMP mitigation measures which align with ESIA* | Environmental mitigation measures included in CESMP (No.) | 81.82% | Good | 100% | 10% | Environmental mitigation measures included in CESMP / Environmental mitigation measures recommended in ESIA | >80% | 60-80% | <60% |  | Construction Planning Maturity | 89% | 70% |  | Construction | 92% |  | 1 | 1
| Environmental mitigation measures recommended in ESIA (No.) | [17 empty] | 2
Does each project have Environmental Permits in place? | Authority Issued Environmental Permit for Constrution Works (Text) | Yes | Good | 100% | 5% | Review of projects with Environmental Permits in place? | Yes | Partially Applied | No | [8 empty] | 2 | 3
Can the DevCo demondstrate oversight or verification of Contractors compliance with Environmental Permit conditions? | Environmental Audit Report or Environmental Compliance Report (Text) | Yes | Good | 100% | 5% | Review of projects with Environmental Audit Report or Environmental Compliance Reports? | Yes | Partially Applied | No | [8 empty] | 3 | 4
Has the Construction Execution Plan been updated to reflect the latest stage of construction? | Update of construction execution plan (Text) | Yes | Good | 100% | 10% | Update of construction execution plan | Yes | Partially Applied | No | [8 empty] | 4 | 5
Has the construction sequence and method statement been reviewed and approved? | Review and approval of Construction sequence & method statement (Text) | Partially Applied | Satisfactory | 66% | 10% | Review and approval of construction sequence and method statement | Yes | Partially Applied | No | [8 empty] | 5 | 6
Has adequate planning been carried out to identify required area and location for worksite provisions including construction yards etc? | Development Site Logistics Map (Text) | Yes | Good | 100% | 10% | Sufficent work site with lay down areas | Yes | Partially Applied | No | [8 empty] | 6 | 7
Have Traffic Simulations been completed in preparing the Site & Logistics Plan? | Completion of Traffic Simulations (Text) | Yes | Good | 100% | 10% | Completion of traffic simulations | Yes | Partially Applied | No | [8 empty] | 7 | 8
The contractor & PMC able to demonstrate Project Execution Planning occuring in the last 12 months including Packaging & Phasing, Site & Logistics Planning & Procurement Strategy Planning | Masterplan Delivery Strategy (Text) | Yes | Good | 100% | 10% | Precinct wide planning was completed for each of the Masterplans which form the basis of the tender specification for each project.by the contractor ,but reported to the DevCo in a detail monthly construction Progress report | Yes | Partially Applied | No | [8 empty] | 8 | 9
% of Stakeholder MOU** / LUPs*** not executed in accordance with critical lead time | Number of Stakeholder MOU or Land Use Permits not executed on time (No.) | 38.1% | Satisfactory | 66% | 20% | Number of Stakeholder MOU or Land Use Permits not executed on time/ Total number of Stakeholder MOU or Land Use Permits required | <20% | 20-60% | >60% | [8 empty] | 9 | 13
| Total Stakeholder MOU or Land Use Permits required (No.) | [17 empty] | 14
Does the DevCo adequately plan, track & monitor stakeholder applications? | Stakeholder Dashboard (Text) | Yes | Good | 100% | 10% | Review of stakeholder dashboard | Yes | Partially Applied | No | [8 empty] | 10 | 15
% of Workforce Hired against Workforce Estimates | Forecast workforce requirements (No.) | 94.12% | Good | 100% | 30% | Actual workforce employed / forecast workforce requirements | >90% | 70-90% | <70% |  | Workforce Resource Availability | 100% | 30% |  |  |  |  | 11 | 17
| Actual workforce employed (No.) | [17 empty] | 18
Does the DevCo have an active governance role in assessing Labor Camp capacity to meet worforce demand? | Contractors Worker Camp Policy (Text) | <quarterly | Good | 100% | 30% | As part of the tender selection criteria the DevCo visits and inspects the contractors worker compound, they also undertake regular inspections throughout construction. | <quarterly | >quarterly | No | [8 empty] | 12 | 21
% of Material Supply Capacity against Material Demand Estimates | Forecast number of batching / crushing plants/ precast yards, etc. (No.) | 87.33% | Good | 100% | 40% | Actual number of batching plants / forecast number of batching plants | >80% | 40-80% | <40% | [8 empty] | 13 | 22
| Actual number of batching / crushing plants/ precast yards, etc. (No.) | [17 empty] | 23
Average Technical Submittal closeout Cycle Time (No.) | Average Technical Submittal closeout Cycle Time (No.) | 20 | Satisfactory | 66% | 10% | Summation of closeout cycle time / number of projects | <10 days | 10-21 days | >21 days | 20 | Adherence to Design | 96% | 70% |  | Quality | 89% |  | 14 | 24
% of approved shop drawing reviews vs planned | Total number of shop drawing review requests (No.) | 94.65% | Good | 100% | 15% | Total number of shop drawing reviews approved / Total number of shop drawing review requests | >90% | 60-90% | <60% | [8 empty] | 15 | 25
| Total number of shop drawing reviews approved (No.) | [17 empty] | 26
% of approved product waivers vs product specified | Total number of product sample & material approvals requested (No.) | 98.29% | Good | 100% | 15% | Total number of product sample & materials approved / Total number of product sample & material approvals requested | >90% | 60-90% | <60% | [8 empty] | 16 | 27
| Total number of product sample & materials approved (No.) | [17 empty] | 28
% of Certified As-Built Drawing Packages vs Planned | Number of As-Built Drawing review requests (No.) | 99.96% | Good | 100% | 20% | Number of As-built reviews / approvals / Number of As-Built review requests | >80% | 60-80% | <60% | [8 empty] | 17 | 29
| Number of As-Built Drawings reviews approved (No.) | [17 empty] | 30
MIR Inspection Rate | Total number of MIRs requested (No.) | 98.99% | Good | 100% | 10% | Number of MIR Inspected / Total number of MIRs requested | >80% | 60-80% | <60% | [8 empty] | 18 | 31
| Total number of MIRs inspected (No.) | [17 empty] | 32
MIR Acceptance and Approval Rate | Total number of MIRs approved (No.) | 97.97% | Good | 100% | 10% | Number of Approved MIR / Total number of MIRs requested | >80% | 60-80% | <60% | [8 empty] | 19 | 33
WIR Inspection Rate | Total number of WIRs requested (No.) | 91.8% | Good | 100% | 10% | Number of WIR Inspected / Total number of WIRs requested | >80% | 60-80% | <60% | [8 empty] | 20 | 34
| Total number of WIRs inspected (No.) | [17 empty] | 35
WIR Acceptance and Approval Rate | Total number of WIRs approved (No.) | 85.01% | Good | 100% | 10% | Number of Approved WIR / Total number of WIRs requested | >80% | 60-80% | <60% | [8 empty] | 21 | 36
Does the frequency of Audits align with the QMP? | Required Audit frequency (Text) | Data Not Available | Needs Improvement | 33% | 20% | Alignment of audit frequency | Yes | Partially Applied | No |  | Quality Assurance / Quality Control (QA/QC) | 73% | 30% |  |  |  |  | 22 | 37
Has the DevCo verified the Contractor's ISO Certification and Audit schedule is upto date? | Copy of Contractor's ISO certification or most recent ISO Audit (Text) | Yes | Good | 100% | 20% | Review of contractors audit | Yes | Partially Applied | No | [8 empty] | 23 | 38
% closure of Non-Conformance Reports (NCR) | Total number of defects & NCRs (No.) | 93.75% | Good | 100% | 40% | Number of Non-Conformance Reports Closed / Total Number of Non-Conformance Reports | >80% | 60-80% | <60% | [8 empty] | 24 | 39
| Total number of closed defects & NCRs (No.) | [17 empty] | 40
Average NCRs closeout Cycle Time | Average time to close NCRs (No.) | 105 | Needs Improvement | 33% | 20% | Sum (NCR Closeout cycle time)/Total number of Non-Conformance Reports | <10 days | 10-21 days | >21 days | [8 empty] | 25 | 41
Does the DevCo have an active Procurement Management Plan/Policy? | Procurement Approach (Text) | Partially Applied | Satisfactory | 66% | 20% | Review of DevCoProcurement Management Plan/Policy | Yes | Partially Applied | No |  | Procurement & Contracting Compliance | 59% | 30% |  | Procurement | 54% |  | 26 | 49
| Date of latest approved Procurement Plan (Text) | [17 empty] | 50
Average no. days for claims to be closed out | Claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures (No.) | 100 | Needs Improvement | 33% | 20% | Average number of days based on guidelines from FIDIC silver book | <42 days | 42 - 90 Days | >90 Days | [8 empty] | 27 | 51
Is the DevCo actively conducting tender award assessments and it is well documented? | Tender award assessment documentation (Text) | Partially Applied | Satisfactory | 66% | 20% | Review of Tendar Award Assessment | Yes | Partially Applied | No | [8 empty] | 28 | 52
Is the DevCo undertaking due diligence of the vendors appointed? | Due diligence tender evaluation documents (Text) | Partially Applied | Satisfactory | 66% | 20% | Review of Due Diligence Evaluation | Yes | Partially Applied | No | [8 empty] | 29 | 53
Did the DevCo complete a Supply Chain Risk-Market Intelligence Assessment in the last quarter? | Supply Chain Risk-Market Intelligence Assessment (Text) | Partially Applied | Satisfactory | 66% | 20% | Completion of supply chain risk-market intelligence assessment | Yes |  | No | [8 empty] | 30 | 54
% of procurement activities executed as planned in the Annual Procurement Plan | Total number of procurement activities (No.) | 29.17% | Satisfactory | 66% | 30% | Number of procurement activities executed as planned / Total number of procurement activities | >60% | 20-60% | <20% |  | Procurement & Contracting Execution Performance | 52% | 70% |  |  |  |  | 31 | 55
| Number of procurement activities executed as planned (No.) | [17 empty] | 56
% of deviations in total awarded contract value with approved TDC | Value of Awarded Contract (No.) | 100% | Needs Improvement | 33% | 30% | (Value of Contract Awarded - Tender Cost Estimate) / Value of Award Contract | <20% | 20-60% | >60% | [8 empty] | 32 | 57
| Tender Cost Estimate (No.) | [17 empty] | 58
% of contracts with pending claims | % of contracts with filed claims (%) | 32.5% | Satisfactory | 66% | 20% | % of contracts with filed claims | <20% | 20-60% | >60% | [8 empty] | 33 | 62
% of Payment Certificates and payments being processed within the contractual payment terms? | % payment paid within contractual terms (%) | 98.7% | Needs Improvement | 33% | 10% | Processing of payment certificates and payments | <10% | 10-20% | >20% | [8 empty] | 34 | 64
Are Vendor performance assessment occurring which capture financial instability, delays, repeated quality issues in real-time? | Alignment of sourcing strategies with project schedules and requirements (Text) | Partially Applied | Satisfactory | 66% | 10% | Vendor performance assessment | Yes | Partially Applied | No | [8 empty] | 35 | 66
Does the HSE Management Manual have adequate provision for identification and escalation of high risk activities? | Escalation criteria for high risk activities (Text) | Yes | Good | 100% | 4% | Provision for identification and escalation of high risk activities | Yes | Partially Applied | No |  | HSE Compliance | 78% | 50% |  | HSE and Welfare | 80% |  | 36 | 68
Has the DevCo provided a NCR Safety Register? | NCR safety register (Text) | No | Needs Improvement | 33% | 1% | Review of NCR safety register | Yes | Partially Applied | No | [8 empty] | 37 | 69
Is the rate of review of the Safety Risk Register in accordance with the HSE Management Manual? | HSE Risk Register Review Rate (Text) | Yes | Good | 100% | 2% | Review rate of safety risk register | Yes | Partially Applied | No | [8 empty] | 38 | 70
% of closed Safety Risk items | Total number of Safety Risk items (No.) | 92.81% | Good | 100% | 4% | Total number of closed Safety Risk items / Total number of safety risk items | >80% | 60-80% | <60% | [8 empty] | 39 | 71
| Total number of closed Safety Risk items (No.) | [17 empty] | 72
Average cycle time to close Safety Risk items | Cycle time to close Safety Risk items (in days) (No.) | 30 | Needs Improvement | 33% | 4% | To input final number Sum (Cycle time to close safety risk items) / Total number of closed safety risk items | <7 days | 7-14 days | >14 days | [8 empty] | 40 | 73
Has the DevCo provided a a Safety Incident Register? | Safety incident register (Text) | No | Needs Improvement | 33% | 1% | Review of safety incident register | Yes | Partially Applied | No | [8 empty] | 41 | 74
Average cycle time to close Safety Incident | Cycle time to close Safety Incident (in days) (No.) | 30 | Needs Improvement | 33% | 4% | To input final number. Sum (Cycle time to close safety incident) / Total number of closed safety incidents | <7 days | 7-14 days | >14 days | [8 empty] | 42 | 75
Is the emergency drill rate compliant with EEPP? | Planned number of Emergency Drills (No.) | Yes | Good | 100% | 5% | Compliance of emergency drill rate | Yes | Partially Applied | No | [8 empty] | 43 | 76
| Actual number of Emergency Drills (No.) | [17 empty] | 77
| Recommended time to complete Emergency drills (No.) | [17 empty] | 78
| Actual Time to complete Emergency drills (No.) | [17 empty] | 79
Fatality Rate (FR) | No. of incidents resulting in fatality or severe impairment per 200,000 work hours (No.) | 0 | Good | 100% | 15% | No. of incidents resulting in fatality or severe impairment per 200,000 work hours | 0% | 0.001-0.0199 | >0.02 | [8 empty] | 44 | 82
Lost Time Injury Frequency Rate (LTIFR) | No. of incidents resulting in lost time per 200,000 work hours (No.) | 0 | Good | 100% | 10% | No. of incidents resulting in lost time per 200,000 work hours | <0.1 | 0.1-1.5 | >1.5 | [8 empty] | 45 | 83
Total Recordable Incident Rate (TRIR) | No. of recordable incidents per 200,000 work hours (No.) | 0 | Good | 100% | 10% | No. of recordable incidents per 200,000 work hours | <0.5 | 0.5-5 | >5 | [8 empty] | 46 | 84
Near Miss Rate | No. of near misses recorded per 200,000 work hours (No.) | 0.73 | Satisfactory | 66% | 15% | No. of near misses recorded per 200,000 work hours | >30 | 0.1-30 | 0% | [8 empty] | 47 | 85
Safety Observation Rate | No. of safety observation recorded per 200,000 work hours (No.) | 346 | Good | 100% | 10% | No. of safety observation recorded per 200,000 work hours | >200 | 10-200 | <10 | [8 empty] | 48 | 86
Is there evidence of Leadership Safety Walks occuring? | Total number of Safety Walks with Leadership (No.) | Data Not Available | Needs Improvement | 33% | 15% | Total number of Safety Walks with Leadership / Total number of Safety Walks | Yes | Partially Applied | No | [8 empty] | 49 | 88
Is the DevCo tracking & monitoring Grievances? | Total number of grievances (No.) | Yes | Good | 100% | 15% | Review of Welfare Monitoring documentation | Yes | Partially Applied | No |  | Welfare Compliance | 83% | 50% |  |  |  |  | 50 | 90
Has the DevCo demonstrated active management in closing out Grievances? | Cycle time to close grievances (No.) | Yes | Good | 100% | 10% | Review of Welfare Monitoring documentation | Yes | Partially Applied | No | [8 empty] | 51 | 91
Does the DevCo set targets and monitor the minimum number of HSE & Welfare staff vs the total workforce? | DevCo staffing register (Text) | Yes | Good | 100% | 20% | Review of Welfare Monitoring documentation | Yes | Partially Applied | No | [8 empty] | 52 | 94
Does the DevCo track and monitor closeout of welfare observations? | Total number of Closed Welfare Observations (No.) | Yes | Good | 100% | 10% | Review of Welfare Monitoring documentation | Yes | Partially Applied | No | [8 empty] | 53 | 96
Has the DevCo demonstrated closeout of Welfare Non-compliances is occuring? | Total Closed Welfare Non-compliances (No.) | Yes | Good | 100% | 20% | Review of Welfare Monitoring documentation | Yes | Partially Applied | No | [8 empty] | 54 | 97
Is frequency of Labor Accommodation Inspection occurring in accordance with VMMP? | Mitigation measures in the event of welfare audit observations & recommendations (Text) | No | Needs Improvement | 33% | 25% | Labor accommodation inspection frequency | Yes | Partially Applied | No | [8 empty] | 55 | 98
Go to Main Page
Go to Document
Go to Input
Note on A6: DC-AC-001
Note on B6: DC-DP-001
Note on B7: DC-DP-002
Note on A8: DC-AC-002
Note on B8: DC-DP-003
Note on A9: DC-AC-003
Note on B9: DC-DP-004
Note on A10: DC-AC-004
Note on B10: DC-DP-005
Note on A11: DC-AC-005
Note on B11: DC-DP-006
Note on A12: DC-AC-006
Note on B12: DC-DP-007
Note on A13: DC-AC-007
Note on B13: DC-DP-008
Note on A14: DC-AC-008
Note on B14: DC-DP-009
Note on A15: DC-AC-009
Note on B15: DC-DP-013
Note on B16: DC-DP-014
Note on A17: DC-AC-010
Note on B17: DC-DP-015
Note on A18: DC-AC-011
Note on B18: DC-DP-017
Note on B19: DC-DP-018
Note on A20: DC-AC-012
Note on B20: DC-DP-021
Note on A21: DC-AC-013
Note on B21: DC-DP-022
Note on B22: DC-DP-023
Note on A23: DC-AC-014
Note on B23: DC-DP-024
Note on A24: DC-AC-015
Note on B24: DC-DP-025
Note on B25: DC-DP-026
Note on A26: DC-AC-016
Note on B26: DC-DP-027
Note on B27: DC-DP-028
Note on A28: DC-AC-017
Note on B28: DC-DP-029
Note on B29: DC-DP-030
Note on A30: DC-AC-018
Note on B30: DC-DP-031
Note on B31: DC-DP-032
Note on A32: DC-AC-019
Note on B32: DC-DP-033
Note on A33: DC-AC-020
Note on B33: DC-DP-034
Note on B34: DC-DP-035
Note on A35: DC-AC-021
Note on B35: DC-DP-036
Note on A36: DC-AC-022
Note on B36: DC-DP-037
Note on A37: DC-AC-023
Note on B37: DC-DP-038
Note on A38: DC-AC-024
Note on B38: DC-DP-039
Note on B39: DC-DP-040
Note on A40: DC-AC-025
Note on B40: DC-DP-041
Note on A41: DC-AC-026
Note on B41: DC-DP-049
Note on B42: DC-DP-050
Note on A43: DC-AC-027
Note on B43: DC-DP-051
Note on A44: DC-AC-028
Note on B44: DC-DP-052
Note on A45: DC-AC-029
Note on B45: DC-DP-053
Note on A46: DC-AC-030
Note on B46: DC-DP-054
Note on A47: DC-AC-031
Note on B47: DC-DP-055
Note on B48: DC-DP-056
Note on A49: DC-AC-032
Note on B49: DC-DP-057
Note on B50: DC-DP-058
Note on A51: DC-AC-033
Note on B51: DC-DP-062
Note on A52: DC-AC-034
Note on B52: DC-DP-064
Note on A53: DC-AC-035
Note on B53: DC-DP-066
Note on A54: DC-AC-036
Note on B54: DC-DP-068
Note on A55: DC-AC-037
Note on B55: DC-DP-069
Note on A56: DC-AC-038
Note on B56: DC-DP-070
Note on A57: DC-AC-039
Note on B57: DC-DP-071
Note on B58: DC-DP-072
Note on A59: DC-AC-040
Note on B59: DC-DP-073
Note on A60: DC-AC-041
Note on B60: DC-DP-074
Note on A61: DC-AC-042
Note on B61: DC-DP-075
Note on A62: DC-AC-043
Note on B62: DC-DP-076
Note on B63: DC-DP-077
Note on B64: DC-DP-078
Note on B65: DC-DP-079
Note on A66: DC-AC-044
Note on B66: DC-DP-082
Note on A67: DC-AC-045
Note on B67: DC-DP-083
Note on A68: DC-AC-046
Note on B68: DC-DP-084
Note on A69: DC-AC-047
Note on B69: DC-DP-085
Note on A70: DC-AC-048
Note on B70: DC-DP-086
Note on A71: DC-AC-049
Note on B71: DC-DP-088
Note on A72: DC-AC-050
Note on B72: DC-DP-090
Note on A73: DC-AC-051
Note on B73: DC-DP-091
Note on A74: DC-AC-052
Note on B74: DC-DP-094
Note on A75: DC-AC-053
Note on B75: DC-DP-096
Note on A76: DC-AC-054
Note on B76: DC-DP-097
Note on A77: DC-AC-055
Note on B77: DC-DP-098

## InterviewQuestion(D&C)
PIF Project Lighthouse
InterviewQuestion(D&C)
SN | Question | Date of Interview | Response | Internal Comment | Follow Up Question
1 | What are the challenges in implementation of the Project Execution Plan and how are you managing those? | 2025-05-09 16:05
2 | Have there been any setbacks with the required land acquisition, if so, what are they and how do you plan to overcome the issues? | 2025-05-09 16:05
3 | Have any delays occurred due to stakeholder objections; how did you resolve the issue? | 2025-05-09 16:05
4 | Have there been any challenges with labor camp establishment, number, quality or provision of amenities in accordance with workforce estimates? | 2025-05-09 16:05
5 | Have there been any challenges in hiring the required skilled labor workforce, how do you plan to overcome this? | 2025-05-09 16:05
6 | How do you track and record workforce retention and turnover rate? | 2025-05-09 16:05
7 | How do you track and record plant/ equipment downtime? | 2025-05-09 16:05
8 | What are the reasons for any deviations from the approved design intent? | 2025-05-09 16:05
9 | Have there been delays in the approval's workflow, if so, what actions have been taken to resolve the delays? | 2025-05-09 16:05
10 | Have material or product availability and lead times led to substitution requests? | 2025-05-09 16:05
11 | Has the required number of ITPs been signed off throughout construction? | 2025-05-09 16:05
12 | Out of all the defects and NCRs raised, how many are closed out? | 2025-05-09 16:05
13 | What are the challenges preventing adherence to the planned number of audits, what measures have you undertaken to resolve the challenges? | 2025-05-09 16:05
14 | Have any Vendors failed to deliver the work under contact, what has been done to resolve the issue and to track Vendor performance? | 2025-05-09 16:05
15 | What strategies are in place to catch up on the procurement schedule, can you show evidence this is working? | 2025-05-09 16:05
16 | What level of market intelligence has been applied to the Supply Chain Risk Assessment, provide example. | 2025-05-09 16:05
17 | Is the DevCo aware of suppliers/contractors not fulfilling service delivery compliance requirement as per contract terms (contract KPI compliance). Are there any mitigation measures in place? Provide example. | 2025-05-09 16:05
18 | Are there any claims or disputes resulting in financial risk, project disruption or legal escalation? Are these resolved within contractually agreed timelines? What is the plan for resolution? | 2025-05-09 16:05
19 | Were there procurement bottlenecks due to approval delays, bid evaluation inefficiencies, or poor planning, negatively impacting project schedules, what is being done to resolve this? Provide example. | 2025-05-09 16:05
20 | Of the incidents / safety concerns raised, are there any that are difficult to resolve and why? | 2025-05-09 16:05
21 | What mitigation measures have been implemented as a result of incidents and safety observations raised? How many have had mitigation measures put in place? Provide an example. | 2025-05-09 16:05
22 | Are there any recurring incidents / safety observations outside of your control, if so, please provide detail? | 2025-05-09 16:05
23 | What are the challenges preventing leadership safety walks, what measures have you undertaken to resolve the challenges? | 2025-05-09 16:05
24 | Have there been challenges in sourcing qualified HSE&W leaders? If so, what have you done to resolve the shortfall, such as training? Do you maintain a training register? If so, please provide a sample. | 2025-05-09 16:05
25 | What mitigation measures have been implemented as a result of welfare audit observations & recommendations? | 2025-05-09 16:05
Go to Main Page

## AddDataPoint(D&C)
PIF Project Lighthouse
AddDataPoint(D&C) | [5 empty] | Land Acquisition Requirements |  |  |  |  | Quality Audits |  |  | Procurement Packages |  |  |  |  | Incident Management | [5 empty] | Compliance Management - Audits/Inspections |  |  |  |  | Compliance Management - Actions |  |  |  |  | Safety Trainings
SN | Data Source | Additional Data Point | Input Value | Scorecard Visualization |  | SN | Program | Acquired (Ha) | Under Negotiation (Ha) | Pending (Ha) | SN | Month | Number of Quality Audits | SN | Parameter | Baseline | Actual | Forecast | SN | Incident Category | Number of Incidents (To-Date) | Number of Investigations in Progress | Number of Investigations Completed | Number of Investigations Pending Approval | SN | Audits/Inspections | In Progress_audits | Completed_audits | Remaining Planned | SN | Actions | In Progress_actions | Completed_actions | Pending Approval | SN | Year | Value_training
1 |  | Packaging & Phasing Strategy (Text) |  | Used for Dashboard | 10 | 1 |  |  |  |  | 1 | Jan |  | 1 |  |  |  |  | 1 | Fatalities |  |  |  |  | 1 | HSE Audit |  |  |  | 1 | HSE |  |  |  | 1 | Jan
2 |  | Execution & Site Logistics (Text) |  | Used for Dashboard | 11 | 2 |  |  |  |  | 2 | Feb |  | 2 |  |  |  |  | 2 | Severe Impairment |  |  |  |  | 2 | Welfare Inspection |  |  |  | 2 | Welfare |  |  |  | 2 | Feb
3 |  | Procurement Strategy (Text) |  | Used for Dashboard | 12 | 3 |  |  |  |  | 3 | Mar | [6 empty] | 3 | Lost Time Incidents | [14 empty] | 3 | Mar
4 |  | Land Acquisition Requirements (Program, Acquired (Ha), Under Negotiation (Ha), Pending (Ha)) (No.) |  | Used for Dashboard (Manual) | 16 | [5 empty] | 4 | Apr | [6 empty] | 4 | Recordable Incidents | [14 empty] | 4 | Apr
5 |  | Workforce Availability (Text) |  | Used for Dashboard | 19 | [5 empty] | 5 | May | [6 empty] | 5 | Near Misses | [14 empty] | 5 | May
6 |  | Resource Availability (Text) |  | Used for Dashboard | 20 | [5 empty] | 6 | Jun | [22 empty] | 6 | Jun
7 |  | Number of NCRs open for between 30 and 60 days (No.) |  | Used for Dashboard | 42 | [5 empty] | 7 | Jul | [22 empty] | 7 | Jul
8 |  | Number of NCRs open for more than 60 days (No.) |  | Used for Dashboard | 43 | [5 empty] | 8 | Aug | [22 empty] | 8 | Aug
9 |  | Leadership engagement (Text) |  | Used for Dashboard | 44 | [5 empty] | 9 | Sep | [22 empty] | 9 | Sep
10 |  | Total number of ITPs requested (No.) |  | Used for Dashboard | 45 | [5 empty] | 10 | Oct | [22 empty] | 10 | Oct
11 |  | Total number of ITPs completed (No.) |  | Used for Dashboard | 46 | [5 empty] | 11 | Nov | [22 empty] | 11 | Nov
12 |  | Completeness of Quality Management Plan (Text) |  | Used for Dashboard | 47 | [5 empty] | 12 | Dec | [22 empty] | 12 | Dec
13 |  | Quality Audits (SN, Month, Number of Quality Audits) |  | Used for Dashboard (Manual) | 48
14 |  | Contract clauses (Text) |  | Used for Dashboard | 59
15 |  | Procurement Management Plan (Text) |  | Used for Dashboard | 60
16 |  | Scope / design maturity (Text) |  | Used for Dashboard | 61
17 |  | Tender pack quality (Text) |  | Used for Dashboard | 63
18 |  | % payment paid within contractual terms (%) |  | Used for Dashboard | 65
19 |  | Procurement Packages (SN, Parameter, Baseline, Actual, Forecast) (No.) |  | Used for Dashboard (Manual) | 67
20 |  | Number of Notifiable Incidents (No.) |  | Used for Dashboard | 80
21 |  | Number of Infringement Notices (No.) |  | Used for Dashboard | 81
22 |  | Incident Management (SN, Incident Category, Number of Incidents, Number of Investigations in Progress, Number of Investigations Completed, Number of Investigations Pending Approval) (No.) |  | Used for Dashboard (Manual) | 89
23 |  | Total Site Manhours (No.) |  | Used for Dashboard | 95
24 |  | Compliant Management - Audits/Inspections (Audit/Inspections, InProgress_audits, Completed_audits, Remaining Planned) |  | Used for Dashboard (Manual) | 99
25 |  | Compliance Management - Actions (Action, InProgress_actions, Completed_actions, Pending Approval) (Text) |  | Used for Dashboard (Manual) | 100
26 |  | Incident Management (Incident Category, Number of Incidents, Number of Investigations in Progress, Number of Investigations Completed, Number of Investigations Pending Approval) (No.) |  | Used for Dashboard (Manual) | 101
27 |  | Safety Trainings (Year, Value_training) |  | Used for Dashboard (Manual) | 102
Go to Main Page
Note on C6: DC-DP-010
Note on C7: DC-DP-011
Note on C8: DC-DP-012
Note on C9: DC-DP-016
Note on C10: DC-DP-019
Note on C11: DC-DP-020
Note on C12: DC-DP-042
Note on C13: DC-DP-043
Note on C14: DC-DP-044
Note on C15: DC-DP-045
Note on C16: DC-DP-046
Note on C17: DC-DP-047
Note on C18: DC-DP-048
Note on C19: DC-DP-059
Note on C20: DC-DP-060
Note on C21: DC-DP-061
Note on C22: DC-DP-063
Note on C23: DC-DP-065
Note on C24: DC-DP-067
Note on C25: DC-DP-080

## DevCoAssessmentInput(CE&O)
PIF Project Lighthouse
DevCoAssessmentInput(CE&O)
Assessment Criteria | Data Point | Input Value | Data Source | Assessor Remarks | Assessment Time Stamp | Reviewer Remarks | Review Time Stamp | Formula
Budget Variance | PIF Approved Capex budget (Initial Business Plan) | 204358702695.6711 | DR-003-01 | This is the reported budget approved by the Board of Director in the cost report in Q3 2023. This is not the budget at the time of the DevCo inception. |  |  |  | [Forecast Budget - PIF Approved Capex budget (Initial Business Plan)]/ PIF Approved Capex budget (Initial Business Plan) | 1 | 1
| Forecast budget (EAC) | 349203458382.3173 | DR-003-01 | The value reported in the cost report considers the total development cost at completion. However, this forecast is not the budget approved by the Board of Director and may still evolve. There is a significant budget increase over a short period. There is also a SAR 10bn budget for projects that are either cancelled, on hold or not initiated, highlighting the opportunity of a potential saving. | [5 empty] | 2
% of projects having Budget Variance | Number of Projects with Budget Variance | 102 | DR-065 | 102 projects (including approved and unapproved) have had variations from their original approved COST ESTIMATE (due to increasing uncommitted costs and update in Order of Cost estimates as a result of updation of Master plan and concept designs) |  |  |  | Number of Projects with Budget Variance / Total number of Projects | 2 | 3
| Total number of projects (No.) | 239 | DR-003-01 | - The total number of projects has been taken from the Cost Report. - This number of split in 4 portfolios and 39 Districts. - There are 9 projects on hold, 4 projects cancelled and 2 projects not initiated. | [5 empty] | 4
% of projects with contingency utilization rate > 1 | Number of projects with contingency utilization > 1 | Data Not Available | DR-003-01 | The contingency utilised as per the Cost data template provided shows no projects having utilised contingency. However, an increase in the allocated contigency is noted. This matter has been discussed with DevCo, and they are expected to provide clarity on this requirement |  |  |  | (Number of projects with contingency utilization > 1) / (Total number of projects) | 3 | 6
% of projects with Approved Change Requests (design/construction) having a cost impact greater than 2% | No. of projects with approved change request having a cost impact greater than 2% | Data Not Available | DR-003-01 | A number of projects have been affected by variations. However, the report is not specifically highlighting those which cost impact are over 2% of the budget. |  |  |  | (No. of projects with approved change request having a cost impact greater than 2%) / (Total number of projects) | 4 | 8
% of projects with Approved Claims | No. of projects with approved claims | 1 | DR-054 | The Commercial report does not explicitly address approved claims but rather reports the top 10 claims only. However, DR-054 (Claim register) indicated only 1 project with an approved claim. (SAR0.83m). The scoring here reports the data provided in DR-054. Should we choose to consider the commercial report, the rating and score will change accordingly. |  |  |  | (No. of projects with approved claims) / (Total number of projects) | 5 | 11
% of provisional sums of the latest PIF Approved Capex budget | Total provisional sums | Data Not Available | DR-003-01 | Although the DevCo is reporting using provisional sums budget to fund some projects (eg super packages), there is no indication of the utilisation of provisional sums. DevCo has confirmed that it is available at the project level and was requested to provide this data. |  |  |  | Total Provisional Sums/Latest Approved Budget | 6 | 23
| Latest Approved budget (No.) | Data Not Available | DR-003-01 | The latest provisionnal sums approved budget is not reported in any document provided. | [5 empty] | 24
% of variance of Allocated Provisional sums against the awarded amount | Actual Utilized Provisional Sums | Data Not Available | DR-003-01 | Although the DevCo is reporting using provisional sums budget to fund some projects (eg super packages), there is no indication of the utilisation of provisional sums |  |  |  | (Total Provisional Sums−Actual Utilized Provisional Sums)/Total Provisional Sums | 7 | 25
Go to Main Page
Go to Document
Go to Analysis
Note on A6: CEO-AC-001
Note on B6: CEO-DP-001
Note on B7: CEO-DP-002
Note on A8: CEO-AC-002
Note on B8: CEO-DP-003
Note on B9: CEO-DP-004
Note on A10: CEO-AC-003
Note on B10: CEO-DP-006
Note on A11: CEO-AC-004
Note on B11: CEO-DP-008
Note on A12: CEO-AC-005
Note on B12: CEO-DP-011
Note on A13: CEO-AC-006
Note on B13: CEO-DP-023
Note on B14: CEO-DP-024
Note on A15: CEO-AC-007
Note on B15: CEO-DP-025

## DevCoAssessmentAnalysis(CE&O)
PIF Project Lighthouse
DevCoAssessmentAnalysis(CE&O)
Assessment Criteria | Data Point | Value | Rating | Score | Assessment Criteria Weightage | Assessment Guideline/Formula | Good | Satisfactory | Needs Improvement | Remarks 1 | Performance Signal | Performance Signal Score | Performance Signals Weightage | Remarks 2 | Key Topic | Key Topic Score | Remarks 3
Number of Projects with Budget Variance | PIF Approved Capex budget (Initial Business Plan) (No.) | 70.88% | Needs Improvement | 33% | 80% | [Forecast Budget - PIF Approved Capex budget (Initial Business Plan)]/ PIF Approved Capex budget (Initial Business Plan) | <10% | 10-20% | >20% | 102 | Budget Variance | 33% | 60% | DR-065 | Overall Budget | 38% | 102 projects( ncluding approved and un approved) have had variations from their original approved COST ESTIMATE (due to increasing uncommitted costs and update in Order of Cost estimates as a result of updation of Master plan and concept designs) | 1 | 1
| Forecast budget (EAC) (No.) | [17 empty] | 2
Budget Variance | Number of Projects with Budget Variance (No.) | 42.68% | Needs Improvement | 33% | 20% | Number of Projects with Budget Variance / Total number of Projects | <10% | 10-30% | >30% | 102 | [7 empty] | 2 | 3
| Total number of projects (No.) | [17 empty] | 4
% of projects with contingency utilization rate > 1 | Number of projects with contingency utilization > 1 (No.) | Data Not Available | Needs Improvement | 33% | 20% | (Number of projects with contingency utilization > 1) / (Total number of projects) | <10% | 10-30% | >30% | The DevCo has addressed contigencies in its commercial update report. However, the specific data point is not reported. The scoring reflects this fact. The specific data point has therefore been requested from the DevCo and should easily be provided by the DevCo. The scoring will naturally improve upon provision of such data. | Budget Trend | 59% | 20% |  |  |  |  | 3 | 6
% of projects with Approved Change Requests (design/construction) having a cost impact greater than 2% | No. of projects with approved change request having a cost impact greater than 2% (No.) | Data Not Available | Needs Improvement | 33% | 40% | (No. of projects with approved change request having a cost impact greater than 2%) / (Total number of projects) | <5% | 5-15% | >15% | The DevCo has a change register. However, the specific data point is not reported. The scoring reflects this fact. The specific data point has therefore been requested from the DevCo and should easily be provided by the DevCo. The scoring will naturally improve upon provision of such data. | [7 empty] | 4 | 8
% of projects with Approved Claims | No. of projects with approved claims (No.) | 0.4184% | Good | 100% | 40% | (No. of projects with approved claims) / (Total number of projects) | <2% | 2-5% | >5% | The Commercial report does not explicitly address approved claims but rather reports the top 10 claims only. However, DR-054 (Claim register) indicated only 1 project with an approved claim. (SAR0.83m). The scoring here reports the data provided in DR-054. Should we choose to consider the commercial report, the rating and score will change accordingly. | [7 empty] | 5 | 11
% of provisional sums of the latest PIF Approved Capex budget | Total provisional sums (No.) | Data Not Available | Needs Improvement | 33% | 40% | Total Provisional Sums/Latest Approved Budget | <5% | 5-15% | >15% | The DevCo reported in the commercial update report that provisional sums have been used to fund projects. However, the specific data points are not reported. The scoring reflects this fact. The specific data points have therefore been requested from the DevCo and should easily be provided by the DevCo. The scoring will naturally improve upon provision of such data. | Provisional Sum Utilization | 33% | 20% |  |  |  |  | 6 | 23
| Latest Approved budget (No.) | [17 empty] | 24
% of variance of Allocated Provisional sums against the awarded amount | Actual Utilized Provisional Sums (No.) | Data Not Available | Needs Improvement | 33% | 60% | (Total Provisional Sums−Actual Utilized Provisional Sums)/Total Provisional Sums | <10% | 10-20% | >20% | The DevCo reported in the commercial update report that provisional sums have been used to fund projects. However, the specific data point is not reported. The scoring reflects this fact. The specific data point has therefore been requested from the DevCo and should easily be provided by the DevCo. The scoring will naturally improve upon provision of such data. | [7 empty] | 7 | 25
Go to Main Page
Go to Document
Go to Input
Note on A6: CEO-AC-001
Note on B6: CEO-DP-001
Note on B7: CEO-DP-002
Note on A8: CEO-AC-002
Note on B8: CEO-DP-003
Note on B9: CEO-DP-004
Note on A10: CEO-AC-003
Note on B10: CEO-DP-006
Note on A11: CEO-AC-004
Note on B11: CEO-DP-008
Note on A12: CEO-AC-005
Note on B12: CEO-DP-011
Note on A13: CEO-AC-006
Note on B13: CEO-DP-023
Note on B14: CEO-DP-024
Note on A15: CEO-AC-007
Note on B15: CEO-DP-025

## InterviewQuestion(CE&O)
PIF Project Lighthouse
InterviewQuestion(CE&O)
SN | Question | Date of Interview | Response | Internal Comment | Follow Up Question
1 | What corrective actions were taken when a project exceeds its budget? | 2025-05-09 16:05
2 | What had been the three key factors contributing to budget overruns? | 2025-05-09 16:05
3 | Based on the revisions to the budget did the DevCo perform any trend analysis to understand the root cause factors contributing to such revisions and was the same recorded in the lessons learnt repository? | 2025-05-09 16:05
4 | Which project categories or project stages requested for more budget than planned? | 2025-05-09 16:05
5 | Was the scope of work identified for Provisional sums defined at concept stage? | 2025-05-09 16:05
6 | Was the amount estimated based on historical benchmarking rates? If yes, please provide a sample. | 2025-05-09 16:05
Go to Main Page

## AddDataPoint(CE&O)
PIF Project Lighthouse
AddDataPoint(CE&O) | [5 empty] | Budget Performance
SN | Data Source | Additional Data Point | Input Value | Scorecard Visualization |  | Year | Budget Value (Baseline) in M SAR | Budget Value (Revised) in M SAR | Budget Value (Forecast) in M SAR
1 | DR-003-01 | Total Expenditure to Date | 33213178137.7779 | Used for Dashboard | 5
2 | DR-003-01 | Contingency utilized at DevCo level | 1183022352 | Used for Dashboard | 7
3 |  | Value of Changes in Design Stage |  | Used for Dashboard | 9
4 |  | Value of Changes in Construction Stage |  | Used for Dashboard | 10
5 |  | Number of Changes (Concept MP) |  | Used for Dashboard | 12
6 |  | Number of Changes (Detailed MP) |  | Used for Dashboard | 13
7 |  | Number of Changes (Concept Design) |  | Used for Dashboard | 14
8 |  | Number of Changes (Detailed Design) |  | Used for Dashboard | 15
9 |  | Number of Changes (Construction) |  | Used for Dashboard | 16
10 |  | Total Awarded Cost | 83140439457.2953 | Used for Dashboard | 17
11 |  | Approved Variations and Claims |  | Used for Dashboard | 18
12 | DR-065 | Uncommitted Cost | 266140780170.0221 | Used for Dashboard | 19
13 |  | Pending Variations |  | Used for Dashboard | 20
14 |  | Anticipated Variations |  | Used for Dashboard | 21
15 |  | Budget Performance (Year, Budget Value Baseline, Budget Value Revised, Budget Value Forecast) (No.) |  | Used for Dashboard (Manual) | 22
Go to Main Page
Note on C6: CEO-DP-005
Note on C7: CEO-DP-007
Note on C8: CEO-DP-009
Note on C9: CEO-DP-010
Note on C10: CEO-DP-012
Note on C11: CEO-DP-013
Note on C12: CEO-DP-014
Note on C13: CEO-DP-015
Note on C14: CEO-DP-016
Note on C15: CEO-DP-017
Note on C16: CEO-DP-018
Note on C17: CEO-DP-019
Note on C18: CEO-DP-020
Note on C19: CEO-DP-021
Note on C20: CEO-DP-022

## DevCoAssessmentInput(I&T)
PIF Project Lighthouse
DevCoAssessmentInput(I&T)
Assessment Criteria | Data Point | Input Value | Data Source | Assessor Remarks | Assessment Time Stamp | Reviewer Remarks | Review Time Stamp | Formula
Is there an innovation Strategy or document that lists the key focus areas and initiatives across design, construction and operation and aligned with DevCo strategic plan? | Availability of an innovation strategy (%) | 5% | DR-067-01 | DevCo’s framework is currently decentralized (across all departments). Each department pursues innovation which would bring value to their respective function. DevCo targets the creation of a centralized innovation hub to integrate innovation efforts across all departments |  |  |  | Innovation Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10% | 1 | 1
| Alignment of innovation strategy with DevCo Strategic Plan (%) | 5% | DR-067-01 | High level description of alignment of innovation initiatives to overall DevCo strategy | [5 empty] | 2
| List of focus areas of innovation and technology (%) | 10% | DR-067-01 | 7 focus areas identified: construction methods & systems, smart city services, digital transformation, security strategy & design, mobility, sustainability and built environment | [5 empty] | 3
| List of innovative initiatives throughout project lifecycle (design, construction and operation) (%) | 10% | DR-067-01 | 15 innovation initiatives in progress | [5 empty] | 4
| Availability of innovation cost-benefit analysis (%) | 0% |  | N.A. | [5 empty] | 5
| Availability of implementation roadmap (%) | 5% | DR-067-01 | Implementation roadmap only available for individual initatives but not for an overall strategy | [5 empty] | 6
| Process for innovation (%) | 5% | DR-067-01 | No holistic DevCo-level innovation process and framework, but individual departments have their own approach to adopting innovation. | [5 empty] | 7
| Budget of implementation (%) | 5% | DR-068 | No overall budget seen. But there is a smart city team coordinating and overseeing all implementation across masterplans | [5 empty] | 8
Is there a smart city Strategy or document that lists the key focus areas of smart city aligned with DevCo strategic plan? | Availability of a smart city strategy (%) | 15% | DR-068 | Robust Smart City Strategy. |  |  |  | Smart City Strategy: Availability 15%; Strategic Alignment 15%; Adequate key focus areas 10%; Adequate detailed initiatives 10%; Smart city goals nad KPIs 10%; CBA 10%; Implementation Roadmap 10%; Process formulated 10%; Budget of implementation 10% | 2 | 10
| Alignment of smart city strategy with DevCo Strategic Plan (%) | 15% | DR-068 | Smart Diriyah Strategy aligns with overall organization outcome focusing on sustainability, heritage and liveability. | [5 empty] | 11
| List of Smart City focus areas (%) | 10% | DR-068 | 5 main pillars defined | [5 empty] | 12
| List of smart city initiatives within each key focus area (%) | 10% | DR-068 | 50 smart services identified | [5 empty] | 13
| Availability of smart city goals and set of KPIs (%) | 5% | DR-068 | Limited specific KPIs and goals | [5 empty] | 14
| Availability of smart city cost-benefit analysis (%) | 8% | DR-068 | Individual initiatives will require respective business case | [5 empty] | 15
| Implementation Roadmap for selected smart city initiatives (%) | 5% | DR-068 | Fragmented across masterplans with no overarching roadmap | [5 empty] | 16
| Process for smart city implementation (%) | 8% | DR-068 | Multiple documents and guidelines including smart city service design process map, smart city stakeholder engagement matrix and smart city compliance checklist | [5 empty] | 17
| Budget of implementation (%) | 5% | DR-068 | No overall budget seen. But there is a smart city team coordinating and overseeing all implementation across masterplans | [5 empty] | 18
Is there an impact assessment report or identified process/ guidelines to evaluate the impact of the innovation / smart city technologies adoption on DevCo performance? | Availability of approach / process and guidelines to evaluate the impact of implementing innovations and technologies (%) | 15% | DR-068 | Evidence of department-level assessment and evaluation of initiatives but these are not consistent across departments |  |  |  | Adoption on DevCo performance? Robust assessment process and guidelines - 30%; Availability of sample of impact assessment report - 30%; Availability of action plan - 10%; Use of innovative tools/platforms/dashboards - 30% | 3 | 20
| Availability of sample of impact assessment report (%) | 0% |  | N.A. | [5 empty] | 21
| Availability of action plan (%) | 10% | DR-068 | Roadmap and use cases identified for initiatives such as Digital Twin | [5 empty] | 22
| Use of innovative tools/platforms/dashboards (%) | 0% |  | N.A. | [5 empty] | 23
Is there evidence for innovation / smart city technologies successful implementation (in final design report, master plan or other)? | Innovation Adoption Effectiveness Index (strategy & leadership alignment) (%) | 0% |  | N.A. |  |  |  | Effectiveness index in the mentioned areas is an evaluation of successful implementation (Up to 8.3% for each element of the innovation adoption effective index) (Up to 10% for each element of the smart city adoption effective index) | 4 | 24
| Innovation Adoption Effectiveness Index (skilled human resources) (%) | 0% |  | N.A. | [5 empty] | 25
| Innovation Adoption Effectiveness Index (planning & governance) (%) | 4% | DR-068 | Evidence of planning and governance at initiative-level delivering successes such as for Digital Twin in engagement with different user groups to identify and prioritise use cases | [5 empty] | 26
| Innovation Adoption Effectiveness Index (process management) (%) | 4% | DR-068 | Evidence of process management at initiative-level delivering successes such as for Digital Twin with clear roles and responsbilities and deliverables | [5 empty] | 27
| Innovation Adoption Effectiveness Index (partnerships and collaboration) (%) | 8.3% | DR-068 | Evidence of working closely with internal and external stakeholders for innovation initiatives | [5 empty] | 28
| Innovation Adoption Effectiveness Index (resource management) (%) | 6% | DR-068 | Individual department pursue their own initiatives | [5 empty] | 29
| Smart City Adoption Effectiveness Index (strategy & leadership alignment) (%) | 8.3% | DR-068 | Smart Diriyah Strategy aligns with overall organization outcome focusing on sustainability, heritage and liveability. | [5 empty] | 30
| Smart City Adoption Effectiveness Index (infrastructure readiness) (%) | 2% | DR-068 | No deployment seen in completed assets, e.g. Bujairi | [5 empty] | 31
| Smart City Adoption Effectiveness Index (planning & governance) (%) | 6% | DR-068 | Multiple documents and guidelines including smart city service design process map, smart city stakeholder engagement matrix and smart city compliance checklist. No evidence of the final completed checklists | [5 empty] | 32
| Smart City Adoption Effectiveness Index (stakeholder alignment) (%) | 2% | DR-068 | Stakeholder management plan did not appear to have been developed at the onset requiring intensive engagement closer to implementation | [5 empty] | 33
| Smart City Adoption Effectiveness Index (realized benefits & performance) (%) | 4% | DR-068 | None so far. Only some level of validation in smart city platform testbed | [5 empty] | 34
Are there Pilot or R&D projects conducted? | Availability of innovation/smart city piloting or R&D procedures (%) | 5% | DR-068 | No holistic DevCo-level innovation process and framework, but individual departments have their own approach to adopting innovation. |  |  |  | Pilot or R&D projects conducted? Availability - 20%; Adequate list of focus areas - 35%; Procedure - 15%; Outcome assessment robustness - 30% | 5 | 35
| List of focus areas (%) | 30% | DR-068 | 7 focus areas identified: construction methods & systems, smart city services, digital transformation, security strategy & design, mobility, sustainability and built environment. 15 innovation initiatives in progress | [5 empty] | 36
| Procedure (%) | 5% | DR-068 | No holistic DevCo-level innovation process and framework, but individual departments have their own approach to adopting innovation. | [5 empty] | 37
| Robustness of assessment of pilot and R&D outcomes (%) | 0% |  | No evidence of assessment of pilots | [5 empty] | 38
% of pilot / R&D Projects Transitioned into Full-Scale | Number of pilot projects (No.) | 15 | DR-068 | 7 focus areas identified: construction methods & systems, smart city services, digital transformation, security strategy & design, mobility, sustainability and built environment. 15 innovation initiatives in progress |  |  |  | [(Number of pilots that are scaled successfully + Number of R&D projects that are successfully piloted or fully-scaled) / (Number of pilot projects + Number of R&D projects)] | 6 | 39
| Number of R&D projects (No.) | 0 |  | N.A. | [5 empty] | 40
| Number of pilot projects that are scaled successfully (No.) | 3 | DR-068 | Mud bricks, Diriyah digital ecosystem, automation of commercial workflows, | [5 empty] | 41
| Number of R&D projects that are successfully piloted or fully-scaled (No.) | 0 |  | N.A. | [5 empty] | 42
Availability of Innovation unit / department with structured team | Availability of Innovation unit/department (%) | 0% |  | No innovation unit/department |  |  |  | Availability of Innovation: Availability - 20%; Adequate Key positions planned in the org. structure - 30%; Unit/department position within the company hierarchy - 20%; Qualifications of the innovation team - 30% | 7 | 43
| Key positions planned in the innovation unit/department (%) | 0% |  | No innovation unit/department | [5 empty] | 44
| Innovation unit/department within the company hierachy (%) | 0% |  | No innovation unit/department | [5 empty] | 45
| Qualifications of the innovation team (%) | 0% |  | No innovation unit/department | [5 empty] | 46
Availability of Innovation and Technology Strategy / Process & Framework | Innovation Unit Strategy / Process & Framework (%) | 10% | DR-067-01 | No holistic DevCo-level innovation process and framework, but individual departments have their own approach to adopting innovation. |  |  |  | Availability - 50% Implementation of the unit/department framework/ process - 50% | 8 | 47
| Implementation of innovation department process / framework (%) | 10% | DR-067-01 | No holistic DevCo-level innovation process and framework, but individual departments have their own approach to adopting innovation. | [5 empty] | 48
Go to Main Page
Go to Document
Go to Analysis
Note on A6: SO-AC-001
Note on B6: SO-DP-001
Note on B7: SO-DP-002
Note on B8: SO-DP-003
Note on B9: SO-DP-004
Note on B10: SO-DP-005
Note on B11: SO-DP-006
Note on B12: SO-DP-007
Note on B13: SO-DP-008
Note on A14: SO-AC-002
Note on B14: SO-DP-010
Note on B15: SO-DP-011
Note on B16: SO-DP-012
Note on B17: SO-DP-013
Note on B18: SO-DP-014
Note on B19: SO-DP-015
Note on B20: SO-DP-016
Note on B21: SO-DP-017
Note on B22: SO-DP-018
Note on A23: SO-AC-003
Note on B23: SO-DP-020
Note on B24: SO-DP-021
Note on B25: SO-DP-022
Note on B26: SO-DP-023
Note on A27: SO-AC-004
Note on B27: SO-DP-024
Note on B28: SO-DP-025
Note on B29: SO-DP-026
Note on B30: SO-DP-027
Note on B31: SO-DP-028
Note on B32: SO-DP-029
Note on B33: SO-DP-030
Note on B34: SO-DP-031
Note on B35: SO-DP-032
Note on B36: SO-DP-033
Note on B37: SO-DP-034
Note on A38: SO-AC-005
Note on B38: SO-DP-035
Note on B39: SO-DP-036
Note on B40: SO-DP-037
Note on B41: SO-DP-038
Note on A42: SO-AC-006
Note on B42: SO-DP-039
Note on B43: SO-DP-040
Note on B44: SO-DP-041
Note on B45: SO-DP-042
Note on A46: SO-AC-007
Note on B46: SO-DP-043
Note on B47: SO-DP-044
Note on B48: SO-DP-045
Note on B49: SO-DP-046
Note on A50: SO-AC-008
Note on B50: SO-DP-047
Note on B51: SO-DP-048

## DevCoAssessmentAnalysis(I&T)
PIF Project Lighthouse
DevCoAssessmentAnalysis(I&T)
Assessment Criteria | Data Point | Value | Rating | Score | Assessment Criteria Weightage | Assessment Guideline/Formula | Good | Satisfactory | Needs Improvement | Remarks 1 | Performance Signal | Performance Signal Score | Performance Signals Weightage | Remarks 2 | Key Topic | Key Topic Score | Remarks 3
Is there an innovation Strategy or document that lists the key focus areas and initiatives across design, construction and operation and aligned with DevCo strategic plan? | Availability of an innovation strategy (%) | 45% | Needs Improvement | 33% | 30% | Innovation Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10% | >75% | 60-75% | <60% | DevCo’s framework is currently decentralized (across all departments). DevCo targets the creation of a centralized innovation hub to integrate innovation efforts across all departments | Innovation & Technology Deployment | 53% | 40% | Robust smart city strategy and processes however no deployment seen in completed projects | Innovation and Technology Adoption | 41% | While there is a smart city strategy, initiatives have not been operationalized yet. Despite having innovation initiatives in different areas, the lack of a structured process for innovation means efforts are not well-coordinated across the organization. | 1 | 1
| Alignment of innovation strategy with DevCo Strategic Plan (%) | [17 empty] | 2
| List of focus areas of innovation and technology (%) | [17 empty] | 3
| List of innovative initiatives throughout project lifecycle (design, construction and operation) (%) | [17 empty] | 4
| Availability of innovation cost-benefit analysis (%) | [17 empty] | 5
| Availability of implementation roadmap (%) | [17 empty] | 6
| Process for innovation (%) | [17 empty] | 7
| Budget of implementation (%) | [17 empty] | 8
Is there a smart city Strategy or document that lists the key focus areas of smart city aligned with DevCo strategic plan? | Availability of a smart city strategy (%) | 81% | Good | 100% | 30% | Smart City Strategy: Availability 15%; Strategic Alignment 15%; Adequate key focus areas 10%; Adequate detailed initiatives 10%; Smart city goals nad KPIs 10%; CBA 10%; Implementation Roadmap 10%; Process formulated 10%; Budget of implementation 10% | >75% | 60-75% | <60% | Robust Smart City Strategy but no application in completed assets. Full segregation between projects in the Smart Cities' infrastructure, systems, and operations contracts could be considered a risk that may increase costs and cause a lack of integration | [7 empty] | 2 | 10
| Alignment of smart city strategy with DevCo Strategic Plan (%) | [17 empty] | 11
| List of Smart City focus areas (%) | [17 empty] | 12
| List of smart city initiatives within each key focus area (%) | [17 empty] | 13
| Availability of smart city goals and set of KPIs (%) | [17 empty] | 14
| Availability of smart city cost-benefit analysis (%) | [17 empty] | 15
| Implementation Roadmap for selected smart city initiatives (%) | [17 empty] | 16
| Process for smart city implementation (%) | [17 empty] | 17
| Budget of implementation (%) | [17 empty] | 18
Is there an impact assessment report or identified process/ guidelines to evaluate the impact of the innovation / smart city technologies adoption on DevCo performance? | Availability of approach / process and guidelines to evaluate the impact of implementing innovations and technologies (%) | 25% | Needs Improvement | 33% | 10% | Adoption on DevCo performance? Robust assessment process and guidelines - 30%; Availability of sample of impact assessment report - 30%; Availability of action plan - 10%; Use of innovative tools/platforms/dashboards - 30% | >75% | 60-75% | <60% | [8 empty] | 3 | 20
| Availability of sample of impact assessment report (%) | [17 empty] | 21
| Availability of action plan (%) | [17 empty] | 22
| Use of innovative tools/platforms/dashboards (%) | [17 empty] | 23
Is there evidence for innovation / smart city technologies successful implementation (in final design report, master plan or other)? | Innovation Adoption Effectiveness Index (strategy & leadership alignment) (%) | 44.6% | Needs Improvement | 33% | 30% | Effectiveness index in the mentioned areas is an evaluation of successful implementation (Up to 8.3% for each element of the innovation adoption effective index) (Up to 10% for each element of the smart city adoption effective index) | >75% | 60-75% | <60% | No application of smart city initiatives in completed assets Insufficient stakeholder management | [7 empty] | 4 | 24
| Innovation Adoption Effectiveness Index (skilled human resources) (%) | [17 empty] | 25
| Innovation Adoption Effectiveness Index (planning & governance) (%) | [17 empty] | 26
| Innovation Adoption Effectiveness Index (process management) (%) | [17 empty] | 27
| Innovation Adoption Effectiveness Index (partnerships and collaboration) (%) | [17 empty] | 28
| Innovation Adoption Effectiveness Index (resource management) (%) | [17 empty] | 29
| Smart City Adoption Effectiveness Index (strategy & leadership alignment) (%) | [17 empty] | 30
| Smart City Adoption Effectiveness Index (infrastructure readiness) (%) | [17 empty] | 31
| Smart City Adoption Effectiveness Index (planning & governance) (%) | [17 empty] | 32
| Smart City Adoption Effectiveness Index (stakeholder alignment) (%) | [17 empty] | 33
| Smart City Adoption Effectiveness Index (realized benefits & performance) (%) | [17 empty] | 34
Are there Pilot or R&D projects conducted? | Availability of innovation/smart city piloting or R&D procedures (%) | 40% | Needs Improvement | 33% | 50% | Pilot or R&D projects conducted? Availability - 20%; Adequate list of focus areas - 35%; Procedure - 15%; Outcome assessment robustness - 30% | >75% | 60-75% | <60% | Conduct of pilots for different use cases across 7 focus areas: construction methods & systems, smart city services, digital transformation, security strategy & design, mobility, sustainability and built environment. However, efforts are not well-coordinated | Pilot and R&D Transition Rate | 33% | 30% | Innovation initiatives in 7 area including construction methods, digital integration, mobility and sustainability. However, efforts are not well coordinated across the organization |  |  |  | 5 | 35
| List of focus areas (%) | [17 empty] | 36
| Procedure (%) | [17 empty] | 37
| Robustness of assessment of pilot and R&D outcomes (%) | [17 empty] | 38
% of pilot / R&D Projects Transitioned into Full-Scale | Number of pilot projects (No.) | 20% | Needs Improvement | 33% | 50% | [(Number of pilots that are scaled successfully + Number of R&D projects that are successfully piloted or fully-scaled) / (Number of pilot projects + Number of R&D projects)] | >75% | 60-75% | <60% | Pilot projects shared have progressed to implementation. However, no proper mechanism to initiate, perform, track and document pilot projects among all departments | [7 empty] | 6 | 39
| Number of R&D projects (No.) | [17 empty] | 40
| Number of pilot projects that are scaled successfully (No.) | [17 empty] | 41
| Number of R&D projects that are successfully piloted or fully-scaled (No.) | [17 empty] | 42
Availability of Innovation unit / department with structured team | Availability of Innovation unit/department (%) | 0% | Needs Improvement | 33% | 50% | Availability of Innovation: Availability - 20%; Adequate Key positions planned in the org. structure - 30%; Unit/department position within the company hierarchy - 20%; Qualifications of the innovation team - 30% | >60% | 40-60% | <40% | No central innovation unit/department Plans for an innovation hub | Organization Maturity Towards Innovation Adoption | 33% | 30% | No robust and effective processes for innovation management and are staggered across divisions |  |  |  | 7 | 43
| Key positions planned in the innovation unit/department (%) | [17 empty] | 44
| Innovation unit/department within the company hierachy (%) | [17 empty] | 45
| Qualifications of the innovation team (%) | [17 empty] | 46
Availability of Innovation and Technology Strategy / Process & Framework | Innovation Unit Strategy / Process & Framework (%) | 20% | Needs Improvement | 33% | 50% | Availability - 50% Implementation of the unit/department framework/ process - 50% | >50% | 50% | <50% | No holistic DevCo-level innovation process and framework, but individual departments have their own approach to adopting innovation | [7 empty] | 8 | 47
| Implementation of innovation department process / framework (%) | [17 empty] | 48
Go to Main Page
Go to Document
Go to Input
Note on A6: SO-AC-001
Note on B6: SO-DP-001
Note on B7: SO-DP-002
Note on B8: SO-DP-003
Note on B9: SO-DP-004
Note on B10: SO-DP-005
Note on B11: SO-DP-006
Note on B12: SO-DP-007
Note on B13: SO-DP-008
Note on A14: SO-AC-002
Note on B14: SO-DP-010
Note on B15: SO-DP-011
Note on B16: SO-DP-012
Note on B17: SO-DP-013
Note on B18: SO-DP-014
Note on B19: SO-DP-015
Note on B20: SO-DP-016
Note on B21: SO-DP-017
Note on B22: SO-DP-018
Note on A23: SO-AC-003
Note on B23: SO-DP-020
Note on B24: SO-DP-021
Note on B25: SO-DP-022
Note on B26: SO-DP-023
Note on A27: SO-AC-004
Note on B27: SO-DP-024
Note on B28: SO-DP-025
Note on B29: SO-DP-026
Note on B30: SO-DP-027
Note on B31: SO-DP-028
Note on B32: SO-DP-029
Note on B33: SO-DP-030
Note on B34: SO-DP-031
Note on B35: SO-DP-032
Note on B36: SO-DP-033
Note on B37: SO-DP-034
Note on A38: SO-AC-005
Note on B38: SO-DP-035
Note on B39: SO-DP-036
Note on B40: SO-DP-037
Note on B41: SO-DP-038
Note on A42: SO-AC-006
Note on B42: SO-DP-039
Note on B43: SO-DP-040
Note on B44: SO-DP-041
Note on B45: SO-DP-042
Note on A46: SO-AC-007
Note on B46: SO-DP-043
Note on B47: SO-DP-044
Note on B48: SO-DP-045
Note on B49: SO-DP-046
Note on A50: SO-AC-008
Note on B50: SO-DP-047
Note on B51: SO-DP-048

## InterviewQuestion(I&T)
PIF Project Lighthouse
InterviewQuestion(I&T)
SN | Question | Date of Interview | Response | Internal Comment | Follow Up Question
1 | If there is no innovation or smart city strategy, is there a document that lists the areas and initiatives for innovation and smart city technology applied during the design, construction, and operations stages? | 2025-05-09 16:05
2 | Are there guidelines for assessing the impact of innovation and smart city technologies on DevCo performance? | 2025-05-09 16:05
3 | If there is no pilot or R&D register, did you conduct any pilot or R&D projects? what is the number of conducted pilot/ R&D projects? Please provide a sample. | 2025-05-09 16:05
4 | What is the number of pilots / R&D projects that are scaled successfully? | 2025-05-09 16:05
5 | Is there an Innovation unit / department setup? How does the hierarchy look like? | 2025-05-09 16:05
6 | Is there an Innovation Unit strategy/ Process and Framework? If yes, please share a document relating to this. | 2025-05-09 16:05
Go to Main Page

## AddDataPoint(I&T)
PIF Project Lighthouse
AddDataPoint(I&T)
SN | Data Source | Additional Data Point | Input Value | Scorecard Visualization
1 |  | Implementation Success Rate for Innovation Strategy (%) |  | Used for Dashboard | 9
2 |  | Implementation Success Rate for Smart City Strategy (%) |  | Used for Dashboard | 19
Go to Main Page
Note on C6: IT-DP-009
Note on C7: IT-DP-019

## DevCoAssessmentInput(S&O)
PIF Project Lighthouse
DevCoAssessmentInput(S&O)
Assessment Criteria | Data Point | Input Value | Data Source | Assessor Remarks | Assessment Time Stamp | Reviewer Remarks | Review Time Stamp | Formula
Availability of Technical Function Strategy | Availability of strategy | Yes, but very brief | DR-013-01 DR-013-02 DR-013-03 DR-013-04 DR-013-05 DR-018-01 DR-072-01 DR-072-02 DR-072-03 DR-072-05 | 1. Limited technical function strategies related to Design and Delievery are observed at the Master Plan level. 2. While DevCo has defined vision and objectives, there are no documented technical strategy at the DevCo level. 3. Key functional areas such as cost, time, and quality lack formal strategic documentation. |  |  |  | Give 'satisfactory' score if there is a technical function strategy, but it is very general and does not provide specific details of the strategy | 1 | 1
Alignment of Technical Strategy with Organizational Strategy | Alignment of technical functions' strategy and initiatives with the overarching organizational strategy | Misaligned | DR-073 DR-072-05 | 1. No evidence of a clear linkage between technical strategies and organizational objectives. 2. Existing initiatives and new initatives not explicitly mapped to DevCo’s objectives. |  |  |  | Assess if elements of technical strategy is aligned with organizational strategy. "Well aligned " score if key elements of technical strategy such as guidelines are well documented or presented during the meeting with DevCo. | 2 | 2
Severity of Key Challenges Faced in Strategy Execution Technically | Key challenges in strategy execution | Data Not Available |  | No data available on challenges faced during strategy execution. |  |  |  | "Severe" score if challenges faced can impact strategy execution significantly (in terms of time, cost and/or quality) | 3 | 3
Availability of Technical KPIs | Availability of KPIs | Yes, but very brief | DR-074 | 1. Currently there are 15 KPIs identified at the DevCo level, only 7 are technical. 2. Of these 7, only 5 cascade to the Group level, with limited coverage of cost (2) and quality (1). 3. Time-related KPIs receive the most emphasis (4), while areas such as constructability and ESG are not represented. |  |  |  | Give 'satisfactory' score if there are technical KPIs, but they are very generic | 4 | 6
Progress of Achievement of KPIs for Technical Team | Total Number of KPIs set for the preceding year | Yes, but very brief | DR-074 | Currently there are 15 KPIs identified across all functions. Out of Which 7 KPIs are Technical covering Quality, Cost, Time and there are 8 KPIs are Non Technical covering Financial Performance, H&S, Compliance etc. |  |  |  | Number of KPIs achieved / Total Number of KPIs set for the same period | 5 | 7
| Number of KPIs achieved in the preceding year | Data Not Available |  | KPI achievement data was not received, and therefore, progress assessment remains inconclusive. | [5 empty] | 8
Appropriateness of KPIs for Technical Team | Alignment of key KPIs aligning with Cost, Time and Quality | Significant deviation from industry benchmarks | DR-074 | Quality and Cost receives the least attention which is misaligned with industry norms where quality is a core metric. KPI framework does not reflect a balanced or comprehensive technical performance view. No documented ESG or role specific KPIs for areas such as design, constructability. |  |  |  | Expected elements from industry benchmarks: 1. Schedule adherence 2. Budget adherence 3. Quality Adherence | 6 | 9
Criticality of Vacant/Missing Positions in Organization | Key positions which are missing, if any | Moderate | DR-077 | 1. Around 128 key position at leadership level are vacant, out of which 100 are technical related. 2. No defined RACI exists at the staff level, leading to unclear responsibilities and limited accountability, especially for critical technical roles which are vacant. |  |  |  | "Severe" if more than 25% of technical department head (N-2 or 3) and above are vacant Technical department head: person leading a technical function (depends on organization size) "Moderate" if 2 position for technical department head are vacant | 7 | 11
Appropriateness of Qualifications in Recruitment of Vacant Technical Department Head Positions | Qualifications of job descriptions for vacant technical department head positions - are they appropriate? | Data Not Available |  | No data available on Job description of vacant positions |  |  |  | "Critical" score if there is little to no relevance in the requested qualifications to the role | 8 | 12
Robustness of Policy/Guideline/Procedure Communication | List of policies/procedures communicated to all employees | Strong | DR-002 DR-013 DR-079 | Policy, procedure, and guidelines are documented and available. |  |  |  | Strong if these are done: 1. Regular update and review of policies (3 mths) 2. All relevant policies/guidelines captured 3. Easy access (one repository with easy to find link) 4. Multi-channels to inform updates to documents e.g. email, intranet | 9 | 15
Robustness of Policy/Guideline/Procedure Compliance Monitoring Framework | Monitoring of policies and procedures compliance | Moderate | DR-001 DR-002 DR-003 DR-079 | 1. Policies and procedures exists with well defined Governance RACI matrix. 2. The only observation is that scheduling and costing are handled on different systems which could lead to fragmented data and limit performance tracking |  |  |  | Strong if these are done: 1. Regular internal audits of processes (ongoing and rotation of topics/departments) 2. Independent internal audit department reporting directly to CEO or Board 3. Whistleblowing policy 4. Regular training for all staff (annual) | 10 | 17
Robustness of Board Reporting Framework | Frequency of reporting to Board and PIF | Moderate | DR-002 DR-003 DR-072-05 DR-079 | 1. Board reporting frequencies are clearly defined and well documented 2. Well defined framework present for defining Operating model and ownership transfer. 3. no documented records of series of board meeting registers or minutes. |  |  |  | Strong if all of these following points are done: 1. Board reporting policy covering frequency/trigger for updates 2. Register of Board Papers/Presentations 3. Register of Board meetings and meeting minutes | 11 | 19
Availability of Technical Function Strategy and KPIs
Availability of Technical Function Strategy and KPIs
Availability of Technical Function Strategy and KPIs
Robustness of Board Reporting Framework Frequency of reporting to Board and PIF
Robustness of Board Reporting Framework Frequency of reporting to Board and PIF
Robustness of Board Reporting Framework Frequency of reporting to Board and PIF
Go to Main Page
Go to Document
Go to Analysis
Note on A6: SO-AC-001
Note on B6: SO-DP-001
Note on A7: SO-AC-002
Note on B7: SO-DP-002
Note on A8: SO-AC-003
Note on B8: SO-DP-003
Note on A9: SO-AC-004
Note on B9: SO-DP-006
Note on A10: SO-AC-005
Note on B10: SO-DP-007
Note on B11: SO-DP-008
Note on A12: SO-AC-006
Note on B12: SO-DP-009
Note on A13: SO-AC-007
Note on B13: SO-DP-011
Note on A14: SO-AC-008
Note on B14: SO-DP-012
Note on A15: SO-AC-009
Note on B15: SO-DP-015
Note on A16: SO-AC-010
Note on B16: SO-DP-017
Note on A17: SO-AC-011
Note on B17: SO-DP-019

## DevCoAssessmentAnalysis(S&O)
PIF Project Lighthouse
DevCoAssessmentAnalysis(S&O)
Assessment Criteria | Data Point | Value | Rating | Score | Assessment Criteria Weightage | Assessment Guideline/Formula | Good | Satisfactory | Needs Improvement | Remarks 1 | Performance Signal | Performance Signal Score | Performance Signals Weightage | Remarks 2 | Key Topic | Key Topic Score | Remarks 3
Availability of Technical Function Strategy | Availability of strategy (Text) | Yes, but very brief | Satisfactory | 66% | 30% | Give 'satisfactory' score if there is a technical function strategy, but it is very general and does not provide specific details of the strategy | Yes | Yes, but very brief | No | Strategy available at the Masterplan level interms of guidelines but not defined at DevCo level. | Technical Strategy Achievement | 42% | 20% |  | Technical Strategy and Enablers | 56% |  | 1 | 1
Alignment of Technical Strategy with Organizational Strategy | Alignment of technical functions' strategy and initiatives with the overarching organizational strategy (Text) | Misaligned | Needs Improvement | 33% | 30% | Assess if elements of technical strategy is aligned with organizational strategy. "Well aligned " score if key elements of technical strategy such as guidelines are well documented or presented during the meeting with DevCo. | Well-aligned | Some gaps | Misaligned | There are only 4 initiatives covering Mobility, Sustainability, Security strategy and Smart cities. Some important topics missing like Constructability, Innovation, ESG, Standardization, etc. | [7 empty] | 2 | 2
Severity of Key Challenges Faced in Strategy Execution Technically | Key challenges in strategy execution (Text) | Data Not Available | Needs Improvement | 33% | 40% | "Severe" score if challenges faced can impact strategy execution significantly (in terms of time, cost and/or quality) | Minor | Moderate | Severe | No data available on challenges faced during strategy execution. | [7 empty] | 3 | 3
Availability of Technical KPIs | Availability of KPIs (Text) | Yes, but very brief | Satisfactory | 66% | 40% | Give 'satisfactory' score if there are technical KPIs, but they are very generic | Yes | Yes, but very brief | No | 15 KPIs at DevCo level. Some important KPIs around topics like Quality, Compliance, ESG are missing. | Technical KPI Achievement | 46% | 20% |  |  |  |  | 4 | 6
Progress of Achievement of KPIs for Technical Team | Total Number of KPIs set for the preceding year (No.) | Data Not Available | Needs Improvement | 33% | 20% | Number of KPIs achieved / Total Number of KPIs set for the same period | >75% | 50-75% | <50% | No KPI progress or achievement data available | [7 empty] | 5 | 7
| Number of KPIs achieved in the preceding year (No.) | [17 empty] | 8
Appropriateness of KPIs for Technical Team | Alignment of key KPIs aligning with Cost, Time and Quality | Significant deviation from industry benchmarks | Needs Improvement | 33% | 40% | Expected elements from industry benchmarks: 1. Schedule adherence 2. Budget adherence 3. Quality Adherence | Aligned with industry benchmarks | Some gaps with industry benchmarks | Significant deviation from industry benchmarks | Some important KPIs around topics like Quality, Compliance, ESG are missing. | [7 empty] | 6 | 9
Criticality of Vacant/Missing Positions in Organization | Key positions which are missing, if any (Text) | Moderate | Satisfactory | 66% | 60% | "Severe" if more than 25% of technical department head (N-2 or 3) and above are vacant Technical department head: person leading a technical function (depends on organization size) "Moderate" if 2 position for technical department head are vacant | Minor | Moderate | Severe | 128 key position at leadership level are vacant, out of which 100 are technical related. | Technical Organization | 52% | 30% |  |  |  |  | 7 | 11
Appropriateness of Qualifications in Recruitment of Vacant Technical Department Head Positions | Qualifications of job descriptions for vacant technical department head positions - are they appropriate? (Text) | Data Not Available | Needs Improvement | 33% | 40% | "Critical" score if there is little to no relevance in the requested qualifications to the role | Well-aligned | Some gaps | Misaligned | No data available on Job description of vacant positions | [7 empty] | 8 | 12
Robustness of Policy/Guideline/Procedure Communication | List of policies/procedures communicated to all employees (Text) | Strong | Good | 100% | 30% | Strong if these are done: 1. Regular update and review of policies (3 mths) 2. All relevant policies/guidelines captured 3. Easy access (one repository with easy to find link) 4. Multi-channels to inform updates to documents e.g. email, intranet | Strong | Moderate | Poor | Communication Policy, procedure, and guidelines are present | Technical Control Environment | 76% | 30% |  |  |  |  | 9 | 15
Robustness of Policy/Guideline/Procedure Compliance Monitoring Framework | Monitoring of policies and procedures compliance (Text) | Moderate | Satisfactory | 66% | 40% | Strong if these are done: 1. Regular internal audits of processes (ongoing and rotation of topics/departments) 2. Independent internal audit department reporting directly to CEO or Board 3. Whistleblowing policy 4. Regular training for all staff (annual) | Strong | Moderate | Poor | Scheduling and costing are managed on separate platforms, and the schedule is not cost loaded. | [7 empty] | 10 | 17
Robustness of Board Reporting Framework | Frequency of reporting to Board and PIF (Text) | Moderate | Satisfactory | 66% | 30% | Strong if all of these following points are done: 1. Board reporting policy covering frequency/trigger for updates 2. Register of Board Papers/Presentations 3. Register of Board meetings and meeting minutes | Strong | Moderate | Poor | Board reporting frequencies are clearly defined and well documented. However, there were no documented records of series of board meeting registers or minutes made available. | [7 empty] | 11 | 19
Go to Main Page
Go to Document
Go to Input
Note on A6: SO-AC-001
Note on B6: SO-DP-001
Note on A7: SO-AC-002
Note on B7: SO-DP-002
Note on A8: SO-AC-003
Note on B8: SO-DP-003
Note on A9: SO-AC-004
Note on B9: SO-DP-006
Note on A10: SO-AC-005
Note on B10: SO-DP-007
Note on B11: SO-DP-008
Note on A12: SO-AC-006
Note on B12: SO-DP-009
Note on A13: SO-AC-007
Note on B13: SO-DP-011
Note on A14: SO-AC-008
Note on B14: SO-DP-012
Note on A15: SO-AC-009
Note on B15: SO-DP-015
Note on A16: SO-AC-010
Note on B16: SO-DP-017
Note on A17: SO-AC-011
Note on B17: SO-DP-019

## InterviewQuestion(S&O)
PIF Project Lighthouse
InterviewQuestion(S&O)
SN | Question | Date of Interview | Response | Internal Comment | Follow Up Question
1 | How do the technical functions’ strategy and initiatives align with the overarching organizational strategy? | 2025-05-02 17:10
2 | Share any key challenges faced in executing the strategy from a technical perspective | 2025-05-02 17:10
3 | Are there any vacant/missing roles which are critical and impeding optimal execution of projects? | 2025-05-02
4 | Are there any gaps in experience/qualifications/skill sets of the existing team in delivery of the DevCo’s mandate? | 2025-05-02
5 | How are policies/procedures communicated to all employees? | 2025-05-02
6 | How is compliance with policies and procedures monitored & ensured? | 2025-05-02
7 | What is the framework for reporting to the Board? | 2025-05-02
Go to Main Page

## AddDataPoint(S&O)
PIF Project Lighthouse
AddDataPoint(S&O) | [5 empty] | Unfulfilled Positions |  |  |  | Critical Position Currently Unstaffed/Missing |  | Critical Position Currently Unstaffed |  | Critical Policies Missing |  |  | Critical Technical Platforms Missing |  |  | Top KPI
SN | Data Source | Additional Data Point | Input Value | Scorecard Visualization |  | Department | Total Positions | No of Positions Unfullfiled | % of Position Unfullfilled | Position Vacant | Position Missing | Name of the Department | No of Position Missing | Name of the Policy | Criticality Policies (Y/N) | Availability Policies (Y/N) | Name of the Technical Platform | Criticality Technical (Y/N) | Availability Technical (Y/N) | Name of the KPI | Weightage
1 |  | Completeness & Relevance of Technical Strategy (Text) |  | Used for Dashboard (Manual) | 4 | Project controls | 6 | 1 | 16.66% | Centralised Innovation Team | N | Project controls | 1
2 |  | Mitigation of Key Challenges (Text) |  | Used for Dashboard (Manual) | 5 | Procurment and Contracts Management | 17 | 5 | 29.41% |  |  | Procurment and Contracts Management | 5
3 |  | Assessment of Technical KPIs (No.) |  | Used for Dashboard (Manual) | 10 | Innovation | 0 | 0 | 0 |  |  | Design Management | 20
4 |  | Unfulfilled Positions (Department, Total Positions, No. of Positions Unfulfilled, % of Position Unfulfilled) (No.) |  | Used for Dashboard | 13 | Design Management | 202 | 20 | 9.9% |  |  | Cost Management | 28
5 |  | Organisation Chart (Text) |  | Used for Dashboard (Manual) | 14 | Cost Management | 189 | 28 | 14.81% |  |  | Construction Management | 38
6 |  | List of missing key technical platforms |  | Used for Dashboard | 16 | Construction Management | 176 | 38 | 21.59%
7 |  | List of critical policies missing, if any |  | Used for Dashboard | 18
Go to Main Page
Note on C6: SO-DP-004
Note on C7: SO-DP-005
Note on C8: SO-DP-010
Note on C9: SO-DP-013
Note on C10: SO-DP-014
Note on C11: SO-DP-016
Note on C12: SO-DP-018

## AssessmentSummary
PIF Project Lighthouse
AssessmentSummary | Q1 2025
Section | Performance Signal | Performance Signal Score |  |  | Key Topic | Key Topic Score | Section Score | Remarks
Planning & Monitoring (P&M) | Schedule Adherence | 33% | 50% |  | Overall Progress | 33% | 33%
| Schedule Extension | 33% | 30%
| Schedule Achievability | 33% | 20%
| Risk Governance | 33% | 60% |  | Risk Performance | 33%
| Realized Risk Status | 33% | 40%
Design & Technical (D&T) | CGI and Animation Compliance | 33% | 50% |  | Vision Adherence | 33% | 33%
| Development Program Variance | 33% | 50%
| Construction Design Maturity | 33% | 100% |  | Design for Constructability | 33%
| Design Management Maturity | 33% | 100% |  | Design Management | 33%
| Environmental Compliance Status | 33% | 40% |  | Regulatory Compliance | 33%
| Authority Compliance Status | 33% | 60%
| DevCo ESG Target Achievement | 33% | 80% |  | ESG Target Realization | 33%
| Global ESG Target Alignment | 33% | 20%
Development & Construction (D&C) | Construction Planning Maturity | 33% | 70% |  | Construction | 33% | 33%
| Workforce Resource Availability | 33% | 30%
| Adherence to Design | 33% | 70% |  | Quality | 33%
| Quality Assurance / Quality Control (QA/QC) | 33% | 30%
| Procurement & Contracting Compliance | 33% | 30% |  | Procurement | 33%
| Procurement & Contracting Execution Performance | 33% | 70%
| HSE Compliance | 33% | 50% |  | HSE and Welfare | 33%
| Welfare Compliance | 33% | 50%
Cost Estimation & Optimization (CE&O) | Budget Variance | 33% | 60% | DR-065 | Overall Budget | 33% | 33%
| Budget Trend | 33% | 20%
| Provisional Sum Utilization | 33% | 20%
Innovation & Technology (I&T) | Innovation & Technology Deployment | 33% | 40% |  | Innovation and Technology Adoption | 33% | 33%
| Pilot and R&D Transition Rate | 33% | 30%
| Organization Maturity Towards Innovation Adoption | 33% | 30%
Strategy & Operations (S&O) | Technical Strategy Achievement | 33% | 20% |  | Technical Strategy and Enablers | 33% | 33%
| Technical KPI Achievement | 33% | 20%
| Technical Organization | 33% | 30%
| Technical Control Environment | 33% | 30%
Go to Main Page

## Log
PIF Project Lighthouse
Log
SN | Stakeholder | Identity | Assessor / Reviewer | Stamp | Cell | Section | Data Point | Event
Go to Main Page
Refresh

## User
PIF Project Lighthouse
User
No. | User Name | Password | Identity | Stakeholder Group | Main | Instructions | Glossary&Definitions | DocumentList | Log | InterviewQuestion(P&M) | AddDataPoint(P&M) | DevCoAssessmentInput(P&M) | DevCoAssessmentAnalysis(P&M) | InterviewQuestion(D&T) | AddDataPoint(D&T) | DevCoAssessmentInput(D&T) | DevCoAssessmentAnalysis(D&T) | InterviewQuestion(D&C) | AddDataPoint(D&C) | DevCoAssessmentInput(D&C) | DevCoAssessmentAnalysis(D&C) | InterviewQuestion(CE&O) | AddDataPoint(CE&O) | DevCoAssessmentInput(CE&O) | DevCoAssessmentAnalysis(CE&O) | InterviewQuestion(I&T) | AddDataPoint(I&T) | DevCoAssessmentInput(I&T) | DevCoAssessmentAnalysis(I&T) | InterviewQuestion(S&O) | AddDataPoint(S&O) | DevCoAssessmentInput(S&O) | DevCoAssessmentAnalysis(S&O) | AssessmentSummary | User | Setting | Login
1 | Admin | A_PLH_Data | Administrator | MEINHARDT | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a
2 | AssessorP&M | PLH_P&M | Assessor (P&M) | MEINHARDT | a | a | a | a | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a
3 | AssessorD&T | PLH_D&T | Assessor (D&T) | MEINHARDT | a | a | a | a | a | x | x | x | x | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a
4 | AssessorD&C | PLH_D&C | Assessor (D&C) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a
5 | AssessorCE&O | PLH_CE&O | Assessor (CE&O) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | a
6 | AssessorI&T | PLH_I&T | Assessor (I&T) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a | a | a | a | x | x | x | x | x | x | x | a
7 | AssessorS&O | PLH_S&M | Assessor (S&O) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a | a | a | a | x | x | x | a
8 | ReviewerP&M | PLH_P&M | Reviewer (P&M) | MEINHARDT | a | a | a | a | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a
9 | ReviewerD&T | PLH_D&T | Reviewer (D&T) | MEINHARDT | a | a | a | a | a | x | x | x | x | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a
10 | ReviewerD&C | PLH_D&C | Reviewer (D&C) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a
11 | ReviewerCE&O | PLH_CE&O | Reviewer (CE&O) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | a
12 | ReviewerI&T | PLH_I&T | Reviewer (I&T) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a | a | a | a | x | x | x | x | x | x | x | a
13 | ReviewerS&O | PLH_S&M | Reviewer (S&O) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a | a | a | a | x | x | x | a
Go to Main Page
Refresh

## Setting
PIF Project Lighthouse
Setting | 9 | 4 | 5 | 1 | 2 | 14 | 7 | 52 | 52 | 81
No. | DDLPnM | DDLDnT | DDLDnC | DDLCEnO | DDLInT | DDLSnO | Section | DocID | Document | Formula | 3 | 2 | 1 | Section | P&M |  |  |  | D&T |  |  |  | D&C |  |  |  | CE&O |  |  |  | I&T |  |  |  | S&O
1 | Data Not Available | Data Not Available | 0 | Data Not Available | 0.5 | Aligned with industry benchmarks | General | Cost Data | Cost Data Template | Earned Value (EV) / Planned Value (PV) | >1 | 0.85-1 | <0.85 | P&M | Earned Value (EV) / Planned Value (PV) | >1 | 0.85-1 | <0.85 | (Percentage similarity between Approved CGI and Latest CGI at same angle and scale) + (Percentage similarity between Approved Animation and Latest Animation at same camera angle) / 2 | >70% | 50-70% | <50% | Environmental mitigation measures included in CESMP / Environmental mitigation measures recommended in ESIA | >80% | 60-80% | <60% | [Forecast Budget - PIF Approved Capex budget (Initial Business Plan)]/ PIF Approved Capex budget (Initial Business Plan) | <10% | 10-20% | >20% | Innovation Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10% | >75% | 60-75% | <60% | Give 'satisfactory' score if there is a technical function strategy, but it is very general and does not provide specific details of the strategy | Yes | Yes, but very brief | No | Cost Data | Cost Data Template
2 | No | No | Data Not Available |  | Data Not Available | Data Not Available | Planning & Monitoring | DR-001 | Baseline and Updated Master schedule (including cost linked Milestone summary for earned value, planned value analysis, and Schedule Updates) | No. of milestones achieved on time/ No. of planned milestones | >70% | 50-70% | <50% | P&M | No. of milestones achieved on time/ No. of planned milestones | >70% | 50-70% | <50% | Material Palette & Finish Schedule matched Approved CGI | >70% | 50-70% | <50% | Update of construction execution plan | Yes |  | No | Number of Projects with Budget Variance / Total number of Projects | <10% | 10-30% | >30% | Smart City Strategy: Availability 15%; Strategic Alignment 15%; Adequate key focus areas 10%; Adequate detailed initiatives 10%; Smart city goals nad KPIs 10%; CBA 10%; Implementation Roadmap 10%; Process formulated 10%; Budget of implementation 10% | >75% | 60-75% | <60% | Assess if elements of technical strategy is aligned with organizational strategy. "Average" score if key elements of organizational strategy is not addressed in technical strategy | Well-aligned | Some gaps | Misaligned | DR-001 | Baseline and Updated Master schedule (including cost linked Milestone summary for earned value, planned value analysis, and Schedule Updates)
3 | Yes | Partially Applied | No |  |  | Minor | Design & Technical | DR-002 | Program Management Plan | Number of projects with approved change requests in design phase since inception with time impact of more than 1 month / Total number of projects in design phase | <30% | 30-70% | >70% | P&M | Number of projects with approved change requests in design phase since inception with time impact of more than 1 month / Total number of projects in design phase | <30% | 30-70% | >70% | The Design and Technical Guidelines exist | Yes |  | No | Review and approval of construction sequence and method statement | Yes |  | No | (Number of projects with contingency utilization > 1) / (Total number of projects) | <10% | 10-30% | >30% | Adoption on DevCo performance? Robust assessment process and guidelines - 30%; Availability of sample of impact assessment report - 30%; Availability of action plan - 10%; Use of innovative tools/platforms/dashboards - 30% | >75% | 60-75% | <60% | "Severe" score if challenges faced can impact strategy execution significantly (in terms of time, cost and/or quality) | Minor | Moderate | Severe | DR-002 | Program Management Plan
4 | Yes, but inadequate | Yes | Partially Applied |  |  | Misaligned | Development & Construction | DR-003 | Latest Approved Monthly Progress Report | Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months / Total number of projects in construction phase | <30% | 30-70% | >70% | P&M | Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months / Total number of projects in construction phase | <30% | 30-70% | >70% | Material Palette & Finish Schedule aligns with Look & Feel Guideline | >70% | 50-70% | <50% | Sufficient land acquired | Yes |  | No | (No. of projects with approved change request having a cost impact greater than 2%) / (Total number of projects) | <5% | 5-15% | >15% | Effectiveness index in the mentioned areas is an evaluation of successful implementation (Up to 8.3% for each element of the innovation adoption effective index) (Up to 10% for each element of the smart city adoption effective index) | >75% | 60-75% | <60% | Give 'satisfactory' score if there are technical KPIs, but they are very generic | Yes | Yes, but very brief | No | DR-003 | Latest Approved Monthly Progress Report
5 | Yes, but less than 1% |  | Yes |  |  | Moderate | Cost Estimation & Optimization | DR-004 | Change request register (covering latest approved schedule extension requests) | (Number of Projects with Approved Schedule Extension)/Total Number of Projects) | <20% | 20-40% | >40% | P&M | (Number of Projects with Approved Schedule Extension)/Total Number of Projects) | <20% | 20-40% | >40% | (Latest BUA - Approved BUA) / Approved BUA | <15% | 15-30% | >30% | Completion of traffic simulations | Yes |  | No | (No. of projects with approved claims) / (Total number of projects) | <2% | 2-5% | >5% | Pilot or R&D projects conducted? Availability - 20%; Adequate list of focus areas - 35%; Procedure - 15%; Outcome assessment robustness - 30% | >75% | 60-75% | <60% | Number of KPIs achieved / Total Number of KPIs set for the same period | >75% | 50-75% | <50% | DR-004 | Change request register (covering latest approved schedule extension requests)
6 | Yes, but less than 5% |  |  |  |  | No | Innovation & Technology | DR-005 | Latest approved risk mapping / risk register (including mitigation plans) documented at DevCo level and the list of Stakeholders | Number of projects with forecast completion date beyond the latest approved schedule / [No. of projects with schedule extension (design stage) + No. of projects with schedule extension (construction stage)] | <20% | 20-40% | >40% | P&M | Number of projects with forecast completion date beyond the latest approved schedule / [No. of projects with schedule extension (design stage) + No. of projects with schedule extension (construction stage)] | <20% | 20-40% | >40% | (Latest Land Area - Approved Land Area) / Approved Land Area | <15% | 15-30% | >30% | Date of latest approved Project Execution Plan less than 12 months from Current Date | Yes |  | No | Total Provisional Sums/Latest Approved Budget | <5% | 5-15% | >15% | [(Number of pilots that are scaled successfully + Number of R&D projects that are successfully piloted or fully-scaled) / (Number of pilot projects + Number of R&D projects)] | >40% | 20-40% | <20% | Expected elements from industry benchmarks: 1. Schedule adherence 2. Budget adherence 3. Employee attrition 4. HSE and Welfare 5. ESG | Aligned with industry benchmarks | Some gaps with industry benchmarks | Significant deviation from industry benchmarks | DR-005 | Latest approved risk mapping / risk register (including mitigation plans) documented at DevCo level and the list of Stakeholders
7 | Yes, but less than 0.5% |  |  |  |  | Poor | Strategy & Operations | DR-006 | Lookahead Schedules / Short-term execution plans (e.g., 4-week or 6-week lookahead) | "Satisfactory Score" if key project stakeholders (engineering, procurement, construction, client teams) were formally briefed, discussed on the forecast date includ any foreseen risks but no formal sign off doc on the forecast finish date is available | Yes | Yes, but inadequate | No | P&M | "Satisfactory Score" if key project stakeholders (engineering, procurement, construction, client teams) were formally briefed, discussed on the forecast date includ any foreseen risks but no formal sign off doc on the forecast finish date is available | Yes | Yes, but inadequate | No | (Latest Population - Approved Population) / Approved Population | <30% | 30-40% | >40% | Number of Stakeholder MOU or Land Use Permits not executed on time/ Total number of Stakeholder MOU or Land Use Permits required | <20% | 20-60% | >60% | (Total Provisional Sums−Actual Utilized Provisional Sums)/Total Provisional Sums | <10% | 10-20% | >20% | Availability of Innovation: Availability - 20%; Adequate Key positions planned in the org. structure - 30%; Unit/department position within the company hierarchy - 20%; Qualifications of the innovation team - 30% | >60% | 40-60% | <40% | "Severe" if more than 25% of technical department head (N-2 or 3) and above are vacant Technical department head: person leading a technical function (depends on organization size) "Moderate" if 2 position for technical department head are vacant | Minor | Moderate | Severe | DR-006 | Lookahead Schedules / Short-term execution plans (e.g., 4-week or 6-week lookahead)
8 | Yes, but less than 1 month |  |  |  |  | Severe |  | DR-007 | Sample of project level approved risk register | "Satisfactory" if new activities as per the risks identified and discussions with stakeholders are added in the revised programme but do not have logical relationships and there is no comparison of the critical path analysis before and after date change | Yes | Yes, but inadequate | No | P&M | "Satisfactory" if new activities as per the risks identified and discussions with stakeholders are added in the revised programme but do not have logical relationships and there is no comparison of the critical path analysis before and after date change | Yes | Yes, but inadequate | No | Modularized Construction Cost / Total Construction Cost | >40% | 20-40% | <20% | Actual workforce employed / forecast workforce requirements | >90% | 70-90% | <70% |  |  |  |  | Availability - 50% Implementation of the unit/department framework/ process - 50% | >50% | 50% | <50% | "Critical" score if there is little to no relevance in the requested qualifications to the role | Well-aligned | Some gaps | Misaligned | DR-007 | Sample of project level approved risk register
9 | Yes, but less than 2 weeks |  |  |  |  | Significant deviation from industry benchmarks |  | DR-008 | Risk Management Plan | Satisfactory Score if - Contingency allocated but not aligning with the risk severity as per the heat map | Yes | Yes, but inadequate | No | P&M | Satisfactory Score if - Contingency allocated but not aligning with the risk severity as per the heat map | Yes | Yes, but inadequate | No | Constructability Report exists | Yes |  | No | Actual number of labor camps / Forecast number of labor camps | >90% | 70-90% | <70% | [8 empty] | Strong if these are done: 1. Regular update and review of policies (3 mths) 2. All relevant policies/guidelines captured 3. Easy access (one repository with easy to find link) 4. Multi-channels to inform updates to documents e.g. email, intranet | Strong | Moderate | Poor | DR-008 | Risk Management Plan
10 | [5 empty] | Some gaps |  | DR-009 | Latest Updated Cost report | Satisfactory Score if - the deferment was less than 1 month | No | Yes, but less than 1 month | Yes | P&M | Satisfactory Score if - the deferment was less than 1 month | No | Yes, but less than 1 month | Yes | Consideration of design for enabling work package | Yes |  | No | Actual number of batching plants / forecast number of batching plants | >80% | 40-80% | <40% | [8 empty] | Strong if these are done: 1. Regular internal audits of processes (ongoing and rotation of topics/departments) 2. Independent internal audit department reporting directly to CEO or Board 3. Whistleblowing policy 4. Regular training for all staff (annual) | Strong | Moderate | Poor | DR-009 | Latest Updated Cost report
11 | [5 empty] | Some gaps with industry benchmarks |  | DR-010 | Program Tracker | Satisfactory Score if - the cost overrun was less than 5% | No | Yes, but less than 5% | Yes | P&M | Satisfactory Score if - the cost overrun was less than 5% | No | Yes, but less than 5% | Yes | LOD Documented matches LOD Required | Yes |  | No | Adherence to Technical Submittals Review Cycle Time | Yes |  | No | [8 empty] | Strong if all of these following points are done: 1. Board reporting policy covering frequency/trigger for updates 2. Register of Board Papers/Presentations 3. Register of Board meetings and meeting minutes | Strong | Moderate | Poor | DR-010 | Program Tracker
12 | [5 empty] | Strong |  | DR-011 | Original Approved and Latest version of CGI & Animation (Material Palette & Finish Schedule) | Satisfactory Score if - the cost overrun was less than 1% | No | Yes, but less than 1% | Yes | P&M | Satisfactory Score if - the cost overrun was less than 1% | No | Yes, but less than 1% | Yes | BIM Documentation exists | Yes |  | No | Total number of shop drawing reviews approved / Total number of shop drawing review requests | >90% | 60-90% | <60% | [12 empty] | DR-011 | Original Approved and Latest version of CGI & Animation (Material Palette & Finish Schedule)
13 | [5 empty] | Yes |  | DR-012 | Original Approved and Latest version of the Drawings | Number of Controlled Risks / Total number of identified risks | >70% | 40-70% | <40% | P&M | Number of Controlled Risks / Total number of identified risks | >70% | 40-70% | <40% | Review Latest Approved Design Strategy and compare with the Stage Gate Design Report | Yes |  | No | Total number of product sample & materials approved / Total number of product sample & material approvals requested | >90% | 60-90% | <60% | [12 empty] | DR-012 | Original Approved and Latest version of the Drawings
14 | [5 empty] | Yes, but very brief |  | DR-013 | DevCo Design & Technical Guidelines (including, but not limited to, Look & Feel Design Guidelines) | Satisfactory Score if - the risks were identified, mitigations planned but not communicated to all the relevant stakeholders. And the risk register is updated | Yes | Yes, but inadequate | No | P&M | Satisfactory Score if - the risks were identified, mitigations planned but not communicated to all the relevant stakeholders. And the risk register is updated | Yes | Yes, but inadequate | No | Check the Design Review & Verification Register, assess if correct number of Design Reviews have occurred in accordance with the Design Management Report | >70% | 50-70% | <50% | Number of As-built reviews / approvals / Number of As-Built review requests | >80% | 60-80% | <60% | [12 empty] | DR-013 | DevCo Design & Technical Guidelines (including, but not limited to, Look & Feel Design Guidelines)
15 | [7 empty] | DR-014 | Design Report / Return Brief Report (including approved and latest Asset Area Schedule & Population) | Satisfactory Score if - the time impact is less than 2 weeks for Design phase completion and less than 1 month of Construction Phase Completion | No | Yes, but less than 2 weeks | Yes | P&M | Satisfactory Score if - the time impact is less than 2 weeks for Design phase completion and less than 1 month of Construction Phase Completion | No | Yes, but less than 2 weeks | Yes | Closed Corrective Actions / Total Corrective Actions | >70% | 40-70% | <40% | Number of MIR Inspected / Total number of MIRs requested | >80% | 60-80% | <60% | [12 empty] | DR-014 | Design Report / Return Brief Report (including approved and latest Asset Area Schedule & Population)
16 | [7 empty] | DR-015 | Latest Stage Gate Cost Plan | Satisfactory Score if - the cost impact is less than 0.5% of the identified risk costing | No | Yes, but less than 0.5% | Yes | P&M | Satisfactory Score if - the cost impact is less than 0.5% of the identified risk costing | No | Yes, but less than 0.5% | Yes | Average number of days between Date Corrective Action is recorded in the Corrective Action Register and the Date Corrective Action is Closed | <14days | 14-30days | >30days | Number of Approved MIR / Total number of MIRs requested | >80% | 60-80% | <60% | [12 empty] | DR-015 | Latest Stage Gate Cost Plan
17 | [7 empty] | DR-016 | Report including constructability feasibility and construction methodology | (Percentage similarity between Approved CGI and Latest CGI at same angle and scale) + (Percentage similarity between Approved Animation and Latest Animation at same camera angle) / 2 | >70% | 50-70% | <50% | D&T |  |  |  |  | Average number of days between Design Review Submittals and Completion of the Design Reviews compared to the number of days required to complete the Design Reviews in accordance with the Design Management Report | Yes |  | No | Number of WIR Inspected / Total number of WIRs requested | >80% | 60-80% | <60% | [12 empty] | DR-016 | Report including constructability feasibility and construction methodology
18 | [7 empty] | DR-017 | Digital Information Management Plan | Material Palette & Finish Schedule matched Approved CGI | >70% | 50-70% | <50% | D&T |  |  |  |  | Independent Certification exists | Yes |  | No | [16 empty] | DR-017 | Digital Information Management Plan
19 | [7 empty] | DR-018 | Latest Project Execution Plan (including Design Strategy, Packaging Strategy and Phasing Strategy) | The Design and Technical Guidelines exist | Yes |  | No | D&T |  |  |  |  | The Infrastructure and Engineering Report references the Regional Infrastructure & Mobility Plans and demonstrates adoption of Regional Strategies | Yes |  | No | [16 empty] | DR-018 | Latest Project Execution Plan (including Design Strategy, Packaging Strategy and Phasing Strategy)
20 | [7 empty] | DR-019 | Design Master Schedule | Material Palette & Finish Schedule aligns with Look & Feel Guideline | >70% | 50-70% | <50% | D&T |  |  |  |  | Key Environmental Risks and Site Environmental Factors are covered in the Environmental Compliance Report | Yes |  | No | [16 empty] | DR-019 | Design Master Schedule
21 | [7 empty] | DR-020 | Procedures and Governance for design approvals and change management | (Latest BUA - Approved BUA) / Approved BUA | <15% | 15-30% | >30% | D&T |  |  |  |  | Total Number of Code Compliance Violations taken from the Code Compliance Assessment Report | <10% | 10-30% | >30% | [16 empty] | DR-020 | Procedures and Governance for design approvals and change management
22 | [7 empty] | DR-021 | Design Basis Report and Stage Gate Design Report (including Design Management Report, Design Reviews & Verifications Register) | (Latest Land Area - Approved Land Area) / Approved Land Area | <15% | 15-30% | >30% | D&T |  |  |  |  | Total Waivers Approved / Total Waiver Applications Submitted | >70% | 50-70% | <50% | [16 empty] | DR-021 | Design Basis Report and Stage Gate Design Report (including Design Management Report, Design Reviews & Verifications Register)
23 | [7 empty] | DR-022 | Infrastructure and Engineering report (including Water, Energy, Waste, Infrastructure & Mobility Plans) | (Latest Population - Approved Population) / Approved Population | <30% | 30-40% | >40% | D&T | [24 empty] | DR-022 | Infrastructure and Engineering report (including Water, Energy, Waste, Infrastructure & Mobility Plans)
24 | [7 empty] | DR-023 | Environmental and Social Impact Assessment | Modularized Construction Cost / Total Construction Cost | >40% | 20-40% | <20% | D&T | [24 empty] | DR-023 | Environmental and Social Impact Assessment
25 | [7 empty] | DR-024 | Environmental Compliance Report | Constructability Report exists | Yes |  | No | D&T | [24 empty] | DR-024 | Environmental Compliance Report
26 | [7 empty] | DR-025 | Register of Authority Engagement, Approvals and Waivers | Consideration of design for enabling work package | Yes |  | No | D&T | [24 empty] | DR-025 | Register of Authority Engagement, Approvals and Waivers
27 | [7 empty] | DR-026 | Stakeholder Management Plan (including Stakeholder Management Tracker) | LOD Documented matches LOD Required | Yes |  | No | D&T | [24 empty] | DR-026 | Stakeholder Management Plan (including Stakeholder Management Tracker)
28 | [7 empty] | DR-027 | Baseline ESG Strategy and Latest Annual ESG Report | BIM Documentation exists | Yes |  | No | D&T | [24 empty] | DR-027 | Baseline ESG Strategy and Latest Annual ESG Report
29 | [7 empty] | DR-028 | Construction Environmental and Social Management Plan (including Environmental Permit Register) | Review Latest Approved Design Strategy and compare with the Stage Gate Design Report | Yes |  | No | D&T | [24 empty] | DR-028 | Construction Environmental and Social Management Plan (including Environmental Permit Register)
30 | [7 empty] | DR-029 | Construction Execution Plan | Check the Design Review & Verification Register, assess if correct number of Design Reviews have occurred in accordance with the Design Management Report | >70% | 50-70% | <50% | D&T | [24 empty] | DR-029 | Construction Execution Plan
31 | [7 empty] | DR-030 | Site and Logistics Plan (including traffic simulations) | Closed Corrective Actions / Total Corrective Actions | >70% | 40-70% | <40% | D&T | [24 empty] | DR-030 | Site and Logistics Plan (including traffic simulations)
32 | [7 empty] | DR-031 | Interface Management Plan (including Stakeholder Management Plan*, Communication Plan & Contractor Staging Plan and Commissioning, Handover & Close-out Plan) | Average number of days between Date Corrective Action is recorded in the Corrective Action Register and the Date Corrective Action is Closed | <14days | 14-30days | >30days | D&T | [24 empty] | DR-031 | Interface Management Plan (including Stakeholder Management Plan*, Communication Plan & Contractor Staging Plan and Commissioning, Handover & Close-out Plan)
33 | [7 empty] | DR-032 | Workforce Planning Strategy | Average number of days between Design Review Submittals and Completion of the Design Reviews compared to the number of days required to complete the Design Reviews in accordance with the Design Management Report | Yes |  | No | D&T | [24 empty] | DR-032 | Workforce Planning Strategy
34 | [7 empty] | DR-033 | Construction Progress Report (including workforce numbers) | Independent Certification exists | Yes |  | No | D&T | [24 empty] | DR-033 | Construction Progress Report (including workforce numbers)
35 | [7 empty] | DR-034 | Register of Technical Queries | The Infrastructure and Engineering Report references the Regional Infrastructure & Mobility Plans and demonstrates adoption of Regional Strategies | Yes |  | No | D&T | [24 empty] | DR-034 | Register of Technical Queries
36 | [7 empty] | DR-035 | Register of Shop Drawing Reviews | Key Environmental Risks and Site Environmental Factors are covered in the Environmental Compliance Report | Yes |  | No | D&T | [24 empty] | DR-035 | Register of Shop Drawing Reviews
37 | [7 empty] | DR-036 | Register of Material & Product Approval / Product Substitution or Change Requests | Total Number of Code Compliance Violations taken from the Code Compliance Assessment Report | <10% | 10-30% | >30% | D&T | [24 empty] | DR-036 | Register of Material & Product Approval / Product Substitution or Change Requests
38 | [7 empty] | DR-037 | Register of As-Built Drawings | Total Waivers Approved / Total Waiver Applications Submitted | >70% | 50-70% | <50% | D&T | [24 empty] | DR-037 | Register of As-Built Drawings
39 | [7 empty] | DR-038 | Register of Material Inspection Requests | Environmental mitigation measures included in CESMP / Environmental mitigation measures recommended in ESIA | >80% | 60-80% | <60% | D&C | [24 empty] | DR-038 | Register of Material Inspection Requests
40 | [7 empty] | DR-039 | Register of Work Inspection Requests | Update of construction execution plan | Yes |  | No | D&C | [24 empty] | DR-039 | Register of Work Inspection Requests
41 | [7 empty] | DR-040 | Quality Management Manual (QMP) | Review and approval of construction sequence and method statement | Yes |  | No | D&C | [24 empty] | DR-040 | Quality Management Manual (QMP)
42 | [7 empty] | DR-041 | Latest Monthly Quality Report, including defects and NCR data | Sufficient land acquired | Yes |  | No | D&C | [24 empty] | DR-041 | Latest Monthly Quality Report, including defects and NCR data
43 | [7 empty] | DR-042 | Inspection Test Plan (ITP) | Completion of traffic simulations | Yes |  | No | D&C | [24 empty] | DR-042 | Inspection Test Plan (ITP)
44 | [7 empty] | DR-043 | Sample of project specific Project Quality Plan (PQP) | Date of latest approved Project Execution Plan less than 12 months from Current Date | Yes |  | No | D&C | [24 empty] | DR-043 | Sample of project specific Project Quality Plan (PQP)
45 | [7 empty] | DR-044 | Latest Quality Audit Report | Number of Stakeholder MOU or Land Use Permits not executed on time/ Total number of Stakeholder MOU or Land Use Permits required | <20% | 20-60% | >60% | D&C | [24 empty] | DR-044 | Latest Quality Audit Report
46 | [7 empty] | DR-045 | Procurement Management Plan (including annual procurement lookahead and pre-qualified vendor database) | Actual workforce employed / forecast workforce requirements | >90% | 70-90% | <70% | D&C | [24 empty] | DR-045 | Procurement Management Plan (including annual procurement lookahead and pre-qualified vendor database)
47 | [7 empty] | DR-046 | Sample of Tender Award Report | Actual number of labor camps / Forecast number of labor camps | >90% | 70-90% | <70% | D&C | [24 empty] | DR-046 | Sample of Tender Award Report
48 | [7 empty] | DR-047 | Procurement and Contracting Risk Register | Actual number of batching plants / forecast number of batching plants | >80% | 40-80% | <40% | D&C | [24 empty] | DR-047 | Procurement and Contracting Risk Register
49 | [7 empty] | DR-048 | List of Appointed Vendors (including due-diligence checks) | Adherence to Technical Submittals Review Cycle Time | Yes |  | No | D&C | [24 empty] | DR-048 | List of Appointed Vendors (including due-diligence checks)
50 | [7 empty] | DR-049 | Supply Chain Risk Assessment | Total number of shop drawing reviews approved / Total number of shop drawing review requests | >90% | 60-90% | <60% | D&C | [24 empty] | DR-049 | Supply Chain Risk Assessment
51 | [7 empty] | DR-050 | Current Procurement Schedule | Total number of product sample & materials approved / Total number of product sample & material approvals requested | >90% | 60-90% | <60% | D&C | [24 empty] | DR-050 | Current Procurement Schedule
52 | [7 empty] | DR-051 | Sample of Signed Agreement / Awarded Contract | Number of As-built reviews / approvals / Number of As-Built review requests | >80% | 60-80% | <60% | D&C | [24 empty] | DR-051 | Sample of Signed Agreement / Awarded Contract
53 | [9 empty] | Number of MIR Inspected / Total number of MIRs requested | >80% | 60-80% | <60% | D&C
54 | [9 empty] | Number of Approved MIR / Total number of MIRs requested | >80% | 60-80% | <60% | D&C
55 | [9 empty] | Number of WIR Inspected / Total number of WIRs requested | >80% | 60-80% | <60% | D&C
56 | [9 empty] | [Forecast Budget - PIF Approved Capex budget (Initial Business Plan)]/ PIF Approved Capex budget (Initial Business Plan) | <10% | 10-20% | >20% | CE&O
57 | [9 empty] | Number of Projects with Budget Variance / Total number of Projects | <10% | 10-30% | >30% | CE&O
58 | [9 empty] | (Number of projects with contingency utilization > 1) / (Total number of projects) | <10% | 10-30% | >30% | CE&O
59 | [9 empty] | (No. of projects with approved change request having a cost impact greater than 2%) / (Total number of projects) | <5% | 5-15% | >15% | CE&O
60 | [9 empty] | (No. of projects with approved claims) / (Total number of projects) | <2% | 2-5% | >5% | CE&O
61 | [9 empty] | Total Provisional Sums/Latest Approved Budget | <5% | 5-15% | >15% | CE&O
62 | [9 empty] | (Total Provisional Sums−Actual Utilized Provisional Sums)/Total Provisional Sums | <10% | 10-20% | >20% | CE&O
63 | [9 empty] | Innovation Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10% | >75% | 60-75% | <60% | I&T
64 | [9 empty] | Smart City Strategy: Availability 15%; Strategic Alignment 15%; Adequate key focus areas 10%; Adequate detailed initiatives 10%; Smart city goals nad KPIs 10%; CBA 10%; Implementation Roadmap 10%; Process formulated 10%; Budget of implementation 10% | >75% | 60-75% | <60% | I&T
65 | [9 empty] | Adoption on DevCo performance? Robust assessment process and guidelines - 30%; Availability of sample of impact assessment report - 30%; Availability of action plan - 10%; Use of innovative tools/platforms/dashboards - 30% | >75% | 60-75% | <60% | I&T
66 | [9 empty] | Effectiveness index in the mentioned areas is an evaluation of successful implementation (Up to 8.3% for each element of the innovation adoption effective index) (Up to 10% for each element of the smart city adoption effective index) | >75% | 60-75% | <60% | I&T
67 | [9 empty] | Pilot or R&D projects conducted? Availability - 20%; Adequate list of focus areas - 35%; Procedure - 15%; Outcome assessment robustness - 30% | >75% | 60-75% | <60% | I&T
68 | [9 empty] | [(Number of pilots that are scaled successfully + Number of R&D projects that are successfully piloted or fully-scaled) / (Number of pilot projects + Number of R&D projects)] | >40% | 20-40% | <20% | I&T
69 | [9 empty] | Availability of Innovation: Availability - 20%; Adequate Key positions planned in the org. structure - 30%; Unit/department position within the company hierarchy - 20%; Qualifications of the innovation team - 30% | >60% | 40-60% | <40% | I&T
70 | [9 empty] | Availability - 50% Implementation of the unit/department framework/ process - 50% | >50% | 0.5 | <50% | I&T
71 | [9 empty] | Give 'satisfactory' score if there is a technical function strategy, but it is very general and does not provide specific details of the strategy | Yes | Yes, but very brief | No | S&O
72 | [9 empty] | Assess if elements of technical strategy is aligned with organizational strategy. "Average" score if key elements of organizational strategy is not addressed in technical strategy | Well-aligned | Some gaps | Misaligned | S&O
73 | [9 empty] | "Severe" score if challenges faced can impact strategy execution significantly (in terms of time, cost and/or quality) | Minor | Moderate | Severe | S&O
74 | [9 empty] | Give 'satisfactory' score if there are technical KPIs, but they are very generic | Yes | Yes, but very brief | No | S&O
75 | [9 empty] | Number of KPIs achieved / Total Number of KPIs set for the same period | >75% | 50-75% | <50% | S&O
76 | [9 empty] | Expected elements from industry benchmarks: 1. Schedule adherence 2. Budget adherence 3. Employee attrition 4. HSE and Welfare 5. ESG | Aligned with industry benchmarks | Some gaps with industry benchmarks | Significant deviation from industry benchmarks | S&O
77 | [9 empty] | "Severe" if more than 25% of technical department head (N-2 or 3) and above are vacant Technical department head: person leading a technical function (depends on organization size) "Moderate" if 2 position for technical department head are vacant | Minor | Moderate | Severe | S&O
78 | [9 empty] | "Critical" score if there is little to no relevance in the requested qualifications to the role | Well-aligned | Some gaps | Misaligned | S&O
79 | [9 empty] | Strong if these are done: 1. Regular update and review of policies (3 mths) 2. All relevant policies/guidelines captured 3. Easy access (one repository with easy to find link) 4. Multi-channels to inform updates to documents e.g. email, intranet | Strong | Moderate | Poor | S&O
80 | [9 empty] | Strong if these are done: 1. Regular internal audits of processes (ongoing and rotation of topics/departments) 2. Independent internal audit department reporting directly to CEO or Board 3. Whistleblowing policy 4. Regular training for all staff (annual) | Strong | Moderate | Poor | S&O
81 | [9 empty] | Strong if all of these following points are done: 1. Board reporting policy covering frequency/trigger for updates 2. Register of Board Papers/Presentations 3. Register of Board meetings and meeting minutes | Strong | Moderate | Poor | S&O
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
Go to Main Page
Refresh
Consolidate D&F
Compare D&F