## Sheet1
DevCo | Additional Data Point | Input Value | Year | Value Completed (Baseline) in M SAR | Value Completed (Actual) in M SAR | Value Completed (Forecast) in M SAR | Risk Category | Number of Risk Items | Risk | Source | Potential Impact | Risk Rating | Risk Status | Current Measures | Assessment Criteria | Value | Key Topic | Key Topic Score | Rating | Remarks 3 | Data Point | Input Value | Additional Data Point | Input Value | Year | Budget Value (Baseline) in M SAR | Budget Value (Revised) in M SAR | Budget Value (Forecast) in M SAR | Assessment Criteria | Value | Rating | Remarks 3 | Key Topic | Key Topic Score | Data Point | Input Value | Number of Quality Audits | Month | Additional Data Point | Input Value | Parameter | Baseline | Actual | Forecast | Incident Category | Number of Incidents (To-Date) | Number of Investigations in Progress | Number of Investigations Completed | Number of Investigations Pending Approval | Audits/Inspections | In Progress_audits | Completed_audits | Remaining Planned | Actions | In Progress_actions | Completed_actions | Pending Approval | Year | Value_training | Program | Acquired (Ha) | Under Negotiation (Ha) | Pending (Ha) | Value | Assessment Criteria | Value | Key Topic | Key Topic Score | Performance Signal | Performance Signal Score | Rating | Assessment Criteria | Data Point | Input Value | Additional Data Point | Input Value | Assessment Criteria | Value | Rating | Performance Signal Score | Performance Signal | Key Topic | Key Topic Score | Assessment Criteria | Data Point | Input Value | Weightage | Name of the KPI | Additional Data Point | Input Value | Name of the Policy | Criticality Policies (Y/N) | Availability Policies (Y/N) | Name of the Technical Platform | Criticality Technical (Y/N) | Availability Technical (Y/N) | Department | Total Positions | No of Positions Unfullfiled | Position Vacant | Position Missing | Name of the Department | No of Position Missing | % of Position Unfullfiled | Rating | Assessment Criteria | Value | Key Topic | Key Topic Score | Score | Performance Signal | Performance Signal Score | Assessment Criteria | Data Point | Input Value | Remarks 3 | Performance Signal | Performance Signal Score | Value | Rating | Assessment Criteria | Key Topic | Key Topic Score | Input Value | Data Point
Diriyah | Latest Approved Completion Date​ | 31/05/2029 | 2025 |  |  |  | Risk 1 |  | Risk 1 | [5 empty] | DevCo Schedule Performance Index (SPI) | 0.65958 | Overall Progress | 0.65 | Needs Improvement |  | Planned Value (PV) | 55.49 | Total Expenditure to Date | 33213178137.7779 |  |  |  |  | Number of Projects with Budget Variance | 0.70878 | Needs Improvement | 102 projects( ncluding approved and un approved) have had variations from their original approved COST ESTIMATE (due to increasing uncommitted costs and update in Order of Cost estimates as a result of updation of Master plan and concept designs) | Overall Budget | 0.38 | PIF Approved Capex budget (Initial Business Plan) | 204358702695.6711 |  | Jan | Packaging & Phasing Strategy (Text) | [5 empty] | Fatalities |  |  |  |  | HSE Audit |  |  |  | HSE |  |  |  | Jan | [6 empty] | % of CESMP mitigation measures which align with ESIA* | 0.81818 | Construction | 0.92 | Construction Planning Maturity | 0.89 | Good | % of CESMP mitigation measures which align with ESIA* | Environmental mitigation measures included in CESMP (No.) | 9 | Implementation Success Rate for Innovation Strategy (%) |  | Is there an innovation Strategy or document that lists the key focus areas and initiatives across design, construction and operation and aligned with DevCo strategic plan? | 0.45 | Needs Improvement | 0.53 | Innovation & Technology Deployment | Innovation and Technology Adoption | 0.41 | Is there an innovation Strategy or document that lists the key focus areas and initiatives across design, construction and operation and aligned with DevCo strategic plan? | Availability of an innovation strategy (%) | 0.05 |  |  | Completeness & Relevance of Technical Strategy (Text) | [7 empty] | Project controls | 6 | 1 | Centralised Innovation Team | N | Project controls | 1 |  | Satisfactory | Availability of Technical Function Strategy | Yes, but very brief | Technical Strategy and Enablers | 0.56 | 0.66 | Technical Strategy Achievement | 0.42 | Availability of Technical Function Strategy | Availability of strategy | Yes, but very brief |  | CGI and Animation Compliance | 0.92 | 0.9 | Good | Similarity between original/approved and latest CGI and availability of animation with a close match at same angle | Vision Adherence | 0.96 | 0.9 | Percentage similarity between Approved CGI and Latest CGI at same angle and scale
Diriyah | Forecast Completion Date​ | 2029-01-06 | 2026 |  |  |  | Risk 2 |  | Risk 2 | [11 empty] | Earned Value (EV) | 36.6 | Contingency utilized at DevCo level | 1183022352 | [10 empty] | Forecast budget (EAC) | 349203458382.3173 |  | Feb | Execution & Site Logistics (Text) | [5 empty] | Severe Impairment |  |  |  |  | Welfare Inspection |  |  |  | Welfare |  |  |  | Feb | [14 empty] | Environmental mitigation measures recommended in ESIA (No.) | 11 | Implementation Success Rate for Smart City Strategy (%) | [9 empty] | Alignment of innovation strategy with DevCo Strategic Plan (%) | 0.05 |  |  | Mitigation of Key Challenges (Text) | [7 empty] | Procurment and Contracts Management | 17 | 5 |  |  | Procurment and Contracts Management | 5 |  | Needs Improvement | Alignment of Technical Strategy with Organizational Strategy | Misaligned |  |  | 0.33 |  |  | Alignment of Technical Strategy with Organizational Strategy | Alignment of technical functions' strategy and initiatives with the overarching organizational strategy | Misaligned |  |  |  | Partially Applied | Satisfactory | Similarity between original/approved and latest CGI and availability of animation with a close match at same angle |  |  | Partially Applied | Availability of Approved Animation and Latest Animation with a close match, at the same camera angle (Text)
Diriyah | Approved baseline completion date | 31/05/2029 | 2027 |  |  |  | Risk 3 |  | Risk 3 | [5 empty] | % milestone achievement in accordance with the approved business plan | 0.9 |  |  | Good |  | No. of planned milestones | 1050 | Value of Changes in Design Stage | [5 empty] | Budget Variance | 0.42678 | Needs Improvement |  |  |  | Number of Projects with Budget Variance | 102 |  | Mar | Procurement Strategy (Text) | [5 empty] | Lost Time Incidents | [12 empty] | Mar | [6 empty] | Does each project have Environmental Permits in place? | Yes |  |  |  |  | Good | Does each project have Environmental Permits in place? | Authority Issued Environmental Permit for Constrution Works (Text) | Yes | [10 empty] | List of focus areas of innovation and technology (%) | 0.1 |  |  | Assessment of Technical KPIs (No.) | [7 empty] | Innovation | 0 | 0 |  |  | Design Management | 20 |  | Needs Improvement | Severity of Key Challenges Faced in Strategy Execution Technically | Data Not Available |  |  | 0.33 |  |  | Severity of Key Challenges Faced in Strategy Execution Technically | Key challenges in strategy execution | Data Not Available |  |  |  | 0.7 | Satisfactory | Material Palette & Finish Schedule |  |  | 0.7 | Material Palette & Finish Schedule
Diriyah | Planned duration up to a specific phase as per approved Baseline programme |  | 2028 |  |  |  | Risk 4 |  | Risk 4 | [11 empty] | No. of milestones achieved on time | 945 | Value of Changes in Construction Stage | [11 empty] | Total number of projects (No.) | 239 |  | Apr | Land Acquisition Requirements (Program, Acquired (Ha), Under Negotiation (Ha), Pending (Ha)) (No.) | [5 empty] | Recordable Incidents | [12 empty] | Apr | [6 empty] | Can the DevCo demondstrate oversight or verification of Contractors compliance with Environmental Permit conditions? | Yes |  |  |  |  | Good | Can the DevCo demondstrate oversight or verification of Contractors compliance with Environmental Permit conditions? | Environmental Audit Report or Environmental Compliance Report (Text) | Yes | [10 empty] | List of innovative initiatives throughout project lifecycle (design, construction and operation) (%) | 0.1 |  |  | Unfulfilled Positions (Department, Total Positions, No. of Positions Unfulfilled, % of Position Unfulfilled) (No.) | [7 empty] | Design Management | 202 | 20 |  |  | Cost Management | 28 |  | Satisfactory | Availability of Technical KPIs | Yes, but very brief |  |  | 0.66 | Technical KPI Achievement | 0.46 | Availability of Technical KPIs | Availability of KPIs | Yes, but very brief |  |  |  | Yes | Good | Does the DevCo have Design & Technical Guidelines (including Look & Feel Design Guidelines)? |  |  | Yes | Design and Technical Guidelines
Diriyah | Duration taken to complete works up to the specific phase |  | 2029 |  |  |  | Risk 5 |  | Risk 5 | [5 empty] | % of projects with approved change requests in design phase since inception with time impact of more than 1 month | 0.033898 |  |  | Good |  | Total number of projects in design phase | 118 | Number of Changes (Concept MP) | [5 empty] | % of projects with contingency utilization rate > 1 | Data Not Available | Needs Improvement |  |  |  | Number of projects with contingency utilization > 1 | Data Not Available |  | May | Workforce Availability (Text) | [5 empty] | Near Misses | [12 empty] | May | [6 empty] | Has the Construction Execution Plan been updated to reflect the latest stage of construction? | Yes |  |  |  |  | Good | Has the Construction Execution Plan been updated to reflect the latest stage of construction? | Update of construction execution plan (Text) | Yes | [10 empty] | Availability of innovation cost-benefit analysis (%) | 0 |  |  | Organisation Chart (Text) | [7 empty] | Cost Management | 189 | 28 |  |  | Construction Management | 38 |  | Needs Improvement | Progress of Achievement of KPIs for Technical Team | Data Not Available |  |  | 0.33 |  |  | Progress of Achievement of KPIs for Technical Team | Total Number of KPIs set for the preceding year | Yes, but very brief |  |  |  | Yes | Good | Do DevCo projects comply with DDTG? |  |  | Yes | Look & Feel Guideline
Diriyah | Recovery Plan | Not Available | [6 empty] | Risk 6 | [11 empty] | Number of projects with approved change requests in design phase since inception with time impact of more than 1 month | 4 | Number of Changes (Detailed MP) | [5 empty] | % of projects with Approved Change Requests (design/construction) having a cost impact greater than 2% | Data Not Available | Needs Improvement |  |  |  | No. of projects with approved change request having a cost impact greater than 2% | Data Not Available |  | Jun | Resource Availability (Text) | [18 empty] | Jun | [6 empty] | Has the construction sequence and method statement been reviewed and approved? | Partially Applied |  |  |  |  | Satisfactory | Has the construction sequence and method statement been reviewed and approved? | Review and approval of Construction sequence & method statement (Text) | Partially Applied | [10 empty] | Availability of implementation roadmap (%) | 0.05 |  |  | List of missing key technical platforms | [7 empty] | Construction Management | 176 | 38 | [14 empty] | Number of KPIs achieved in the preceding year | Data Not Available |  | Development Program Variance | 1 | 0.029333 | Good | % variance from approved Built-Up Area (BUA) |  |  | 9352242 | Latest BUA
Diriyah | Extent of all EOT (design stage) | Not Available | [6 empty] | Risk 7 | [5 empty] | % of projects with approved change requests in construction phase since inception with time impact of more than 4 months | 0.18841 |  |  | Good |  | Total number of projects in construction phase | 69 | Number of Changes (Concept Design) | [5 empty] | % of projects with Approved Claims | 0.0041841 | Good |  |  |  | No. of projects with approved claims | 1 |  | Jul | Number of NCRs open for between 30 and 60 days (No.) | [18 empty] | Jul | [6 empty] | Has adequate planning been carried out to identify required area and location for worksite provisions including construction yards etc? | Yes |  |  |  |  | Good | Has adequate planning been carried out to identify required area and location for worksite provisions including construction yards etc? | Development Site Logistics Map (Text) | Yes | [10 empty] | Process for innovation (%) | 0.05 |  |  | List of critical policies missing, if any | [15 empty] | Needs Improvement | Appropriateness of KPIs for Technical Team | Significant deviation from industry benchmarks |  |  | 0.33 |  |  | Appropriateness of KPIs for Technical Team | Alignment of key KPIs aligning with Cost, Time and Quality | Significant deviation from industry benchmarks | [8 empty] | 9085728 | Approved BUA
Diriyah | Extent of all EOT (const. stage) | Not Available | [6 empty] | Risk 8 | [11 empty] | Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months | 13 | Number of Changes (Detailed Design) | [5 empty] | % of provisional sums of the latest PIF Approved Capex budget | Data Not Available | Needs Improvement |  |  |  | Total provisional sums | Data Not Available |  | Aug | Number of NCRs open for more than 60 days (No.) | [18 empty] | Aug | [6 empty] | Have Traffic Simulations been completed in preparing the Site & Logistics Plan? | Yes |  |  |  |  | Good | Have Traffic Simulations been completed in preparing the Site & Logistics Plan? | Completion of Traffic Simulations (Text) | Yes | [10 empty] | Budget of implementation (%) | 0.05 | [18 empty] | Satisfactory | Criticality of Vacant/Missing Positions in Organization | Moderate |  |  | 0.66 | Technical Organization | 0.52 | Criticality of Vacant/Missing Positions in Organization | Key positions which are missing, if any | Moderate |  |  |  | -0.053357 | Good | % variance in land use permit area |  |  | 68302884 | Latest Land Area
Diriyah | Schedule Chart (Value Completed Baseline, Value Completed Actual, Value Completed Forecast) (No.) | [7 empty] | Risk 9 | [5 empty] | % of projects with approved schedule extension | 0.17112 |  |  | Good |  | No. of Approved EOTs | 32 | Number of Changes (Construction) | [11 empty] | Latest Approved budget (No.) | Data Not Available |  | Sep | Leadership engagement (Text) | [18 empty] | Sep | [6 empty] | The contractor & PMC able to demonstrate Project Execution Planning occuring in the last 12 months including Packaging & Phasing, Site & Logistics Planning & Procurement Strategy Planning | Yes |  |  |  |  | Good | The contractor & PMC able to demonstrate Project Execution Planning occuring in the last 12 months including Packaging & Phasing, Site & Logistics Planning & Procurement Strategy Planning | Masterplan Delivery Strategy (Text) | Yes |  |  | Is there a smart city Strategy or document that lists the key focus areas of smart city aligned with DevCo strategic plan? | 0.81 | Good |  |  |  |  | Is there a smart city Strategy or document that lists the key focus areas of smart city aligned with DevCo strategic plan? | Availability of a smart city strategy (%) | 0.15 | [18 empty] | Needs Improvement | Appropriateness of Qualifications in Recruitment of Vacant Technical Department Head Positions | Data Not Available |  |  | 0.33 |  |  | Appropriateness of Qualifications in Recruitment of Vacant Technical Department Head Positions | Qualifications of job descriptions for vacant technical department head positions - are they appropriate? | Data Not Available | [8 empty] | 72152766 | Approved Land Area
Diriyah | No. of unresolved issues | [7 empty] | Risk 10 | [11 empty] | No. of projects with schedule extension (design stage) | 6 | Total Awarded Cost | 83140439457.2953 |  |  |  |  | % of variance of Allocated Provisional sums against the awarded amount | Data Not Available | Needs Improvement |  |  |  | Actual Utilized Provisional Sums | Data Not Available |  | Oct | Total number of ITPs requested (No.) | [18 empty] | Oct | [6 empty] | % of Stakeholder MOU** / LUPs*** not executed in accordance with critical lead time | 0.38095 |  |  |  |  | Satisfactory | % of Stakeholder MOU** / LUPs*** not executed in accordance with critical lead time | Number of Stakeholder MOU or Land Use Permits not executed on time (No.) | 24 | [10 empty] | Alignment of smart city strategy with DevCo Strategic Plan (%) | 0.15 | [18 empty] | Good | Robustness of Policy/Guideline/Procedure Communication | Strong |  |  | 1 | Technical Control Environment | 0.76 | Robustness of Policy/Guideline/Procedure Communication | List of policies/procedures communicated to all employees | Strong |  |  |  | -0.031161 | Good | Approved Population |  |  | 85346 | Latest Population
Diriyah | No. of (Open) Inherent Risks | 51 | [18 empty] | No. of projects with schedule extension (construction stage) | 8 | Approved Variations and Claims | [14 empty] | Nov | Total number of ITPs completed (No.) | [18 empty] | Nov | [14 empty] | Total Stakeholder MOU or Land Use Permits required (No.) | 63 | [10 empty] | List of Smart City focus areas (%) | 0.1 | [18 empty] | Satisfactory | Robustness of Policy/Guideline/Procedure Compliance Monitoring Framework | Moderate |  |  | 0.66 |  |  | Robustness of Policy/Guideline/Procedure Compliance Monitoring Framework | Monitoring of policies and procedures compliance | Moderate | [8 empty] | 88091 | Approved Population
Diriyah | No. of (Closed) Residual Risks | 65 | [12 empty] | % of projects with Forecast completion date beyond the latest approved schedule | 0.45989 |  |  | Needs Improvement |  | Number of projects with forecast completion date beyond the latest approved schedule | 86 | Uncommitted Cost | 266140780170.0221 | [13 empty] | Dec | Completeness of Quality Management Plan (Text) | [18 empty] | Dec | [6 empty] | Does the DevCo adequately plan, track & monitor stakeholder applications? | Yes |  |  |  |  | Good | Does the DevCo adequately plan, track & monitor stakeholder applications? | Stakeholder Dashboard (Text) | Yes | [10 empty] | List of smart city initiatives within each key focus area (%) | 0.1 | [18 empty] | Satisfactory | Robustness of Board Reporting Framework | Moderate |  |  | 0.66 |  |  | Robustness of Board Reporting Framework | Frequency of reporting to Board and PIF | Moderate |  | Construction Design Maturity | 0.83 | Partially Applied | Satisfactory | Have all DevCos completed a Constructability assessment for complex/iconic projects? | Design for Constructability | 0.83 | Partially Applied | Constructability Report (Text)
Diriyah | Project-level risks (including low, medium, and high severity) | available | [12 empty] | Is the Forecast Finish Date at a given data date based on the alignment and buy-in from project teams and other listed stakeholders? | Yes, but inadequate |  |  | Satisfactory |  | Total list of stakeholders and their commitment to the forecast finish date (Text) | Yes, but inadequate | Pending Variations | [15 empty] | Quality Audits (SN, Month, Number of Quality Audits) | [25 empty] | % of Workforce Hired against Workforce Estimates | 0.94118 |  |  | Workforce Resource Availability | 1 | Good | % of Workforce Hired against Workforce Estimates | Forecast workforce requirements (No.) | 15300 | [10 empty] | Availability of smart city goals and set of KPIs (%) | 0.05 | [32 empty] | Partially Applied | Satisfactory | Was design for Enabling Work Package considerd as part of the design process to ensure the readiness of the site for the main construction work? |  |  | Partially Applied | Assessment of enabling works required
Diriyah | Extra Cost due to Unresolved Issues | Not Available | [12 empty] | Based on the risks identified and approved change requests, has the DevCo conducted a sensitivity assessment on the forecast completion at a given data date? | Yes, but inadequate |  |  | Satisfactory |  | Identified risks with probability and impact ratings and Historical Project Performance (SPI, past variances, Productivity Trends) | Yes, but inadequate | Anticipated Variations | [15 empty] | Contract clauses (Text) | [33 empty] | Actual workforce employed (No.) | 14400 | [10 empty] | Availability of smart city cost-benefit analysis (%) | 0.08 | [32 empty] | Yes | Good | Are documentation packages meeting the LOD requirements of the latest Design Stage Gate? |  |  | 350 | LOD Required
Diriyah | Top 10 Risks (Risk, Source, Potential Impact, Risk Rating, RIsk Status, Current Measures) (Text) | [13 empty] | Has DevCo allocated risk contingency for the identified risks? | Yes, but inadequate | Risk Performance | 0.55 | Satisfactory |  | Risk severity and Risk mapping | Yes, but inadequate | Budget Performance (Year, Budget Value Baseline, Budget Value Revised, Budget Value Forecast) (No.) | [15 empty] | Procurement Management Plan (Text) | [25 empty] | Does the DevCo have an active governance role in assessing Labor Camp capacity to meet worforce demand? | <quarterly |  |  |  |  | Good | Does the DevCo have an active governance role in assessing Labor Camp capacity to meet worforce demand? | Contractors Worker Camp Policy (Text) | <quarterly | [10 empty] | Implementation Roadmap for selected smart city initiatives (%) | 0.05 | [37 empty] | 350 | LOD Documented (drawing sample from Design Report)
Diriyah | Top 5 Risk Categories (RIsk Category, Number of RIsk Items) (Text) | [13 empty] | Was there any deferment in the project completion date due to unidentified risks? | Data Not Available |  |  | Needs Improvement |  | Source of the unidentified risk | Data Not Available | [16 empty] | Scope / design maturity (Text) | [25 empty] | % of Material Supply Capacity against Material Demand Estimates | 0.87333 |  |  |  |  | Good | % of Material Supply Capacity against Material Demand Estimates | Forecast number of batching / crushing plants/ precast yards, etc. (No.) | 45000 | [10 empty] | Process for smart city implementation (%) | 0.08 | [32 empty] | Yes | Good | Have all projects adopted digital delivery using BIM and/or GIS? |  |  | Yes | Projects adopting digital delivery using BIM/GIS (Text)
Diriyah | [14 empty] | Was there any Cost Overrun because of identified risk? | Yes, but less than 5% |  |  | Satisfactory |  | % of cost overrun from the latest approved budget due to identified risk | Yes, but less than 5% | [16 empty] | Tender pack quality (Text) | [33 empty] | Actual number of batching / crushing plants/ precast yards, etc. (No.) | 39300 | [10 empty] | Budget of implementation (%) | 0.05 | [30 empty] | Design Management Maturity | 0.69 | No | Needs Improvement | Is project delivery occurring in accordance with the latest approved design strategy? | Design Management | 0.69 | No | Approved Design Strategy (Text)
Diriyah | [14 empty] | Was there any Cost Overrun because of unidentified risk? | Data Not Available |  |  | Needs Improvement |  | % of cost overrun from the latest approved budget due to unidentified risk | Data Not Available | [16 empty] | % payment paid within contractual terms (%) | [25 empty] | Average Technical Submittal closeout Cycle Time (No.) | 20 | Quality | 0.89 | Adherence to Design | 0.96 | Satisfactory | Average Technical Submittal closeout Cycle Time | Average Technical Submittal closeout Cycle Time (No.) | 20 |  |  | Is there an impact assessment report or identified process/ guidelines to evaluate the impact of the innovation / smart city technologies adoption on DevCo performance? | 0.25 | Needs Improvement |  |  |  |  | Is there an impact assessment report or identified process/ guidelines to evaluate the impact of the innovation / smart city technologies adoption on DevCo performance? | Availability of approach / process and guidelines to evaluate the impact of implementing innovations and technologies (%) | 0.15 | [32 empty] | 0.8 | Good | % of projects with completed technical design/peer reviews and verifications/certifications as required for the latest Design Stage Gate |  |  | 0.8 | % of projects with completed design reviews and verification register (%)
Diriyah | [14 empty] | Risk Control Rate of the identified risks at DevCo Level | 1 |  |  | Good |  | Number of controlled risks | 123 | [16 empty] | Procurement Packages (SN, Parameter, Baseline, Actual, Forecast) (No.) | [25 empty] | % of approved shop drawing reviews vs planned | 0.94648 |  |  |  |  | Good | % of approved shop drawing reviews vs planned | Total number of shop drawing review requests (No.) | 14760 | [10 empty] | Availability of sample of impact assessment report (%) | 0 | [32 empty] | Yes | Good | Availability of robust design management plan and appropriate design review trackers/registers |  |  | Yes | Design Management Plan and Design Review Trackers/Registers (Text)
Diriyah | [20 empty] | Total number of identified risks | 123 | [16 empty] | Number of Notifiable Incidents (No.) | [33 empty] | Total number of shop drawing reviews approved (No.) | 13970 | [10 empty] | Availability of action plan (%) | 0.1 | [32 empty] | Partially Applied | Satisfactory | Is the average cycle time to complete reviews and certifications in accordance with the Design Management Report? |  |  | Partially Applied | Days taken to complete Design Reviews
Diriyah | [14 empty] | Is the DevCo fully compliant with Risk Management Plan requirements? | Yes, but inadequate |  |  | Satisfactory |  | Risk Manager or Risk Committee overseeing risk governance | Yes, but inadequate | [16 empty] | Number of Infringement Notices (No.) | [25 empty] | % of approved product waivers vs product specified | 0.98286 |  |  |  |  | Good | % of approved product waivers vs product specified | Total number of product sample & material approvals requested (No.) | 1342 | [10 empty] | Use of innovative tools/platforms/dashboards (%) | 0 | [32 empty] | No | Needs Improvement | Has the DevCo engaged independent certification of major critical elements? |  |  | No | Level of review and verification required for Stage Gate
Diriyah | [14 empty] | Is there a difference in the time impact forecast before and after the risk event has triggered? | Data Not Available |  |  | Needs Improvement |  | Difference between anticipated and actual effects on time and cost, after the risk event triggered | Data Not Available | [16 empty] | Incident Management (SN, Incident Category, Number of Incidents, Number of Investigations in Progress, Number of Investigations Completed, Number of Investigations Pending Approval) (No.) | [33 empty] | Total number of product sample & materials approved (No.) | 1319 |  |  | Is there evidence for innovation / smart city technologies successful implementation (in final design report, master plan or other)? | 0.446 | Needs Improvement |  |  |  |  | Is there evidence for innovation / smart city technologies successful implementation (in final design report, master plan or other)? | Innovation Adoption Effectiveness Index (strategy & leadership alignment) (%) | 0 | [30 empty] | Environmental Compliance Status | 0.83 | Yes | Good | Are the master DevCo designs integrated with Regional Infrastructure & Mobility Plans? | Regulatory Compliance | 0.84 | Yes | Regional Strategies
Diriyah | [14 empty] | Is there a difference in the Cost impact forecast before and after the risk event has triggered? | Data Not Available |  |  | Needs Improvement |  | Reasons on the difference between anticipated and actual effects on time and cost | Data Not Available | [16 empty] | Total Site Manhours (No.) | [25 empty] | % of Certified As-Built Drawing Packages vs Planned | 0.99959 |  |  |  |  | Good | % of Certified As-Built Drawing Packages vs Planned | Number of As-Built Drawing review requests (No.) | 4827 | [10 empty] | Innovation Adoption Effectiveness Index (skilled human resources) (%) | 0 | [32 empty] | Partially Applied | Satisfactory | Do all projects comply with environmental guidelines in accordance with ESIA? |  |  | Partially Applied | Extent of compliance to environmental guidelines
Diriyah | [38 empty] | Compliant Management - Audits/Inspections (Audit/Inspections, InProgress_audits, Completed_audits, Remaining Planned) | [33 empty] | Number of As-Built Drawings reviews approved (No.) | 4825 | [10 empty] | Innovation Adoption Effectiveness Index (planning & governance) (%) | 0.04 | [30 empty] | Authority Compliance Status | 0.86 | 0.1 | Satisfactory | % of projects with Code Compliance Violations |  |  | 0.1 | % of Code Compliance Violations (%)
Diriyah | [38 empty] | Compliance Management - Actions (Action, InProgress_actions, Completed_actions, Pending Approval) (Text) | [25 empty] | MIR Inspection Rate | 0.98986 |  |  |  |  | Good | MIR Inspection Rate | Total number of MIRs requested (No.) | 296 | [10 empty] | Innovation Adoption Effectiveness Index (process management) (%) | 0.04 | [32 empty] | Yes | Good | Availability of proper Register of Authority Engagement, Approvals and Waivers |  |  | Yes | Register of Authority Engagement, Approvals and Waivers (Text)
Diriyah | [38 empty] | Incident Management (Incident Category, Number of Incidents, Number of Investigations in Progress, Number of Investigations Completed, Number of Investigations Pending Approval) (No.) | [33 empty] | Total number of MIRs inspected (No.) | 293 | [10 empty] | Innovation Adoption Effectiveness Index (partnerships and collaboration) (%) | 0.083 | [32 empty] | Partially Applied | Satisfactory | Have all required Stakeholder Submittals been issued as planned? |  |  | Partially Applied | Stakeholder Submittal Date
Diriyah | [38 empty] | Safety Trainings (Year, Value_training) | [25 empty] | MIR Acceptance and Approval Rate | 0.97973 |  |  |  |  | Good | MIR Acceptance and Approval Rate | Total number of MIRs approved (No.) | 290 | [10 empty] | Innovation Adoption Effectiveness Index (resource management) (%) | 0.06 | [32 empty] | Yes | Good | Availability of robust Stakeholder Management Plan in place |  |  | Yes | Stakeholder Management Plan (Text)
Diriyah | [64 empty] | WIR Inspection Rate | 0.91805 |  |  |  |  | Good | WIR Inspection Rate | Total number of WIRs requested (No.) | 5430 | [10 empty] | Smart City Adoption Effectiveness Index (strategy & leadership alignment) (%) | 0.083 | [32 empty] | Yes | Good | Does the Stakeholder Engagement Plan include proactive communication process to ensure timely coordination and approvals? |  |  | Yes | Scheduled Design Stage Gate Completion
Diriyah | [72 empty] | Total number of WIRs inspected (No.) | 4985 | [10 empty] | Smart City Adoption Effectiveness Index (infrastructure readiness) (%) | 0.02 | [32 empty] | Partially Applied | Satisfactory | Availability of proper tracking and closure procedure for stakeholder comments |  |  | Partially Applied | Stakeholder Comments Tracking and Closure Procedure (Text)
Diriyah | [64 empty] | WIR Acceptance and Approval Rate | 0.85009 |  |  |  |  | Good | WIR Acceptance and Approval Rate | Total number of WIRs approved (No.) | 4616 | [10 empty] | Smart City Adoption Effectiveness Index (planning & governance) (%) | 0.06 | [30 empty] | DevCo ESG Target Achievement | 0.33 | Data Not Available | Needs Improvement | % of projects achieving DevCo ESG Targets | ESG Target Realization | 0.46 | Data Not Available | Planned ESG Target
Diriyah | [64 empty] | Does the frequency of Audits align with the QMP? | Data Not Available |  |  | Quality Assurance / Quality Control (QA/QC) | 0.73 | Needs Improvement | Does the frequency of Audits align with the QMP? | Required Audit frequency (Text) | [11 empty] | Smart City Adoption Effectiveness Index (stakeholder alignment) (%) | 0.02 | [37 empty] | Data Not Available | Actual ESG Target
Diriyah | [64 empty] | Has the DevCo verified the Contractor's ISO Certification and Audit schedule is upto date? | Yes |  |  |  |  | Good | Has the DevCo verified the Contractor's ISO Certification | Copy of Contractor's ISO certification or most recent ISO Audit (Text) | Yes | [10 empty] | Smart City Adoption Effectiveness Index (realized benefits & performance) (%) | 0.04 | [30 empty] | Global ESG Target Alignment | 1 | Yes | Good | Does the DevCo ESG Target align with globally recognized Best Practice Targets? |  |  | Yes | Alignment with globally recognized Best Practice Targets
Diriyah | [64 empty] | % closure of Non-Conformance Reports (NCR) | 0.9375 |  |  |  |  | Good | % closure of Non-Conformance Reports (NCR) | Total number of defects & NCRs (No.) | 96 |  |  | Are there Pilot or R&D projects conducted? | 0.4 | Needs Improvement | 0.33 | Pilot and R&D Transition Rate |  |  | Are there Pilot or R&D projects conducted? | Availability of innovation/smart city piloting or R&D procedures (%) | 0.05
Diriyah | [72 empty] | Total number of closed defects & NCRs (No.) | 90 | [10 empty] | List of focus areas (%) | 0.3
Diriyah | [64 empty] | Average NCRs closeout Cycle Time | 105 |  |  |  |  | Needs Improvement | Average NCRs closeout Cycle Time | Average time to close NCRs (No.) | 105 | [10 empty] | Procedure (%) | 0.05
Diriyah | [64 empty] | Does the DevCo have an active Procurement Management Plan/Policy? | Partially Applied | Procurement | 0.54 | Procurement & Contracting Compliance | 0.59 | Satisfactory | Does the DevCo have an active Procurement Management Plan/Policy? | Procurement Approach (Text) | Partially Applied | [10 empty] | Robustness of assessment of pilot and R&D outcomes (%) | 0
Diriyah | [72 empty] | Date of latest approved Procurement Plan (Text) |  |  |  | % of pilot / R&D Projects Transitioned into Full-Scale | 0.2 | Needs Improvement |  |  |  |  | % of pilot / R&D Projects Transitioned into Full-Scale | Number of pilot projects (No.) | 15
Diriyah | [64 empty] | Average no. days for claims to be closed out | 100 |  |  |  |  | Needs Improvement | Average no. days for claims to be closed out | Claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures (No.) | 100 | [10 empty] | Number of R&D projects (No.) | 0
Diriyah | [64 empty] | Is the DevCo actively conducting tender award assessments and it is well documented? | Partially Applied |  |  |  |  | Satisfactory | Is the DevCo actively conducting tender award assessments and it is well documented? | Tender award assessment documentation (Text) | Partially Applied | [10 empty] | Number of pilot projects that are scaled successfully (No.) | 3
Diriyah | [64 empty] | Is the DevCo undertaking due diligence of the vendors appointed? | Partially Applied |  |  |  |  | Satisfactory | Is the DevCo undertaking due diligence of the vendors appointed? | Due diligence tender evaluation documents (Text) | Partially Applied | [10 empty] | Number of R&D projects that are successfully piloted or fully-scaled (No.) | 0
Diriyah | [64 empty] | Did the DevCo complete a Supply Chain Risk-Market Intelligence Assessment in the last quarter? | Partially Applied |  |  |  |  | Satisfactory | Did the DevCo complete a Supply Chain Risk-Market Intelligence Assessment in the last quarter? | Supply Chain Risk-Market Intelligence Assessment (Text) | Partially Applied |  |  | Availability of Innovation unit / department with structured team | 0 | Needs Improvement | 0.33 | Organization Maturity Towards Innovation Adoption |  |  | Availability of Innovation unit / department with structured team | Availability of Innovation unit/department (%) | 0
Diriyah | [64 empty] | % of procurement activities executed as planned in the Annual Procurement Plan | 0.29167 |  |  | Procurement & Contracting Execution Performance | 0.52 | Satisfactory | % of procurement activities executed as planned in the Annual Procurement Plan | Total number of procurement activities (No.) | 48 | [10 empty] | Key positions planned in the innovation unit/department (%) | 0
Diriyah | [72 empty] | Number of procurement activities executed as planned (No.) | 14 | [10 empty] | Innovation unit/department within the company hierachy (%) | 0
Diriyah | [64 empty] | % of deviations in total awarded contract value with approved TDC | 1 |  |  |  |  | Needs Improvement | % of deviations in total awarded contract value with approved TDC | Value of Awarded Contract (No.) | 50.15 | [10 empty] | Qualifications of the innovation team (%) | 0
Diriyah | [72 empty] | Tender Cost Estimate (No.) |  |  |  | Availability of Innovation and Technology Strategy / Process & Framework | 0.2 | Needs Improvement |  |  |  |  | Availability of Innovation and Technology Strategy / Process & Framework | Innovation Unit Strategy / Process & Framework (%) | 0.1
Diriyah | [64 empty] | % of contracts with pending claims | 0.325 |  |  |  |  | Satisfactory | % of contracts with pending claims | % of contracts with filed claims (%) | 0.325 | [10 empty] | Implementation of innovation department process / framework (%) | 0.1
Diriyah | [64 empty] | % of Payment Certificates and payments being processed within the contractual payment terms? | 0.987 |  |  |  |  | Needs Improvement | % of Payment Certificates and payments being processed within the contractual payment terms? | % payment paid within contractual terms (%) | 0.987
Diriyah | [64 empty] | Are Vendor performance assessment occurring which capture financial instability, delays, repeated quality issues in real-time? | Partially Applied |  |  |  |  | Satisfactory | Are Vendor performance assessment occurring which capture financial instability, delays, repeated quality issues in real-time? | Alignment of sourcing strategies with project schedules and requirements (Text) | Partially Applied
Diriyah | [64 empty] | Does the HSE Management Manual have adequate provision for identification and escalation of high risk activities? | Yes | HSE and Welfare | 0.8 | HSE Compliance | 0.78 | Good | Does the HSE Management Manual have adequate provision for identification and escalation of high risk activities? | Escalation criteria for high risk activities (Text) | Yes
Diriyah | [64 empty] | Has the DevCo provided a NCR Safety Register? | No |  |  |  |  | Needs Improvement | Has the DevCo provided a NCR Safety Register? | NCR safety register (Text) | No
Diriyah | [64 empty] | Is the rate of review of the Safety Risk Register in accordance with the HSE Management Manual? | Yes |  |  |  |  | Good | Is the rate of review of the Safety Risk Register in accordance with the HSE Management Manual? | HSE Risk Register Review Rate (Text) | Yes
Diriyah | [64 empty] | % of closed Safety Risk items | 0.92809 |  |  |  |  | Good | % of closed Safety Risk items | Total number of Safety Risk items (No.) | 2823
Diriyah | [72 empty] | Total number of closed Safety Risk items (No.) | 2620
Diriyah | [64 empty] | Average cycle time to close Safety Risk items | 30 |  |  |  |  | Needs Improvement | Average cycle time to close Safety Risk items | Cycle time to close Safety Risk items (in days) (No.) | 30
Diriyah | [64 empty] | Has the DevCo provided a a Safety Incident Register? | No |  |  |  |  | Needs Improvement | Has the DevCo provided a a Safety Incident Register? | Safety incident register (Text) | No
Diriyah | [64 empty] | Average cycle time to close Safety Incident | 30 |  |  |  |  | Needs Improvement | Average cycle time to close Safety Incident | Cycle time to close Safety Incident (in days) (No.) | 30
Diriyah | [64 empty] | Is the emergency drill rate compliant with EEPP? | Yes |  |  |  |  | Good | Is the emergency drill rate compliant with EEPP? | Planned number of Emergency Drills (No.) | 5
Diriyah | [72 empty] | Actual number of Emergency Drills (No.) | 11
Diriyah | [72 empty] | Recommended time to complete Emergency drills (No.) | Data Not Available
Diriyah | [72 empty] | Actual Time to complete Emergency drills (No.) | Data Not Available
Diriyah | [64 empty] | Fatality Rate (FR) | 0 |  |  |  |  | Good | Fatality Rate (FR) | No. of incidents resulting in fatality or severe impairment per 200,000 work hours (No.) | 0
Diriyah | [64 empty] | Lost Time Injury Frequency Rate (LTIFR) | 0 |  |  |  |  | Good | Lost Time Injury Frequency Rate (LTIFR) | No. of incidents resulting in lost time per 200,000 work hours (No.) | 0
Diriyah | [64 empty] | Total Recordable Incident Rate (TRIR) | 0 |  |  |  |  | Good | Total Recordable Incident Rate (TRIR) | No. of recordable incidents per 200,000 work hours (No.) | 0
Diriyah | [64 empty] | Near Miss Rate | 0.73 |  |  |  |  | Satisfactory | Near Miss Rate | No. of near misses recorded per 200,000 work hours (No.) | 0.73
Diriyah | [64 empty] | Safety Observation Rate | 346 |  |  |  |  | Good | Safety Observation Rate | No. of safety observation recorded per 200,000 work hours (No.) | 346
Diriyah | [64 empty] | Is there evidence of Leadership Safety Walks occuring? | Data Not Available |  |  |  |  | Needs Improvement | Is there evidence of Leadership Safety Walks occuring? | Total number of Safety Walks with Leadership (No.) | Yes
Diriyah | [64 empty] | Is the DevCo tracking & monitoring Grievances? | Yes |  |  | Welfare Compliance | 0.83 | Good | Is the DevCo tracking & monitoring Grievances? | Total number of grievances (No.) | Yes
Diriyah | [64 empty] | Has the DevCo demonstrated active management in closing out Grievances? | Yes |  |  |  |  | Good | Has the DevCo demonstrated active management in closing out Grievances? | Cycle time to close grievances (No.) | No
Diriyah | [64 empty] | Does the DevCo set targets and monitor the minimum number of HSE & Welfare staff vs the total workforce? | Yes |  |  |  |  | Good | Does the DevCo set targets and monitor the minimum number of HSE & Welfare staff vs the total workforce? | DevCo staffing register (Text) | No
Diriyah | [64 empty] | Does the DevCo track and monitor closeout of welfare observations? | Yes |  |  |  |  | Good | Does the DevCo track and monitor closeout of welfare observations? | Total number of Closed Welfare Observations (No.) | Yes
Diriyah | [64 empty] | Has the DevCo demonstrated closeout of Welfare Non-compliances is occuring? | Yes |  |  |  |  | Good | Has the DevCo demonstrated closeout of Welfare Non-compliances is occuring? | Total Closed Welfare Non-compliances (No.) | No
Diriyah | [64 empty] | Is frequency of Labor Accommodation Inspection occurring in accordance with VMMP? | No |  |  |  |  | Needs Improvement | Is frequency of Labor Accommodation Inspection occurring in accordance with VMMP? | Mitigation measures in the event of welfare audit observations & recommendations (Text) | No
Qiddiya | Latest Approved Completion Date​ | 31/05/2029 | 2025 |  |  |  | Risk 1 |  | Risk 1 | [5 empty] | DevCo Schedule Performance Index (SPI) | 0.65958 | Overall Progress | 0.65 | Needs Improvement |  | Planned Value (PV) | 55.49 | Total Expenditure to Date | 33213178137.7779 |  |  |  |  | Number of Projects with Budget Variance | 0.70878 | Needs Improvement | 102 projects( ncluding approved and un approved) have had variations from their original approved COST ESTIMATE (due to increasing uncommitted costs and update in Order of Cost estimates as a result of updation of Master plan and concept designs) | Overall Budget | 0.38 | PIF Approved Capex budget (Initial Business Plan) | 204358702695.6711 |  | Jan | Packaging & Phasing Strategy (Text) | [5 empty] | Fatalities |  |  |  |  | HSE Audit |  |  |  | HSE |  |  |  | Jan | [6 empty] | % of CESMP mitigation measures which align with ESIA* | 0.81818 | Construction | 0.92 | Construction Planning Maturity | 0.89 | Good | % of CESMP mitigation measures which align with ESIA* | Environmental mitigation measures included in CESMP (No.) | 9 | Implementation Success Rate for Innovation Strategy (%) |  | Is there an innovation Strategy or document that lists the key focus areas and initiatives across design, construction and operation and aligned with DevCo strategic plan? | 0.45 | Needs Improvement | 0.53 | Innovation & Technology Deployment | Innovation and Technology Adoption | 0.41 | Is there an innovation Strategy or document that lists the key focus areas and initiatives across design, construction and operation and aligned with DevCo strategic plan? | Availability of an innovation strategy (%) | 0.05 |  |  | Completeness & Relevance of Technical Strategy (Text) | [7 empty] | Project controls | 6 | 1 | Centralised Innovation Team | N | Project controls | 1 |  | Satisfactory | Availability of Technical Function Strategy | Yes, but very brief | Technical Strategy and Enablers | 0.56 | 0.66 | Technical Strategy Achievement | 0.42 | Availability of Technical Function Strategy | Availability of strategy | Yes, but very brief |  | CGI and Animation Compliance | 0.92 | 0.9 | Good | Similarity between original/approved and latest CGI and availability of animation with a close match at same angle | Vision Adherence | 0.96 | 0.9 | Percentage similarity between Approved CGI and Latest CGI at same angle and scale
Qiddiya | Forecast Completion Date​ | 2029-01-06 | 2026 |  |  |  | Risk 2 |  | Risk 2 | [11 empty] | Earned Value (EV) | 36.6 | Contingency utilized at DevCo level | 1183022352 | [10 empty] | Forecast budget (EAC) | 349203458382.3173 |  | Feb | Execution & Site Logistics (Text) | [5 empty] | Severe Impairment |  |  |  |  | Welfare Inspection |  |  |  | Welfare |  |  |  | Feb | [14 empty] | Environmental mitigation measures recommended in ESIA (No.) | 11 | Implementation Success Rate for Smart City Strategy (%) | [9 empty] | Alignment of innovation strategy with DevCo Strategic Plan (%) | 0.05 |  |  | Mitigation of Key Challenges (Text) | [7 empty] | Procurment and Contracts Management | 17 | 5 |  |  | Procurment and Contracts Management | 5 |  | Needs Improvement | Alignment of Technical Strategy with Organizational Strategy | Misaligned |  |  | 0.33 |  |  | Alignment of Technical Strategy with Organizational Strategy | Alignment of technical functions' strategy and initiatives with the overarching organizational strategy | Misaligned |  |  |  | Partially Applied | Satisfactory | Similarity between original/approved and latest CGI and availability of animation with a close match at same angle |  |  | Partially Applied | Availability of Approved Animation and Latest Animation with a close match, at the same camera angle (Text)
Qiddiya | Approved baseline completion date | 31/05/2029 | 2027 |  |  |  | Risk 3 |  | Risk 3 | [5 empty] | % milestone achievement in accordance with the approved business plan | 0.9 |  |  | Good |  | No. of planned milestones | 1050 | Value of Changes in Design Stage | [5 empty] | Budget Variance | 0.42678 | Needs Improvement |  |  |  | Number of Projects with Budget Variance | 102 |  | Mar | Procurement Strategy (Text) | [5 empty] | Lost Time Incidents | [12 empty] | Mar | [6 empty] | Does each project have Environmental Permits in place? | Yes |  |  |  |  | Good | Does each project have Environmental Permits in place? | Authority Issued Environmental Permit for Constrution Works (Text) | Yes | [10 empty] | List of focus areas of innovation and technology (%) | 0.1 |  |  | Assessment of Technical KPIs (No.) | [7 empty] | Innovation | 0 | 0 |  |  | Design Management | 20 |  | Needs Improvement | Severity of Key Challenges Faced in Strategy Execution Technically | Data Not Available |  |  | 0.33 |  |  | Severity of Key Challenges Faced in Strategy Execution Technically | Key challenges in strategy execution | Data Not Available |  |  |  | 0.7 | Satisfactory | Material Palette & Finish Schedule |  |  | 0.7 | Material Palette & Finish Schedule
Qiddiya | Planned duration up to a specific phase as per approved Baseline programme |  | 2028 |  |  |  | Risk 4 |  | Risk 4 | [11 empty] | No. of milestones achieved on time | 945 | Value of Changes in Construction Stage | [11 empty] | Total number of projects (No.) | 239 |  | Apr | Land Acquisition Requirements (Program, Acquired (Ha), Under Negotiation (Ha), Pending (Ha)) (No.) | [5 empty] | Recordable Incidents | [12 empty] | Apr | [6 empty] | Can the DevCo demondstrate oversight or verification of Contractors compliance with Environmental Permit conditions? | Yes |  |  |  |  | Good | Can the DevCo demondstrate oversight or verification of Contractors compliance with Environmental Permit conditions? | Environmental Audit Report or Environmental Compliance Report (Text) | Yes | [10 empty] | List of innovative initiatives throughout project lifecycle (design, construction and operation) (%) | 0.1 |  |  | Unfulfilled Positions (Department, Total Positions, No. of Positions Unfulfilled, % of Position Unfulfilled) (No.) | [7 empty] | Design Management | 202 | 20 |  |  | Cost Management | 28 |  | Satisfactory | Availability of Technical KPIs | Yes, but very brief |  |  | 0.66 | Technical KPI Achievement | 0.46 | Availability of Technical KPIs | Availability of KPIs | Yes, but very brief |  |  |  | Yes | Good | Does the DevCo have Design & Technical Guidelines (including Look & Feel Design Guidelines)? |  |  | Yes | Design and Technical Guidelines
Qiddiya | Duration taken to complete works up to the specific phase |  | 2029 |  |  |  | Risk 5 |  | Risk 5 | [5 empty] | % of projects with approved change requests in design phase since inception with time impact of more than 1 month | 0.033898 |  |  | Good |  | Total number of projects in design phase | 118 | Number of Changes (Concept MP) | [5 empty] | % of projects with contingency utilization rate > 1 | Data Not Available | Needs Improvement |  |  |  | Number of projects with contingency utilization > 1 | Data Not Available |  | May | Workforce Availability (Text) | [5 empty] | Near Misses | [12 empty] | May | [6 empty] | Has the Construction Execution Plan been updated to reflect the latest stage of construction? | Yes |  |  |  |  | Good | Has the Construction Execution Plan been updated to reflect the latest stage of construction? | Update of construction execution plan (Text) | Yes | [10 empty] | Availability of innovation cost-benefit analysis (%) | 0 |  |  | Organisation Chart (Text) | [7 empty] | Cost Management | 189 | 28 |  |  | Construction Management | 38 |  | Needs Improvement | Progress of Achievement of KPIs for Technical Team | Data Not Available |  |  | 0.33 |  |  | Progress of Achievement of KPIs for Technical Team | Total Number of KPIs set for the preceding year | Yes, but very brief |  |  |  | Yes | Good | Do DevCo projects comply with DDTG? |  |  | Yes | Look & Feel Guideline
Qiddiya | Recovery Plan | Not Available | [6 empty] | Risk 6 | [11 empty] | Number of projects with approved change requests in design phase since inception with time impact of more than 1 month | 4 | Number of Changes (Detailed MP) | [5 empty] | % of projects with Approved Change Requests (design/construction) having a cost impact greater than 2% | Data Not Available | Needs Improvement |  |  |  | No. of projects with approved change request having a cost impact greater than 2% | Data Not Available |  | Jun | Resource Availability (Text) | [18 empty] | Jun | [6 empty] | Has the construction sequence and method statement been reviewed and approved? | Partially Applied |  |  |  |  | Satisfactory | Has the construction sequence and method statement been reviewed and approved? | Review and approval of Construction sequence & method statement (Text) | Partially Applied | [10 empty] | Availability of implementation roadmap (%) | 0.05 |  |  | List of missing key technical platforms | [7 empty] | Construction Management | 176 | 38 | [14 empty] | Number of KPIs achieved in the preceding year | Data Not Available |  | Development Program Variance | 1 | 0.029333 | Good | % variance from approved Built-Up Area (BUA) |  |  | 9352242 | Latest BUA
Qiddiya | Extent of all EOT (design stage) | Not Available | [6 empty] | Risk 7 | [5 empty] | % of projects with approved change requests in construction phase since inception with time impact of more than 4 months | 0.18841 |  |  | Good |  | Total number of projects in construction phase | 69 | Number of Changes (Concept Design) | [5 empty] | % of projects with Approved Claims | 0.0041841 | Good |  |  |  | No. of projects with approved claims | 1 |  | Jul | Number of NCRs open for between 30 and 60 days (No.) | [18 empty] | Jul | [6 empty] | Has adequate planning been carried out to identify required area and location for worksite provisions including construction yards etc? | Yes |  |  |  |  | Good | Has adequate planning been carried out to identify required area and location for worksite provisions including construction yards etc? | Development Site Logistics Map (Text) | Yes | [10 empty] | Process for innovation (%) | 0.05 |  |  | List of critical policies missing, if any | [15 empty] | Needs Improvement | Appropriateness of KPIs for Technical Team | Significant deviation from industry benchmarks |  |  | 0.33 |  |  | Appropriateness of KPIs for Technical Team | Alignment of key KPIs aligning with Cost, Time and Quality | Significant deviation from industry benchmarks | [8 empty] | 9085728 | Approved BUA
Qiddiya | Extent of all EOT (const. stage) | Not Available | [6 empty] | Risk 8 | [11 empty] | Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months | 13 | Number of Changes (Detailed Design) | [5 empty] | % of provisional sums of the latest PIF Approved Capex budget | Data Not Available | Needs Improvement |  |  |  | Total provisional sums | Data Not Available |  | Aug | Number of NCRs open for more than 60 days (No.) | [18 empty] | Aug | [6 empty] | Have Traffic Simulations been completed in preparing the Site & Logistics Plan? | Yes |  |  |  |  | Good | Have Traffic Simulations been completed in preparing the Site & Logistics Plan? | Completion of Traffic Simulations (Text) | Yes | [10 empty] | Budget of implementation (%) | 0.05 | [18 empty] | Satisfactory | Criticality of Vacant/Missing Positions in Organization | Moderate |  |  | 0.66 | Technical Organization | 0.52 | Criticality of Vacant/Missing Positions in Organization | Key positions which are missing, if any | Moderate |  |  |  | -0.053357 | Good | % variance in land use permit area |  |  | 68302884 | Latest Land Area
Qiddiya | Schedule Chart (Value Completed Baseline, Value Completed Actual, Value Completed Forecast) (No.) | [7 empty] | Risk 9 | [5 empty] | % of projects with approved schedule extension | 0.17112 |  |  | Good |  | No. of Approved EOTs | 32 | Number of Changes (Construction) | [11 empty] | Latest Approved budget (No.) | Data Not Available |  | Sep | Leadership engagement (Text) | [18 empty] | Sep | [6 empty] | The contractor & PMC able to demonstrate Project Execution Planning occuring in the last 12 months including Packaging & Phasing, Site & Logistics Planning & Procurement Strategy Planning | Yes |  |  |  |  | Good | The contractor & PMC able to demonstrate Project Execution Planning occuring in the last 12 months including Packaging & Phasing, Site & Logistics Planning & Procurement Strategy Planning | Masterplan Delivery Strategy (Text) | Yes |  |  | Is there a smart city Strategy or document that lists the key focus areas of smart city aligned with DevCo strategic plan? | 0.81 | Good |  |  |  |  | Is there a smart city Strategy or document that lists the key focus areas of smart city aligned with DevCo strategic plan? | Availability of a smart city strategy (%) | 0.15 | [18 empty] | Needs Improvement | Appropriateness of Qualifications in Recruitment of Vacant Technical Department Head Positions | Data Not Available |  |  | 0.33 |  |  | Appropriateness of Qualifications in Recruitment of Vacant Technical Department Head Positions | Qualifications of job descriptions for vacant technical department head positions - are they appropriate? | Data Not Available | [8 empty] | 72152766 | Approved Land Area
Qiddiya | No. of unresolved issues | [7 empty] | Risk 10 | [11 empty] | No. of projects with schedule extension (design stage) | 6 | Total Awarded Cost | 83140439457.2953 |  |  |  |  | % of variance of Allocated Provisional sums against the awarded amount | Data Not Available | Needs Improvement |  |  |  | Actual Utilized Provisional Sums | Data Not Available |  | Oct | Total number of ITPs requested (No.) | [18 empty] | Oct | [6 empty] | % of Stakeholder MOU** / LUPs*** not executed in accordance with critical lead time | 0.38095 |  |  |  |  | Satisfactory | % of Stakeholder MOU** / LUPs*** not executed in accordance with critical lead time | Number of Stakeholder MOU or Land Use Permits not executed on time (No.) | 24 | [10 empty] | Alignment of smart city strategy with DevCo Strategic Plan (%) | 0.15 | [18 empty] | Good | Robustness of Policy/Guideline/Procedure Communication | Strong |  |  | 1 | Technical Control Environment | 0.76 | Robustness of Policy/Guideline/Procedure Communication | List of policies/procedures communicated to all employees | Strong |  |  |  | -0.031161 | Good | Approved Population |  |  | 85346 | Latest Population
Qiddiya | No. of (Open) Inherent Risks | 51 | [18 empty] | No. of projects with schedule extension (construction stage) | 8 | Approved Variations and Claims | [14 empty] | Nov | Total number of ITPs completed (No.) | [18 empty] | Nov | [14 empty] | Total Stakeholder MOU or Land Use Permits required (No.) | 63 | [10 empty] | List of Smart City focus areas (%) | 0.1 | [18 empty] | Satisfactory | Robustness of Policy/Guideline/Procedure Compliance Monitoring Framework | Moderate |  |  | 0.66 |  |  | Robustness of Policy/Guideline/Procedure Compliance Monitoring Framework | Monitoring of policies and procedures compliance | Moderate | [8 empty] | 88091 | Approved Population
Qiddiya | No. of (Closed) Residual Risks | 65 | [12 empty] | % of projects with Forecast completion date beyond the latest approved schedule | 0.45989 |  |  | Needs Improvement |  | Number of projects with forecast completion date beyond the latest approved schedule | 86 | Uncommitted Cost | 266140780170.0221 | [13 empty] | Dec | Completeness of Quality Management Plan (Text) | [18 empty] | Dec | [6 empty] | Does the DevCo adequately plan, track & monitor stakeholder applications? | Yes |  |  |  |  | Good | Does the DevCo adequately plan, track & monitor stakeholder applications? | Stakeholder Dashboard (Text) | Yes | [10 empty] | List of smart city initiatives within each key focus area (%) | 0.1 | [18 empty] | Satisfactory | Robustness of Board Reporting Framework | Moderate |  |  | 0.66 |  |  | Robustness of Board Reporting Framework | Frequency of reporting to Board and PIF | Moderate |  | Construction Design Maturity | 0.83 | Partially Applied | Satisfactory | Have all DevCos completed a Constructability assessment for complex/iconic projects? | Design for Constructability | 0.83 | Partially Applied | Constructability Report (Text)
Qiddiya | Project-level risks (including low, medium, and high severity) | available | [12 empty] | Is the Forecast Finish Date at a given data date based on the alignment and buy-in from project teams and other listed stakeholders? | Yes, but inadequate |  |  | Satisfactory |  | Total list of stakeholders and their commitment to the forecast finish date (Text) | Yes, but inadequate | Pending Variations | [15 empty] | Quality Audits (SN, Month, Number of Quality Audits) | [25 empty] | % of Workforce Hired against Workforce Estimates | 0.94118 |  |  | Workforce Resource Availability | 1 | Good | % of Workforce Hired against Workforce Estimates | Forecast workforce requirements (No.) | 15300 | [10 empty] | Availability of smart city goals and set of KPIs (%) | 0.05 | [32 empty] | Partially Applied | Satisfactory | Was design for Enabling Work Package considerd as part of the design process to ensure the readiness of the site for the main construction work? |  |  | Partially Applied | Assessment of enabling works required
Qiddiya | Extra Cost due to Unresolved Issues | Not Available | [12 empty] | Based on the risks identified and approved change requests, has the DevCo conducted a sensitivity assessment on the forecast completion at a given data date? | Yes, but inadequate |  |  | Satisfactory |  | Identified risks with probability and impact ratings and Historical Project Performance (SPI, past variances, Productivity Trends) | Yes, but inadequate | Anticipated Variations | [15 empty] | Contract clauses (Text) | [33 empty] | Actual workforce employed (No.) | 14400 | [10 empty] | Availability of smart city cost-benefit analysis (%) | 0.08 | [32 empty] | Yes | Good | Are documentation packages meeting the LOD requirements of the latest Design Stage Gate? |  |  | 350 | LOD Required
Qiddiya | Top 10 Risks (Risk, Source, Potential Impact, Risk Rating, RIsk Status, Current Measures) (Text) | [13 empty] | Has DevCo allocated risk contingency for the identified risks? | Yes, but inadequate | Risk Performance | 0.55 | Satisfactory |  | Risk severity and Risk mapping | Yes, but inadequate | Budget Performance (Year, Budget Value Baseline, Budget Value Revised, Budget Value Forecast) (No.) | [15 empty] | Procurement Management Plan (Text) | [25 empty] | Does the DevCo have an active governance role in assessing Labor Camp capacity to meet worforce demand? | <quarterly |  |  |  |  | Good | Does the DevCo have an active governance role in assessing Labor Camp capacity to meet worforce demand? | Contractors Worker Camp Policy (Text) | <quarterly | [10 empty] | Implementation Roadmap for selected smart city initiatives (%) | 0.05 | [37 empty] | 350 | LOD Documented (drawing sample from Design Report)
Qiddiya | Top 5 Risk Categories (RIsk Category, Number of RIsk Items) (Text) | [13 empty] | Was there any deferment in the project completion date due to unidentified risks? | Data Not Available |  |  | Needs Improvement |  | Source of the unidentified risk | Data Not Available | [16 empty] | Scope / design maturity (Text) | [25 empty] | % of Material Supply Capacity against Material Demand Estimates | 0.87333 |  |  |  |  | Good | % of Material Supply Capacity against Material Demand Estimates | Forecast number of batching / crushing plants/ precast yards, etc. (No.) | 45000 | [10 empty] | Process for smart city implementation (%) | 0.08 | [32 empty] | Yes | Good | Have all projects adopted digital delivery using BIM and/or GIS? |  |  | Yes | Projects adopting digital delivery using BIM/GIS (Text)
Qiddiya | [14 empty] | Was there any Cost Overrun because of identified risk? | Yes, but less than 5% |  |  | Satisfactory |  | % of cost overrun from the latest approved budget due to identified risk | Yes, but less than 5% | [16 empty] | Tender pack quality (Text) | [33 empty] | Actual number of batching / crushing plants/ precast yards, etc. (No.) | 39300 | [10 empty] | Budget of implementation (%) | 0.05 | [30 empty] | Design Management Maturity | 0.69 | No | Needs Improvement | Is project delivery occurring in accordance with the latest approved design strategy? | Design Management | 0.69 | No | Approved Design Strategy (Text)
Qiddiya | [14 empty] | Was there any Cost Overrun because of unidentified risk? | Data Not Available |  |  | Needs Improvement |  | % of cost overrun from the latest approved budget due to unidentified risk | Data Not Available | [16 empty] | % payment paid within contractual terms (%) | [25 empty] | Average Technical Submittal closeout Cycle Time (No.) | 20 | Quality | 0.89 | Adherence to Design | 0.96 | Satisfactory | Average Technical Submittal closeout Cycle Time | Average Technical Submittal closeout Cycle Time (No.) | 20 |  |  | Is there an impact assessment report or identified process/ guidelines to evaluate the impact of the innovation / smart city technologies adoption on DevCo performance? | 0.25 | Needs Improvement |  |  |  |  | Is there an impact assessment report or identified process/ guidelines to evaluate the impact of the innovation / smart city technologies adoption on DevCo performance? | Availability of approach / process and guidelines to evaluate the impact of implementing innovations and technologies (%) | 0.15 | [32 empty] | 0.8 | Good | % of projects with completed technical design/peer reviews and verifications/certifications as required for the latest Design Stage Gate |  |  | 0.8 | % of projects with completed design reviews and verification register (%)
Qiddiya | [14 empty] | Risk Control Rate of the identified risks at DevCo Level | 1 |  |  | Good |  | Number of controlled risks | 123 | [16 empty] | Procurement Packages (SN, Parameter, Baseline, Actual, Forecast) (No.) | [25 empty] | % of approved shop drawing reviews vs planned | 0.94648 |  |  |  |  | Good | % of approved shop drawing reviews vs planned | Total number of shop drawing review requests (No.) | 14760 | [10 empty] | Availability of sample of impact assessment report (%) | 0 | [32 empty] | Yes | Good | Availability of robust design management plan and appropriate design review trackers/registers |  |  | Yes | Design Management Plan and Design Review Trackers/Registers (Text)
Qiddiya | [20 empty] | Total number of identified risks | 123 | [16 empty] | Number of Notifiable Incidents (No.) | [33 empty] | Total number of shop drawing reviews approved (No.) | 13970 | [10 empty] | Availability of action plan (%) | 0.1 | [32 empty] | Partially Applied | Satisfactory | Is the average cycle time to complete reviews and certifications in accordance with the Design Management Report? |  |  | Partially Applied | Days taken to complete Design Reviews
Qiddiya | [14 empty] | Is the DevCo fully compliant with Risk Management Plan requirements? | Yes, but inadequate |  |  | Satisfactory |  | Risk Manager or Risk Committee overseeing risk governance | Yes, but inadequate | [16 empty] | Number of Infringement Notices (No.) | [25 empty] | % of approved product waivers vs product specified | 0.98286 |  |  |  |  | Good | % of approved product waivers vs product specified | Total number of product sample & material approvals requested (No.) | 1342 | [10 empty] | Use of innovative tools/platforms/dashboards (%) | 0 | [32 empty] | No | Needs Improvement | Has the DevCo engaged independent certification of major critical elements? |  |  | No | Level of review and verification required for Stage Gate
Qiddiya | [14 empty] | Is there a difference in the time impact forecast before and after the risk event has triggered? | Data Not Available |  |  | Needs Improvement |  | Difference between anticipated and actual effects on time and cost, after the risk event triggered | Data Not Available | [16 empty] | Incident Management (SN, Incident Category, Number of Incidents, Number of Investigations in Progress, Number of Investigations Completed, Number of Investigations Pending Approval) (No.) | [33 empty] | Total number of product sample & materials approved (No.) | 1319 |  |  | Is there evidence for innovation / smart city technologies successful implementation (in final design report, master plan or other)? | 0.446 | Needs Improvement |  |  |  |  | Is there evidence for innovation / smart city technologies successful implementation (in final design report, master plan or other)? | Innovation Adoption Effectiveness Index (strategy & leadership alignment) (%) | 0 | [30 empty] | Environmental Compliance Status | 0.83 | Yes | Good | Are the master DevCo designs integrated with Regional Infrastructure & Mobility Plans? | Regulatory Compliance | 0.84 | Yes | Regional Strategies
Qiddiya | [14 empty] | Is there a difference in the Cost impact forecast before and after the risk event has triggered? | Data Not Available |  |  | Needs Improvement |  | Reasons on the difference between anticipated and actual effects on time and cost | Data Not Available | [16 empty] | Total Site Manhours (No.) | [25 empty] | % of Certified As-Built Drawing Packages vs Planned | 0.99959 |  |  |  |  | Good | % of Certified As-Built Drawing Packages vs Planned | Number of As-Built Drawing review requests (No.) | 4827 | [10 empty] | Innovation Adoption Effectiveness Index (skilled human resources) (%) | 0 | [32 empty] | Partially Applied | Satisfactory | Do all projects comply with environmental guidelines in accordance with ESIA? |  |  | Partially Applied | Extent of compliance to environmental guidelines
Qiddiya | [38 empty] | Compliant Management - Audits/Inspections (Audit/Inspections, InProgress_audits, Completed_audits, Remaining Planned) | [33 empty] | Number of As-Built Drawings reviews approved (No.) | 4825 | [10 empty] | Innovation Adoption Effectiveness Index (planning & governance) (%) | 0.04 | [30 empty] | Authority Compliance Status | 0.86 | 0.1 | Satisfactory | % of projects with Code Compliance Violations |  |  | 0.1 | % of Code Compliance Violations (%)
Qiddiya | [38 empty] | Compliance Management - Actions (Action, InProgress_actions, Completed_actions, Pending Approval) (Text) | [25 empty] | MIR Inspection Rate | 0.98986 |  |  |  |  | Good | MIR Inspection Rate | Total number of MIRs requested (No.) | 296 | [10 empty] | Innovation Adoption Effectiveness Index (process management) (%) | 0.04 | [32 empty] | Yes | Good | Availability of proper Register of Authority Engagement, Approvals and Waivers |  |  | Yes | Register of Authority Engagement, Approvals and Waivers (Text)
Qiddiya | [38 empty] | Incident Management (Incident Category, Number of Incidents, Number of Investigations in Progress, Number of Investigations Completed, Number of Investigations Pending Approval) (No.) | [33 empty] | Total number of MIRs inspected (No.) | 293 | [10 empty] | Innovation Adoption Effectiveness Index (partnerships and collaboration) (%) | 0.083 | [32 empty] | Partially Applied | Satisfactory | Have all required Stakeholder Submittals been issued as planned? |  |  | Partially Applied | Stakeholder Submittal Date
Qiddiya | [38 empty] | Safety Trainings (Year, Value_training) | [25 empty] | MIR Acceptance and Approval Rate | 0.97973 |  |  |  |  | Good | MIR Acceptance and Approval Rate | Total number of MIRs approved (No.) | 290 | [10 empty] | Innovation Adoption Effectiveness Index (resource management) (%) | 0.06 | [32 empty] | Yes | Good | Availability of robust Stakeholder Management Plan in place |  |  | Yes | Stakeholder Management Plan (Text)
Qiddiya | [64 empty] | WIR Inspection Rate | 0.91805 |  |  |  |  | Good | WIR Inspection Rate | Total number of WIRs requested (No.) | 5430 | [10 empty] | Smart City Adoption Effectiveness Index (strategy & leadership alignment) (%) | 0.083 | [32 empty] | Yes | Good | Does the Stakeholder Engagement Plan include proactive communication process to ensure timely coordination and approvals? |  |  | Yes | Scheduled Design Stage Gate Completion
Qiddiya | [72 empty] | Total number of WIRs inspected (No.) | 4985 | [10 empty] | Smart City Adoption Effectiveness Index (infrastructure readiness) (%) | 0.02 | [32 empty] | Partially Applied | Satisfactory | Availability of proper tracking and closure procedure for stakeholder comments |  |  | Partially Applied | Stakeholder Comments Tracking and Closure Procedure (Text)
Qiddiya | [64 empty] | WIR Acceptance and Approval Rate | 0.85009 |  |  |  |  | Good | WIR Acceptance and Approval Rate | Total number of WIRs approved (No.) | 4616 | [10 empty] | Smart City Adoption Effectiveness Index (planning & governance) (%) | 0.06 | [30 empty] | DevCo ESG Target Achievement | 0.33 | Data Not Available | Needs Improvement | % of projects achieving DevCo ESG Targets | ESG Target Realization | 0.46 | Data Not Available | Planned ESG Target
Qiddiya | [64 empty] | Does the frequency of Audits align with the QMP? | Data Not Available |  |  | Quality Assurance / Quality Control (QA/QC) | 0.73 | Needs Improvement | Does the frequency of Audits align with the QMP? | Required Audit frequency (Text) | [11 empty] | Smart City Adoption Effectiveness Index (stakeholder alignment) (%) | 0.02 | [37 empty] | Data Not Available | Actual ESG Target
Qiddiya | [64 empty] | Has the DevCo verified the Contractor's ISO Certification and Audit schedule is upto date? | Yes |  |  |  |  | Good | Has the DevCo verified the Contractor's ISO Certification | Copy of Contractor's ISO certification or most recent ISO Audit (Text) | Yes | [10 empty] | Smart City Adoption Effectiveness Index (realized benefits & performance) (%) | 0.04 | [30 empty] | Global ESG Target Alignment | 1 | Yes | Good | Does the DevCo ESG Target align with globally recognized Best Practice Targets? |  |  | Yes | Alignment with globally recognized Best Practice Targets
Qiddiya | [64 empty] | % closure of Non-Conformance Reports (NCR) | 0.9375 |  |  |  |  | Good | % closure of Non-Conformance Reports (NCR) | Total number of defects & NCRs (No.) | 96 |  |  | Are there Pilot or R&D projects conducted? | 0.4 | Needs Improvement | 0.33 | Pilot and R&D Transition Rate |  |  | Are there Pilot or R&D projects conducted? | Availability of innovation/smart city piloting or R&D procedures (%) | 0.05
Qiddiya | [72 empty] | Total number of closed defects & NCRs (No.) | 90 | [10 empty] | List of focus areas (%) | 0.3
Qiddiya | [64 empty] | Average NCRs closeout Cycle Time | 105 |  |  |  |  | Needs Improvement | Average NCRs closeout Cycle Time | Average time to close NCRs (No.) | 105 | [10 empty] | Procedure (%) | 0.05
Qiddiya | [64 empty] | Does the DevCo have an active Procurement Management Plan/Policy? | Partially Applied | Procurement | 0.54 | Procurement & Contracting Compliance | 0.59 | Satisfactory | Does the DevCo have an active Procurement Management Plan/Policy? | Procurement Approach (Text) | Partially Applied | [10 empty] | Robustness of assessment of pilot and R&D outcomes (%) | 0
Qiddiya | [72 empty] | Date of latest approved Procurement Plan (Text) |  |  |  | % of pilot / R&D Projects Transitioned into Full-Scale | 0.2 | Needs Improvement |  |  |  |  | % of pilot / R&D Projects Transitioned into Full-Scale | Number of pilot projects (No.) | 15
Qiddiya | [64 empty] | Average no. days for claims to be closed out | 100 |  |  |  |  | Needs Improvement | Average no. days for claims to be closed out | Claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures (No.) | 100 | [10 empty] | Number of R&D projects (No.) | 0
Qiddiya | [64 empty] | Is the DevCo actively conducting tender award assessments and it is well documented? | Partially Applied |  |  |  |  | Satisfactory | Is the DevCo actively conducting tender award assessments and it is well documented? | Tender award assessment documentation (Text) | Partially Applied | [10 empty] | Number of pilot projects that are scaled successfully (No.) | 3
Qiddiya | [64 empty] | Is the DevCo undertaking due diligence of the vendors appointed? | Partially Applied |  |  |  |  | Satisfactory | Is the DevCo undertaking due diligence of the vendors appointed? | Due diligence tender evaluation documents (Text) | Partially Applied | [10 empty] | Number of R&D projects that are successfully piloted or fully-scaled (No.) | 0
Qiddiya | [64 empty] | Did the DevCo complete a Supply Chain Risk-Market Intelligence Assessment in the last quarter? | Partially Applied |  |  |  |  | Satisfactory | Did the DevCo complete a Supply Chain Risk-Market Intelligence Assessment in the last quarter? | Supply Chain Risk-Market Intelligence Assessment (Text) | Partially Applied |  |  | Availability of Innovation unit / department with structured team | 0 | Needs Improvement | 0.33 | Organization Maturity Towards Innovation Adoption |  |  | Availability of Innovation unit / department with structured team | Availability of Innovation unit/department (%) | 0
Qiddiya | [64 empty] | % of procurement activities executed as planned in the Annual Procurement Plan | 0.29167 |  |  | Procurement & Contracting Execution Performance | 0.52 | Satisfactory | % of procurement activities executed as planned in the Annual Procurement Plan | Total number of procurement activities (No.) | 48 | [10 empty] | Key positions planned in the innovation unit/department (%) | 0
Qiddiya | [72 empty] | Number of procurement activities executed as planned (No.) | 14 | [10 empty] | Innovation unit/department within the company hierachy (%) | 0
Qiddiya | [64 empty] | % of deviations in total awarded contract value with approved TDC | 1 |  |  |  |  | Needs Improvement | % of deviations in total awarded contract value with approved TDC | Value of Awarded Contract (No.) | 50.15 | [10 empty] | Qualifications of the innovation team (%) | 0
Qiddiya | [72 empty] | Tender Cost Estimate (No.) |  |  |  | Availability of Innovation and Technology Strategy / Process & Framework | 0.2 | Needs Improvement |  |  |  |  | Availability of Innovation and Technology Strategy / Process & Framework | Innovation Unit Strategy / Process & Framework (%) | 0.1
Qiddiya | [64 empty] | % of contracts with pending claims | 0.325 |  |  |  |  | Satisfactory | % of contracts with pending claims | % of contracts with filed claims (%) | 0.325 | [10 empty] | Implementation of innovation department process / framework (%) | 0.1
Qiddiya | [64 empty] | % of Payment Certificates and payments being processed within the contractual payment terms? | 0.987 |  |  |  |  | Needs Improvement | % of Payment Certificates and payments being processed within the contractual payment terms? | % payment paid within contractual terms (%) | 0.987
Qiddiya | [64 empty] | Are Vendor performance assessment occurring which capture financial instability, delays, repeated quality issues in real-time? | Partially Applied |  |  |  |  | Satisfactory | Are Vendor performance assessment occurring which capture financial instability, delays, repeated quality issues in real-time? | Alignment of sourcing strategies with project schedules and requirements (Text) | Partially Applied
Qiddiya | [64 empty] | Does the HSE Management Manual have adequate provision for identification and escalation of high risk activities? | Yes | HSE and Welfare | 0.8 | HSE Compliance | 0.78 | Good | Does the HSE Management Manual have adequate provision for identification and escalation of high risk activities? | Escalation criteria for high risk activities (Text) | Yes
Qiddiya | [64 empty] | Has the DevCo provided a NCR Safety Register? | No |  |  |  |  | Needs Improvement | Has the DevCo provided a NCR Safety Register? | NCR safety register (Text) | No
Qiddiya | [64 empty] | Is the rate of review of the Safety Risk Register in accordance with the HSE Management Manual? | Yes |  |  |  |  | Good | Is the rate of review of the Safety Risk Register in accordance with the HSE Management Manual? | HSE Risk Register Review Rate (Text) | Yes
Qiddiya | [64 empty] | % of closed Safety Risk items | 0.92809 |  |  |  |  | Good | % of closed Safety Risk items | Total number of Safety Risk items (No.) | 2823
Qiddiya | [72 empty] | Total number of closed Safety Risk items (No.) | 2620
Qiddiya | [64 empty] | Average cycle time to close Safety Risk items | 30 |  |  |  |  | Needs Improvement | Average cycle time to close Safety Risk items | Cycle time to close Safety Risk items (in days) (No.) | 30
Qiddiya | [64 empty] | Has the DevCo provided a a Safety Incident Register? | No |  |  |  |  | Needs Improvement | Has the DevCo provided a a Safety Incident Register? | Safety incident register (Text) | No
Qiddiya | [64 empty] | Average cycle time to close Safety Incident | 30 |  |  |  |  | Needs Improvement | Average cycle time to close Safety Incident | Cycle time to close Safety Incident (in days) (No.) | 30
Qiddiya | [64 empty] | Is the emergency drill rate compliant with EEPP? | Yes |  |  |  |  | Good | Is the emergency drill rate compliant with EEPP? | Planned number of Emergency Drills (No.) | 5
Qiddiya | [72 empty] | Actual number of Emergency Drills (No.) | 11
Qiddiya | [72 empty] | Recommended time to complete Emergency drills (No.) | Data Not Available
Qiddiya | [72 empty] | Actual Time to complete Emergency drills (No.) | Data Not Available
Qiddiya | [64 empty] | Fatality Rate (FR) | 0 |  |  |  |  | Good | Fatality Rate (FR) | No. of incidents resulting in fatality or severe impairment per 200,000 work hours (No.) | 0
Qiddiya | [64 empty] | Lost Time Injury Frequency Rate (LTIFR) | 0 |  |  |  |  | Good | Lost Time Injury Frequency Rate (LTIFR) | No. of incidents resulting in lost time per 200,000 work hours (No.) | 0
Qiddiya | [64 empty] | Total Recordable Incident Rate (TRIR) | 0 |  |  |  |  | Good | Total Recordable Incident Rate (TRIR) | No. of recordable incidents per 200,000 work hours (No.) | 0
Qiddiya | [64 empty] | Near Miss Rate | 0.73 |  |  |  |  | Satisfactory | Near Miss Rate | No. of near misses recorded per 200,000 work hours (No.) | 0.73
Qiddiya | [64 empty] | Safety Observation Rate | 346 |  |  |  |  | Good | Safety Observation Rate | No. of safety observation recorded per 200,000 work hours (No.) | 346
Qiddiya | [64 empty] | Is there evidence of Leadership Safety Walks occuring? | Data Not Available |  |  |  |  | Needs Improvement | Is there evidence of Leadership Safety Walks occuring? | Total number of Safety Walks with Leadership (No.) | Yes
Qiddiya | [64 empty] | Is the DevCo tracking & monitoring Grievances? | Yes |  |  | Welfare Compliance | 0.83 | Good | Is the DevCo tracking & monitoring Grievances? | Total number of grievances (No.) | Yes
Qiddiya | [64 empty] | Has the DevCo demonstrated active management in closing out Grievances? | Yes |  |  |  |  | Good | Has the DevCo demonstrated active management in closing out Grievances? | Cycle time to close grievances (No.) | No
Qiddiya | [64 empty] | Does the DevCo set targets and monitor the minimum number of HSE & Welfare staff vs the total workforce? | Yes |  |  |  |  | Good | Does the DevCo set targets and monitor the minimum number of HSE & Welfare staff vs the total workforce? | DevCo staffing register (Text) | No
Qiddiya | [64 empty] | Does the DevCo track and monitor closeout of welfare observations? | Yes |  |  |  |  | Good | Does the DevCo track and monitor closeout of welfare observations? | Total number of Closed Welfare Observations (No.) | Yes
Qiddiya | [64 empty] | Has the DevCo demonstrated closeout of Welfare Non-compliances is occuring? | Yes |  |  |  |  | Good | Has the DevCo demonstrated closeout of Welfare Non-compliances is occuring? | Total Closed Welfare Non-compliances (No.) | No
Qiddiya | [64 empty] | Is frequency of Labor Accommodation Inspection occurring in accordance with VMMP? | No |  |  |  |  | Needs Improvement | Is frequency of Labor Accommodation Inspection occurring in accordance with VMMP? | Mitigation measures in the event of welfare audit observations & recommendations (Text) | No

## Glossary
SN | Section | Term | Description
1 | Cost Estimation & Optimization | Actual Cost (AC) | Actual Cost is the total cost incurred for work completed on a project at a given point in time. It includes all direct and indirect costs spent on labor, materials, equipment, and other expenses.
2 | Cost Estimation & Optimization | Aggregated Budget Variance | Cumulative difference between total budgeted figures and actual results across multiple categories or projects, highlighting overall financial performance deviations within a specific period
3 | Planning & Monitoring | Aggregated SPI | Indication of overall schedule performance at DevCo level
4 | Development & Construction | Annual Procurement Plan / Strategy | The Procurement Plan is required to be reviewed and updated by the DevCo as a minimum annually and submitted to PIF for approval in accordance with the requirements of the Project Execution Plan.
5 | General | Authority | Each development stage requires approval. The Authority is the relevant party responsible for the approval at the relevant stage (e.g. CEO, Founding Board etc.)
6 | Design & Technical | BUA | Built Up Area (BUA) is the total area being developed or constructed. It is the Gross Floor Area (GFA) plus Parking plus any Service Area.
7 | Cost Estimation & Optimization | Budget Variance (BV) | Extent of variance in budget
8 | Cost Estimation & Optimization | Budget At Completion (BAC) | The Budget at Completion (BAC) represents the total budgeted cost for all the work planned for a project
9 | Cost Estimation & Optimization | Estimate To Complete (ETC) | The estimated cost required to complete the remaining work of a project
10 | Cost Estimation & Optimization | Estimate At Completion (EAC) | Total forecasted cost of the project based on the ongoing
11 | General | Business Plan | Documentation developed by PIF informing the Vision and key objectives of the project
12 | General | Change Management Log | A document summarising the status of all proposed and approved Variations
13 | General | Change Management Procedure | Procedural document stipulating the requirements to be met when administering any amendment to a Contract or Project.
14 | Cost Estimate & Optimization | Contingency Utilization Rate (CUR) | Percentage of a project’s allocated contingency fund that has been used to address unforeseen costs or risks, reflecting the efficiency of contingency planning and management.
15 | Development & Construction | Contract Management Policy | A policy outlining award and management of contracts between DevCo and Vendors.
16 | Cost Estimate & Optimization | Cost Estimate and Optimization (CE&O) | Technical function which covers cost benchmarks for development of budgets, and cost optimization levers
17 | Cost Estimate & Optimization | Cost Report | A document provided on an interim basis to inform of the current financial status of a Project
18 | Design & Technical | Design and Technical (D&T) | Technical Function which covers all design-related topics of a project including architecture, engineering, masterplanning, infrastructure and environment & sustainability
19 | Development & Construction | Development and Construction (D&C) | Technical function which covers construction project execution plans, contract management and procurement, and construction quality and Health, Safety and Environment (HSE) topics
20 | Planning & Monitoring | Earned Value (EV) | Value of the work that is completed at a given time, measured against the budgeted cost.
21 | Planning & Monitoring | Extension of Time (EOT) | Extension of Time is a contractual provision in construction allowing the project completion date to be extended due to unforeseen delays beyond the contractor’s control, ensuring fairness and mitigating penalties.
22 | Design & Technical | Gross Floor Area (GFA) | Gross Floor Area (GFA) is the total floor area of a building including any underground saleable or leasable area but excluding parking and underground technical/service areas. The GFA is calculated based on the distance from external wall to external wall.
23 | Innovation & Technology | Innovation and Technology (I&T) | Technical function which covers incorporation of high-impact advanced technologies and methodologies across the entire project life cycle, and implementation of smart city use cases.
24 | Development & Construction | Inspection Test Plan (ITP) | A document which specifies the manatory Inspection, Witness and Hold Points throughout construction that must be verified by a suitably qualified person before works are authorised to proceed.
25 | General | Key Performance Indicator (KPI) | Key quantifiable indicators of progress toward an intended result
26 | Development & Construction | Non-Conformance Report (NCR) | Non-Conformance Report is a quality management document that identifies, tracks, and records deviations from specified standards, facilitating process improvement and quality control.
27 | Cost Estimate & Optimization | Planned Budget (PB) | It represents how much is expected to be spent at a given point in time from the Approved Over All Budget (BAC)
28 | Planning & Monitoring | Planned Value (PV) | The amount of work that was planned to be completed at a given time as per the approved Schedule.
29 | Planning & Monitoring | Planning and Monitoring (P&M) | Technical Function which covers schedule development and monitoring, and risk management
30 | Development & Construction | Procurement Strategy | Methodical approach for determining the contractural relationship and agreements between DevCo and Vendors
31 | Development & Construction | Procurement Procedures Manual | A manual which details every aspect of the tendering and overall procurement activities.
32 | Development & Construction | Project Execution Plan (PEP) | Project Execution Plan prepared initially by PIF as part of the Business Plan Stage, which is then passed to the DevCo to lead, review and update from Masterplan Stage onwards
33 | Development & Construction | Request For Information (RFI) | A formal communication tool for requesing information
34 | Development & Construction | Rework Cost | Indication of the rework done due to quality, design etc issues
35 | Planning & Monitoring | Schedule Performance Index (SPI) | Indication of project schedule performance
36 | Cost Estimate & Optimization | Soft Cost | Soft costs are indirect, non-physical expenses in a construction project that are not directly tied to labor, materials, or physical construction work.
37 | General | Stage | The description of the Project Stage as per Development Company and PIF terminology.
38 | Strategy & Operations | Strategy & Organization | Technical Function which covers topics around strategy development and execution, people and tools.
39 | Design & Technical | Value Engineering | Process to derive greater value within a Project seeking improvement in time and/ or cost outcomes
40 | Development & Construction | Vendor Database | A database of Vendors, including pre-qualified Vendors, Vendor appraisal and performance assessment and a list of blacklisted Vendors.
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## OrgChart
DevCo | EmployeeID | Group | Label | ManagerID | Sub-Label

## ScheduleMatrix
DevCo | CostOverrun | Criticality | DelayInSchedule | ForecastCompletionYear | Priority | ProjectID | ProjectStage | ProjectType | ProjectValue
Diriyah | No | Priority | Yes | Completed | Yes | Project A | Design | Residential | 1.5
Diriyah | Yes | Standard | No | 2027 | No | Project B | Construction | Commercial | 1
Diriyah | No | Priority | No | Completed | No | Project C | Initiation | Mixed Use | 2
Diriyah | Yes | Standard | Yes | 2030 | Yes | Project D | Construction | Residential | 1.5
Diriyah | No | Priority | No | 2028 | No | Project E | Design | Hospitality | 3
Qiddiya | No | Priority | Yes | Completed | Yes | Project A | Design | Residential | 1.5
Qiddiya | Yes | Standard | No | 2027 | No | Project B | Construction | Commercial | 1
Qiddiya | No | Priority | No | Completed | No | Project C | Initiation | Mixed Use | 2
Qiddiya | Yes | Standard | Yes | 2030 | Yes | Project D | Construction | Residential | 1.5
Qiddiya | No | Priority | No | 2028 | No | Project E | Design | Hospitality | 3

## AssessmentSummary
DevCo | Remarks | ReportingPeriod