## Sheet1
DevCo | Additional Data Point | Value | Year | Value Completed (Baseline) in M SAR | Value Completed (Actual) in M SAR | Value Completed (Forecast) in M SAR | Risk Category | Number of Risk Items | Risk | Source | Potential Impact | Risk Rating | Risk Status | Current Measures | Assessment Criteria | Value | Key Topic | Key Topic Score | Rating | Remarks 3 | Additional Data Point | Value | Year | Budget Value (Baseline) in M SAR | Budget Value (Revised) in M SAR | Budget Value (Forecast) in M SAR | Assessment Criteria | Value | Rating | Remarks 3 | Key Topic | Key Topic Score | Data Point | Input Value | Number of Quality Audits | Month | Additional Data Point | Value | Parameter | Baseline | Actual | Forecast | Incident Category | Number of Incidents (To-Date) | Number of Investigations in Progress | Number of Investigations Completed | Number of Investigations Pending Approval | Audits/Inspections | In Progress_audits | Completed_audits | Remaining Planned | Actions | In Progress_actions | Completed_actions | Pending Approval | Year | Value_training | Program | Acquired (Ha) | Under Negotiation (Ha) | Pending (Ha) | Assessment Criteria | Value | Key Topic | Key Topic Score | Performance Signal | Performance Signal Score | Rating | Assessment Criteria | Data Point | Input Value | Additional Data Point | Value | Assessment Criteria | Value | Rating | Performance Signal Score | Performance Signal | Key Topic | Key Topic Score | Weightage | Name of the KPI | Additional Data Point | Value | Name of the Policy | Criticality Policies (Y/N) | Availability Policies (Y/N) | Name of the Technical Platform | Criticality Technical (Y/N) | Availability Technical (Y/N) | EmployeeID | ManagerID | Label | Group | Sub-Label | Rating | Assessment Criteria | Value | Key Topic | Key Topic Score | Score | Performance Signal | Performance Signal Score | Assessment Criteria | Data Point | Input Value | Remarks 3 | Performance Signal | Performance Signal Score | Value | Rating | Assessment Criteria | Key Topic | Key Topic Score | Input Value | Data Point | Remarks
Diriyah | Latest Approved Completion Date​ | Q2-28 | 2025 | 0 |  |  | Risk 1 | 19 | Risk 1 | Contractor | Cost | High | Open | Measure 02 | DevCo Schedule Performance Index (SPI) | 0.9 | Overall Progress | 2.1 | Satisfactory | Key milestones are on track, with some delivered ahead of schedule. There are delays expected of ongoing projects due to complexities related to infrastructure | Estimate to Completion Declared by DevCo | 3200000000 | 2023 | 400 | 400 | 400 | Budget Variance | 0.10714 | Satisfactory | Significant increase in budget due to inadequate contingency planning | Overall Budget | 1.68 | PIF Approved Capex budget (Initial Business Plan) | 2800000000 | 2 | Jan | No. of Site Access Required | 180 | Count | 186 | 129 | 50 | Fatalities | 0 | 0 | 0 | 0 | HSE Audit | 3 | 5 | 4 | HSE | 6 | 22 | 12 | Jan | 30 | Program 1 | 50 | 25 | 5 | % of CESMP mitigation measures which align with ESIA* | 0.5 | Construction | 2.51 | Construction Planning Maturity | 2.3 | Needs Improvement | % of CESMP mitigation measures which align with ESIA* | Environmental mitigation measures included in CESMP | 10 | Implementation Success Rate for Innovation Strategy | 50 | Is there an innovation Strategy or document that lists the key focus areas and initiatives across design, construction and operation and aligned with DevCo strategic plan? | 0.4 | Needs Improvement | 1.7 | Innovation & Technology Deployment | Innovation and Technology Adoption | 1.43 | 20 | KPI 1 | Strategy Planning and Review | 3 | Design Stage Gate Approval Procedures | Y | N | Cost Management Platform | Y | N | 1 |  | Chief Development Officer | Filled | CDO | Satisfactory | Availability of Technical Function Strategy | Yes, but very brief | Technical Strategy and Enablers | 2.57 | 2 | Technical Strategy Achievement | 2.3 | Availability of Technical Function Strategy | Availability of strategy | Yes, but very brief | DevCo has maintained adherence to the Vision, with a few outstanding variance approvals pending. The DevCo has demonstrated poor consideration for construction methodology simplification during the design phase, however, is demonstrating effective use of BIM software for interdisciplinary coordination across most projects. | CGI and Animation Compliance | 2.4 | 0.4 | Needs Improvement | Similarity between Original/Approved and Latest CGI and Animation | Vision Adherence | 2.7 | 0.2 | Percentage similarity between Approved CGI and Latest CGI at same angle and scale | DevCo performance is generally good. While overall progress is delayed by 12 months, these are largely due to unforeseen circumstances and DevCo has shown ability to recover some of the delays. The lack of a smart city strategy and DevCo-level ESG targets and irregular adherence to procurement control processes are key areas for improvement.
Diriyah | Forecast Completion Date​ | Q1-29 | 2026 | 1250 | 1250 |  | Risk 2 | 16 | Risk 2 | Source A | Impact O | Med | Ongoing | Measure 01 | [6 empty] | Total Expenditure to Date | 100000000 | 2024 | 1000 | 1200 | 1200 | [6 empty] | Forecast budget (EAC) | 3100000000 | 5 | Feb | No. of Site Access Provided | 120 | Value | 16100 | 9600 | 6800 | Severe Impairment | 1 | 0 | 1 | 0 | Welfare Inspection | 2 | 4 | 4 | Welfare | 25 | 10 | 7 | Feb | 40 | Program 2 | 230 | 40 | 30 | [8 empty] | Environmental mitigation measures recommended in ESIA | 20 | Innovation Adoption Effectiveness Index (strategy & leadership alignment) | 1 | [7 empty] | 20 | KPI 2 | Explicit Mapping against Organization Strategy | 3 | [6 empty] | 2 | 1 | Head | Filled | Development | Good | Alignment of Technical Strategy with Organizational Strategy | Well-aligned |  |  | 3 |  |  | Alignment of Technical Strategy with Organizational Strategy | Alignment of technical functions' strategy and initiatives with the overarching organizational strategy | Well-aligned | [8 empty] | 0.6 | Percentage similarity between Approved Animation and Latest Animation at same camera angle
Diriyah | Approved baseline completion date | Q3-27 | 2027 | 2000 | 1550 | 1550 | Risk 3 | 12 | Risk 3 | Source B | Impact P | High | Open | Measure 04 | % milestone achievement in accordance with the approved business plan | 0.7 |  |  | Satisfactory |  | Contingency budgeted at DevCo level | 20000000 | 2025 | 1500 | 1800 | 1800 | % of projects having Budget Variance | 0.75 | Needs Improvement |  |  |  | Number of Projects with Budget Variance | 15 | 3 | Mar | Packaging & Phasing Strategy | Good |  |  |  |  | Lost Time Incidents | 3 | 0 | 1 | 2 | [8 empty] | Mar | 38 | Program 3 | 10 | 80 | 10 | Has the Construction Execution Plan been updated to reflect the latest stage of construction? | Yes |  |  |  |  | Good | Has the Construction Execution Plan been updated to reflect the latest stage of construction? | Update of construction execution plan | Yes | Innovation Adoption Effectiveness Index (skilled human resources) | 3 | [7 empty] | 15 | KPI 3 | Benchmarking and Industry Standards | 3 | [6 empty] | 3 | 1 | Head | Filled | Projects | Satisfactory | Severity of Key Challenges Faced in Strategy Execution Technically | Moderate |  |  | 2 |  |  | Severity of Key Challenges Faced in Strategy Execution Technically | Key challenges in strategy execution | Moderate |  |  |  | Yes | Good | Does the Latest Material Palette & Finish Schedule support the look of the Approved CGI? |  |  | Yes | Material Palette & Finish Schedule
Diriyah | No. of schedule iterations | 8 | 2028 | 3100 |  | 2200 | Risk 4 | 7 | Risk 4 | Source F | Impact T | Med | Closed | Measure 05 | [6 empty] | Contingency utilized at DevCo level | 7500000 | 2026 | 2000 | 2200 | 2300 | [6 empty] | Total number of projects | 20 | 1 | Apr | Execution & Site Logistics | Satisfactory |  |  |  |  | Recordable Incidents | 14 | 3 | 11 | 0 | [8 empty] | Apr | 35 |  |  |  |  | Has the construction sequence and method statement been reviewed and approved? | No |  |  |  |  | Needs Improvement | Has the construction sequence and method statement been reviewed and approved? | Review and approval of Construction sequence & method statement | No | Innovation Adoption Effectiveness Index (planning & governance) | 2 | [7 empty] | 10 | KPI 4 | Performance Management | 3 | [6 empty] | 4 | 1 | Head | Filled | Masterplan | Satisfactory | Availability of Technical KPIs | Yes, but very brief |  |  | 2 | Technical KPI Achievement | 2.6 | Availability of Technical KPIs | Availability of KPIs | Yes, but very brief |  |  |  | Yes | Good | Does the DevCo have Design & Technical Guidelines (including Look & Feel Design Guidelines)? |  |  | Yes | Design and Technical Guidelines
Diriyah | Planned duration up to a specific phase as per approved Baseline programme | 120 | 2029 |  |  | 3100 | Risk 5 | 5 | Risk 5 | PMC | Reputation | Low | Ongoing | Measure 06 | % of projects with approved change requests in design phase since inception with time impact of more than 1 month | 0.22222 |  |  | Good |  | Contingency Utilization Rate |  | 2027 | 2500 | 2750 | 2900 | % of projects with contingency utilization rate > 1 | 0.25 | Satisfactory |  |  |  | Number of projects with contingency utilization > 1 | 5 | 0 | May | Procurement Strategy | Good |  |  |  |  | Near Misses | 26 | 2 | 21 | 3 | [8 empty] | May | 0 |  |  |  |  | Is total land acquisition sufficient to achieve the area required for construction site logistics? | No |  |  |  |  | Needs Improvement | Is total land acquisition sufficient to achieve the area required for construction site logistics? | Planned Area provision for site offices, amenities, laydown areas, storage facilities, workforce accommodations | Average | Innovation Adoption Effectiveness Index (process management) | 4 | [7 empty] | 10 | KPI 5 | Communication and Implementation | 2 | [6 empty] | 5 | 1 | HSE | Missing | HSE | Good | Progress of Achievement of KPIs for Technical Team | 0.8 |  |  | 3 |  |  | Progress of Achievement of KPIs for Technical Team | Total Number of KPIs set for the preceding year | 20 |  |  |  | No | Good | Do DevCo projects comply with DDTG? |  |  | No | Look & Feel Guideline
Diriyah | Duration taken to complete works up to the specific phase | 145 | [6 empty] | Risk 6 | Source C | Impact Q | Med | Open | Measure 07 | [6 empty] | Value of Changes in Design Stage | 200000 | 2028 | 2800 | 3100 | 3200 | % of projects with Approved Change Requests (design/construction) having a cost impact greater than 2% | 0.6 | Needs Improvement |  |  |  | No. of projects with approved change request having a cost impact greater than 2% | 12 | 0 | Jun | Required area for land acquisition | [18 empty] | Jun | 0 | [12 empty] | Actual Area provision for site offices, amenities, laydown areas, storage facilities, workforce accommodations | No | Innovation Adoption Effectiveness Index (partnerships and collaboration) | 2 | [7 empty] | 25 | Others | Clear and Documented Process | 2 | [6 empty] | 6 | 2 | Chief Devt | Filled | MP1 | [9 empty] | Number of KPIs achieved in the preceding year | 16 |  | Development Program Variance | 3 | 0.14286 | Good | % variance from approved Built-Up Area (BUA) |  |  | 16 | Latest BUA
Diriyah | Recovery Plan | Needs Improvement | [6 empty] | Risk 7 | Source D | Impact R | Low | Closed | Measure 08 | % of projects with approved change requests in construction phase since inception with time impact of more than 4 months | 0.54545 |  |  | Satisfactory |  | Value of Changes in Construction Stage | 5000000 |  |  |  |  | % of projects with Approved Claims | 0.5 | Needs Improvement |  |  |  | No. of projects with approved claims | 10 | 0 | Jul | Mitigation of Project Execution Plan implementation challenges | [18 empty] | Jul | 0 |  |  |  |  | Have Traffic Simulations been completed in preparing the Site & Logistics Plan? | Yes |  |  |  |  | Good | Have Traffic Simulations been completed in preparing the Site & Logistics Plan? | Completion of Traffic Simulations | Yes | Innovation Adoption Effectiveness Index (resource management) | 0.6 | [9 empty] | Technology Utilization | 3 | [6 empty] | 7 | 2 | Chief Devt | Filled | MP2 | Good | Appropriateness of KPIs for Technical Team | Aligned with industry benchmarks |  |  | 3 |  |  | Appropriateness of KPIs for Technical Team |  | Aligned with industry benchmarks | [8 empty] | 14 | Approved BUA
Diriyah | Extent of all EOT (design stage) | 3 | [6 empty] | Risk 8 | Supplier | Time | High | Closed | Measure 09 | [6 empty] | Number of Changes (Concept MP) | 0 |  |  |  |  | % of provisional sums of the latest PIF Approved Capex budget | 0.00068966 | Good |  |  |  | Total provisional sums | 2000000 | 0 | Aug | Occurred delays due to stakeholder objections | [18 empty] | Aug | 0 |  |  |  |  | Has the Project Execution Plan been updated and approved in the last 12 months? | Yes |  |  |  |  | Good | Has the Project Execution Plan been updated and approved in the last 12 months? | Date of latest approved Procurement Plan | 2025-03-25 | Implementation Success Rate for Smart City Strategy | 70 | [9 empty] | Risk Management and Technical Planning Deficiencies | Yes | [6 empty] | 8 | 2 | Chief Devt | Vacant | MP3 | Good | Criticality of Vacant/Missing Positions in Organization | Minor |  |  | 3 | Technical Organization | 3 | Criticality of Vacant/Missing Positions in Organization | Key positions which are missing, if any | Minor |  |  |  | 0.041667 | Good | % variance in land use permit area |  |  | 2.5 | Latest Land Area
Diriyah | Extent of all EOT (const. stage) | 6 | [6 empty] | Risk 9 | CAA | Impact M | High | Closed | Measure 10 | % of projects with approved schedule extension | 0.65 |  |  | Needs Improvement |  | Number of Changes (Detailed MP) | 3 | [10 empty] | Latest Approved budget | 2900000000 | 0 | Sep | Workforce Planning and Availability | Needs Improvement | [17 empty] | Sep | 0 |  |  |  |  | % of Stakeholder MOU** / LUPs*** not executed in accordance with critical lead time | 0.05 |  |  |  |  | Good | % of Stakeholder MOU** / LUPs*** not executed in accordance with critical lead time | Number of Stakeholder MOU or Land Use Permits not executed on time | 5 | Number of Smart City Use Cases | 10 | Is there a smart city Strategy or document that lists the key focus areas of smart city aligned with DevCo strategic plan? | 0.4 | Needs Improvement | [6 empty] | Technology Integration and Adaptation Challenges | Yes | [6 empty] | 9 | 3 | Project Lead | Vacant | MP1 | Good | Appropriateness of Qualifications in Recruitment of Vacant Technical Department Head Positions | Minor |  |  | 3 |  |  | Appropriateness of Qualifications in Recruitment of Vacant Technical Department Head Positions | Qualifications of job descriptions for vacant technical department head positions - are they appropriate? | Minor | [8 empty] | 2.4 | Approved Land Area
Diriyah | No. of unresolved issues | 7 | [6 empty] | Risk 10 | Source E | Impact S | Med | Ongoing | Measure 11 | [6 empty] | Number of Changes (Concept Design) | 2 |  |  |  |  | % of variance of Allocated Provisional sums against the awarded amount | 2.5 | Needs Improvement |  |  |  | Actual Utilized Provisional Sums | 800000 | 0 | Oct | Resource Planning and Availability | Good | [17 empty] | Oct | 0 | [12 empty] | Total Stakeholder MOU or Land Use Permits required | 100 | Smart City Adoption Effectiveness Index (strategy & leadership alignment) | 2 | [9 empty] | Data Management and Information Flow | Yes | [6 empty] | 10 | 3 | Project Lead | Filled | MP2 | Good | Robustness of Policy/Guideline/Procedure Communication | Strong |  |  | 3 | Technical Control Environment | 2.3 | Robustness of Policy/Guideline/Procedure Communication | List of policies/procedures communicated to all employees | Strong |  |  |  | 0.052632 | Good | % variance from approved population |  |  | 1000 | Latest Population
Diriyah | No. of (Open) Inherent Risks | 15 | [18 empty] | Number of Changes (Detailed Design) | 6 | [12 empty] | 0 | Nov | Workforce retention track record | [18 empty] | Nov | 0 |  |  |  |  | % of Workforce Hired against Workforce Estimates | 1.1 |  |  | Workforce Resource Availability | 3 | Good | % of Workforce Hired against Workforce Estimates | Forecast workforce requirements | 10000 | Smart City Adoption Effectiveness Index (infrastructure readiness) | 2 | [9 empty] | Supply Chain and Logistics | No | [6 empty] | 11 | 3 | Project Lead | Filled | MP3 | Satisfactory | Robustness of Policy/Guideline/Procedure Compliance Monitoring Framework | Moderate |  |  | 2 |  |  | Robustness of Policy/Guideline/Procedure Compliance Monitoring Framework | Monitoring of policies and procedures compliance | Moderate | [8 empty] | 950 | Approved Population
Diriyah | No. of (Closed) Residual Risks | 35 | [12 empty] | % of projects with Forecast completion date beyond the latest approved schedule | 0.23077 |  |  | Satisfactory |  | Number of Changes (Construction) | 8 | [12 empty] | 0 | Dec | Turnover rate track record | [18 empty] | Dec | 0 | [12 empty] | Actual workforce employed | 11000 | Smart City Adoption Effectiveness Index (planning & governance) | 3 | [9 empty] | Cross-Functional Coordination and Communication | Yes | [6 empty] | 12 | 3 | Lead | Missing | Stakeholder Interface | Satisfactory | Robustness of Board Reporting Framework | Moderate |  |  | 2 |  |  | Robustness of Board Reporting Framework | Frequency of reporting to Board and PIF | Moderate |  | Construction Design Maturity | 2.8 | 0.33333 | Satisfactory | % value of modularization compared to the total construction value | Design for Constructability | 2.8 | 0.01 | Value of Modularized Construction Cost
Diriyah | Project-level risks (including low, medium, and high severity) | 65 | [12 empty] | Is the Forecast Finish Date at a given data date based on the alignment and buy-in from project teams and other listed stakeholders? | Yes |  |  | Good |  | Total Awarded Cost | 15000000 | [14 empty] | Plant/equipment downtime track record | [24 empty] | % of Labor Camp Capacity against Workforce Estimates | 1 |  |  |  |  | Good | % of Labor Camp Capacity against Workforce Estimates | Forecast number of labor camps | 6 | Smart City Adoption Effectiveness Index (stakeholder alignment) | 1 | [9 empty] | Adaptability to Market Conditions | Yes | [30 empty] | 0.03 | Value of Total Construction Cost
Diriyah | Procedures for risk management | Satisfactory | [12 empty] | Based on the risks identified and approved change requests, has the DevCo conducted a sensitivity assessment on the forecast completion at a given data date? | Yes, but inadequate |  |  | Satisfactory |  | Approved Variations and Claims | 5200000 | [14 empty] | Number of technical queries raised | [32 empty] | Actual number of labor camps | 6 | Smart City Adoption Effectiveness Index (realized benefits & performance) | 0.5 | [9 empty] | Alignment with Critical Success Factors | 3 | [25 empty] | Yes | Good | Have all projects completed a Constructability Report/Document? |  |  | Yes | Date and Revision of Constructability Report
Diriyah | Risks identified and corresponding impact on schedule | NIL | [12 empty] | Has DevCo allocated risk contingency for the identified risks? | Yes | Risk Performance | 2.38 | Good | Key risks include a mix of internal and external risks. Key external risks relate to material supply and logistics. Proactive actions have been taken to mitigate these risks. However, there has been an impact on the project delivery. | Uncommitted Cost | 300000000 | [14 empty] | Number of technical queries closed | [24 empty] | % of Material Supply Capacity against Material Demand Estimates | 1.3333 |  |  |  |  | Good | % of Material Supply Capacity against Material Demand Estimates | Forecast number of batching / crushing plants/ precast yards, etc. | 3 | [11 empty] | Inclusion of both Lagging and Leading Indicators | 3 | [25 empty] | Yes | Good | Was design for Enabling Work Package considerd as part of the design process to ensure the readiness of the site for the main construction work? |  |  | Yes | Assessment of enabling works required
Diriyah | Extra Cost due to Unresolved Issues | 1700000 | [12 empty] | Was there any deferment in the project completion date due to unidentified risks? | Yes, but less than 1 month |  |  | Satisfactory |  | Pending Variations | 0 | [14 empty] | Average time to complete shop drawing reviews | [32 empty] | Actual number of batching / crushing plants/ precast yards, etc. | 4 | [11 empty] | Stakeholder Engagement in KPI Development | 2 | [25 empty] | Yes | Good | Are documentation packages meeting the LOD requirements of the latest Design Stage Gate? |  |  | Yes | LOD Required
Diriyah | [14 empty] | Was there any Cost Overrun because of identified risk? | No |  |  | Good |  | Anticipated Variations | 1 | [14 empty] | Number of shop drawing review conducted | 14550 | [23 empty] | Did DevCo adhere to Technical Submittals Review Cycle Time (RCT)? | Yes | Quality | 2.88 | Adherence to Design | 3 | Good | Did DevCo adhere to Technical Submittals Review Cycle Time (RCT)? | Time taken for closure of technical queries | Yes |  |  | Is there an impact assessment report or identified process/ guidelines to evaluate the impact of the innovation / smart city technologies adoption on DevCo performance? | 0.6 | Satisfactory | [6 empty] | Comprehensive Coverage of Key Performance Areas | 3 | [30 empty] | Yes | LOD Documented (drawing sample from Design Report)
Diriyah | [14 empty] | Was there any Cost Overrun because of unidentified risk? | Yes, but less than 1% |  |  | Satisfactory | [17 empty] | Number of material / product substitution requests | [32 empty] | Technical Submittal Review Cycle Time (RCT) | Yes | [11 empty] | Continuous Improvement and Review | 3 | [25 empty] | Yes | Good | Have all projects adopted digital delivery using BIM and/or GIS? |  |  | Yes | % of projects adopting digital delivery using BIM/GIS
Diriyah | [14 empty] | Risk Control Rate of the identified risks at DevCo Level | 0.8125 |  |  | Good | [17 empty] | Average time to approve product sample & materials | [24 empty] | % of approved shop drawing reviews vs planned | 0.94648 |  |  |  |  | Good | % of approved shop drawing reviews vs planned | Total number of shop drawing review requests | 14760 | [11 empty] | Total Positions | 500 | [23 empty] | Design Management Maturity | 2.6 | Yes | Good | Is project delivery occurring in accordance with the latest approved design strategy? | Design Management | 2.6 | Yes | Date of Latest Approved Design Strategy
Diriyah | [36 empty] | Product & Material Approval Rate | [32 empty] | Total number of shop drawing reviews approved | 13970 | [11 empty] | Vacant Positions | 100 | [25 empty] | 0.1 | Needs Improvement | % of projects with completed technical design/peer reviews and verifications/certifications as required for the latest Design Stage Gate |  |  | 0.1 | Number of projects with completed design reviews and verification register
Diriyah | [14 empty] | Is the DevCo fully compliant with Risk Management Plan requirements? | No |  |  | Needs Improvement | [17 empty] | Number of as-built drawing review conducted | 485 | [23 empty] | % of approved product waivers vs product specified | 0.986 |  |  |  |  | Good | % of approved product waivers vs product specified | Total number of product sample & material approvals requested | 1000 |  |  | Is there evidence for innovation / smart city technologies successful implementation (in final design report, master plan or other)? | Yes | Good | [6 empty] | Management Positions | 50 | [25 empty] | 0.85 | Good | % of Corrective Actions closed |  |  | 40 | Total Corrective Actions
Diriyah | [14 empty] | Is there a difference in the time impact forecast before and after the risk event has triggered? | Yes, but less than 2 weeks |  |  | Satisfactory | [17 empty] | Average time to approve As-built rejections / iterations | [32 empty] | Total number of product sample & materials approved | 986 | [11 empty] | Vacant Management Positions | 5 | [30 empty] | 34 | Number of Closed Corrective Actions
Diriyah | [14 empty] | Is there a difference in the Cost impact forecast before and after the risk event has triggered? | Yes, but less than 0.5% |  |  | Satisfactory | [17 empty] | As-Built Drawing Approval Rate | [24 empty] | % of Certified As-Built Drawing Packages vs Planned | 0.95 |  |  |  |  | Good | % of Certified As-Built Drawing Packages vs Planned | Number of As-Built Drawing review requests | 500 |  |  | Are there Pilot or R&D projects conducted? | 0.55 | Needs Improvement | 1 | Pilot and R&D Transition Rate | [31 empty] | 14 | Satisfactory | Average Cycle time to close corrective actions |  |  | 14 | Days taken to Close Corrective Actions
Diriyah | [36 empty] | Average time to complete MIRs and close out approvals | [32 empty] | Number of As-Built Drawings reviews approved | 475 | [38 empty] | Yes | Good | Is the average cycle time to complete reviews and certifications in accordance with the Design Management Report? |  |  | Yes | Days taken to complete Design Reviews
Diriyah | [36 empty] | Average time to complete WIRs and close out approvals | [24 empty] | MIR Inspection Rate | 0.98333 |  |  |  |  | Good | MIR Inspection Rate | Total number of MIRs requested | 120 | [38 empty] | Yes | Good | Has the DevCo engaged independent certification of major critical elements? |  |  | Yes | Level of review and verification required for Stage Gate
Diriyah | [36 empty] | Number of NCRs open for between 30 and 60 days | 23 | [31 empty] | Total number of MIRs inspected | 118 | [36 empty] | Environmental Compliance Status | 2 | No | Needs Improvement | Are all project designs integrated with Regional Infrastructure & Mobility Plans? | Regulatory Compliance | 2.12 | No | Regional Strategies
Diriyah | [36 empty] | Number of NCRs open for more than 60 days | 5 | [23 empty] | MIR Acceptance and Approval Rate | 0.91667 |  |  |  |  | Good | MIR Acceptance and Approval Rate | Total number of MIRs approved | 110 |  |  | % of pilot / R&D Projects Transitioned into Full-Scale | 0.13043 | Needs Improvement | [33 empty] | Yes | Good | Do all projects comply with environmental guidelines in accordance with ESIA? |  |  | Yes | Extent of compliance to environmental guidelines
Diriyah | [36 empty] | Leadership engagement | Satisfactory | [23 empty] | WIR Inspection Rate | 0.97143 |  |  |  |  | Good | WIR Inspection Rate | Total number of WIRs requested | 350 | [36 empty] | Authority Compliance Status | 2.2 | 0.15 | Satisfactory | % of projects with Code Compliance Violations |  |  | 0.15 | Total Number of Code Compliance Violations
Diriyah | [36 empty] | Total number of ITPs requested | 100 | [31 empty] | Total number of WIRs inspected | 340 | [38 empty] | 1.0476 | Good | % of approved deviation waivers against compliant codes & standards |  |  | 21 | Total Waiver Applications Submitted
Diriyah | [36 empty] | Total number of ITPs attended | 98 | [23 empty] | WIR Acceptance and Approval Rate | 0.95714 |  |  |  |  | Good | WIR Acceptance and Approval Rate | Total number of WIRs approved | 335 | [43 empty] | 22 | Total Waivers Approved
Diriyah | [36 empty] | Total number of ITPs approved | 87 | [23 empty] | Does the frequency of Audits align with the QMP? | Yes |  |  | Quality Assurance / Quality Control (QA/QC) | 2.6 | Good | Does the frequency of Audits align with the QMP? | Required Audit frequency | Yes |  |  | Availability of Innovation unit / department with structured team | 0 | Needs Improvement | 1.5 | Organization Maturity Towards Innovation Adoption | [31 empty] | Yes | Good | Have all required Stakeholder Submittals been issued? |  |  | Yes | Stakeholder Submittal Date
Diriyah | [36 empty] | Total number of ITPs completed | 85 | [23 empty] | % closure of Non-Conformance Reports (NCR) | 0.96667 |  |  |  |  | Good | % closure of Non-Conformance Reports (NCR) | Total number of defects & NCRs | 150 | [38 empty] | 0.31746 | Needs Improvement | % of time critical Stakeholder Approvals Pending impacting Design Stage Gate completion |  |  | 0.2 | Number of Stakeholder Approvals Pending
Diriyah | [36 empty] | Total number Quality Reports completed | [32 empty] | Total number of closed defects & NCRs | 145 | [43 empty] | 0.63 | Total number of stakeholder approvals required
Diriyah | [36 empty] | Completeness of Quality Management Plan | Needs Improvement | [23 empty] | Average NCRs closeout Cycle Time | 23 |  |  |  |  | Needs Improvement | Average NCRs closeout Cycle Time | Average time to close NCRs | 23 | [38 empty] | Yes | Good | Does the Stakeholder Engagement Plan include proactive communication process to ensure timley coordination and approvals? |  |  | Yes | Scheduled Design Stage Gate Completion
Diriyah | [36 empty] | Required number of ITPs signed off throughout construction | [24 empty] | % of procurement packages delivered within the planned lead times defined in the PMP | 0.86 | Procurement | 2.1 | Procurement & Contracting Compliance | 2.8 | Good | % of procurement packages delivered within the planned lead times defined in the PMP | Planned Procurement Package Lead Time | 100 |  |  | Availability of Innovation and Technology Strategy / Process & Framework | 0.5 | Satisfactory | [33 empty] | 0.19048 | Needs Improvement | % of Stakeholder Comments Closed |  |  | 21 | Total Stakeholder Comments
Diriyah | [36 empty] | Total number of raised closed-out defects & NCRs | [32 empty] | Actual Procurement Package Delivery Time | 86 | [43 empty] | 4 | Stakeholder Comments Closed
Diriyah | [36 empty] | Forecasted Procurement Budget | [24 empty] | % of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures | 0.875 |  |  |  |  | Good | % of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures | Total number of claims and variations | 800 | [36 empty] | DevCo ESG Target Achievement | 1 | 0 | Needs Improvement | % of projects achieving DevCo ESG Targets | ESG Target Realization | 1 | 1 | Planned ESG Target
Diriyah | [36 empty] | Actual Procurement Budget | [32 empty] | Total number of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures | 700 | [43 empty] | 0 | Actual ESG Target
Diriyah | [36 empty] | Vendor Database | [24 empty] | % of packages procured with 100% complete, compliant and well-structured documentation | 0.6 |  |  |  |  | Satisfactory | % of packages procured with 100% complete, compliant and well-structured documentation | Total number of packages | 0.5 | [36 empty] | Global ESG Target Alignment | 1 | No | Needs Improvement | Does the DevCo ESG Target align with globally recognized Best Practice Targets? |  |  | No | Alignment with globally recognized Best Practice Targets
Diriyah | [36 empty] | Vendor Shortlist | [32 empty] | Total number of packages procured with 100% complete, compliant and well-structured documentation | 0.3
Diriyah | [36 empty] | Vendor Awarded | [24 empty] | % of awarded contracts where vendors appointed passed full due diligence checks | 1.2857 |  |  |  |  | Good | % of awarded contracts where vendors appointed passed full due diligence checks | No. of awarded contracts where vendors appointed passed full due-diligence checks | 0.9
Diriyah | [36 empty] | Vendor KPIs | [32 empty] | Total number of awarded contracts | 0.7
Diriyah | [36 empty] | Vendor Performance Database | [24 empty] | Did the DevCo complete a Supply Chain Risk-Market Intelligence Assessment in the last quarter? | Yes |  |  |  |  | Good | Did the DevCo complete a Supply Chain Risk-Market Intelligence Assessment in the last quarter? | Supply Chain Risk-Market Intelligence Assessment | Yes
Diriyah | [36 empty] | Tender return date: Planned / Actual | [24 empty] | % of procurement activities executed as planned in the Annual Procurement Plan | 0.69355 |  |  | Procurement & Contracting Execution Performance | 1.8 | Needs Improvement | % of procurement activities executed as planned in the Annual Procurement Plan | Total number of procurement activities | 186
Diriyah | [36 empty] | Tender Review & award time: Planned / actual | [32 empty] | Number of procurement activities executed as planned | 129
Diriyah | [36 empty] | Pre-Tender Cost Estimate | [24 empty] | % of deviations in total awarded contract value with tender cost estimates | 0.091166 |  |  |  |  | Good | % of deviations in total awarded contract value with tender cost estimates | Value of Awarded Contract | 35.32
Diriyah | [36 empty] | Tender Performance Index | [32 empty] | Tender Cost Estimate | 32.1
Diriyah | [36 empty] | Contract clauses | Satisfactory | [23 empty] | % of contracts with filed claims | 10 |  |  |  |  | Needs Improvement | % of contracts with filed claims | Number of contracts with filed claims | 10
Diriyah | [36 empty] | Procurement Management Plan | Good | [23 empty] | Are Payment Certificates and payments being processed in accordance with the Contract terms and conditions? | Yes |  |  |  |  | Good | Are Payment Certificates and payments being processed in accordance with the Contract terms and conditions? | Processing of payment certificates and payments | Yes
Diriyah | [36 empty] | Scope / design maturity | Satisfactory | [23 empty] | Are Vendor performance assessment occurring which capture financial instability, delays, repeated quality issues in real-time? | No |  |  |  |  | Needs Improvement | Are Vendor performance assessment occurring which capture financial instability, delays, repeated quality issues in real-time? | Alignment of sourcing strategies with project schedules and requirements | No
Diriyah | [36 empty] | Compliance with local content regulations / policies | [24 empty] | Does the HSE Management Manual have adequate provision for identification and escalation of high risk activities? | Yes | HSE and Welfare | 2.435 | HSE Compliance | 2.47 | Good | Does the HSE Management Manual have adequate provision for identification and escalation of high risk activities? | Escalation criteria for high risk activities | Yes
Diriyah | [36 empty] | Dispute rate | [24 empty] | Is the rate of review of the Safety Risk Register in accordance with the HSE Management Manual? | Yes |  |  |  |  | Good | Is the rate of review of the Safety Risk Register in accordance with the HSE Management Manual? | HSE Risk Register Review Rate | Yes
Diriyah | [36 empty] | Claims processing cycle time | [24 empty] | % of closed Safety Risk items | 0.83333 |  |  |  |  | Good | % of closed Safety Risk items | Total number of Safety Risk items | 0.9
Diriyah | [36 empty] | No. of related CRs being requested during or after tendering phase due to identified scope gap | [32 empty] | Total number of closed Safety Risk items | 0.75
Diriyah | [36 empty] | Vendor Performance Assessment | Good | [23 empty] | Average cycle time to close Safety Risk items | 14 Days |  |  |  |  | Needs Improvement | Average cycle time to close Safety Risk items | Cycle time to close Safety Risk items | 14 Days
Diriyah | [36 empty] | Tender pack quality | Satisfactory | [23 empty] | Average cycle time to close Safety Incident | 0.65 |  |  |  |  | Good | Average cycle time to close Safety Incident | Cycle time to close Safety Incident | 20
Diriyah | [36 empty] | % payment paid within contractual terms | 80 | [31 empty] | Total number of closed safety incidents | 13
Diriyah | [36 empty] | Planned Packages | [24 empty] | Is the emergency drill rate compliant with EEPP? | No |  |  |  |  | Needs Improvement | Is the emergency drill rate compliant with EEPP? | Planned number of Emergency Drills | 35
Diriyah | [36 empty] | Awarded Packages | [32 empty] | Actual number of Emergency Drills | 20
Diriyah | [36 empty] | Trade Most at Risk | [32 empty] | Recommended time to complete Emergency drills | 5 Days
Diriyah | [36 empty] | Highest Risk Work Site | [32 empty] | Actual Time to complete Emergency drills | 10 Days
Diriyah | [36 empty] | Number of planned audits | [24 empty] | Fatality Rate (FR) | 0 |  |  |  |  | Good | Fatality Rate (FR) | No. of incidents resulting in fatality or severe impairment per 200,000 work hours | 0
Diriyah | [36 empty] | Number of conducted audits | [24 empty] | Lost Time Injury Frequency Rate (LTIFR) | 0 |  |  |  |  | Good | Lost Time Injury Frequency Rate (LTIFR) | No. of incidents resulting in lost time per 200,000 work hours | 0
Diriyah | [36 empty] | Number of Notifiable Incidents | 6 | [23 empty] | Total Recordable Incident Rate (TRIR) | 0 |  |  |  |  | Good | Total Recordable Incident Rate (TRIR) | No. of recordable incidents per 200,000 work hours | 0
Diriyah | [36 empty] | Number of Infringement Notices | 2 | [23 empty] | Near Miss Rate | 3 |  |  |  |  | Satisfactory | Near Miss Rate | No. of near misses recorded per 200,000 work hours | 3
Diriyah | [36 empty] | Total Safe Manhours | [24 empty] | Safety Observation Rate | 8 |  |  |  |  | Needs Improvement | Safety Observation Rate | No. of safety observation recorded per 200,000 work hours | 8
Diriyah | [36 empty] | Total number of closed Corrective actions | [24 empty] | Leadership Safety Walk Rate | 0.73 |  |  |  |  | Good | Leadership Safety Walk Rate | Total number of Safety Walks | 300
Diriyah | [36 empty] | Inspection Pass Rate | [32 empty] | Total number of Safety Walks with Leadership | 219
Diriyah | [36 empty] | No. of recurring incidents / safety observations outside control | [24 empty] | % of Grievances Closed | 1 |  |  | Welfare Compliance | 2.4 | Good | % of Grievances Closed | Number of grievances closed | 5
Diriyah | [36 empty] | Total Site Manhours | 180000000 | [31 empty] | Total number of grievances | 5
Diriyah | [36 empty] | Welfare of labor camps | [24 empty] | Average Cycle Time to Close Grievances | Good |  |  |  |  | Needs Improvement | Average Cycle Time to Close Grievances | Cycle time to close grievances | Good
Diriyah | [36 empty] | Welfare of site facilities | [24 empty] | % of Welfare Staff vs Total workforce | Good |  |  |  |  | Good | % of Welfare Staff vs Total workforce | Percentage of Welfare Staff against total staff | Good
Diriyah | [36 empty] | Labor accommodation inspection rate | [24 empty] | % closed welfare observations or red flag if 0 observations | 0.75 |  |  |  |  | Good | % closed welfare observations or red flag if 0 observations | Total number of Welfare Observations | 20
Diriyah | [36 empty] | Regulation Compliance | [32 empty] | Total number of Closed Welfare Observations | 15
Diriyah | [61 empty] | % of Welfare Non-compliances closed | 0.58 |  |  |  |  | Needs Improvement | % of Welfare Non-compliances closed | Total Welfare Non-compliances | 100
Diriyah | [69 empty] | Total Closed Welfare Non-compliances | 58
Diriyah | [61 empty] | Average Cycle Time to Close Welfare Non-compliances | 10 Days |  |  |  |  | Needs Improvement | Average Cycle Time to Close Welfare Non-compliances | Cycle time to close Welfare Non-Compliances | 10 Days
Diriyah | [61 empty] | Is frequency of Labor Accommodation Inspection occurring in accordance with VMMP? | Yes |  |  |  |  | Good | Is frequency of Labor Accommodation Inspection occurring in accordance with VMMP? | Mitigation measures in the event of welfare audit observations & recommendations | Yes
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Diriyah
Qiddiya | Latest Approved Completion Date​ | Q1-29 | 2025 | 0 |  |  | Risk 1 | 20 | Risk 1 | Contractor | Cost | Low | Open | Measure 02 | DevCo Schedule Performance Index (SPI) | 0.96 | Overall Progress | 2.13 | Satisfactory | Key milestones are on track, with some delivered ahead of schedule. There are delays expected of ongoing projects due to complexities related to infrastructure | Estimate to Completion Declared by DevCo | 519000000 | 2023 | 400 | 420 | 400 | Budget Variance | -0.11111 | Good | Significant increase in budget due to inadequate contingency planning | Overall Budget | 2.56 | PIF Approved Capex budget (Initial Business Plan) | 450000000 | 2 | Jan | No. of Site Access Required | 180 | Count | 150 | 89 | 99 | Fatalities | 0 | 0 | 0 | 0 | HSE Audit | 3 | 5 | 4 | HSE | 8 | 22 | 3 | Jan | 20 | Program 1 | 50 | 25 | 20 | % of CESMP mitigation measures which align with ESIA* | 0.8 | Construction | 2.58 | Construction Planning Maturity | 2.4 | Satisfactory | % of CESMP mitigation measures which align with ESIA* | Environmental mitigation measures included in CESMP | 0.1 | Implementation Success Rate for Innovation Strategy | 25 | Is there an innovation Strategy or document that lists the key focus areas and initiatives across design, construction and operation and aligned with DevCo strategic plan? | 0.4 | Needs Improvement | 1.7 | Innovation & Technology Deployment | Innovation and Technology Adoption | 1.43 | 20 | KPI 1 | Strategy Planning and Review | 3 | Design Stage Gate Approval Procedures | Y | N | Cost Management Platform | Y | N | 1 |  | Chief Development Officer | Filled | CDO | Satisfactory | Availability of Technical Function Strategy | Yes, but very brief | Technical Strategy and Enablers | 2.23 | 2 | Technical Strategy Achievement | 2.3 | Availability of Technical Function Strategy | Availability of strategy | Yes, but very brief | DevCo has maintained adherence to the Vision, with a few outstanding variance approvals pending. The DevCo has demonstrated poor consideration for construction methodology simplification during the design phase, however, is demonstrating effective use of BIM software for interdisciplinary coordination across most projects. | CGI and Animation Compliance | 2.4 | 0.4 | Needs Improvement | Similarity between Original/Approved and Latest CGI and Animation | Vision Adherence | 1.5 | 0.2 | Percentage similarity between Approved CGI and Latest CGI at same angle and scale | DevCo performance is generally good. While overall progress is delayed by 12 months, these are largely due to unforeseen circumstances and DevCo has shown ability to recover some of the delays. The lack of a smart city strategy and DevCo-level ESG targets and irregular adherence to procurement control processes are key areas for improvement.
Qiddiya | Forecast Completion Date​ | Q3-29 | 2026 | 1350 | 1350 |  | Risk 2 | 18 | Risk 2 | Source A | Impact O | Med | Ongoing | Measure 01 | [6 empty] | Total Expenditure to Date | 100000000 | 2024 | 420 | 440 | 420 | [6 empty] | Forecast budget (EAC) | 500000000 | 5 | Feb | No. of Site Access Provided | 120 | Value | 13200 | 9800 | 12345 | Severe Impairment | 1 | 0 | 1 | 0 | Welfare Inspection | 2 | 4 | 4 | Welfare | 19 | 8 | 3 | Feb | 10 | Program 2 | 230 | 40 | 90 | [8 empty] | Environmental mitigation measures recommended in ESIA | 0.2 | Innovation Adoption Effectiveness Index (strategy & leadership alignment) | 10 | [7 empty] | 20 | KPI 2 | Explicit Mapping against Organization Strategy | 3 | [6 empty] | 2 | 1 | Head | Filled | Development | Good | Alignment of Technical Strategy with Organizational Strategy | Well-aligned |  |  | 3 |  |  | Alignment of Technical Strategy with Organizational Strategy | Alignment of technical functions' strategy and initiatives with the overarching organizational strategy | Well-aligned | [8 empty] | 0.6 | Percentage similarity between Approved Animation and Latest Animation at same camera angle
Qiddiya | Approved baseline completion date | Q2-27 | 2027 | 3200 | 1600 | 1600 | Risk 3 | 15 | Risk 3 | Source B | Impact P | High | Open | Measure 04 | % milestone achievement in accordance with the approved business plan | 0.9 |  |  | Good |  | Contingency budgeted at DevCo level | 2000000 | 2025 | 440 | 460 | 455 | % of projects having Budget Variance | 1 | Needs Improvement |  |  |  | Number of Projects with Budget Variance | 15 | 3 | Mar | Packaging & Phasing Strategy | Good |  |  |  |  | Lost Time Incidents | 3 | 0 | 1 | 2 | [8 empty] | Mar | 18 | Program 3 | 10 | 80 | 40 | Has the Construction Execution Plan been updated to reflect the latest stage of construction? | Yes |  |  |  |  | Good | Has the Construction Execution Plan been updated to reflect the latest stage of construction? | Update of construction execution plan | Yes | Innovation Adoption Effectiveness Index (skilled human resources) | 5 | [7 empty] | 15 | KPI 3 | Benchmarking and Industry Standards | 3 | [6 empty] | 3 | 1 | Head | Filled | Projects | Satisfactory | Severity of Key Challenges Faced in Strategy Execution Technically | Moderate |  |  | 2 |  |  | Severity of Key Challenges Faced in Strategy Execution Technically | Key challenges in strategy execution | Moderate |  |  |  | Yes | Good | Does the Latest Material Palette & Finish Schedule support the look of the Approved CGI? |  |  | Yes | Material Palette & Finish Schedule
Qiddiya | No. of schedule iterations | 8 | 2028 | 4000 |  | 2300 | Risk 4 | 4 | Risk 4 | Source F | Impact T | High | Closed | Measure 05 | [6 empty] | Contingency utilized at DevCo level | 2500000 | 2026 | 460 | 480 | 500 | [6 empty] | Total number of projects | 15 | 1 | Apr | Execution & Site Logistics | Satisfactory |  |  |  |  | Recordable Incidents | 25 | 20 | 4 | 1 | [8 empty] | Apr | 24 |  |  |  |  | Has the construction sequence and method statement been reviewed and approved? | No |  |  |  |  | Needs Improvement | Has the construction sequence and method statement been reviewed and approved? | Review and approval of Construction sequence & method statement | No | Innovation Adoption Effectiveness Index (planning & governance) | 5 | [7 empty] | 10 | KPI 4 | Performance Management | 3 | [6 empty] | 4 | 1 | Head | Filled | Masterplan | Satisfactory | Availability of Technical KPIs | Yes, but very brief |  |  | 2 | Technical KPI Achievement | 2.4 | Availability of Technical KPIs | Availability of KPIs | Yes, but very brief |  |  |  | Yes | Good | Does the DevCo have Design & Technical Guidelines (including Look & Feel Design Guidelines)? |  |  | Yes | Design and Technical Guidelines
Qiddiya | Planned duration up to a specific phase as per approved Baseline programme | 145 | 2029 |  |  | 4000 | Risk 5 | 7 | Risk 5 | PMC | Reputation | Low | Ongoing | Measure 06 | % of projects with approved change requests in design phase since inception with time impact of more than 1 month | 0.16667 |  |  | Good |  | Contingency Utilization Rate | 200000 | 2027 | 480 | 500 | 520 | % of projects with contingency utilization rate > 1 | 0.25 | Satisfactory |  |  |  | Number of projects with contingency utilization > 1 | 12 | 0 | May | Procurement Strategy | Good |  |  |  |  | Near Misses | 29 | 20 | 8 | 1 | [8 empty] | May | 4 |  |  |  |  | Is total land acquisition sufficient to achieve the area required for construction site logistics? | No |  |  |  |  | Needs Improvement | Is total land acquisition sufficient to achieve the area required for construction site logistics? | Planned Area provision for site offices, amenities, laydown areas, storage facilities, workforce accommodations | Average | Innovation Adoption Effectiveness Index (process management) | 5 | [7 empty] | 10 | KPI 5 | Communication and Implementation | 2 | [6 empty] | 6 | 2 | Chief Devt | Vacant | MP1 | Satisfactory | Progress of Achievement of KPIs for Technical Team | 0.5 |  |  | 2 |  |  | Progress of Achievement of KPIs for Technical Team | Total Number of KPIs set for the preceding year | 10 |  |  |  | No | Good | Do DevCo projects comply with DDTG? |  |  | No | Look & Feel Guideline
Qiddiya | Duration taken to complete works up to the specific phase | 160 | [6 empty] | Risk 6 | Source C | Impact Q | Med | Open | Measure 07 | [6 empty] | Value of Changes in Design Stage | 6000000 | 2028 | 500 | 520 | 535 | % of projects with Approved Change Requests (design/construction) having a cost impact greater than 2% | 0.07 | Satisfactory |  |  |  | No. of projects with approved change request having a cost impact greater than 2% | 12 | 0 | Jun | Required area for land acquisition | [18 empty] | Jun | 0 | [12 empty] | Actual Area provision for site offices, amenities, laydown areas, storage facilities, workforce accommodations | No | Innovation Adoption Effectiveness Index (partnerships and collaboration) | 5 | [7 empty] | 25 | Others | Clear and Documented Process | 2 | [6 empty] | 7 | 2 | Chief Devt | Vacant | MP2 | [9 empty] | Number of KPIs achieved in the preceding year | 5 |  | Development Program Variance | 3 | 0.14286 | Good | % variance from approved Built-Up Area (BUA) |  |  | 16 | Latest BUA
Qiddiya | Recovery Plan | Satisfactory | [6 empty] | Risk 7 | Source D | Impact R | Low | Closed | Measure 08 | % of projects with approved change requests in construction phase since inception with time impact of more than 4 months | 0.33333 |  |  | Satisfactory |  | Value of Changes in Construction Stage | 3000000 |  |  |  |  | % of projects with Approved Claims | 0.04 | Satisfactory |  |  |  | No. of projects with approved claims | 10 | 0 | Jul | Mitigation of Project Execution Plan implementation challenges | [18 empty] | Jul | 0 |  |  |  |  | Have Traffic Simulations been completed in preparing the Site & Logistics Plan? | Yes |  |  |  |  | Good | Have Traffic Simulations been completed in preparing the Site & Logistics Plan? | Completion of Traffic Simulations | Yes | Innovation Adoption Effectiveness Index (resource management) | 0.3 | [9 empty] | Technology Utilization | 3 | [6 empty] | 8 | 2 | Chief Devt | Vacant | MP3 | Good | Appropriateness of KPIs for Technical Team | Aligned with industry benchmarks |  |  | 3 |  |  | Appropriateness of KPIs for Technical Team |  | Aligned with industry benchmarks | [8 empty] | 14 | Approved BUA
Qiddiya | Extent of all EOT (design stage) | 4 | [6 empty] | Risk 8 | Supplier | Time | High | Closed | Measure 09 | [6 empty] | Number of Changes (Concept MP) | 0 |  |  |  |  | % of provisional sums of the latest PIF Approved Capex budget | 0.0032787 | Good |  |  |  | Total provisional sums | 2000000 | 0 | Aug | Occurred delays due to stakeholder objections | [18 empty] | Aug | 0 |  |  |  |  | Has the Project Execution Plan been updated and approved in the last 12 months? | Yes |  |  |  |  | Good | Has the Project Execution Plan been updated and approved in the last 12 months? | Date of latest approved Procurement Plan | 2025-08-08 | Implementation Success Rate for Smart City Strategy | 20 | [9 empty] | Risk Management and Technical Planning Deficiencies | Yes | [6 empty] | 9 | 3 | Project Lead | Vacant | MP1 | Good | Criticality of Vacant/Missing Positions in Organization | Minor |  |  | 3 | Technical Organization | 3 | Criticality of Vacant/Missing Positions in Organization | Key positions which are missing, if any | Minor |  |  |  | 0.041667 | Good | % variance in land use permit area |  |  | 2.5 | Latest Land Area
Qiddiya | Extent of all EOT (const. stage) | 8 | [6 empty] | Risk 9 | CAA | Impact M | Low | Closed | Measure 10 | % of projects with approved schedule extension | 0.43333 |  |  | Needs Improvement |  | Number of Changes (Detailed MP) | 6 | [10 empty] | Latest Approved budget | 610000000 | 0 | Sep | Workforce Planning and Availability | Needs Improvement | [17 empty] | Sep | 0 |  |  |  |  | % of Stakeholder MOU** / LUPs*** not executed in accordance with critical lead time | 0.05 |  |  |  |  | Good | % of Stakeholder MOU** / LUPs*** not executed in accordance with critical lead time | Number of Stakeholder MOU or Land Use Permits not executed on time | 5 | Number of Smart City Use Cases | 1 | Is there a smart city Strategy or document that lists the key focus areas of smart city aligned with DevCo strategic plan? | 0.4 | Needs Improvement | [6 empty] | Technology Integration and Adaptation Challenges | Yes | [6 empty] | 10 | 3 | Project Lead | Filled | MP2 | Good | Appropriateness of Qualifications in Recruitment of Vacant Technical Department Head Positions | Minor |  |  | 3 |  |  | Appropriateness of Qualifications in Recruitment of Vacant Technical Department Head Positions | Qualifications of job descriptions for vacant technical department head positions - are they appropriate? | Minor | [8 empty] | 2.4 | Approved Land Area
Qiddiya | No. of unresolved issues | 10 | [6 empty] | Risk 10 | Source E | Impact S | Med | Ongoing | Measure 11 | [6 empty] | Number of Changes (Concept Design) | 3 |  |  |  |  | % of variance of Allocated Provisional sums against the awarded amount | 0.05 | Good |  |  |  | Actual Utilized Provisional Sums | 1200000 | 0 | Oct | Resource Planning and Availability | Good | [17 empty] | Oct | 0 | [12 empty] | Total Stakeholder MOU or Land Use Permits required | 100 | Smart City Adoption Effectiveness Index (strategy & leadership alignment) | 5 | [9 empty] | Data Management and Information Flow | Yes | [6 empty] | 11 | 3 | Project Lead | Filled | MP3 | Satisfactory | Robustness of Policy/Guideline/Procedure Communication | Moderate |  |  | 2 | Technical Control Environment | 1.3 | Robustness of Policy/Guideline/Procedure Communication | List of policies/procedures communicated to all employees | Some gaps with industry benchmarks |  |  |  | 0.052632 | Good | % variance from approved population |  |  | 1000 | Latest Population
Qiddiya | No. of (Open) Inherent Risks | 20 | [18 empty] | Number of Changes (Detailed Design) | 4 | [12 empty] | 0 | Nov | Workforce retention track record | [18 empty] | Nov | 0 |  |  |  |  | % of Workforce Hired against Workforce Estimates | 1 |  |  | Workforce Resource Availability | 3 | Good | % of Workforce Hired against Workforce Estimates | Forecast workforce requirements | 0.4 | Smart City Adoption Effectiveness Index (infrastructure readiness) | 7 | [9 empty] | Supply Chain and Logistics | No | [6 empty] | 12 | 3 | Lead | Missing | Stakeholder Interface | Needs Improvement | Robustness of Policy/Guideline/Procedure Compliance Monitoring Framework | Poor |  |  | 1 |  |  | Robustness of Policy/Guideline/Procedure Compliance Monitoring Framework | Monitoring of policies and procedures compliance | Poor | [8 empty] | 950 | Approved Population
Qiddiya | No. of (Closed) Residual Risks | 45 | [12 empty] | % of projects with Forecast completion date beyond the latest approved schedule | 0.46154 |  |  | Needs Improvement |  | Number of Changes (Construction) | 10 | [12 empty] | 0 | Dec | Turnover rate track record | [18 empty] | Dec | 0 | [12 empty] | Actual workforce employed | 0.4 | Smart City Adoption Effectiveness Index (planning & governance) | 10 | [9 empty] | Cross-Functional Coordination and Communication | Yes | [11 empty] | Needs Improvement | Robustness of Board Reporting Framework | Poor |  |  | 1 |  |  | Robustness of Board Reporting Framework | Frequency of reporting to Board and PIF | Misaligned |  | Construction Design Maturity | 2.8 | 0.33333 | Satisfactory | % value of modularization compared to the total construction value | Design for Constructability | 2.8 | 0.01 | Value of Modularized Construction Cost
Qiddiya | Project-level risks (including low, medium, and high severity) | 80 | [12 empty] | Is the Forecast Finish Date at a given data date based on the alignment and buy-in from project teams and other listed stakeholders? | Yes |  |  | Good |  | Total Awarded Cost | 15000000 | [14 empty] | Plant/equipment downtime track record | [24 empty] | % of Labor Camp Capacity against Workforce Estimates | 1.125 |  |  |  |  | Good | % of Labor Camp Capacity against Workforce Estimates | Forecast number of labor camps | 0.8 | Smart City Adoption Effectiveness Index (stakeholder alignment) | 20 | [9 empty] | Adaptability to Market Conditions | Yes | [30 empty] | 0.03 | Value of Total Construction Cost
Qiddiya | Procedures for risk management | Satisfactory | [12 empty] | Based on the risks identified and approved change requests, has the DevCo conducted a sensitivity assessment on the forecast completion at a given data date? | Yes, but inadequate |  |  | Satisfactory |  | Approved Variations and Claims | 10000000 | [14 empty] | Number of technical queries raised | [32 empty] | Actual number of labor camps | 0.9 | Smart City Adoption Effectiveness Index (realized benefits & performance) | 0.9 | [9 empty] | Alignment with Critical Success Factors | 3 | [25 empty] | Yes | Good | Have all projects completed a Constructability Report/Document? |  |  | Yes | Date and Revision of Constructability Report
Qiddiya | Risks identified and corresponding impact on schedule | NIL | [12 empty] | Has DevCo allocated risk contingency for the identified risks? | Yes | Risk Performance | 2.22 | Good | Key risks include a mix of internal and external risks. Key external risks relate to material supply and logistics. Proactive actions have been taken to mitigate these risks. However, there has been an impact on the project delivery. | Uncommitted Cost | 250000000 | [14 empty] | Number of technical queries closed | [24 empty] | % of Material Supply Capacity against Material Demand Estimates | 1.4 |  |  |  |  | Good | % of Material Supply Capacity against Material Demand Estimates | Forecast number of batching / crushing plants/ precast yards, etc. | 0.5 | [11 empty] | Inclusion of both Lagging and Leading Indicators | 3 | [25 empty] | Yes | Good | Was design for Enabling Work Package considerd as part of the design process to ensure the readiness of the site for the main construction work? |  |  | Yes | Assessment of enabling works required
Qiddiya | Extra Cost due to Unresolved Issues | 2000000 | [12 empty] | Was there any deferment in the project completion date due to unidentified risks? | Yes, but less than 1 month |  |  | Satisfactory |  | Pending Variations | 0 | [14 empty] | Average time to complete shop drawing reviews | [32 empty] | Actual number of batching / crushing plants/ precast yards, etc. | 0.7 | [11 empty] | Stakeholder Engagement in KPI Development | 2 | [25 empty] | Yes | Good | Are documentation packages meeting the LOD requirements of the latest Design Stage Gate? |  |  | Yes | LOD Required
Qiddiya | [14 empty] | Was there any Cost Overrun because of identified risk? | No |  |  | Good |  | Anticipated Variations | 1 | [14 empty] | Number of shop drawing review conducted | 480 | [23 empty] | Did DevCo adhere to Technical Submittals Review Cycle Time (RCT)? | Yes | Quality | 2.72 | Adherence to Design | 2.6 | Good | Did DevCo adhere to Technical Submittals Review Cycle Time (RCT)? | Time taken for closure of technical queries | Yes |  |  | Is there an impact assessment report or identified process/ guidelines to evaluate the impact of the innovation / smart city technologies adoption on DevCo performance? | 0.6 | Satisfactory | [6 empty] | Comprehensive Coverage of Key Performance Areas | 3 | [30 empty] | Yes | LOD Documented (drawing sample from Design Report)
Qiddiya | [14 empty] | Was there any Cost Overrun because of unidentified risk? | Yes, but less than 1% |  |  | Satisfactory | [17 empty] | Number of material / product substitution requests | [32 empty] | Technical Submittal Review Cycle Time (RCT) | Yes | [11 empty] | Continuous Improvement and Review | 3 | [25 empty] | Yes | Good | Have all projects adopted digital delivery using BIM and/or GIS? |  |  | Yes | % of projects adopting digital delivery using BIM/GIS
Qiddiya | [14 empty] | Risk Control Rate of the identified risks at DevCo Level | 0.6 |  |  | Satisfactory | [17 empty] | Average time to approve product sample & materials | [24 empty] | % of approved shop drawing reviews vs planned | 0.99167 |  |  |  |  | Good | % of approved shop drawing reviews vs planned | Total number of shop drawing review requests | 480 | [11 empty] | Total Positions | 500 | [23 empty] | Design Management Maturity | 2.6 | Yes | Good | Is project delivery occurring in accordance with the latest approved design strategy? | Design Management | 2.6 | Yes | Date of Latest Approved Design Strategy
Qiddiya | [36 empty] | Product & Material Approval Rate | [32 empty] | Total number of shop drawing reviews approved | 476 | [11 empty] | Vacant Positions | 100 | [25 empty] | 0.1 | Needs Improvement | % of projects with completed technical design/peer reviews and verifications/certifications as required for the latest Design Stage Gate |  |  | 0.1 | Number of projects with completed design reviews and verification register
Qiddiya | [14 empty] | Is the DevCo fully compliant with Risk Management Plan requirements? | No |  |  | Needs Improvement | [17 empty] | Number of as-built drawing review conducted | 485 | [23 empty] | % of approved product waivers vs product specified | 1 |  |  |  |  | Good | % of approved product waivers vs product specified | Total number of product sample & material approvals requested | 0.3 |  |  | Is there evidence for innovation / smart city technologies successful implementation (in final design report, master plan or other)? | Yes | Good | [6 empty] | Management Positions | 50 | [25 empty] | 0.85 | Good | % of Corrective Actions closed |  |  | 40 | Total Corrective Actions
Qiddiya | [14 empty] | Is there a difference in the time impact forecast before and after the risk event has triggered? | Yes, but less than 2 weeks |  |  | Satisfactory | [17 empty] | Average time to approve As-built rejections / iterations | [32 empty] | Total number of product sample & materials approved | 0.6 | [11 empty] | Vacant Management Positions | 5 | [30 empty] | 34 | Number of Closed Corrective Actions
Qiddiya | [14 empty] | Is there a difference in the Cost impact forecast before and after the risk event has triggered? | Yes, but less than 0.5% |  |  | Satisfactory | [17 empty] | As-Built Drawing Approval Rate | [24 empty] | % of Certified As-Built Drawing Packages vs Planned | 0.75 |  |  |  |  | Satisfactory | % of Certified As-Built Drawing Packages vs Planned | Number of As-Built Drawing review requests | 500 |  |  | Are there Pilot or R&D projects conducted? | 0.55 | Needs Improvement | 1 | Pilot and R&D Transition Rate | [31 empty] | 14 | Satisfactory | Average Cycle time to close corrective actions |  |  | 14 | Days taken to Close Corrective Actions
Qiddiya | [36 empty] | Average time to complete MIRs and close out approvals | [32 empty] | Number of As-Built Drawings reviews approved | 475 | [38 empty] | Yes | Good | Is the average cycle time to complete reviews and certifications in accordance with the Design Management Report? |  |  | Yes | Days taken to complete Design Reviews
Qiddiya | [36 empty] | Average time to complete WIRs and close out approvals | [24 empty] | MIR Inspection Rate | 0.98333 |  |  |  |  | Good | MIR Inspection Rate | Total number of MIRs requested | 120 | [38 empty] | Yes | Good | Has the DevCo engaged independent certification of major critical elements? |  |  | Yes | Level of review and verification required for Stage Gate
Qiddiya | [36 empty] | Number of NCRs open for between 30 and 60 days | 23 | [31 empty] | Total number of MIRs inspected | 118 | [36 empty] | Environmental Compliance Status | 2 | No | Needs Improvement | Are all project designs integrated with Regional Infrastructure & Mobility Plans? | Regulatory Compliance | 2.12 | No | Regional Strategies
Qiddiya | [36 empty] | Number of NCRs open for more than 60 days | 5 | [23 empty] | MIR Acceptance and Approval Rate | 0.66 |  |  |  |  | Satisfactory | MIR Acceptance and Approval Rate | Total number of MIRs approved | 110 |  |  | % of pilot / R&D Projects Transitioned into Full-Scale | 0.13043 | Needs Improvement | [33 empty] | Yes | Good | Do all projects comply with environmental guidelines in accordance with ESIA? |  |  | Yes | Extent of compliance to environmental guidelines
Qiddiya | [36 empty] | Leadership engagement | Satisfactory | [23 empty] | WIR Inspection Rate | 0.97143 |  |  |  |  | Good | WIR Inspection Rate | Total number of WIRs requested | 350 | [36 empty] | Authority Compliance Status | 2.2 | 0.15 | Satisfactory | % of projects with Code Compliance Violations |  |  | 0.15 | Total Number of Code Compliance Violations
Qiddiya | [36 empty] | Total number of ITPs requested | 100 | [31 empty] | Total number of WIRs inspected | 340 | [38 empty] | 1.0476 | Good | % of approved deviation waivers against compliant codes & standards |  |  | 21 | Total Waiver Applications Submitted
Qiddiya | [36 empty] | Total number of ITPs attended | 98 | [23 empty] | WIR Acceptance and Approval Rate | 0.67 |  |  |  |  | Satisfactory | WIR Acceptance and Approval Rate | Total number of WIRs approved | 335 | [43 empty] | 22 | Total Waivers Approved
Qiddiya | [36 empty] | Total number of ITPs approved | 87 | [23 empty] | Does the frequency of Audits align with the QMP? | Yes |  |  | Quality Assurance / Quality Control (QA/QC) | 3 | Good | Does the frequency of Audits align with the QMP? | Required Audit frequency | Yes |  |  | Availability of Innovation unit / department with structured team | 0 | Needs Improvement | 1.5 | Organization Maturity Towards Innovation Adoption | [31 empty] | Yes | Good | Have all required Stakeholder Submittals been issued? |  |  | Yes | Stakeholder Submittal Date
Qiddiya | [36 empty] | Total number of ITPs completed | 85 | [23 empty] | % closure of Non-Conformance Reports (NCR) | 0.96667 |  |  |  |  | Good | % closure of Non-Conformance Reports (NCR) | Total number of defects & NCRs | 150 | [38 empty] | 0.31746 | Needs Improvement | % of time critical Stakeholder Approvals Pending impacting Design Stage Gate completion |  |  | 0.2 | Number of Stakeholder Approvals Pending
Qiddiya | [36 empty] | Total number Quality Reports completed | [32 empty] | Total number of closed defects & NCRs | 145 | [43 empty] | 0.63 | Total number of stakeholder approvals required
Qiddiya | [36 empty] | Completeness of Quality Management Plan | Satisfactory | [23 empty] | Average NCRs closeout Cycle Time | 8 |  |  |  |  | Good | Average NCRs closeout Cycle Time | Average time to close NCRs | 5 Weeks | [38 empty] | Yes | Good | Does the Stakeholder Engagement Plan include proactive communication process to ensure timley coordination and approvals? |  |  | Yes | Scheduled Design Stage Gate Completion
Qiddiya | [36 empty] | Required number of ITPs signed off throughout construction | Needs Improvement | [23 empty] | % of procurement packages delivered within the planned lead times defined in the PMP | 2 | Procurement | 1.97 | Procurement & Contracting Compliance | 2.6 | Good | % of procurement packages delivered within the planned lead times defined in the PMP | Planned Procurement Package Lead Time | 5 |  |  | Availability of Innovation and Technology Strategy / Process & Framework | 0.5 | Satisfactory | [33 empty] | 0.19048 | Needs Improvement | % of Stakeholder Comments Closed |  |  | 21 | Total Stakeholder Comments
Qiddiya | [36 empty] | Total number of raised closed-out defects & NCRs | [32 empty] | Actual Procurement Package Delivery Time | 10 | [43 empty] | 4 | Stakeholder Comments Closed
Qiddiya | [36 empty] | Forecasted Procurement Budget | [24 empty] | % of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures | 0.875 |  |  |  |  | Good | % of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures | Total number of claims and variations | 800 | [36 empty] | DevCo ESG Target Achievement | 1 | 0 | Needs Improvement | % of projects achieving DevCo ESG Targets | ESG Target Realization | 1 | 1 | Planned ESG Target
Qiddiya | [36 empty] | Actual Procurement Budget | [32 empty] | Total number of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures | 700 | [43 empty] | 0 | Actual ESG Target
Qiddiya | [36 empty] | Vendor Database | [24 empty] | % of packages procured with 100% complete, compliant and well-structured documentation | 0.6 |  |  |  |  | Satisfactory | % of packages procured with 100% complete, compliant and well-structured documentation | Total number of packages | 0.5 | [36 empty] | Global ESG Target Alignment | 1 | No | Needs Improvement | Does the DevCo ESG Target align with globally recognized Best Practice Targets? |  |  | No | Alignment with globally recognized Best Practice Targets
Qiddiya | [36 empty] | Vendor Shortlist | [32 empty] | Total number of packages procured with 100% complete, compliant and well-structured documentation | 0.3
Qiddiya | [36 empty] | Vendor Awarded | [24 empty] | % of awarded contracts where vendors appointed passed full due diligence checks | 0.45 |  |  |  |  | Needs Improvement | % of awarded contracts where vendors appointed passed full due diligence checks | No. of awarded contracts where vendors appointed passed full due-diligence checks | 0.9
Qiddiya | [36 empty] | Vendor KPIs | [32 empty] | Total number of awarded contracts | 0.7
Qiddiya | [36 empty] | Vendor Performance Database | [24 empty] | Did the DevCo complete a Supply Chain Risk-Market Intelligence Assessment in the last quarter? | Yes |  |  |  |  | Good | Did the DevCo complete a Supply Chain Risk-Market Intelligence Assessment in the last quarter? | Supply Chain Risk-Market Intelligence Assessment | Yes
Qiddiya | [36 empty] | Tender return date: Planned / Actual | [24 empty] | % of procurement activities executed as planned in the Annual Procurement Plan | 0.66667 |  |  | Procurement & Contracting Execution Performance | 1.7 | Needs Improvement | % of procurement activities executed as planned in the Annual Procurement Plan | Total number of procurement activities | 129
Qiddiya | [36 empty] | Tender Review & award time: Planned / actual | [32 empty] | Number of procurement activities executed as planned | 86
Qiddiya | [36 empty] | Pre-Tender Cost Estimate | [24 empty] | % of deviations in total awarded contract value with tender cost estimates | 0.4 |  |  |  |  | Satisfactory | % of deviations in total awarded contract value with tender cost estimates | Value of Awarded Contract | 0.1
Qiddiya | [36 empty] | Tender Performance Index | [32 empty] | Tender Cost Estimate | 0.06
Qiddiya | [36 empty] | Contract clauses | [24 empty] | % of contracts with filed claims | 0.3 |  |  |  |  | Satisfactory | % of contracts with filed claims | Number of contracts with filed claims | 0.3
Qiddiya | [36 empty] | Procurement Management Plan | Satisfactory | [23 empty] | Are Payment Certificates and payments being processed in accordance with the Contract terms and conditions? | Yes |  |  |  |  | Good | Are Payment Certificates and payments being processed in accordance with the Contract terms and conditions? | Processing of payment certificates and payments | 80
Qiddiya | [36 empty] | Scope / design maturity | Good | [23 empty] | Are Vendor performance assessment occurring which capture financial instability, delays, repeated quality issues in real-time? | No |  |  |  |  | Needs Improvement | Are Vendor performance assessment occurring which capture financial instability, delays, repeated quality issues in real-time? | Alignment of sourcing strategies with project schedules and requirements | No
Qiddiya | [36 empty] | Compliance with local content regulations / policies | Satisfactory | [23 empty] | Does the HSE Management Manual have adequate provision for identification and escalation of high risk activities? | Yes | HSE and Welfare | 2.135 | HSE Compliance | 1.87 | Good | Does the HSE Management Manual have adequate provision for identification and escalation of high risk activities? | Escalation criteria for high risk activities | Yes
Qiddiya | [36 empty] | Dispute rate | [24 empty] | Is the rate of review of the Safety Risk Register in accordance with the HSE Management Manual? | Yes |  |  |  |  | Good | Is the rate of review of the Safety Risk Register in accordance with the HSE Management Manual? | HSE Risk Register Review Rate | Yes
Qiddiya | [36 empty] | Claims processing cycle time | [24 empty] | % of closed Safety Risk items | 0.83333 |  |  |  |  | Good | % of closed Safety Risk items | Total number of Safety Risk items | 0.9
Qiddiya | [36 empty] | No. of related CRs being requested during or after tendering phase due to identified scope gap | [32 empty] | Total number of closed Safety Risk items | 0.75
Qiddiya | [36 empty] | Vendor Performance Assessment | [24 empty] | Average cycle time to close Safety Risk items | 14 Days |  |  |  |  | Needs Improvement | Average cycle time to close Safety Risk items | Cycle time to close Safety Risk items | 14 Days
Qiddiya | [36 empty] | Tender pack quality | Good | [23 empty] | Average cycle time to close Safety Incident | 0.65 |  |  |  |  | Good | Average cycle time to close Safety Incident | Cycle time to close Safety Incident | 20
Qiddiya | [36 empty] | % payment paid within contractual terms | 0.75 | [31 empty] | Total number of closed safety incidents | 13
Qiddiya | [36 empty] | Planned Packages | [24 empty] | Is the emergency drill rate compliant with EEPP? | No |  |  |  |  | Needs Improvement | Is the emergency drill rate compliant with EEPP? | Planned number of Emergency Drills | 35
Qiddiya | [36 empty] | Awarded Packages | [32 empty] | Actual number of Emergency Drills | 20
Qiddiya | [36 empty] | Trade Most at Risk | [32 empty] | Recommended time to complete Emergency drills | 5 Days
Qiddiya | [36 empty] | Highest Risk Work Site | [32 empty] | Actual Time to complete Emergency drills | 10 Days
Qiddiya | [36 empty] | Number of planned audits | [24 empty] | Fatality Rate (FR) | 5 |  |  |  |  | Needs Improvement | Fatality Rate (FR) | No. of incidents resulting in fatality or severe impairment per 200,000 work hours | 5
Qiddiya | [36 empty] | Number of conducted audits | [24 empty] | Lost Time Injury Frequency Rate (LTIFR) | 10 |  |  |  |  | Needs Improvement | Lost Time Injury Frequency Rate (LTIFR) | No. of incidents resulting in lost time per 200,000 work hours | 10
Qiddiya | [36 empty] | Number of Notifiable Incidents | 4 | [23 empty] | Total Recordable Incident Rate (TRIR) | 30 |  |  |  |  | Needs Improvement | Total Recordable Incident Rate (TRIR) | No. of recordable incidents per 200,000 work hours | 30
Qiddiya | [36 empty] | Number of Infringement Notices | 6 | [23 empty] | Near Miss Rate | 60 |  |  |  |  | Good | Near Miss Rate | No. of near misses recorded per 200,000 work hours | 60
Qiddiya | [36 empty] | Total Safe Manhours | 2 | [23 empty] | Safety Observation Rate | 80 |  |  |  |  | Satisfactory | Safety Observation Rate | No. of safety observation recorded per 200,000 work hours | 80
Qiddiya | [36 empty] | Total number of closed Corrective actions | 2 | [23 empty] | Leadership Safety Walk Rate | 0.6 |  |  |  |  | Satisfactory | Leadership Safety Walk Rate | Total number of Safety Walks | 50
Qiddiya | [36 empty] | Inspection Pass Rate | 1 | [31 empty] | Total number of Safety Walks with Leadership | 30
Qiddiya | [36 empty] | No. of recurring incidents / safety observations outside control | [24 empty] | % of Grievances Closed | 1 |  |  | Welfare Compliance | 2.4 | Good | % of Grievances Closed | Number of grievances closed | 5
Qiddiya | [36 empty] | Total Site Manhours | 250000000 | [31 empty] | Total number of grievances | 5
Qiddiya | [36 empty] | Welfare of labor camps | 180000000 | [23 empty] | Average Cycle Time to Close Grievances | Good |  |  |  |  | Needs Improvement | Average Cycle Time to Close Grievances | Cycle time to close grievances | Good
Qiddiya | [36 empty] | Welfare of site facilities | [24 empty] | % of Welfare Staff vs Total workforce | Good |  |  |  |  | Good | % of Welfare Staff vs Total workforce | Percentage of Welfare Staff against total staff | Good
Qiddiya | [36 empty] | Labor accommodation inspection rate | [24 empty] | % closed welfare observations or red flag if 0 observations | 0.75 |  |  |  |  | Good | % closed welfare observations or red flag if 0 observations | Total number of Welfare Observations | 20
Qiddiya | [36 empty] | Regulation Compliance | [32 empty] | Total number of Closed Welfare Observations | 15
Qiddiya | [61 empty] | % of Welfare Non-compliances closed | 0.58 |  |  |  |  | Needs Improvement | % of Welfare Non-compliances closed | Total Welfare Non-compliances | 100
Qiddiya | [69 empty] | Total Closed Welfare Non-compliances | 58
Qiddiya | [61 empty] | Average Cycle Time to Close Welfare Non-compliances | 10 Days |  |  |  |  | Needs Improvement | Average Cycle Time to Close Welfare Non-compliances | Cycle time to close Welfare Non-Compliances | 10 Days
Qiddiya | [61 empty] | Is frequency of Labor Accommodation Inspection occurring in accordance with VMMP? | Yes |  |  |  |  | Good | Is frequency of Labor Accommodation Inspection occurring in accordance with VMMP? | Mitigation measures in the event of welfare audit observations & recommendations | Yes
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya
Qiddiya

## Glossary
SN | Section | Term | Description
1 | Cost Estimation & Optimization | Actual Cost (AC) | Actual Cost is the total cost incurred for work completed on a project at a given point in time. It includes all direct and indirect costs spent on labor, materials, equipment, and other expenses.
2 | Cost Estimation & Optimization | Aggregated Budget Variance | Cumulative difference between total budgeted figures and actual results across multiple categories or projects, highlighting overall financial performance deviations within a specific period
3 | Planning & Monitoring | Aggregated SPI | Indication of overall schedule performance at DevCo level
4 | Development & Construction | Annual Procurement Plan / Strategy | The Procurement Plan is required to be reviewed and updated by the DevCo as a minimum annually and submitted to PIF for approval in accordance with the requirements of the Project Execution Plan.
5 | General | Authority | Each development stage requires approval. The Authority is the relevant party responsible for the approval at the relevant stage (e.g. CEO, Founding Board etc.)
6 | Design & Technical | BUA | Built Up Area (BUA) is the total area being developed or constructed. It is the Gross Floor Area (GFA) plus Parking plus any Service Area.
7 | Cost Estimation & Optimization | Budget Variance (BV) | Extent of variance in budget
8 | Cost Estimation & Optimization | Budget At Completion (BAC) | The Budget at Completion (BAC) represents the total budgeted cost for all the work planned for a project
9 | Cost Estimation & Optimization | Estimate To Complete (ETC) | The estimated cost required to complete the remaining work of a project
10 | Cost Estimation & Optimization | Estimate At Completion (EAC) | Total forecasted cost of the project based on the ongoing
11 | General | Business Plan | Documentation developed by PIF informing the Vision and key objectives of the project
12 | General | Change Management Log | A document summarising the status of all proposed and approved Variations
13 | General | Change Management Procedure | Procedural document stipulating the requirements to be met when administering any amendment to a Contract or Project.
14 | Cost Estimate & Optimization | Contingency Utilization Rate (CUR) | Percentage of a project’s allocated contingency fund that has been used to address unforeseen costs or risks, reflecting the efficiency of contingency planning and management.
15 | Development & Construction | Contract Management Policy | A policy outlining award and management of contracts between DevCo and Vendors.
16 | Cost Estimate & Optimization | Cost Estimate and Optimization (CE&O) | Technical function which covers cost benchmarks for development of budgets, and cost optimization levers
17 | Cost Estimate & Optimization | Cost Report | A document provided on an interim basis to inform of the current financial status of a Project
18 | Design & Technical | Design and Technical (D&T) | Technical Function which covers all design-related topics of a project including architecture, engineering, masterplanning, infrastructure and environment & sustainability
19 | Development & Construction | Development and Construction (D&C) | Technical function which covers construction project execution plans, contract management and procurement, and construction quality and Health, Safety and Environment (HSE) topics
20 | Planning & Monitoring | Earned Value (EV) | Value of the work that is completed at a given time, measured against the budgeted cost.
21 | Planning & Monitoring | Extension of Time (EOT) | Extension of Time is a contractual provision in construction allowing the project completion date to be extended due to unforeseen delays beyond the contractor’s control, ensuring fairness and mitigating penalties.
22 | Design & Technical | Gross Floor Area (GFA) | Gross Floor Area (GFA) is the total floor area of a building including any underground saleable or leasable area but excluding parking and underground technical/service areas. The GFA is calculated based on the distance from external wall to external wall.
23 | Innovation & Technology | Innovation and Technology (I&T) | Technical function which covers incorporation of high-impact advanced technologies and methodologies across the entire project life cycle, and implementation of smart city use cases.
24 | Development & Construction | Inspection Test Plan (ITP) | A document which specifies the manatory Inspection, Witness and Hold Points throughout construction that must be verified by a suitably qualified person before works are authorised to proceed.
25 | General | Key Performance Indicator (KPI) | Key quantifiable indicators of progress toward an intended result
26 | Development & Construction | Non-Conformance Report (NCR) | Non-Conformance Report is a quality management document that identifies, tracks, and records deviations from specified standards, facilitating process improvement and quality control.
27 | Cost Estimate & Optimization | Planned Budget (PB) | It represents how much is expected to be spent at a given point in time from the Approved Over All Budget (BAC)
28 | Planning & Monitoring | Planned Value (PV) | The amount of work that was planned to be completed at a given time as per the approved Schedule.
29 | Planning & Monitoring | Planning and Monitoring (P&M) | Technical Function which covers schedule development and monitoring, and risk management
30 | Development & Construction | Procurement Strategy | Methodical approach for determining the contractural relationship and agreements between DevCo and Vendors
31 | Development & Construction | Procurement Procedures Manual | A manual which details every aspect of the tendering and overall procurement activities.
32 | Development & Construction | Project Execution Plan (PEP) | Project Execution Plan prepared initially by PIF as part of the Business Plan Stage, which is then passed to the DevCo to lead, review and update from Masterplan Stage onwards
33 | Development & Construction | Request For Information (RFI) | A formal communication tool for requesing information
34 | Development & Construction | Rework Cost | Indication of the rework done due to quality, design etc issues
35 | Planning & Monitoring | Schedule Performance Index (SPI) | Indication of project schedule performance
36 | Cost Estimate & Optimization | Soft Cost | Soft costs are indirect, non-physical expenses in a construction project that are not directly tied to labor, materials, or physical construction work.
37 | General | Stage | The description of the Project Stage as per Development Company and PIF terminology.
38 | Strategy & Operations | Strategy & Organization | Technical Function which covers topics around strategy development and execution, people and tools.
39 | Design & Technical | Value Engineering | Process to derive greater value within a Project seeking improvement in time and/ or cost outcomes
40 | Development & Construction | Vendor Database | A database of Vendors, including pre-qualified Vendors, Vendor appraisal and performance assessment and a list of blacklisted Vendors.
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100