## Main
0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | MEINHARDT | Administrator: | Admin
0.8
PLH
PROJECT LIGHTHOUSE
ASSESSMENT GUIDE
DIRIYAH
LOGIN
STRICTLY CONFIDENTIAL
þ Assessment In Progress
þ To Be Assessed
þ To Be Reviewed
þ In Review
þ Assessment Completed
Design
& Technical
(D&T)
Development
& Construction
(D&C)
Cost Estimation
& Optimization
(CE&O)
Innovation
& Technology
(I&T)
Strategy
& Operations
(S&O)
þ Assessment In Progress
þ To Be Assessed
þ To Be Reviewed
þ In Review
þ Assessment Completed
þ Assessment In Progress
þ To Be Assessed
þ To Be Reviewed
þ In Review
þ Assessment Completed
þ Assessment In Progress
þ To Be Assessed
þ To Be Reviewed
þ In Review
þ Assessment Completed
þ Assessment In Progress
þ To Be Assessed
þ To Be Reviewed
þ In Review
þ Assessment Completed
þ Assessment In Progress
þ To Be Assessed
þ To Be Reviewed
þ In Review
þ Assessment Completed
Planning
& Monitoring
(P&M)
UPDATE
DevCo Assessment Input (P&M)
DevCo Assessment Analysis (P&M)
DevCo Assessment Input (D&T)
DevCo Assessment Analysis (D&T)
DevCo Assessment Input (D&C)
DevCo Assessment Analysis (D&C)
DevCo Assessment Input (CE&O)
DevCo Assessment Analysis (CE&O)
DevCo Assessment Input (I&T)
DevCo Assessment Analysis (I&T)
DevCo Assessment Input (S&O)
DevCo Assessment Analysis (S&O)
Interview Question
(P&M)
Interview Question
(D&T)
Interview Question
(D&C)
Interview Question
(CE&O)
Interview Question
(I&T)
Interview Question
(S&O)
Additional Data Points (P&M)
Additional Data Points (D&T)
Additional Data Points (D&C)
Additional Data Points (CE&O)
Additional Data Points (I&T)
Additional Data Points (S&O)
Log
Instructions
Glossary & Definitions
Document List
User
Setting
Get Section Data
Assessment Summary
Q1 2025
Period of Assessment

## Instructions
PIF Project Lighthouse
Instructions
SN | Page | Role | Instructions
1 | Document List |  | This page lists all the documents submitted by the DevCo, which consist the location of the documents and the file names.
2 | DevCo Assessment Input |  | This page is used for the input of data points required for the assessment criteria
3 | DevCo Assessment Input | Assessor | Enter the assessment value for each data point in " INPUT VALUE" column. Note: 1) For non-quantitative AC, use the drop-down box to select the right option 2) The drop down box would have options across all the Assessment critera (AC) and hence you may see drop down values, which are not relevant to the specific AC. Please toggle to the Assessment Analysis page to identify the relevant options to input.
4 | DevCo Assessment Input | Assessor | Input the Document Request Number (for e.g., DR-017) under the "DATA SOURCE" column. Please refer to the Document List for the Document Request (DR) number
5 | DevCo Assessment Input | Assessor | Please note down any remarks in the Assessor Remarks column
6 | DevCo Assessment Input | Reviewer | Please review the findings with the Data Analyst/Assessor and update the "INPUT VALUE" column (if required). For any changes to the "INPUT VALUE" input or to make any additional remarks, please update the "REVIEWER REMARKS" column
7 | DevCo Assessment Analysis | All | A score of 'Good', 'Satisfactory', and 'Critical' will be automatically generated based on each Assessment Criteria's value
8 | DevCo Assessment Analysis | All | Please note down remarks, if any
9 | Interview Questions (IQs) |  | This page is used for the discussions with DevCos
10 | Interview Question | All | Predefined interview questions will be populated here and additional questions can be added as needed.
11 | Interview Question | All | Please note down the conversation/interview date in the "DATE OF INTERVIEW" column
12 | Interview Question | All | Please note down DevCo answers to the interview questions in " RESPONSE" Column
13 | Interview Question | All | Please note down any further queries in "FOLLOW UP QUESTIONS " for easy tracking
14 | Additional Data Points (ADPs) |  | This page is used for the input of additional data points which are not required for the assessment criteria but are needed for the dashboard
15 | Additional Data Points | Data Analyst / Assessor | Please populate the "VALUE" column for each Additional Data Points
Go to Main Page
Refresh

## Glossary&Definitions
PIF Project Lighthouse
Glossary&Definitions
SN | Section | Term | Description
1 | Cost Estimation & Optimization | Actual Cost (AC) | Actual Cost is the total cost incurred for work completed on a project at a given point in time. It includes all direct and indirect costs spent on labor, materials, equipment, and other expenses.
2 | Cost Estimation & Optimization | Aggregated Budget Variance | Cumulative difference between total budgeted figures and actual results across multiple categories or projects, highlighting overall financial performance deviations within a specific period
3 | Planning & Monitoring | Aggregated SPI | Indication of overall schedule performance at DevCo level
4 | Development & Construction | Annual Procurement Plan / Strategy | The Procurement Plan is required to be reviewed and updated by the DevCo as a minimum annually and submitted to PIF for approval in accordance with the requirements of the Project Execution Plan.
5 | General | Authority | Each development stage requires approval. The Authority is the relevant party responsible for the approval at the relevant stage (e.g. CEO, Founding Board etc.)
6 | Design & Technical | BUA | Built Up Area (BUA) is the total area being developed or constructed. It is the Gross Floor Area (GFA) plus Parking plus any Service Area.
7 | Cost Estimation & Optimization | Budget Variance (BV) | Extent of variance in budget
8 | Cost Estimation & Optimization | Budget At Completion (BAC) | The Budget at Completion (BAC) represents the total budgeted cost for all the work planned for a project
9 | Cost Estimation & Optimization | Estimate To Complete (ETC) | The estimated cost required to complete the remaining work of a project
10 | Cost Estimation & Optimization | Estimate At Completion (EAC) | Total forecasted cost of the project based on the ongoing
11 | General | Business Plan | Documentation developed by PIF informing the Vision and key objectives of the project
12 | General | Change Management Log | A document summarising the status of all proposed and approved Variations
13 | General | Change Management Procedure | Procedural document stipulating the requirements to be met when administering any amendment to a Contract or Project.
14 | Cost Estimate & Optimization | Contingency Utilization Rate (CUR) | Percentage of a project’s allocated contingency fund that has been used to address unforeseen costs or risks, reflecting the efficiency of contingency planning and management.
15 | Development & Construction | Contract Management Policy | A policy outlining award and management of contracts between DevCo and Vendors.
16 | Cost Estimate & Optimization | Cost Estimate and Optimization (CE&O) | Technical function which covers cost benchmarks for development of budgets, and cost optimization levers
17 | Cost Estimate & Optimization | Cost Report | A document provided on an interim basis to inform of the current financial status of a Project
18 | Design & Technical | Design and Technical (D&T) | Technical Function which covers all design-related topics of a project including architecture, engineering, masterplanning, infrastructure and environment & sustainability
19 | Development & Construction | Development and Construction (D&C) | Technical function which covers construction project execution plans, contract management and procurement, and construction quality and Health, Safety and Environment (HSE) topics
20 | Planning & Monitoring | Earned Value (EV) | Value of the work that is completed at a given time, measured against the budgeted cost.
21 | Planning & Monitoring | Extension of Time (EOT) | Extension of Time is a contractual provision in construction allowing the project completion date to be extended due to unforeseen delays beyond the contractor’s control, ensuring fairness and mitigating penalties.
22 | Design & Technical | Gross Floor Area (GFA) | Gross Floor Area (GFA) is the total floor area of a building including any underground saleable or leasable area but excluding parking and underground technical/service areas. The GFA is calculated based on the distance from external wall to external wall.
23 | Innovation & Technology | Innovation and Technology (I&T) | Technical function which covers incorporation of high-impact advanced technologies and methodologies across the entire project life cycle, and implementation of smart city use cases.
24 | Development & Construction | Inspection Test Plan (ITP) | A document which specifies the manatory Inspection, Witness and Hold Points throughout construction that must be verified by a suitably qualified person before works are authorised to proceed.
25 | General | Key Performance Indicator (KPI) | Key quantifiable indicators of progress toward an intended result
26 | Development & Construction | Non-Conformance Report (NCR) | Non-Conformance Report is a quality management document that identifies, tracks, and records deviations from specified standards, facilitating process improvement and quality control.
27 | Cost Estimate & Optimization | Planned Budget (PB) | It represents how much is expected to be spent at a given point in time from the Approved Over All Budget (BAC)
28 | Planning & Monitoring | Planned Value (PV) | The amount of work that was planned to be completed at a given time as per the approved Schedule.
29 | Planning & Monitoring | Planning and Monitoring (P&M) | Technical Function which covers schedule development and monitoring, and risk management
30 | Development & Construction | Procurement Strategy | Methodical approach for determining the contractural relationship and agreements between DevCo and Vendors
31 | Development & Construction | Procurement Procedures Manual | A manual which details every aspect of the tendering and overall procurement activities.
32 | Development & Construction | Project Execution Plan (PEP) | Project Execution Plan prepared initially by PIF as part of the Business Plan Stage, which is then passed to the DevCo to lead, review and update from Masterplan Stage onwards
33 | Development & Construction | Request For Information (RFI) | A formal communication tool for requesing information
34 | Development & Construction | Rework Cost | Indication of the rework done due to quality, design etc issues
35 | Planning & Monitoring | Schedule Performance Index (SPI) | Indication of project schedule performance
36 | Cost Estimate & Optimization | Soft Cost | Soft costs are indirect, non-physical expenses in a construction project that are not directly tied to labor, materials, or physical construction work.
37 | General | Stage | The description of the Project Stage as per Development Company and PIF terminology.
38 | Strategy & Operations | Strategy & Organization | Technical Function which covers topics around strategy development and execution, people and tools.
39 | Design & Technical | Value Engineering | Process to derive greater value within a Project seeking improvement in time and/ or cost outcomes
40 | Development & Construction | Vendor Database | A database of Vendors, including pre-qualified Vendors, Vendor appraisal and performance assessment and a list of blacklisted Vendors.
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
Go to Main Page
Refresh

## DocumentList
PIF Project Lighthouse
DocumentList
SN | Document Request ID (Sharepoint) | Document Request | DevCo or Project Level | Document Number | File Name | Date Received | Remarks
1 | Cost Data | Cost Data Template | DevCo
2 | 1 | Baseline and Updated Master schedule (including cost linked Milestone summary for earned value, planned value analysis, Monthly Progress Report and Schedule Updates) | DevCo
3 | 2 | Program Management Plan | DevCo | DR-002-01 | 15th April - Updated DGCL DoA 7 | 2025-05-07 21:29
4 |  |  |  | DR-002-02 | Completion, Handover & Opening (Policy and Process Manual) | 2025-05-07 21:29
5 |  |  |  | DR-002-03 | Development Managment Policy Process Manual_ | 2025-05-07 21:29
6 |  |  |  | DR-002-04 | GCEO Signed Sub-DOA V2 7 | 2025-05-07 21:29
7 |  |  |  | DR-002-05 | 2025.03.20 Periodic Schedule Update - Two Step Approach | 2025-05-07 21:29
8 |  |  |  | DR-002-06 | SW-SWD-550-0000-MAC-GDL-PC-000042 - Integrated Master Schedule Update | 2025-05-07 21:29
9 |  |  |  | DR-002-07 | SW-SWD-550-0000-MAC-PLN-PC-000003 - Schedule Management Plan | 2025-05-07 21:29
10 |  |  |  | DR-002-08 | SW-SWD-550-0000-MAC-PRO-PC-000025 - Integrated Master Schedule Update | 2025-05-07 21:29
11 | 3 | Latest Approved Monthly Progress Report | DevCo | DR-003-01 | DevCo President Commercial Update - Dec -2024 | 2025-05-07 21:29
12 |  |  |  | DR-003-02 | 241226-DC-PMO-GCEO Programme Update - DI DII HD&WH WS | 2025-05-07 21:29
13 |  |  |  | DR-003-03 | 241226-DC-PMO-GCEO Report DI DII HD&WH WS - Dec-24 | 2025-05-07 21:29
14 |  |  |  | DR-003-04 | DevCo President Commercial Update - Dec -2024 | 2025-05-07 21:29
15 | 4 | Change request register (covering latest approved schedule extension requests) | DevCo
16 | 5 | Latest approved risk mapping / risk register (including mitigation plans) documented at DevCo level and the list of Stakeholders | DevCo | DR-005-01 | 00-000-000-0000-MAC-REG-RK-000002(17) DC Portfolio Risk Register_Mar25 (1) | 2025-05-07 21:29
17 |  |  |  | DR-005-02 | 00-000-000-0000-MAC-REG-RK-000003(16) DC Portfolio Issue Register_Mar25 | 2025-05-07 21:29
18 |  |  |  | DR-005-03 | Risk Management Dashboard_New | 2025-05-07 21:29
19 |  |  |  | DR-005-04 | SW-SWD-550-0000-MAC-PRE-RK-000002(11) Principal Risk and Issue Mtg Presentation_Feb25_Final (1) | 2025-05-07 21:29
20 |  |  |  | DR-005-05 | SW-SWD-550-0000-MAC-ROM-RK-000002(08) DC Principal Risk Meeting Minutes_Feb25 | 2025-05-07 21:29
21 | 6 | Lookahead Schedules / Short-term execution plans (e.g., 4-week or 6-week lookahead) | DevCo | DR-006-01 | DC - DevCo Risk Management Procedure (Rev 00) signed | 2025-05-07 21:29
22 | 7 | Sample of project level approved risk register | Project
23 | 8 | Risk Management Plan | DevCo
24 | 9 | Updated Cost report | DevCo
25 | 10 | Program Tracker | DevCo
26 | 11 | Original Approved and Latest version of CGI & Animation (Material Palette & Finish Schedule) at DevCo Level | Project
27 | 12 | Original Approved and Latest version of the Drawings | DevCo
28 | 13 | DevCo Design & Technical Guidelines (including Look & Feel Design Guidelines) | DevCo | DR-013-01 | 123DG_GUIDELINES_Part III_RWK.PDF | 2025-05-07 21:29
29 |  |  |  | DR-013-02 | 240117 [1] DII Residential Design Guidelines.PDF | 2025-05-07 21:29
30 |  |  |  | DR-013-03 | FLS Guidelines | 2025-05-07 21:29
31 |  |  |  | DR-013-04 | MEP Guidelines | 2025-05-07 21:29
32 |  |  |  | DR-013-05 | Structural Guidelines | 2025-05-07 21:29
33 | 14 | Return Brief Report (including approved and latest Asset Area Schedule & Population) | Project
34 | 15 | Latest Stage Gate Cost Plan (Project level) | Project
35 | 16 | Report including constructability feasibility and construction packaging including enabeling work and methodology | Project
36 | 17 | Digital Information Management Plan | DevCo | DR-017-01 | 20231022 Spatial Data GIS Requirements | 2025-05-07 21:29
37 |  |  |  | DR-017-02 | SW-SWD-550-0000-DGD-STD-BM-000001 Employer Information Requirements. | 2025-05-07 21:29
38 |  |  |  | DR-017-03 | SW-SWD-550-0000-DGD-STD-BM-000002 Appendix 01 - Asset Information Requirements | 2025-05-07 21:29
39 |  |  |  | DR-017-04 | SW-SWD-550-0000-DGD-STD-BM-000003 Appendix 01.1-Asset Information Data Structure & Classification. | 2025-05-07 21:29
40 |  |  |  | DR-017-05 | SW-SWD-550-0000-DGD-STD-BM-000004 Appendix 01.2 -Asset Classification&Information Mapping | 2025-05-07 21:29
41 | 18 | Latest Project Execution Plan (including Design Strategy, Packaging Strategy and Phasing Strategy) | DevCo | DR-018-01 | DG2 High Level Delivery Strategy_Final r15MAR25_FK | 2025-05-07 21:29
42 | 19 | Design Master Schedule | DevCo
43 | 20 | Procedures and Governance for design approvals and change management | DevCo | DR-020-01 | Change Approval Map | 2025-05-07 21:29
44 | 21 | Design Basis Report and Stage Gate Design Report (including Design Management Report, Design Reviews & Verifications Register) | Project
45 | 22 | Infrastructure and Engineering report (including Water, Energy, Waste, Infrastructure & Mobility Plans) | DevCo
46 | 23 | Environmental and Social Impact Assessment | DevCo | DR-023-01 | 1. Enviromental Permit GAMEP - DGI - Arabic | 2025-05-07 21:29
47 |  |  |  | DR-023-02 | 2. Environmental permit GAMEP- DGI - Translation | 2025-05-07 21:29
48 |  |  |  | DR-023-03 | 3. Extension letter - Translation | 2025-05-07 21:29
49 |  |  |  | DR-023-04 | 140920-Enviromental Permit GAMEP | 2025-05-07 21:29
50 |  |  |  | DR-023-05 | OG_GN_NCEC_44-8902_بشأن عدم الحاجة لتجديد التصاريح البيئية | 2025-05-07 21:29
51 |  |  |  | DR-023-06 | Diriyah Gate EIA report - 20feb20 | 2025-05-07 21:29
52 |  |  |  | DR-023-07 | Appendix A | 2025-05-07 21:29
53 |  |  |  | DR-023-08 | Appendix B | 2025-05-07 21:29
54 |  |  |  | DR-023-09 | Appendix C | 2025-05-07 21:29
55 |  |  |  | DR-023-10 | Appendix D | 2025-05-07 21:29
56 |  |  |  | DR-023-11 | DG002-KEO-CM-TCR-0000049_OACEMP_rev06 | 2025-05-07 21:29
57 |  |  |  | DR-023-12 | appendix_a_diriyah_gate_development_bujairi_samhan_wh_epc | 2025-05-07 21:29
58 |  |  |  | DR-023-13 | appendix_a_diriyah_gate_development_epc | 2025-05-07 21:29
59 |  |  |  | DR-023-14 | appendix_B_current_contracts_information_08122024 | 2025-05-07 21:29
60 |  |  |  | DR-023-15 | Appendix_C_unpaved_road_chemical_treatment_08122024 | 2025-05-07 21:29
61 |  |  |  | DR-023-16 | Appendix_D_waste_signage_08032024 | 2025-05-07 21:29
62 |  |  |  | DR-023-17 | appendix_E_soil_sampling_and_analysis_procedure_08122024 | 2025-05-07 21:29
63 |  |  |  | DR-023-18 | incident_reporting_forms_investigation_08122024 | 2025-05-07 21:29
64 |  |  |  | DR-023-19 | incident_reporting_forms_notification_24-hr_08122024 | 2025-05-07 21:29
65 |  |  |  | DR-023-20 | mwan_approved_waste_licensed_parties | 2025-05-07 21:29
66 |  |  |  | DR-023-21 | ncec_approved_waste_licensed_parties | 2025-05-07 21:29
67 |  |  |  | DR-023-22 | appendix_H_legal_register_08122024 | 2025-05-07 21:29
68 |  |  |  | DR-023-23 | Appendix_I_waste_management_manifest_arabic | 2025-05-07 21:29
69 |  |  |  | DR-023-24 | Appendix_I_waste_management_manifest_english | 2025-05-07 21:29
70 |  |  |  | DR-023-25 | appendix_J_contractor's_cemp_specific_structure_08122024 | 2025-05-07 21:29
71 |  |  |  | DR-023-26 | appendix_K_CEMP_Compliance_checklist 08122024 | 2025-05-07 21:29
72 |  |  |  | DR-023-27 | appendix_L_demobilization_audit_checklist_08122024 | 2025-05-07 21:29
73 |  |  |  | DR-023-28 | appendix_M_non_conformance_report | 2025-05-07 21:29
74 |  |  |  | DR-023-29 | appendix_N_Pre_Construction-mobilization_audit_checklist_08122024 | 2025-05-07 21:29
75 |  |  |  | DR-023-30 | appendix_O_Air_Quality_Management_checklist_08032024 | 2025-05-07 21:29
76 |  |  |  | DR-023-32 | DG220-JCB-DE-TCR-000081-EIA-Rev03 | 2025-05-07 21:29
77 |  |  |  | DR-023-33 | DG220-JCB-DE-TCR-000063-02-Hydrology Study | 2025-05-07 21:29
78 |  |  |  | DR-023-34 | DG220-JCB-DE-TCR-000064-03 EPEP | 2025-05-07 21:29
79 |  |  |  | DR-023-35 | DG220-JCB-DE-TCR-000095-01_Traffic Noise Modelling Assessment | 2025-05-07 21:29
80 |  |  |  | DR-023-36 | DG220-JCB-DE-TCR-000085-03 Baseline Report | 2025-05-07 21:29
81 |  |  |  | DR-023-37 | DG220-JCB-DE-TCR-000096-02_Traffic ADM | 2025-05-07 21:29
82 |  |  |  | DR-023-38 | Visual Directory | 2025-05-07 21:29
83 |  |  |  | DR-023-39 | DG220-JCB-DE-TCR-000091-02_OCEMP | 2025-05-07 21:29
84 |  |  |  | DR-023-40 | DGII SW-MPL-008-0000-KEO-PLN-EN-000001 | 2025-05-07 21:29
85 |  |  |  | DR-023-41 | DG220-JCB-DE-TCR-000091-02_OCEMP | 2025-05-07 21:29
86 |  |  |  | DR-023-42 | 1. Environmental Permit NCEC - Wadi Safar - Arabic | 2025-05-07 21:29
87 |  |  |  | DR-023-43 | 2. Environmental Permit NCEC - Wadi Safar - Translation | 2025-05-07 21:29
88 |  |  |  | DR-023-44 | 3. Extension letter - Translated | 2025-05-07 21:29
89 |  |  |  | DR-023-45 | Volume 1 | 2025-05-07 21:29
90 |  |  |  | DR-023-46 | Volume 2 | 2025-05-07 21:29
91 |  |  |  | DR-023-47 | Appendix A - GAMEP License | 2025-05-07 21:29
92 |  |  |  | DR-023-48 | Appendix B - Legal and Statutory Requirements from General Authority of Meteorology and Environmental Protection (GAMEP) | 2025-05-07 21:29
93 |  |  |  | DR-023-49 | Appendix C - Ambient Air Quality and Noise Monitoring Report, LEAF Global, January 2020 | 2025-05-07 21:29
94 |  |  |  | DR-023-50 | Appendix D - Geotechnical Investigation Report (Extract), SAFCO, April 2020 | 2025-05-07 21:29
95 |  |  |  | DR-023-51 | Appendix E – Flood Study Report, Jacobs, August 2020 | 2025-05-07 21:29
96 |  |  |  | DR-023-52 | Appendix F – Preliminary Slope Assessment, BuroHappold, January 2020 | 2025-05-07 21:29
97 |  |  |  | DR-023-53 | Appendix G – Outline Environmental Construction Management Plan (O-CEMP) | 2025-05-07 21:29
98 |  |  |  | DR-023-54 | WS-000-000-0000-KEO-PLN-EN-000001OCEMP - Rev01 | 2025-05-07 21:29
99 |  |  |  | DR-023-55 | OG_GN_NCEC_44-8902_بشأن عدم الحاجة لتجديد التصاريح البيئية | 2025-05-07 21:29
100 |  |  |  | DR-023-56 | WS Env. Permit_200007170458 | 2025-05-07 21:29
101 |  |  |  | DR-023-57 | SW-SWD-551-0000-SET-GDL-EV-000004-Ver 01 - NTM Facility Bulletin-Revised_AK_KK_HJ (1) | 2025-05-07 21:29
102 |  |  |  | DR-023-58 | تعميم بشأن معالجة مخالفات رمي مخلفات البناء والحفريات في مدينة الرياض | 2025-05-07 21:29
103 |  |  |  | DR-023-59 | appendix_c_current_contracts_information_20230921 | 2025-05-07 21:29
104 |  |  |  | DR-023-60 | Appendix_d_unpaved_road_chemical_treatment_20230921 | 2025-05-07 21:29
105 |  |  |  | DR-023-61 | Appendix_e_waste_signage_20240330 | 2025-05-07 21:29
106 |  |  |  | DR-023-62 | appendix_f_soil_sampling_and_analysis_procedure_20230921 | 2025-05-07 21:29
107 |  |  |  | DR-023-63 | incident_reporting_forms_investigation_20230921 | 2025-05-07 21:29
108 |  |  |  | DR-023-64 | incident_reporting_forms_notification_24-hr_20230921 | 2025-05-07 21:29
109 |  |  |  | DR-023-65 | mwan_approved_waste_licensed_parties | 2025-05-07 21:29
110 |  |  |  | DR-023-66 | ncec_approved_waste_licensed_parties | 2025-05-07 21:29
111 |  |  |  | DR-023-67 | appendix_i_legal_register_20230921 | 2025-05-07 21:29
112 |  |  |  | DR-023-68 | DC Waste Manifest_Arabic | 2025-05-07 21:29
113 |  |  |  | DR-023-69 | DC Waste Manifest_English | 2025-05-07 21:29
114 |  |  |  | DR-023-70 | appendix_k_contractor's_cemp_specific_structure_20230921 | 2025-05-07 21:29
115 |  |  |  | DR-023-71 | Weekly Environment Inspection Report_Rev02 | 2025-05-07 21:29
116 |  |  |  | DR-023-72 | Pre_Mobilization_Environmental_Checklist_Rev06 Aug 24 | 2025-05-07 21:29
117 |  |  |  | DR-023-73 | DC_TEBS - Methodology Guideline_July 2024 | 2025-05-07 21:29
118 |  |  |  | DR-023-74 | Appendix_o_demobilization_audit_checklist_20230921 | 2025-05-07 21:29
119 |  |  |  | DR-023-75 | NCR - Non-Conformance Report | 2025-05-07 21:29
120 |  |  |  | DR-023-76 | Air Quality Management Checklist | 2025-05-07 21:29
121 |  |  |  | DR-023-77 | Monthly Environmental Report Rev 02 | 2025-05-07 21:29
122 |  |  |  | DR-023-78 | Quarterly CEMP Compliance Review Checklist | 2025-05-07 21:29
123 |  |  |  | DR-023-79 | KPIs and Scoring Criteria | 2025-05-07 21:29
124 |  |  |  | DR-023-80 | 1. DC_Environment Requirements_Contractors_Nov. 2023 | 2025-05-07 21:29
125 |  |  |  | DR-023-81 | 2. DC_Environment Requirements_CSC_Nov. 2023 | 2025-05-07 21:29
126 |  |  |  | DR-023-82 | 3. DC_Environment Requirements_PMC_Nov. 2023 | 2025-05-07 21:29
127 |  |  |  | DR-023-83 | DG-DSQ-000-0000-SSA-SCH-PC-000001(03) | 2025-05-07 21:29
128 |  |  |  | DR-023-84 | Oberoi Hotel CEMP | 2025-05-07 21:29
129 |  |  |  | DR-023-85 | DG-BUJ-106-0000-NSM-PLN-EN-000002 Rev.02 | 2025-05-07 21:29
130 |  |  |  | DR-023-86 | appendix_a_diriyah_gate_development_bujairi_samhan_wh_epc | 2025-05-07 21:29
131 |  |  |  | DR-023-87 | Appendix_d_unpaved_road_chemical_treatment_20230921 | 2025-05-07 21:29
132 |  |  |  | DR-023-88 | Appendix_D_waste_signage_08032024 | 2025-05-07 21:29
133 |  |  |  | DR-023-89 | appendix_g_soil_sampling_and_analysis_procedure_20230921 | 2025-05-07 21:29
134 |  |  |  | DR-023-90 | incident_reporting_forms_investigation_20230921 | 2025-05-07 21:29
135 |  |  |  | DR-023-91 | incident_reporting_forms_notification_24-hr_20230921 | 2025-05-07 21:29
136 |  |  |  | DR-023-92 | ZAB SIGNED AGREEMENT | 2025-05-07 21:29
137 |  |  |  | DR-023-93 | appendix_t_legal_register_20230921 | 2025-05-07 21:29
138 |  |  |  | DR-023-94 | Appendix_j_waste_management_manifest_arabic | 2025-05-07 21:29
139 |  |  |  | DR-023-95 | Appendix_j_waste_management_manifest_english | 2025-05-07 21:29
140 |  |  |  | DR-023-96 | appendix_l_contractor's_cemp_specific_structure_20230921 | 2025-05-07 21:29
141 |  |  |  | DR-023-97 | CEMP COMPLIANCE CHECKLIST | 2025-05-07 21:29
142 |  |  |  | DR-023-98 | appendix_M_demobilization_audit_checklist_20230921 | 2025-05-07 21:29
143 |  |  |  | DR-023-99 | appendix_N_non_conformance_report_20230921 | 2025-05-07 21:29
144 |  |  |  | DR-023-100 | appendix_N_Pre_Construction-mobilization_audit_checklist_08122024 | 2025-05-07 21:29
145 |  |  |  | DR-023-101 | Air Quality Management Checklist for Earthwork Activities - Template | 2025-05-07 21:29
146 |  |  |  | DR-023-102 | 02A. Schedule Narrative- Zallal P3 | 2025-05-07 21:29
147 |  |  |  | DR-023-103 | 02B. Baseline Schedule Zallal Package-3, Rev-04 (6-june-24) | 2025-05-07 21:29
148 |  |  |  | DR-023-104 | Overall Logistic Plan | 2025-05-07 21:29
149 |  |  |  | DR-023-105 | APPENDIX P – ENVIRONMENTAL TRAINING MATRIX | 2025-05-07 21:29
150 |  |  |  | DR-023-106 | DG-BUJ-106-0000-NSM-MTS-CE-000016 Rev.03 | 2025-05-07 21:29
151 |  |  |  | DR-023-107 | DG-BUJ-106-0000-NSM-MTS-CE-000024 Rev.02 | 2025-05-07 21:29
152 |  |  |  | DR-023-108 | DG-BUJ-106-0000-NSM-MTS-CE-000025 Rev.02 | 2025-05-07 21:29
153 |  |  |  | DR-023-109 | DG-BUJ-106-0000-NSM-MTS-CE-000026 | 2025-05-07 21:29
154 |  |  |  | DR-023-110 | DG-BUJ-106-0000-NSM-MTS-CE-000027 Rev.01 | 2025-05-07 21:29
155 |  |  |  | DR-023-111 | DG-BUJ-106-0000-NSM-ORG-AD-000001 Rev.02 | 2025-05-07 21:29
156 |  |  |  | DR-023-112 | Daily Checklist | 2025-05-07 21:29
157 |  |  |  | DR-023-113 | 1. MAINTENANCE RECORD WORK SHOP SEPTEMBER 2024 | 2025-05-07 21:29
158 |  |  |  | DR-023-114 | Spill Kits Checklist | 2025-05-07 21:29
159 |  |  |  | DR-023-115 | LIST OF CHEMICAL REPORT 322823 | 2025-05-07 21:29
160 |  |  |  | DR-023-116 | Drinking Water Checklist | 2025-05-07 21:29
161 |  |  |  | DR-023-117 | Waste Management Checklist | 2025-05-07 21:29
162 | 24 | Environmental Compliance Report | DevCo
163 | 25 | Register of Authority Engagement, Approvals and Waivers | DevCo
164 | 26 | Stakeholder Management Plan (including Stakeholder Engagement Plan and Stakeholder Management Tracker) | DevCo
165 | 27 | Baseline ESG Strategy and Latest Annual ESG Report | DevCo
166 | 28 | Construction Environmental and Social Management Plan (including Environmental Permit Register) | Project
167 | 29 | Construction Execution Plan | Project
168 | 30 | Site and Logistics Plan (including traffic simulations) | Project
169 | 31 | Interface Management Plan (including Stakeholder Management Plan*, Communication Plan & Contractor Staging Plan and Handover & Close-out Plan) | DevCo
170 | 32 | Workforce Planning Strategy | DevCo | DR-032 | IMS_Report-Dec'24-R2 | 2025-05-07 21:29
171 | 33 | Construction Progress Report (including workforce numbers) | Project
172 | 34 | Register of Technical Queries | Project
173 | 35 | Register of Shop Drawing Reviews | Project
174 | 36 | Register of Material & Product Approval / Change Requests | Project
175 | 37 | Register of As-Built Drawings | Project
176 | 38 | Register of Material Inspection Requests | Project
177 | 39 | Register of Work Inspection Requests | Project
178 | 40 | Quality Management Manual (QMP) | DevCo
179 | 41 | Latest Monthly Quality Report, including defects and NCR data | DevCo
180 | 42 | Inspection Test Plan (ITP) | Project
181 | 43 | Sample of project specific Project Quality Plan (PQP) | Project
182 | 44 | Latest Quality Audit Report | Project
183 | 45 | Procurement Management Plan (including annual procurement lookahead and pre-qualified vendor database) | DevCo | DR-045-01 | DR-045a Procurement Executive Dashboard | 2025-05-07 21:29
184 |  |  |  | DR-045-02 | DR-045b-PQQ & Shortlist Process Map | 2025-05-07 21:29
185 | 46 | Sample of Tender Award Report | Project
186 | 47 | Procurement and Contracting Risk Register | DevCo
187 | 48 | List of Appointed Vendors (including due-diligence checks) | DevCo | DR-048-01 | PSPR Extract Appendices | 2025-05-07 21:29
188 |  |  |  | DR-048-02 | PSPR Extract | 2025-05-07 21:29
189 | 49 | Supply Chain Risk Assessment | DevCo | DR-049 | Portfolio Risk and Issue Register Procurement-Extract | 2025-05-07 21:29
190 | 50 | Current Procurement Schedule | DevCo | DR-050 | DR-050 12 Month Forecast | 2025-05-07 21:29
191 | 51 | Sample of Signed Agreement / Awarded Contract | Project
192 | 52 | Sample of Supplier and Contractor Performance Report | DevCo | DR-052-01 | Jacobs Performance | 2025-05-07 21:29
193 |  |  |  | DR-052-02 | Salini Performance | 2025-05-07 21:29
194 | 53 | Contract Execution Register (including Letter of Award and Letter of Commencement) | DevCo | DR-053 | LOA_Contract_New_Tracker_Extract | 2025-05-07 21:29
195 | 54 | Claims Register | DevCo | DR-054 | Claims Register Extract Sample | 2025-05-07 21:29
196 | 55 | Post Tender Clarification (PTC) Register | DevCo | DR-055-01 | DR-055a Tender Report PTC excerpt - PTC log | 2025-05-07 21:29
197 |  |  |  | DR-055-02 | DR-055b Tender Report PTC excerpt log signed | 2025-05-07 21:29
198 | 56 | Payment Register | DevCo | DR-056 | Payments Tracker 31.12.2024 | 2025-05-07 21:29
199 | 57 | HSE Management Manual | DevCo | DR-057-01 | DD-SWD-SW-SWD-000-000-DGD-MAN-HS-000001 (05)_DGCL Construction Occupational Health and Safety Manual | 2025-05-07 21:29
200 |  |  |  | DR-057-02 | DG-DSQ-000-0000-SSA-PLN-HS-000001(04) (3) Approved SSA HSE Plan | 2025-05-07 21:29
201 |  |  |  | DR-057-03 | Oberoi Hotel - HSE Management Plan - WS-WSH-685-0000-USC-PLN-HS-000001 | 2025-05-07 21:29
202 |  |  |  | DR-057-04 | DG-BUJ-106-0000-NSM-PLN-HS-000015 Rev.01 | 2025-05-07 21:29
203 |  |  |  | DR-057-05 | DG-BUJ-106-0000-NSM-PLN-HS-000019 Rev.01 | 2025-05-07 21:29
204 | 58 | HIRAC Methodology & Safety Risk Register | DevCo | DR-058-01 | DG-BUJ-106-0000-NSM-RPT-HS-000045 - Zallal | 2025-05-07 21:29
205 |  |  |  | DR-058-02 | DG-DSQ-000-0000-SSA-PLN-HS-000001(04) (3) Approved SSA HSE Plan | 2025-05-07 21:29
206 | 59 | Sample of Emergency Evacuation & Preparedness Plan (Project level) | Project
207 | 60 | Latest Monthly HSE Report | DevCo | DR-060-01 | DG-DSQ-000-0000-SSA-RPT-HS-000001(07) | 2025-05-07 21:29
208 |  |  |  | DR-060-02 | Zallal Monthly OH&S Trend Analysis Report January 2025 | 2025-05-07 21:29
209 |  |  |  | DR-060-03 | Zallal-OHS Monthly KPIs-Jan- 2025 | 2025-05-07 21:29
210 | 61 | Latest HSE Audit Report | DevCo | DR-061-01 | Monthly PCI - Oberoi Hotel - April 2025 | 2025-05-07 21:29
211 |  |  |  | DR-061-02 | PCI - AGA-P3-6-7 Apr 2025 Score (signed) - DSQ | 2025-05-07 21:29
212 |  |  |  | DR-061-03 | PCI -Jan 2025 | 2025-05-07 21:29
213 |  |  |  | DR-061-04 | PCI SCAR Report Jan 2025 | 2025-05-07 21:29
214 |  |  |  | DR-061-05 | Zallal-PCI Jan 2025-Signed | 2025-05-07 21:29
215 | 62 | Latest Monthly Welfare Monitoring Report | DevCo | DR-062-01 | DG-DSQ-316-0000-AEC-RPT-HS-001081 (00) | 2025-05-07 21:29
216 |  |  |  | DR-062-02 | Zallal Mixed Use- Monthly Welfare Facilities and Transportation Focus Inspection - 19-10-2024 | 2025-05-07 21:29
217 |  |  |  | DR-062-03 | Camp Inspection Report-Oberoi Hotel -April 2025 | 2025-05-07 21:29
218 |  |  |  | DR-062-04 | Focus Inspection Checklist - Drinking & Ablution Water-12022025 | 2025-05-07 21:29
219 |  |  |  | DR-062-05 | Welfare Focused Inspection - Oberoi Hotel - April 2025 | 2025-05-07 21:29
220 | 63 | Welfare Management Manual (including Vendor Management & Monitoring Program) | DevCo | DR-063-01 | 04- Contractors Workers’ Quality of Life and Accommodations Procedures- 2024 - DSQ | 2025-05-07 21:29
221 |  |  |  | DR-063-02 | DG-BUJ-106-0000-NSM-PLN-HS-000021 Rev.02 - Zallal | 2025-05-07 21:29
222 | 64 | Latest Welfare Audit Report | DevCo | DR-064-01 | Accommodation Camp Audit Inspection Report-14 Oct 2024 - Zallal | 2025-05-07 21:29
223 |  |  |  | DR-064-02 | Alpha - Accommodation Camp Audit Inspection Report April 2025 | 2025-05-07 21:29
224 |  |  |  | DR-064-03 | Azzam - Accommodation Camp Audit Inspection Report April 2025 | 2025-05-07 21:29
225 |  |  |  | DR-064-04 | Salboukh - Accommodation Camp Audit Inspection Report April 2025 | 2025-05-07 21:29
226 |  |  |  | DR-064-05 | Camp Inspection Report-Oberoi Hotel -April 2025 | 2025-05-07 21:29
227 |  |  |  | DR-064-06 | Focus Inspection Checklist - Drinking & Ablution Water-12022025 | 2025-05-07 21:29
228 | 65 | Quarterly/annual progress reports for preceding three years (including approved budget, contingency utilization and change requests / claims) | DevCo | DR-065 | Cost Data Template_Diriyah (Dec24) | 2025-05-07 21:29
229 | 66 | Provisional Sums Status | DevCo
230 | 67 | Innovation Strategy (DevCo level) | DevCo | DR-067-01 | 250430_DevCo's innovation strategic approach_vs | 2025-05-07 21:29
231 | 68 | Smart City Strategy (DevCo level) | DevCo | DR-068 | Smart Diriyah overarching strategy (Executive summary) v2 | 2025-05-07 21:29
232 | 69 | Innovation/ smart city impact assessment Report (DevCo level) | DevCo
233 | 70 | Sample(s) of project-level final master plan showing innovation/ Smart city considerations | Project
234 | 71 | Register of Innovation & Technology pilots and R&D projects along with progress tracker | DevCo
235 | 72 | Technical functions' strategy and initiatives | DevCo | DR-072-01 | 20250318_Business plan BoD deck_vDevco.pdf | 2025-05-07 21:29
236 |  |  |  | DR-072-02 | 241027_DevCo_onboarding_v35 (without video) | 2025-05-07 21:29
237 |  |  |  | DR-072-03 | DevCo development capacity_v29 (for PIF) | 2025-05-07 21:29
238 | 73 | Latest report which includes the progress of technical strategy initiatives​ | DevCo | DR-073 | 250503_Portfolio wide projects | 2025-05-07 21:29
239 | 74 | List of technical functions’ KPIs (including baseline and targets) | DevCo | DR-074 | Performance Management Handbook v37.1 | 2025-05-07 21:29
240 | 75 | Latest report which includes the progress of achievement of technical functions’ KPIs | DevCo | DR-075 | E-Annual plan components and details v1 | 2025-05-07 21:29
241 | 76 | Company Organization chart (that shows the availability of innovation unit/ department) (listed in Strategy & Operations) | DevCo | DR-076-01 | Busness Development | 2025-05-07 21:29
242 |  |  |  | DR-076-02 | Commercial Leasing | 2025-05-07 21:29
243 |  |  |  | DR-076-03 | Commercial | 2025-05-07 21:29
244 |  |  |  | DR-076-04 | Design | 2025-05-07 21:29
245 |  |  |  | DR-076-05 | DevCo Organization Chart | 2025-05-07 21:29
246 |  |  |  | DR-076-06 | Development DG1 | 2025-05-07 21:29
247 |  |  |  | DR-076-07 | Development DG2 | 2025-05-07 21:29
248 |  |  |  | DR-076-08 | Development WS | 2025-05-07 21:29
249 |  |  |  | DR-076-09 | Materplanning | 2025-05-07 21:29
250 |  |  |  | DR-076-10 | OHSS Str 29.4.25 | 2025-05-07 21:29
251 |  |  |  | DR-076-11 | Projects | 2025-05-07 21:29
252 |  |  |  | DR-076-12 | Retail Leasing | 2025-05-07 21:29
253 |  |  |  | DR-076-13 | Sales | 2025-05-07 21:29
254 | 77 | Strategic DevCo technical workforce planning report, including capacity and competency planning | DevCo | DR-077 | DevCo Workforce | 2025-05-07 21:29
255 | 78 | Register of Approved technical-related policies and procedures | DevCo
256 | 79 | Register of technical platforms | DevCo
Go to P&M
Go to D&T
Go to D&C
Go to CE&O
Go to I&T
Go to S&O
Go to Main Page
Refresh
Add Document
Delete Document

## DevCoAssessmentInput(P&M)
PIF Project Lighthouse
DevCoAssessmentInput(P&M)
Assessment Criteria | Data Point | Input Value | Data Source | Assessor Remarks | Assessment Time Stamp | Reviewer Remarks | Review Time Stamp | Formula
DevCo Schedule Performance Index (SPI) | Planned Value (PV) | 55.49 | [5 empty] | Earned Value (EV) / Planned Value (PV)
| Earned Value (EV) | 36.6
% milestone achievement in accordance with the approved business plan | No. of planned milestones | 0.2029 | [5 empty] | No. of milestones achieved on time/ No. of planned milestones
| No. of milestones achieved on time | 0.15459
% of projects with approved change requests in design phase since inception with time impact of more than 1 month | Total number of projects in design phase | 54 | [5 empty] | Number of projects with approved change requests in design phase since inception with time impact of more than 1 month / Total number of projects in design phase
Number of projects with approved change requests in design phase since inception with time impact of more than 1 month
% of projects with approved change requests in construction phase since inception with time impact of more than 4 months | Total number of projects in construction phase | 69 | [5 empty] | Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months / Total number of projects in construction phase
Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months
% of projects with approved schedule extension | No. of Approved EOTs | [6 empty] | (Number of Projects with Approved Schedule Extension)/Total Number of Projects)
No. of projects with schedule extension (design stage)
No. of projects with schedule extension (construction stage)
% of projects with Forecast completion date beyond the latest approved schedule | Number of projects with forecast completion date beyond the latest approved schedule | 0.29952 | [5 empty] | Number of projects with forecast completion date beyond the latest approved schedule / [No. of projects with schedule extension (design stage) + No. of projects with schedule extension (construction stage)]
Is the Forecast Finish Date at a given data date based on the alignment and buy-in from project teams and other listed stakeholders? | Total list of stakeholders and their commitment to the forecast finish date | [6 empty] | "Satisfactory Score" if key project stakeholders (engineering, procurement, construction, client teams) were formally briefed, discussed on the forecast date includ any foreseen risks but no formal sign off doc on the forecast finish date is available
Based on the risks identified and approved change requests, has the DevCo conducted a sensitivity assessment on the forecast completion at a given data date? | Identified risks with probability and impact ratings and Historical Project Performance (SPI, past variances, Productivity Trends) | Yes, but inadequate | [5 empty] | "Satisfactory" if new activities as per the risks identified and discussions with stakeholders are added in the revised programme but do not have logical relationships and there is no comparison of the critical path analysis before and after date change
Has DevCo allocated risk contingency for the identified risks? | Risk severity and Risk mapping | Yes | [5 empty] | Satisfactory Score if - Contingency allocated but not aligning with the risk severity as per the heat map
Was there any deferment in the project completion date due to unidentified risks? | Source of the unidentified risk | Data Not Available | [5 empty] | Satisfactory Score if - the deferment was less than 1 month
Was there any Cost Overrun because of identified risk? | % of cost overrun from the latest approved budget due to identified risk | Yes, but less than 5% | [5 empty] | Satisfactory Score if - the cost overrun was less than 5%
Was there any Cost Overrun because of unidentified risk? | % of cost overrun from the latest approved budget due to unidentified risk | [6 empty] | Satisfactory Score if - the cost overrun was less than 1%
Risk Control Rate of the identified risks at DevCo Level | Number of controlled risks | 116 | [5 empty] | Number of Controlled Risks / Total number of identified risks
| Total number of identified risks | 116
Is the DevCo fully compliant with Risk Management Plan requirements? | Risk Manager or Risk Committee overseeing risk governance | Yes, but inadequate | [5 empty] | Satisfactory Score if - the risks were identified, mitigations planned but not communicated to all the relevant stakeholders. And the risk register is updated
Is there a difference in the time impact forecast before and after the risk event has triggered? | Difference between anticipated and actual effects on time and cost, after the risk event triggered | [6 empty] | Satisfactory Score if - the time impact is less than 2 weeks for Design phase completion and less than 1 month of Construction Phase Completion
Is there a difference in the Cost impact forecast before and after the risk event has triggered? | Reasons on the difference between anticipated and actual effects on time and cost | [6 empty] | Satisfactory Score if - the cost impact is less than 0.5% of the identified risk costing
Go to Main Page
Refresh
Go to Document
Go to Analysis

## DevCoAssessmentAnalysis(P&M)
PIF Project Lighthouse
DevCoAssessmentAnalysis(P&M)
Assessment Criteria | Data Point | Value | Rating | Score | Assessment Criteria Weightage | Assessment Guideline/Formula | Good | Satisfactory | Needs Improvement | Remarks 1 | Performance Signal | Performance Signal Score | Performance Signals Weightage | Remarks 2 | Key Topic | Key Topic Score | Remarks 3
DevCo Schedule Performance Index (SPI) | Planned Value (PV) | 0.65958 | Needs Improvement | 1 | 70% | Earned Value (EV) / Planned Value (PV) | >1 | 0.85-1 | <0.85 |  | Schedule Adherence | 1.6 | 50% |  | Overall Progress | 1.34
Earned Value (EV)
% milestone achievement in accordance with the approved business plan | No. of planned milestones | 76.19% | Good | 3 | 30% | No. of milestones achieved on time/ No. of planned milestones | >70% | 50-70% | <50%
No. of milestones achieved on time
% of projects with approved change requests in design phase since inception with time impact of more than 1 month | Total number of projects in design phase | 0% | Needs Improvement | 1 | 40% | Number of projects with approved change requests in design phase since inception with time impact of more than 1 month / Total number of projects in design phase | <30% | 30-70% | >70% |  | Schedule Extension | 1 | 30%
Number of projects with approved change requests in design phase since inception with time impact of more than 1 month
% of projects with approved change requests in construction phase since inception with time impact of more than 4 months | Total number of projects in construction phase | 0% | Needs Improvement | 1 | 40% | Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months / Total number of projects in construction phase | <30% | 30-70% | >70%
Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months
% of projects with approved schedule extension | No. of Approved EOTs | 0% | Needs Improvement | 1 | 20% | (Number of Projects with Approved Schedule Extension)/Total Number of Projects) | <20% | 20-40% | >40%
No. of projects with schedule extension (design stage)
No. of projects with schedule extension (construction stage)
% of projects with Forecast completion date beyond the latest approved schedule | Number of projects with forecast completion date beyond the latest approved schedule | Data Not Available | Needs Improvement | 1 | 60% | Number of projects with forecast completion date beyond the latest approved schedule / [No. of projects with schedule extension (design stage) + No. of projects with schedule extension (construction stage)] | <20% | 20-40% | >40% |  | Schedule Achievability | 1.2 | 20%
Is the Forecast Finish Date at a given data date based on the alignment and buy-in from project teams and other listed stakeholders? | Total list of stakeholders and their commitment to the forecast finish date | 0% | Needs Improvement | 1 | 20% | "Satisfactory Score" if key project stakeholders (engineering, procurement, construction, client teams) were formally briefed, discussed on the forecast date includ any foreseen risks but no formal sign off doc on the forecast finish date is available | Yes | Yes, but inadequate | No
Based on the risks identified and approved change requests, has the DevCo conducted a sensitivity assessment on the forecast completion at a given data date? | Identified risks with probability and impact ratings and Historical Project Performance (SPI, past variances, Productivity Trends) | Yes, but inadequate | Satisfactory | 2 | 20% | "Satisfactory" if new activities as per the risks identified and discussions with stakeholders are added in the revised programme but do not have logical relationships and there is no comparison of the critical path analysis before and after date change | Yes | Yes, but inadequate | No
Has DevCo allocated risk contingency for the identified risks? | Risk severity and Risk mapping | Yes | Good | 3 | 20% | Satisfactory Score if - Contingency allocated but not aligning with the risk severity as per the heat map | Yes | Yes, but inadequate | No |  | Risk Governance | 1.7 | 60% |  | Risk Performance | 1.82
Was there any deferment in the project completion date due to unidentified risks? | Source of the unidentified risk | Data Not Available | Needs Improvement | 1 | 30% | Satisfactory Score if - the deferment was less than 1 month | No | Yes, but less than 1 month | Yes
Was there any Cost Overrun because of identified risk? | % of cost overrun from the latest approved budget due to identified risk | Yes, but less than 5% | Satisfactory | 2 | 30% | Satisfactory Score if - the cost overrun was less than 5% | No | Yes, but less than 5% | Yes
Was there any Cost Overrun because of unidentified risk? | % of cost overrun from the latest approved budget due to unidentified risk | 0% | Needs Improvement | 1 | 20% | Satisfactory Score if - the cost overrun was less than 1% | No | Yes, but less than 1% | Yes
Risk Control Rate of the identified risks at DevCo Level | Number of controlled risks | 100% | Good | 3 | 40% | Number of Controlled Risks / Total number of identified risks | >70% | 40-70% | <40% |  | Realized Risk Status | 2 | 40%
Total number of identified risks
Is the DevCo fully compliant with Risk Management Plan requirements? | Risk Manager or Risk Committee overseeing risk governance | Yes, but inadequate | Satisfactory | 2 | 20% | Satisfactory Score if - the risks were identified, mitigations planned but not communicated to all the relevant stakeholders. And the risk register is updated | Yes | Yes, but inadequate | No
Is there a difference in the time impact forecast before and after the risk event has triggered? | Difference between anticipated and actual effects on time and cost, after the risk event triggered | 0% | Needs Improvement | 1 | 20% | Satisfactory Score if - the time impact is less than 2 weeks for Design phase completion and less than 1 month of Construction Phase Completion | No | Yes, but less than 2 weeks | Yes
Is there a difference in the Cost impact forecast before and after the risk event has triggered? | Reasons on the difference between anticipated and actual effects on time and cost | 0% | Needs Improvement | 1 | 20% | Satisfactory Score if - the cost impact is less than 0.5% of the identified risk costing | No | Yes, but less than 0.5% | Yes
Go to Main Page
Refresh
Go to Document
Go to Input

## InterviewQuestion(P&M)
PIF Project Lighthouse
InterviewQuestion(P&M)
SN | Question | Date of Interview | Response | Internal Comment | Follow Up Question
1 | In case the project is behind schedule, is there a recovery program to address the delay? | 2025-05-09 16:05
2 | What factors led to approve the change(s) in the completion date (design/construction/stakeholder approvals)? | 2025-05-09 16:05
3 | Using a sample project, please show how an in-depth analysis was conducted to ensure how realistic the remaining duration of the project planned/ forecasted was, critical path defined, considering resource availability, project constraints, and risk factors in order to avoid likelihood of schedule slippages & cost overruns. | 2025-05-09 16:05
4 | Did the approved schedule consider the risks identified during the Risk Assessment stage? | 2025-05-09 18:10
5 | What percentage of projects have an approved risk register? | 2025-05-09 16:05
6 | What percentage of risk associated costs is a part of total budget? | 2025-05-09 16:05
7 | After the risk event triggered, was there a difference between the anticipated and actual effects on time and cost? If so, what were the reasons and what is the plan to reduce the further overrun. | 2025-05-09 16:05
Go to Main Page
Refresh

## AddDataPoint(P&M)
PIF Project Lighthouse
AddDataPoint(P&M) |  |  |  |  | Schedule Chart |  |  |  | Top 10 Risks | [5 empty] | Top 5 Risk Categories |  | Project Overview
SN | Data Source | Additional Data Point | Value | Scorecard Visualization | Year | Value Completed (Baseline) in M SAR | Value Completed (Actual) in M SAR | Value Completed (Forecast) in M SAR | Risk | Source | Potential Impact | Risk Rating | Risk Status | Current Measures | Risk Category | Number of Risk Items | ProjectID | ForecastCompletionYear | ProjectType | ProjectStage | Criticality | DelayInSchedule | CostOverrun | Priority | ProjectValue
1 |  | Latest Approved Completion Date​ |  |  | 2025
2 |  | Forecast Completion Date​ |  |  | 2026
3 |  | Approved baseline completion date |  |  | 2027
4 |  | No. of schedule iterations |  |  | 2028
5 |  | Planned duration up to a specific phase as per approved Baseline programme |  |  | 2029
6 |  | Duration taken to complete works up to the specific phase
7 |  | Recovery Plan
8 |  | Extent of all EOT (design stage)
9 |  | Extent of all EOT (const. stage)
10 |  | No. of unresolved issues
11 |  | No. of (Open) Inherent Risks
12 |  | No. of (Closed) Residual Risks
13 |  | Project-level risks (including low, medium, and high severity)
14 |  | Procedures for risk management
15 |  | Risks identified and corresponding impact on schedule
16 |  | Extra Cost due to Unresolved Issues
Go to Main Page
Refresh

## DevCoAssessmentInput(D&T)
PIF Project Lighthouse
DevCoAssessmentInput(D&T)
Assessment Criteria | Data Point | Input Value | Data Source | Assessor Remarks | Assessment Time Stamp | Reviewer Remarks | Review Time Stamp | Formula
Similarity between Original/Approved and Latest CGI and Animation | Percentage similarity between Approved CGI and Latest CGI at same angle and scale | 70% | DR-011-01 | The sample projects show high level of similarity between the different design stage has been maintained. However, tracking for the changes is not provided. |  |  |  | (Percentage similarity between Approved CGI and Latest CGI at same angle and scale) + (Percentage similarity between Approved Animation and Latest Animation at same camera angle) / 2
| Percentage similarity between Approved Animation and Latest Animation at same camera angle | 0% |  | No data provided.
Does the Latest Material Palette & Finish Schedule support the look of the Approved CGI? | Material Palette & Finish Schedule | 0.7 | DR-011-01 | The sample projects show high level of similarity between the different design stage has been maintained. However, tracking for the changes is not provided. |  |  |  | Material Palette & Finish Schedule matched Approved CGI
Does the DevCo have Design & Technical Guidelines (including Look & Feel Design Guidelines)? | Design and Technical Guidelines | Yes | DR-013-01 |  |  |  |  | The Design and Technical Guidelines exist
Do DevCo projects comply with DDTG? | Look & Feel Guideline | Yes | DR-012-01 |  |  |  |  | Material Palette & Finish Schedule aligns with Look & Feel Guideline
% variance from approved Built-Up Area (BUA) | Latest BUA | [6 empty] | (Latest BUA - Approved BUA) / Approved BUA
Approved BUA
% variance in land use permit area | Latest Land Area | [6 empty] | (Latest Land Area - Approved Land Area) / Approved Land Area
Approved Land Area
% variance from approved population | Latest Population | [6 empty] | (Latest Population - Approved Population) / Approved Population
Approved Population
% value of modularization compared to the total construction value | Value of Modularized Construction Cost | [6 empty] | Modularized Construction Cost / Total Construction Cost
Value of Total Construction Cost
Have all projects completed a Constructability Report/Document? | Date and Revision of Constructability Report | No | DR-015-01 |  |  |  |  | Constructability Report exists
Was design for Enabling Work Package considerd as part of the design process to ensure the readiness of the site for the main construction work? | Assessment of enabling works required | No | DR-015-01 |  |  |  |  | Consideration of design for enabling work package
Are documentation packages meeting the LOD requirements of the latest Design Stage Gate? | LOD Required | Yes | DR-017-01 |  |  |  |  | LOD Documented matches LOD Required
LOD Documented (drawing sample from Design Report)
Have all projects adopted digital delivery using BIM and/or GIS? | % of projects adopting digital delivery using BIM/GIS | Yes | DR-017-01 |  |  |  |  | BIM Documentation exists
Is project delivery occurring in accordance with the latest approved design strategy? | Date of Latest Approved Design Strategy | [6 empty] | Review Latest Approved Design Strategy and compare with the Stage Gate Design Report
% of projects with completed technical design/peer reviews and verifications/certifications as required for the latest Design Stage Gate | Number of projects with completed design reviews and verification register | 0.4 | DR-018-01 |  |  |  |  | Check the Design Review & Verification Register, assess if correct number of Design Reviews have occurred in accordance with the Design Management Report
% of Corrective Actions closed | Total Corrective Actions | [6 empty] | Closed Corrective Actions / Total Corrective Actions
Number of Closed Corrective Actions
Average Cycle time to close corrective actions | Days taken to Close Corrective Actions | [6 empty] | Average number of days between Date Corrective Action is recorded in the Corrective Action Register and the Date Corrective Action is Closed
Is the average cycle time to complete reviews and certifications in accordance with the Design Management Report? | Days taken to complete Design Reviews | [6 empty] | Average number of days between Design Review Submittals and Completion of the Design Reviews compared to the number of days required to complete the Design Reviews in accordance with the Design Management Report
Has the DevCo engaged independent certification of major critical elements? | Level of review and verification required for Stage Gate | [6 empty] | Independent Certification exists
Are all project designs integrated with Regional Infrastructure & Mobility Plans? | Regional Strategies | Yes | DR-012-01 |  |  |  |  | The Infrastructure and Engineering Report references the Regional Infrastructure & Mobility Plans and demonstrates adoption of Regional Strategies
Do all projects comply with environmental guidelines in accordance with ESIA? | Extent of compliance to environmental guidelines | Yes | DR-023-01 |  |  |  |  | Key Environmental Risks and Site Environmental Factors are covered in the Environmental Compliance Report
% of projects with Code Compliance Violations | Total Number of Code Compliance Violations | 0.1 | DR-022 |  |  |  |  | Total Number of Code Compliance Violations taken from the Code Compliance Assessment Report
% of approved deviation waivers against compliant codes & standards | Total Waiver Applications Submitted | [6 empty] | Total Waivers Approved / Total Waiver Applications Submitted
Total Waivers Approved
Have all required Stakeholder Submittals been issued? | Stakeholder Submittal Date | Yes | DR-026-01 |  |  |  |  | Stakeholder Submittal Dates are in accordance with the Stakeholder Management Plan to ensure approvals can be achieved in line with Stage Gate completion requirements
% of time critical Stakeholder Approvals Pending impacting Design Stage Gate completion | Number of Stakeholder Approvals Pending | [6 empty] | Number of Stakeholder approvals pending / Total number of stakeholder approvals required
Total number of stakeholder approvals required
Does the Stakeholder Engagement Plan include proactive communication process to ensure timley coordination and approvals? | Scheduled Design Stage Gate Completion | Yes | DR-026-01 |  |  |  |  | Proactive communication in Stakeholder Engagement Plan
% of Stakeholder Comments Closed | Total Stakeholder Comments | [6 empty] | Stakeholder Comments Closed / Total Stakeholder Comments
Stakeholder Comments Closed
% of projects achieving DevCo ESG Targets | Planned ESG Target | [6 empty] | Actual ESG Target / Planned ESG Target
Actual ESG Target
Does the DevCo ESG Target align with globally recognized Best Practice Targets? | Alignment with globally recognized Best Practice Targets | No | DR-027 |  |  |  |  | Alignment with globally recognized Best Practice Targets
Go to Main Page
Refresh
Go to Document
Go to Analysis

## DevCoAssessmentAnalysis(D&T)
PIF Project Lighthouse
DevCoAssessmentAnalysis(D&T)
Assessment Criteria | Data Point | Value | Rating | Score | Assessment Criteria Weightage | Assessment Guideline /Formula | Good | Satisfactory | Needs Improvement | Remarks 1 | Performance Signal | Performance Signal Score | Performance Signals Weightage | Remarks 2 | Key Topic | Key Topic Score | Remarks 3
Similarity between Original/Approved and Latest CGI and Animation | Percentage similarity between Approved CGI and Latest CGI at same angle and scale | 35% | Needs Improvement | 1 | 30% | (Percentage similarity between Approved CGI and Latest CGI at same angle and scale) + (Percentage similarity between Approved Animation and Latest Animation at same camera angle) / 2 | >70% | 50-70% | <50% |  | CGI and Animation Compliance | 2.2 | 50% |  | Vision Adherence | 1.6
Percentage similarity between Approved Animation and Latest Animation at same camera angle
Does the Latest Material Palette & Finish Schedule support the look of the Approved CGI? | Material Palette & Finish Schedule | 70% | Satisfactory | 2 | 20% | Material Palette & Finish Schedule matched Approved CGI | >70% | 50-70% | <50%
Does the DevCo have Design & Technical Guidelines (including Look & Feel Design Guidelines)? | Design and Technical Guidelines | Yes | Good | 3 | 20% | The Design and Technical Guidelines exist | Yes |  | No
Do DevCo projects comply with DDTG? | Look & Feel Guideline | Yes | Good | 3 | 30% | Material Palette & Finish Schedule aligns with Look & Feel Guideline | >70% | 50-70% | <50%
% variance from approved Built-Up Area (BUA) | Latest BUA | Data Not Available | Needs Improvement | 1 | 30% | (Latest BUA - Approved BUA) / Approved BUA | <15% | 15-30% | >30% |  | Development Program Variance | 1 | 50%
Approved BUA
% variance in land use permit area | Latest Land Area | Data Not Available | Needs Improvement | 1 | 30% | (Latest Land Area - Approved Land Area) / Approved Land Area | <15% | 15-30% | >30%
Approved Land Area
% variance from approved population | Latest Population | Data Not Available | Needs Improvement | 1 | 40% | (Latest Population - Approved Population) / Approved Population | <30% | 30-40% | >40%
Approved Population
% value of modularization compared to the total construction value | Value of Modularized Construction Cost | Data Not Available | Needs Improvement | 1 | 20% | Modularized Construction Cost / Total Construction Cost | >40% | 20-40% | <20% |  | Construction Design Maturity | 1.4 | 100% |  | Design for Constructability | 1.4
Value of Total Construction Cost
Have all projects completed a Constructability Report/Document? | Date and Revision of Constructability Report | No | Needs Improvement | 1 | 20% | Constructability Report exists | Yes |  | No
Was design for Enabling Work Package considerd as part of the design process to ensure the readiness of the site for the main construction work? | Assessment of enabling works required | No | Needs Improvement | 1 | 20% | Consideration of design for enabling work package | Yes |  | No
Are documentation packages meeting the LOD requirements of the latest Design Stage Gate? | LOD Required | No | Needs Improvement | 1 | 20% | LOD Documented matches LOD Required | Yes |  | No
LOD Documented (drawing sample from Design Report)
Have all projects adopted digital delivery using BIM and/or GIS? | % of projects adopting digital delivery using BIM/GIS | Yes | Good | 3 | 20% | BIM Documentation exists | Yes |  | No
Is project delivery occurring in accordance with the latest approved design strategy? | Date of Latest Approved Design Strategy | 0% | Needs Improvement | 1 | 10% | Review Latest Approved Design Strategy and compare with the Stage Gate Design Report | Yes |  | No |  | Design Management Maturity | 1 | 100% |  | Design Management | 1
% of projects with completed technical design/peer reviews and verifications/certifications as required for the latest Design Stage Gate | Number of projects with completed design reviews and verification register | 40% | Needs Improvement | 1 | 20% | Check the Design Review & Verification Register, assess if correct number of Design Reviews have occurred in accordance with the Design Management Report | >70% | 50-70% | <50%
% of Corrective Actions closed | Total Corrective Actions | Data Not Available | Needs Improvement | 1 | 10% | Closed Corrective Actions / Total Corrective Actions | >70% | 40-70% | <40%
Number of Closed Corrective Actions
Average Cycle time to close corrective actions | Days taken to Close Corrective Actions | 0 | Needs Improvement | 1 | 10% | Average number of days between Date Corrective Action is recorded in the Corrective Action Register and the Date Corrective Action is Closed | <14days | 14-30days | >30days
Is the average cycle time to complete reviews and certifications in accordance with the Design Management Report? | Days taken to complete Design Reviews | 0% | Needs Improvement | 1 | 20% | Average number of days between Design Review Submittals and Completion of the Design Reviews compared to the number of days required to complete the Design Reviews in accordance with the Design Management Report | Yes |  | No
Has the DevCo engaged independent certification of major critical elements? | Level of review and verification required for Stage Gate | 0% | Needs Improvement | 1 | 30% | Independent Certification exists | Yes |  | No
Are all project designs integrated with Regional Infrastructure & Mobility Plans? | Regional Strategies | Yes | Good | 3 | 50% | The Infrastructure and Engineering Report references the Regional Infrastructure & Mobility Plans and demonstrates adoption of Regional Strategies | Yes |  | No |  | Environmental Compliance Status | 3 | 40% |  | Regulatory Compliance | 2.28
Do all projects comply with environmental guidelines in accordance with ESIA? | Extent of compliance to environmental guidelines | Yes | Good | 3 | 50% | Key Environmental Risks and Site Environmental Factors are covered in the Environmental Compliance Report | Yes |  | No
% of projects with Code Compliance Violations | Total Number of Code Compliance Violations | 10% | Satisfactory | 2 | 20% | Total Number of Code Compliance Violations taken from the Code Compliance Assessment Report | <10% | 10-30% | >30% |  | Authority Compliance Status | 1.8 | 60%
% of approved deviation waivers against compliant codes & standards | Total Waiver Applications Submitted | Data Not Available | Needs Improvement | 1 | 20% | Total Waivers Approved / Total Waiver Applications Submitted | >70% | 50-70% | <50%
Total Waivers Approved
Have all required Stakeholder Submittals been issued? | Stakeholder Submittal Date | Yes | Good | 3 | 15% | Stakeholder Submittal Dates are in accordance with the Stakeholder Management Plan to ensure approvals can be achieved in line with Stage Gate completion requirements | Yes |  | No
% of time critical Stakeholder Approvals Pending impacting Design Stage Gate completion | Number of Stakeholder Approvals Pending | Data Not Available | Needs Improvement | 1 | 15% | Number of Stakeholder approvals pending / Total number of stakeholder approvals required | <20% | 20-30% | >30%
Total number of stakeholder approvals required
Does the Stakeholder Engagement Plan include proactive communication process to ensure timley coordination and approvals? | Scheduled Design Stage Gate Completion | Yes | Good | 3 | 15% | Proactive communication in Stakeholder Engagement Plan | Yes |  | No
% of Stakeholder Comments Closed | Total Stakeholder Comments | Data Not Available | Needs Improvement | 1 | 15% | Stakeholder Comments Closed / Total Stakeholder Comments | >70% | 50-70% | <50%
Stakeholder Comments Closed
% of projects achieving DevCo ESG Targets | Planned ESG Target | Data Not Available | Needs Improvement | 1 | 100% | Actual ESG Target / Planned ESG Target | >70% | 50-70% | <50% |  | DevCo ESG Target Achievement | 1 | 80% |  | ESG Target Realization | 1
Actual ESG Target
Does the DevCo ESG Target align with globally recognized Best Practice Targets? | Alignment with globally recognized Best Practice Targets | No | Needs Improvement | 1 | 100% | Alignment with globally recognized Best Practice Targets | Yes |  | No |  | Global ESG Target Alignment | 1 | 20%
Go to Main Page
Refresh
Go to Document
Go to Input

## InterviewQuestion(D&T)
PIF Project Lighthouse
InterviewQuestion(D&T)
SN | Question | Date of Interview | Response | Internal Comment | Follow Up Question
1 | How was the supply chain assessment done for materials & finishes required to achieve the Vision at point of incorporation? | 2025-05-09 16:05
2 | What were the reasons for any changes from original approved designs to latest design, and at which stage were these changes approved? | 2025-05-09 16:05
3 | Have the project designs aligned with DevCo Design & Technical Guidelines? Have there been any challenges adhering to the Vision? Provide an example how this has been resolved. | 2025-05-09 16:05
4 | Has the variance to the Development Program been submitted for approval? | 2025-05-09 16:05
5 | What were the reasons for the variance between the current business plan and latest development program? Were these submitted for approval? | 2025-05-09 16:05
6 | What is the impact, if any, on the business plan with these changes? Are there mitigation measures in place? | 2025-05-09 16:05
7 | Are there any outstanding FB directions and resolutions relating to design and development program? If so, please provide. | 2025-05-09 16:05
8 | Was the Vision assessed for construction viability at point of incorporation? | 2025-05-09 16:05
9 | How was designing for constructability incorporated in the design process? | 2025-05-09 16:05
10 | Have enabling works been considered to ensure the site is ready for development? | 2025-05-09 16:05
11 | Do all projects adopt digital delivery using BIM/GIS? If not, how are they managing coordination? | 2025-05-09 16:05
12 | What challenges has the DevCo faced in achieving the Design Strategy, how have these been overcome and has the PEP been updated and approved to reflect the changes. Provide example | 2025-05-09 16:05
13 | Has the DevCo had any difficulty engaging independent/peer design reviews for critical design packages. What method is used for design verification & certification? | 2025-05-09 16:05
14 | How has the design accommodated the regional guidelines and requirements (e.g. infrastructure, mobility, environment)? | 2025-05-09 16:05
15 | What are the environmental risks identified and how have they been mitigated? | 2025-05-09 16:05
16 | Are there any deviations from KSA or local codes and guidelines, justified by international/industry best practices? | 2025-05-09 16:05
17 | Has engagement commenced with all required stakeholders and what is the rate of closure of conditions and requirements? | 2025-05-09 16:05
18 | What are the challenges in meeting the targets? | 2025-05-09 16:05
Go to Main Page
Refresh

## AddDataPoint(D&T)
PIF Project Lighthouse
AddDataPoint(D&T)
SN | Data Source | Additional Data Point | Value | Scorecard Visualization
1 |  | Date & Revision of Construction Management Plan
2 |  | Date & Revision of Notional Construction Sequencing Drawing
3 |  | Key Environmental Risks
4 |  | Site Environmental Factors
5 |  | Approved GFA
6 |  | Latest GFA
Go to Main Page
Refresh

## DevCoAssessmentInput(D&C)
PIF Project Lighthouse
DevCoAssessmentInput(D&C)
Assessment Criteria | Data Point | Input Value | Data Source | Assessor Remarks | Assessment Time Stamp | Reviewer Remarks | Review Time Stamp | Formula
% of CESMP mitigation measures which align with ESIA* | Environmental mitigation measures included in CESMP |  |  | Currently under review. Samples for Oberoi Hotel and Diriyah Square, these are currently being reviewed for compliance against the EIA |  |  |  | Environmental mitigation measures included in CESMP / Environmental mitigation measures recommended in ESIA
| Environmental mitigation measures recommended in ESIA |  | DR-23-03 | Comprehensive & Detailed EIA provided for Diriyah Gate
Has the Construction Execution Plan been updated to reflect the latest stage of construction? | Update of construction execution plan | Data Not Available | 27/11/2024 | Currently under Review. Comprehensive Sample provided for Diriyah Square |  |  |  | Update of construction execution plan
Has the construction sequence and method statement been reviewed and approved? | Review and approval of Construction sequence & method statement | Data Not Available |  | DG2 High Level Delivery Strategy_Final r15MAR25_FK Please supply more Documentation reflecting on the projects |  |  |  | Review and approval of construction sequence and method statement
Is total land acquisition sufficient to achieve the area required for construction site logistics? | Planned Area provision for site offices, amenities, laydown areas, storage facilities, workforce accommodations | Data Not Available | DR-018-01 |  |  |  |  | Sufficient land acquired
| Actual Area provision for site offices, amenities, laydown areas, storage facilities, workforce accommodations | Data Not Available | DR-018-01 | Insufficient information unable to verify were the actual land for construction , with out any lay down , site office etc.
Have Traffic Simulations been completed in preparing the Site & Logistics Plan? | Completion of Traffic Simulations | Data Not Available | DR-018-01 | Assessed against whats been supplied , it appears to be in line with the documentation |  |  |  | Completion of traffic simulations
Has the Project Execution Plan been updated and approved in the last 12 months? | Date of latest approved Procurement Plan | 2025-03-25 | DR-018-01 | DR.029.02 Bujairi District Phase 2 - Feb 2023 |  |  |  | Date of latest approved Procurement Plan less than 12 months from Current Date
% of Stakeholder MOU** / LUPs*** not executed in accordance with critical lead time | Number of Stakeholder MOU or Land Use Permits not executed on time | Dec24' | DR-018-01 | Theres slides showing Data ,but we require more information showing % Stakeholders / verse Permits not executed on time |  |  |  | Number of Stakeholder MOU or Land Use Permits not executed on time/ Total number of Stakeholder MOU or Land Use Permits required
| Total Stakeholder MOU or Land Use Permits required | DEC24' | DR-018-01 | Theres slides showing Data ,but we require more information showing % Stakeholders / verse Permits not executed on time
% of Workforce Hired against Workforce Estimates | Forecast workforce requirements | 15300 | DR-032-01 | Budgeted Manhours - All Districts & Infrastructure |  |  |  | Actual workforce employed / forecast workforce requirements
| Actual workforce employed | 14400 | DR-032-01 | All District & Infrastructure - Resource statis
% of Labor Camp Capacity against Workforce Estimates | Forecast number of labor camps |  | DR-032-01 | Labor Subsistence Plan , not enough information on the documentation please supply more relevant docs |  |  |  | Actual number of labor camps / Forecast number of labor camps
| Actual number of labor camps |  | DR-032-01 | Labor Subsistence Plan , not enough information on the documentation please supply more relevant docs
% of Material Supply Capacity against Material Demand Estimates | Forecast number of batching / crushing plants/ precast yards, etc. | 45000 | DR-032 | Assessed against concrete batching plant requirements forecasted in the IMS report. Generally, based on the number of operating batching plants, concrete demand can be met. A projected shortfall for 2 months may occur based on the current peak demand projections. |  |  |  | Actual number of batching plants / forecast number of batching plants
| Actual number of batching / crushing plants/ precast yards, etc. | 39300 | DR-32-01
Did DevCo adhere to Technical Submittals Review Cycle Time (RCT)? | Time taken for closure of technical queries |  | DR-036 | Insufficient information unable to verify as this information is on XL our DATA team will need to extract this information to convert it . |  |  |  | Adherence to Technical Submittals Review Cycle Time
| Technical Submittal Review Cycle Time (RCT) |  | DR-036 | Insufficient information unable to verify as this information is on XL our DATA team will need to extract this information to convert it .
% of approved shop drawing reviews vs planned | Total number of shop drawing review requests | 14760 | DR-35-01 |  |  |  |  | Total number of shop drawing reviews approved / Total number of shop drawing review requests
| Total number of shop drawing reviews approved | 13970 | DR-35-01
% of approved product waivers vs product specified | Total number of product sample & material approvals requested | 5 | DR-35-01 | Insufficient information unable to verify as this information is on XL our DATA team will need to extract this information to convert it . |  |  |  | Total number of product sample & materials approved / Total number of product sample & material approvals requested
| Total number of product sample & materials approved | 245 | DR-036 | Insufficient information unable to verify as this information is on XL our DATA team will need to extract this information to convert it .
% of Certified As-Built Drawing Packages vs Planned | Number of As-Built Drawing review requests |  | DR-035 | Insufficient information unable to verify as this information is on XL our DATA team will need to extract this information to convert it . |  |  |  | Number of As-built reviews / approvals / Number of As-Built review requests
| Number of As-Built Drawings reviews approved |  | DR-035 | Insufficient information unable to verify as this information is on XL our DATA team will need to extract this information to convert it .
MIR Inspection Rate | Total number of MIRs requested | 245 | DR-34-01 | Quality Monthly Report , also please supply a current Mir construction statement not a ISO certificate |  |  |  | Number of MIR Inspected / Total number of MIRs requested
| Total number of MIRs inspected | 153 | DR-34-01 | Quality Monthl;y Report
MIR Acceptance and Approval Rate | Total number of MIRs approved | 245 | DR-34-01 | , please supply a live construction document showing live Mir acceptances |  |  |  | Number of Approved MIR / Total number of MIRs requested
WIR Inspection Rate | Total number of WIRs requested | 5430 | DR-34-01 | Quality Monthl;y Report |  |  |  | Number of WIR Inspected / Total number of WIRs requested
| Total number of WIRs inspected | 4985 | DR_034-01 | Quality Monthly Report , can you please supply a current construction WIR statement not a ISO
WIR Acceptance and Approval Rate | Total number of WIRs approved | 5040 | DR-043 | Quality Monthl;y Report , please supply a current construction WIR statement |  |  |  | Number of Approved WIR / Total number of WIRs requested
Does the frequency of Audits align with the QMP? | Required Audit frequency | Data Not Available | DR-44/ DR-43 | 90% of the schedule Audits completed |  |  |  | Alignment of audit frequency
% closure of Non-Conformance Reports (NCR) | Total number of defects & NCRs | 59 | DR-044 / DR-043 | 13 Ncr , 38 observations ,8 opportunity for improvement . Can you please supply a quality construction Audit |  |  |  | Number of Non-Conformance Reports Closed / Total Number of Non-Conformance Reports
| Total number of closed defects & NCRs | 53 | DR-044 / DR-043 | Refer Doc no :DG-DSQ-000-0000-jll-QMS |  | 0.9
Average NCRs closeout Cycle Time | Average time to close NCRs | 2 weeks | DR-044 /DR-043 | Ncr to be closed out 2 weeks from receiving the report |  |  |  | Sum (NCR Closeout cycle time)/Total number of Non-Conformance Reports
% of procurement packages delivered within the planned lead times defined in the PMP | Number of Planned Procurement Packages | [6 empty] | Number of Procurement Packages Delivered on Time / Number of Planned Procurement Packages
Number of Procurement Packages Delivered on Time
% of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures | Total number of claims and variations | [6 empty] | Total number of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures / Total number of claims and variations
Total number of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures
% of packages procured with 100% complete, compliant and well-structured documentation | Total number of packages | [6 empty] | Total number of packages procured with 100% complete, compliant and well-structured documentation / Total number of packages
Total number of packages procured with 100% complete, compliant and well-structured documentation
% of awarded contracts where vendors appointed passed full due diligence checks | No. of awarded contracts where vendors appointed passed full due-diligence checks | [6 empty] | No. of awarded contracts where vendors appointed passed full due-diligence checks / Total number of awarded contracts
Total number of awarded contracts
Did the DevCo complete a Supply Chain Risk-Market Intelligence Assessment in the last quarter? | Supply Chain Risk-Market Intelligence Assessment |  | DR-049 | Supply Chain Risk appears to be an ongoing item flagged in the risk register, factors noted include: Shipping delays due to regional conflicts Parallel giga projects competing for resources impacting cost of materials and causing delays |  |  |  | Completion of supply chain risk-market intelligence assessment
% of procurement activities executed as planned in the Annual Procurement Plan | Total number of procurement activities | 186 | [5 empty] | Number of procurement activities executed as planned / Total number of procurement activities
| Number of procurement activities executed as planned | 129
% of deviations in total awarded contract value with tender cost estimates | Value of Awarded Contract | 35.32 | [5 empty] | (Value of Contract Awarded - Tender Cost Estimate) / Value of Award Contract
| Tender Cost Estimate | 32.1
% of contracts with filed claims | Number of contracts with filed claims | [6 empty] | Number of contracts with filed claims / Total number of awarded contracts
Are Payment Certificates and payments being processed in accordance with the Contract terms and conditions? | Processing of payment certificates and payments | [6 empty] | Processing of payment certificates and payments
Are Vendor performance assessment occurring which capture financial instability, delays, repeated quality issues in real-time? | Alignment of sourcing strategies with project schedules and requirements | [6 empty] | Vendor performance assessment
Does the HSE Management Manual have adequate provision for identification and escalation of high risk activities? | Escalation criteria for high risk activities | 0 | DR-057-01 DR-057-02 DR-057-03 DR-057-05 | Diriyah Gate Company Construction Occupational Health and Safety Manual- Document number: DD-SWD-000-000-DGD-MAN-HS-000001 Rev 05 March 2023. Section 3.2 Definitions- Identifies and defines "Acceptable Risk" . Section 5.3.6- Contractor and Supply Chain outlines requirements for a project risk register. Diriyah Gate Company Limited- DD-SWD-SW-SWD-000-SSA-PLN-HS-000001 (04). Unable to verify that evidence was available for a process for the identification and escalation of high risk activities. Salini Saudi Arabia- Project HSE Plan-Diriyah Square Structural Works to the Above Ground assists-DSQ Package 03,06,07- DG-DSQ-000-0000-SSA-PLN-HS-000001(04) Unable to verify within Project HSE Plan that evidence was available for a process the escalation of high risk activities. UCC Saudi Company- Project Name: Oberoi Hotel and Branded Residences-Project Number: US0033- WS-UCC-HSE-0001 unable to verify within the HSE Management Plan that there is an adequate provision for the escalation of identified high risks. Request copy of USC-IMS-HSE-6003E Hazard Identification and Risk Assessment. Al-Zallal Mixed Used OH&S Plan Rv01- Unable to verify a process for the escalation of identified high risk activities. Noted that they have defined "acceptable risk". Unable to verify that any of the sample HSE Management Manuals provided have a documented process to define the organizations acceptable risk level and managements actions to be taken, if the accessed risk is higher than that level. |  |  |  | Provision for identification and escalation of high risk activities
Is the rate of review of the Safety Risk Register in accordance with the HSE Management Manual? | HSE Risk Register Review Rate | Data Not Available | DR-057-02 and DR-058-02 are the same document. Additional evidence is required. | Diriyah Gate Company Limited- DD-SWD-SW-SWD-000-00001 (04). Has identified a review frequency rate of annually. Salini Saudi Arabia- DG-DSQ-000-0000-SSA-PLN-HS-000001 (04), Dated 25 Aug 2024 - In section 5.2.1 states that the project HSE risk register will be reviewed as required. Oberoi Hotel -WS-WSH-685-0000-HSE-PLN-HS-00001- Plan does specify that that a formal review will be undertaken monthly. Al-Zallal Mixed Used OH&S Plan- DG-BUJ-106-0000-NSM-PLN. Able to verify a required review rate of the safety risk register. Zallal Mixed Used- Project Risk Register DG-BUJ-106-0000-NSM-RPT-HS-000045 Rev 0 dated 08 May 2024. |  |  |  | Review rate of safety risk register
% of closed Safety Risk items | Total number of Safety Risk items | 830 Salini 193 DGCL | DR-060-01 DR-060-02 DR-060-03 | Salini Monthly HSE Report April 2025- 830 HSE observations recorded. Closed 556 HSE observations, Open 185 HSE observations, Overdue 101 HSE observations. GP HSE observations 89. DGCL (Hill International)-Monthly OH&S Trend Analysis Report January 2025. This report records the OHS KPI's for this week, year to date and project to date. Section 2.6 states the ratio of SOR closure (Open: Closed) 0:193. OH&S Monthly KPI's (Leading and Lagging indicators) is an extract of the DGCL (Hill International) January 2025 report. |  |  |  | Total number of closed Safety Risk items / Total number of safety risk items
| Total number of closed Safety Risk items | 67% Salini Saudi Arabia 100% DGCL | DR-060-01 DR-060-02 DR-060-03 (extract from DR-060-02 | 67% of the 830 HSE observations recorded were closed based on the information provided in the Salini Monthly HSE Report April 2025. This percentage does not include the 101 identified overdue actions. DGCL Monthlies Trend Analysis Report January 2025- 100% close out rate.
Average cycle time to close Safety Risk items | Cycle time to close Safety Risk items (in days) | Further evidence is required. Access to Salini Saudi Arabia Monthly HSE Observation Tracker required. Access to Al-Zallal Mixed Used HSE Monthly tracker. | DR-060-01 DR-060-02 DR-060-03 (extract from DR-060-02) | Unable to determine based on evidence supplied the exact average time to close out safety risk items. |  |  |  | To input final number Sum (Cycle time to close safety risk items) / Total number of closed safety risk items
Average cycle time to close Safety Incident | Cycle time to close Safety Incident | Further evidence is required. Access to incident register is required. | DR-058 | Unable to determine based on evidence supplied the exact average time to close out safety incidents. |  |  |  | Sum (Cycle time to close safety incident) / Total number of closed safety incidents
| Total number of closed safety incidents | Further evidence is required. Access to incident register is required | DR-058 | Unable to determine based on evidence supplied what the total number of closed safety incidents. While evidence was available for the number of incidents reported.
Is the emergency drill rate compliant with EEPP? | Planned number of Emergency Drills | 3 | DR-057-04 DR-060-01 DR-060-02 Awaiting documents for DR-059 | Zallal Mixed Use- Emergency Management Framework Project ID-322822- Document number- DG-BUJ-106-0000-NSM-PLN-HS-000015 Rev.1. Evidence available in section 1.2 Frequency and main participant that two major emergency drills shall be conducted annually. Salini Saudi Arabia- Project: DSQ-AGA- Structural Works to the Above Ground Assets. DG-DSQ-000-0000-SSA-RPT-HS-000001(07)-Monthly HSE Report April 2025. Three planned emergency drills. |  |  |  | Compliance of emergency drill rate
| Actual number of Emergency Drills | 11 | DR-060-02 Awaiting documents for DR-059 | Salini Saudi Arabia- Project: DSQ-AGA- Structural Works to the Above Ground Assets. Document Reference: DG-DSQ-000-0000-SSA-RPT-HS-000001(07)-Monthly HSE Report April 2025. Two drills undertaken on the 19 March 2025 and 22 April 2025.
| Recommended time to complete Emergency drills | Further evidence is required. Access to completed drills required | DR-057-04 Awaiting documents for DR-059 | Unable to verify with the supplied documentation.
| Actual Time to complete Emergency drills | Further evidence required. Access to completed drill required | DR-057-04 Awaiting documents for DR-059 | Unable to verify with the supplied documentation.
Fatality Rate (FR) | No. of incidents resulting in fatality or severe impairment per 200,000 work hours | 0 | DR-061 | DGCL Monthly OH&S Trend Analysis Report January 2025- Monthly KPI's Section 3.1- Zero recorded fatalities. Salini Saudi Arabia Monthly HSE Report April 2025- Zero fatalities recorded. |  |  |  | No. of incidents resulting in fatality or severe impairment per 200,000 work hours
Lost Time Injury Frequency Rate (LTIFR) | No. of incidents resulting in lost time per 200,000 work hours | 0 | DR-061 | DGCL Monthly OH&S Trend Analysis Report January 2025- Monthly KPI's Section 3.2- Zero recorded LTIs. Salini Saudi Arabia Monthly HSE Report April 2025- Zero LTIs recorded. |  |  |  | No. of incidents resulting in lost time per 200,000 work hours
Total Recordable Incident Rate (TRIR) | No. of recordable incidents per 200,000 work hours | 0 | DR-061 | DGCL Monthly OH&S Trend Analysis Report January 2025- Monthly KPI's Section 3.1- Zero recorded Total Recordable Incident Rate (TRIR) Salini Saudi Arabia Monthly HSE Report April 2025- Zero Total Recordable Incident Rate (TRIR) recorded. |  |  |  | No. of recordable incidents per 200,000 work hours
Near Miss Rate | No. of near misses recorded per 200,000 work hours | 0.76 DGCL 0.20 Salini | DR-061 | DGCL Monthly OH&S Trend Analysis Report January 2025- Monthly KPI's Section 3.6 Near Miss- Zero recorded for the month of January 2025. Twenty-one Near Miss events have been recorded on the project to date. Salini Saudi Arabia Monthly HSE Report April 2025- one Near Miss have been recorded for the month of April 2025 and Four have been recorded for the project to date. |  |  |  | No. of near misses recorded per 200,000 work hours
Safety Observation Rate | No. of safety observation recorded per 200,000 work hours | 353.8 Salini Saudi Arabia 158.7 DGCL | DR-061 | Salini Saudi Arabia- Monthly HSE April 2025- 830 HSE Observations were recorded for a total of 469,224 hours worked for the month. 5,289 Observations have been recorded between 24th October 2024 to April 2025 (Unable to determine safety observation rate for this period). DGCL- Al-Zallal Mixed Used- Monthly OHS January 2025- 193 observations were recorded. |  |  |  | No. of safety observation recorded per 200,000 work hours
Leadership Safety Walk Rate | Total number of Safety Walks | Further evidence is required for actual number of Safety walks/inspections carried out | DR-060-01 DR-060-02 | Salini Saudi Arabia- Monthly HSE Report April 2025- Contractor- Massimo Togna. Unable to verify the number of total safety walks completed. DGCL Monthly OH&S Trend Analysis Report January 2025- States in section 3- Monthly OH&S KPIs-Section 2.6- Four OH&S Safety Leadership Site Walkthroughs were conducted for the month. |  |  |  | Total number of Safety Walks with Leadership / Total number of Safety Walks
| Total number of Safety Walks with Leadership | 219 | DR-060-02 | DGCL Monthly OH&S Trend Analysis Report January 2025- States in section 3- Monthly OH&S KPIs-Section 2.6- 219 OH&S Safety Leadership Site Walkthroughs were conducted for the month.
% of Grievances Closed | Number of grievances closed | Further evidence is required. Welfare facilities/camp hazard observation register required. | DR-062 | Camp inspection Report Oberoi Hotel April 12 2025, No evidence available at the time of the document review that the closure of identified hazards/issues during the camp inspection report have been satisfactorily completed. DSQ P-2 Daily HSE Report- Focus Inspection Welfare Facilities- DG-DSQ-316-0000-AEC-RPT-HS-001081 dated 14/12/2024- 24 welfare related observations were recorded. 17 of the 24 identified observations were responded to by the contractor in the action taken section of the contractor close out response, Unable to verify that identified observations have been satisfactorily closed. |  |  |  | Number of grievances closed / Total number of grievances
| Total number of grievances | Further evidence is required . Welfare facilities/camp hazard observation register. | DR-062-01 | DSQ P-2 Daily HSE Report- Focus Inspection Welfare Facilities- DG-DSQ-316-0000-AEC-RPT-HS-001081 dated 14/12/2024- 24 welfare related observations were recorded. No evidence of the number of grievances was available.
Average Cycle Time to Close Grievances | Cycle time to close grievances | Further evidence is required . Welfare facilities/camp hazard observation register. | DR-062 | Unable to verify the average time to close out identified welfare grievances. |  |  |  | Sum (Cycle time to close grievances) / Total number of grievances
% of Welfare Staff vs Total workforce | Percentage of Welfare Staff against total staff | 0% | DR-063 | DGCL Al-Zallal Mixed Use- Welfare Plan- DG-BUJ-106-0000-NSM-PLN-HS-000021 Rev,2- Does not specifically and document the total number of welfare staff for the total workforce. |  |  |  | Number of Welfare Staff / Total Number of Staff
% closed welfare observations or red flag if 0 observations | Total number of Welfare Observations |  | DR-062 | N/A. Zero inspections resulted in no observations. |  |  |  | Number of Welfare Observations Closed / Total number of Welfare Observations
| Total number of Closed Welfare Observations |  | DR-062 | N/A. Zero inspections resulted in no observations.
% of Welfare Non-compliances closed | Total Welfare Non-compliances | Further evidence is required. Welfare facilities/camp hazard observation register | DR-064 | DSQ P-2 Daily HSE Report- Focus Inspection Welfare Facilities- DG-DSQ-316-0000-AEC-RPT-HS-001081 dated 14/12/2024- 24 welfare related observations were recorded. |  |  |  | Total Closed Welfare Non-compliances / Total Welfare Non-compliances
| Total Closed Welfare Non-compliances | Further evidence is required. Welfare facilities/camp hazard observation register | DR-064 | Unable to verify the total number of closed out welfare non-compliances
Average Cycle Time to Close Welfare Non-compliances | Cycle time to close Welfare Non-Compliances | Further evidence is required. Welfare facilities/camp hazard observation register | DR-064 | Unable to verify the average time to close out identified welfare grievances. |  |  |  | Sum (Cycle time to close Welfare Non-compliances) / Total number of Welfare Non-compliances
Is frequency of Labor Accommodation Inspection occurring in accordance with VMMP? | Mitigation measures in the event of welfare audit observations & recommendations | Data Not Available | DR-064 | Unable to verify what mitigation measures have been accepted and closed out |  |  |  | Labor accommodation inspection frequency
Go to Main Page
Refresh
Go to Document
Go to Analysis
Note on C13: ddmmyyyy

## DevCoAssessmentAnalysis(D&C)
PIF Project Lighthouse
DevCoAssessmentAnalysis(D&C)
Assessment Criteria | Data Point | Value | Rating | Score | Assessment Criteria Weightage | Assessment Guideline/Formula | Good | Satisfactory | Needs Improvement | Remarks 1 | Performance Signal | Performance Signal Score | Performance Signals Weightage | Remarks 2 | Key Topic | Key Topic Score | Remarks 3
% of CESMP mitigation measures which align with ESIA* | Environmental mitigation measures included in CESMP | Data Not Available | Needs Improvement | 1 | 10% | Environmental mitigation measures included in CESMP / Environmental mitigation measures recommended in ESIA | >80% | 60-80% | <60% |  | Construction Planning Maturity | 1.2 | 70% |  | Construction | 1.56
Environmental mitigation measures recommended in ESIA
Has the Construction Execution Plan been updated to reflect the latest stage of construction? | Update of construction execution plan | Data Not Available | Needs Improvement | 1 | 15% | Update of construction execution plan | Yes |  | No
Has the construction sequence and method statement been reviewed and approved? | Review and approval of Construction sequence & method statement | Data Not Available | Needs Improvement | 1 | 15% | Review and approval of construction sequence and method statement | Yes |  | No
Is total land acquisition sufficient to achieve the area required for construction site logistics? | Planned Area provision for site offices, amenities, laydown areas, storage facilities, workforce accommodations | No | Needs Improvement | 1 | 10% | Sufficient land acquired | Yes |  | No
Actual Area provision for site offices, amenities, laydown areas, storage facilities, workforce accommodations
Have Traffic Simulations been completed in preparing the Site & Logistics Plan? | Completion of Traffic Simulations | Data Not Available | Needs Improvement | 1 | 10% | Completion of traffic simulations | Yes |  | No
Has the Project Execution Plan been updated and approved in the last 12 months? | Date of latest approved Procurement Plan | Yes | Good | 3 | 10% | Date of latest approved Procurement Plan less than 12 months from Current Date | Yes |  | No
% of Stakeholder MOU** / LUPs*** not executed in accordance with critical lead time | Number of Stakeholder MOU or Land Use Permits not executed on time | Data Not Available | Needs Improvement | 1 | 30% | Number of Stakeholder MOU or Land Use Permits not executed on time/ Total number of Stakeholder MOU or Land Use Permits required | <20% | 20-60% | >60%
Total Stakeholder MOU or Land Use Permits required
% of Workforce Hired against Workforce Estimates | Forecast workforce requirements | 94.12% | Good | 3 | 30% | Actual workforce employed / forecast workforce requirements | >90% | 70-90% | <70% |  | Workforce Resource Availability | 2.4 | 30%
Actual workforce employed
% of Labor Camp Capacity against Workforce Estimates | Forecast number of labor camps | Data Not Available | Needs Improvement | 1 | 30% | Actual number of labor camps / Forecast number of labor camps | >90% | 70-90% | <70%
Actual number of labor camps
% of Material Supply Capacity against Material Demand Estimates | Forecast number of batching / crushing plants/ precast yards, etc. | 87.33% | Good | 3 | 40% | Actual number of batching plants / forecast number of batching plants | >80% | 40-80% | <40%
Actual number of batching / crushing plants/ precast yards, etc.
Did DevCo adhere to Technical Submittals Review Cycle Time (RCT)? | Time taken for closure of technical queries | Yes | Good | 3 | 10% | Adherence to Technical Submittals Review Cycle Time | Yes |  | No |  | Adherence to Design | 2.5 | 70% |  | Quality | 2.29
Technical Submittal Review Cycle Time (RCT)
% of approved shop drawing reviews vs planned | Total number of shop drawing review requests | 94.65% | Good | 3 | 15% | Total number of shop drawing reviews approved / Total number of shop drawing review requests | >90% | 60-90% | <60%
Total number of shop drawing reviews approved
% of approved product waivers vs product specified | Total number of product sample & material approvals requested | 4900% | Good | 3 | 15% | Total number of product sample & materials approved / Total number of product sample & material approvals requested | >90% | 60-90% | <60%
Total number of product sample & materials approved
% of Certified As-Built Drawing Packages vs Planned | Number of As-Built Drawing review requests | Data Not Available | Needs Improvement | 1 | 20% | Number of As-built reviews / approvals / Number of As-Built review requests | >80% | 60-80% | <60%
Number of As-Built Drawings reviews approved
MIR Inspection Rate | Total number of MIRs requested | 62.45% | Satisfactory | 2 | 10% | Number of MIR Inspected / Total number of MIRs requested | >80% | 60-80% | <60%
Total number of MIRs inspected
MIR Acceptance and Approval Rate | Total number of MIRs approved | 100% | Good | 3 | 10% | Number of Approved MIR / Total number of MIRs requested | >80% | 60-80% | <60%
WIR Inspection Rate | Total number of WIRs requested | 91.8% | Good | 3 | 10% | Number of WIR Inspected / Total number of WIRs requested | >80% | 60-80% | <60%
Total number of WIRs inspected
WIR Acceptance and Approval Rate | Total number of WIRs approved | 92.82% | Good | 3 | 10% | Number of Approved WIR / Total number of WIRs requested | >80% | 60-80% | <60%
Does the frequency of Audits align with the QMP? | Required Audit frequency | Data Not Available | Needs Improvement | 1 | 40% | Alignment of audit frequency | Yes |  | No |  | Quality Assurance / Quality Control (QA/QC) | 1.8 | 30%
% closure of Non-Conformance Reports (NCR) | Total number of defects & NCRs | 89.83% | Good | 3 | 40% | Number of Non-Conformance Reports Closed / Total Number of Non-Conformance Reports | >80% | 60-80% | <60%
Total number of closed defects & NCRs
Average NCRs closeout Cycle Time | Average time to close NCRs | 2 weeks | Needs Improvement | 1 | 20% | Sum (NCR Closeout cycle time)/Total number of Non-Conformance Reports | <10 days | 10-21 days | >21 days
% of procurement packages delivered within the planned lead times defined in the PMP | Number of Planned Procurement Packages | Data Not Available | Needs Improvement | 1 | 20% | Number of Procurement Packages Delivered on Time / Number of Planned Procurement Packages | >80% | 70-80% | 40-70% |  | Procurement & Contracting Compliance | 1 | 30% |  | Procurement | 1.84
Number of Procurement Packages Delivered on Time
% of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures | Total number of claims and variations | Data Not Available | Needs Improvement | 1 | 20% | Total number of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures / Total number of claims and variations | >70% | 50-70% | <50%
Total number of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures
% of packages procured with 100% complete, compliant and well-structured documentation | Total number of packages | Data Not Available | Needs Improvement | 1 | 20% | Total number of packages procured with 100% complete, compliant and well-structured documentation / Total number of packages | >70% | 50-70% | <50%
Total number of packages procured with 100% complete, compliant and well-structured documentation
% of awarded contracts where vendors appointed passed full due diligence checks | No. of awarded contracts where vendors appointed passed full due-diligence checks | Data Not Available | Needs Improvement | 1 | 20% | No. of awarded contracts where vendors appointed passed full due-diligence checks / Total number of awarded contracts | >90% | 90-85% | <85%
Total number of awarded contracts
Did the DevCo complete a Supply Chain Risk-Market Intelligence Assessment in the last quarter? | Supply Chain Risk-Market Intelligence Assessment | 0% | Needs Improvement | 1 | 20% | Completion of supply chain risk-market intelligence assessment | Yes |  | No
% of procurement activities executed as planned in the Annual Procurement Plan | Total number of procurement activities | 69.35% | Good | 3 | 30% | Number of procurement activities executed as planned / Total number of procurement activities | >60% | 20-60% | <20% |  | Procurement & Contracting Execution Performance | 2.2 | 70%
Number of procurement activities executed as planned
% of deviations in total awarded contract value with tender cost estimates | Value of Awarded Contract | 9.117% | Good | 3 | 30% | (Value of Contract Awarded - Tender Cost Estimate) / Value of Award Contract | <20% | 20-60% | >60%
Tender Cost Estimate
% of contracts with filed claims | Number of contracts with filed claims | 0% | Needs Improvement | 1 | 20% | Number of contracts with filed claims / Total number of awarded contracts | <20% | 20-60% | >60%
Are Payment Certificates and payments being processed in accordance with the Contract terms and conditions? | Processing of payment certificates and payments | 0% | Needs Improvement | 1 | 10% | Processing of payment certificates and payments | Yes |  | No
Are Vendor performance assessment occurring which capture financial instability, delays, repeated quality issues in real-time? | Alignment of sourcing strategies with project schedules and requirements | 0% | Needs Improvement | 1 | 10% | Vendor performance assessment | Yes |  | No
Does the HSE Management Manual have adequate provision for identification and escalation of high risk activities? | Escalation criteria for high risk activities | 0% | Needs Improvement | 1 | 5% | Provision for identification and escalation of high risk activities | Yes |  | No |  | HSE Compliance | 1.5 | 50% |  | HSE and Welfare | 1.25
Is the rate of review of the Safety Risk Register in accordance with the HSE Management Manual? | HSE Risk Register Review Rate | Data Not Available | Needs Improvement | 1 | 2% | Review rate of safety risk register | Yes |  | No
% of closed Safety Risk items | Total number of Safety Risk items | Data Not Available | Needs Improvement | 1 | 4% | Total number of closed Safety Risk items / Total number of safety risk items | >80% | 60-80% | <60%
Total number of closed Safety Risk items
Average cycle time to close Safety Risk items | Cycle time to close Safety Risk items (in days) | Further evidence is required. Access to Salini Saudi Arabia Monthly HSE Observation Tracker required. Access to Al-Zallal Mixed Used HSE Monthly tracker. | Needs Improvement | 1 | 4% | To input final number Sum (Cycle time to close safety risk items) / Total number of closed safety risk items | <7 days | 7-14 days | >14 days
Average cycle time to close Safety Incident | Cycle time to close Safety Incident (in days) | Further evidence is required. Access to incident register is required. | Needs Improvement | 1 | 5% | To input final number. Sum (Cycle time to close safety incident) / Total number of closed safety incidents | <7 days | 7-14 days | >14 days
Is the emergency drill rate compliant with EEPP? | Planned number of Emergency Drills | No | Needs Improvement | 1 | 5% | Compliance of emergency drill rate | Yes |  | No
Actual number of Emergency Drills
Recommended time to complete Emergency drills
Actual Time to complete Emergency drills
Fatality Rate (FR) | No. of incidents resulting in fatality or severe impairment per 200,000 work hours | 0 | Needs Improvement | 1 | 15% | No. of incidents resulting in fatality or severe impairment per 200,000 work hours | 0% | 0.001-0.0199 | >0.02
Lost Time Injury Frequency Rate (LTIFR) | No. of incidents resulting in lost time per 200,000 work hours | 0 | Needs Improvement | 1 | 10% | No. of incidents resulting in lost time per 200,000 work hours | <0.1 | 0.1-1.5 | >1.5
Total Recordable Incident Rate (TRIR) | No. of recordable incidents per 200,000 work hours | 0 | Needs Improvement | 1 | 10% | No. of recordable incidents per 200,000 work hours | <0.5 | 0.5-5 | >5
Near Miss Rate | No. of near misses recorded per 200,000 work hours | 0.76 DGCL 0.20 Salini | Good | 3 | 15% | No. of near misses recorded per 200,000 work hours | >30 | 0.1-30 | 0%
Safety Observation Rate | No. of safety observation recorded per 200,000 work hours | 353.8 Salini Saudi Arabia 158.7 DGCL | Good | 3 | 10% | No. of safety observation recorded per 200,000 work hours | >200 | 10-200 | <10
Leadership Safety Walk Rate | Total number of Safety Walks | Data Not Available | Needs Improvement | 1 | 15% | Total number of Safety Walks with Leadership / Total number of Safety Walks | >70% | 50-70% | <50%
Total number of Safety Walks with Leadership
% of Grievances Closed | Number of grievances closed | Data Not Available | Needs Improvement | 1 | 15% | Number of grievances closed / Total number of grievances | >80% | 60-80% | <60% |  | Welfare Compliance | 1 | 50%
Total number of grievances
Average Cycle Time to Close Grievances | Cycle time to close grievances | Further evidence is required . Welfare facilities/camp hazard observation register. | Needs Improvement | 1 | 10% | Sum (Cycle time to close grievances) / Total number of grievances | <14 days | 14-28 days | >28 days
% of Welfare Staff vs Total workforce | Percentage of Welfare Staff against total staff | 0 | Needs Improvement | 1 | 20% | Number of Welfare Staff / Total Number of Staff | >2% | 1-2% | <1%
% closed welfare observations or red flag if 0 observations | Total number of Welfare Observations | Data Not Available | Needs Improvement | 1 | 10% | Number of Welfare Observations Closed / Total number of Welfare Observations | >60% | 40-60% | <40% ; no observations recorded
Total number of Closed Welfare Observations
% of Welfare Non-compliances closed | Total Welfare Non-compliances | Data Not Available | Needs Improvement | 1 | 10% | Total Closed Welfare Non-compliances / Total Welfare Non-compliances | >80% | 60-80% | <60%
Total Closed Welfare Non-compliances
Average Cycle Time to Close Welfare Non-compliances | Cycle time to close Welfare Non-Compliances | Further evidence is required. Welfare facilities/camp hazard observation register | Needs Improvement | 1 | 10% | Sum (Cycle time to close Welfare Non-compliances) / Total number of Welfare Non-compliances | <14 days | 14-28 days | >28 days
Is frequency of Labor Accommodation Inspection occurring in accordance with VMMP? | Mitigation measures in the event of welfare audit observations & recommendations | Data Not Available | Needs Improvement | 1 | 25% | Labor accommodation inspection frequency | Yes |  | No
Go to Main Page
Refresh
Go to Document
Go to Input

## InterviewQuestion(D&C)
PIF Project Lighthouse
InterviewQuestion(D&C)
SN | Question | Date of Interview | Response | Internal Comment | Follow Up Question
1 | What are the challenges in implementation of the Project Execution Plan and how are you managing those? | 2025-05-09 16:05
2 | Have there been any setbacks with the required land acquisition, if so, what are they and how do you plan to overcome the issues? | 2025-05-09 16:05
3 | Have any delays occurred due to stakeholder objections; how did you resolve the issue? | 2025-05-09 16:05
4 | Have there been any challenges with labor camp establishment, number, quality or provision of amenities in accordance with workforce estimates? | 2025-05-09 16:05
5 | Have there been any challenges in hiring the required skilled labor workforce, how do you plan to overcome this? | 2025-05-09 16:05
6 | How do you track and record workforce retention and turnover rate? | 2025-05-09 16:05
7 | How do you track and record plant/ equipment downtime? | 2025-05-09 16:05
8 | What are the reasons for any deviations from the approved design intent? | 2025-05-09 16:05
9 | Have there been delays in the approval's workflow, if so, what actions have been taken to resolve the delays? | 2025-05-09 16:05
10 | Have material or product availability and lead times led to substitution requests? | 2025-05-09 16:05
11 | Has the required number of ITPs been signed off throughout construction? | 2025-05-09 16:05
12 | Out of all the defects and NCRs raised, how many are closed out? | 2025-05-09 16:05
13 | What are the challenges preventing adherence to the planned number of audits, what measures have you undertaken to resolve the challenges? | 2025-05-09 16:05
14 | Have any Vendors failed to deliver the work under contact, what has been done to resolve the issue and to track Vendor performance? | 2025-05-09 16:05
15 | What strategies are in place to catch up on the procurement schedule, can you show evidence this is working? | 2025-05-09 16:05
16 | What level of market intelligence has been applied to the Supply Chain Risk Assessment, provide example. | 2025-05-09 16:05
17 | Is the DevCo aware of suppliers/contractors not fulfilling service delivery compliance requirement as per contract terms (contract KPI compliance). Are there any mitigation measures in place? Provide example. | 2025-05-09 16:05
18 | Are there any claims or disputes resulting in financial risk, project disruption or legal escalation? Are these resolved within contractually agreed timelines? What is the plan for resolution? | 2025-05-09 16:05
19 | Were there procurement bottlenecks due to approval delays, bid evaluation inefficiencies, or poor planning, negatively impacting project schedules, what is being done to resolve this? Provide example. | 2025-05-09 16:05
20 | Of the incidents / safety concerns raised, are there any that are difficult to resolve and why? | 2025-05-09 16:05
21 | What mitigation measures have been implemented as a result of incidents and safety observations raised? How many have had mitigation measures put in place? Provide an example. | 2025-05-09 16:05
22 | Are there any recurring incidents / safety observations outside of your control, if so, please provide detail? | 2025-05-09 16:05
23 | What are the challenges preventing leadership safety walks, what measures have you undertaken to resolve the challenges? | 2025-05-09 16:05
24 | Have there been challenges in sourcing qualified HSE&W leaders? If so, what have you done to resolve the shortfall, such as training? Do you maintain a training register? If so, please provide a sample. | 2025-05-09 16:05
25 | What mitigation measures have been implemented as a result of welfare audit observations & recommendations? | 2025-05-09 16:05
Go to Main Page
Refresh

## AddDataPoint(D&C)
PIF Project Lighthouse
AddDataPoint(D&C) |  |  |  |  | Land Acquisition Requirements |  |  |  |  | Quality Audits |  |  | Procurement Packages |  |  |  |  | Incident Management | [5 empty] | Compliance Management - Audits/Inspections |  |  |  |  | Compliance Management - Actions |  |  |  |  | Safety Trainings
SN | Data Source | Additional Data Point | Value | Scorecard Visualization | SN | Program | Acquired (Ha) | Under Negotiation (Ha) | Pending (Ha) | SN | Month | Number of Quality Audits | SN | Parameter | Baseline | Actual | Forecast | SN | Incident Category | Number of Incidents (To-Date) | Number of Investigations in Progress | Number of Investigations Completed | Number of Investigations Pending Approval | SN | Audits/Inspections | In Progress_audits | Completed_audits | Remaining Planned | SN | Actions | In Progress_actions | Completed_actions | Pending Approval | SN | Year | Value_training
1 |  | No. of Site Access Required |  |  | 1 |  |  |  |  | 1 | Jan |  | 1 | Count |  |  |  | 1 | Fatalities |  |  |  |  | 1 | HSE Audit |  |  |  | 1 | HSE |  |  |  | 1 | Jan
2 |  | No. of Site Access Provided |  |  | 2 |  |  |  |  | 2 | Feb |  | 2 | Value (in M SAR) |  |  |  | 2 | Severe Impairment |  |  |  |  | 2 | Welfare Inspection |  |  |  | 2 | Welfare |  |  |  | 2 | Feb
3 |  | Packaging & Phasing Strategy |  |  | 3 |  |  |  |  | 3 | Mar | [6 empty] | 3 | Lost Time Incidents | [14 empty] | 3 | Mar
4 |  | Execution & Site Logistics | [7 empty] | 4 | Apr | [6 empty] | 4 | Recordable Incidents | [14 empty] | 4 | Apr
5 |  | Procurement Strategy | [7 empty] | 5 | May | [6 empty] | 5 | Near Misses | [14 empty] | 5 | May
6 |  | Required area for land acquisition | [7 empty] | 6 | Jun | [22 empty] | 6 | Jun
7 |  | Mitigation of Project Execution Plan implementation challenges | TBA | [6 empty] | 7 | Jul | [22 empty] | 7 | Jul
8 |  | Occurred delays due to stakeholder objections | [7 empty] | 8 | Aug | [22 empty] | 8 | Aug
9 |  | Workforce Availability | [7 empty] | 9 | Sep | [22 empty] | 9 | Sep
10 |  | Resource Availability | [7 empty] | 10 | Oct | [22 empty] | 10 | Oct
11 |  | Workforce retention track record | [7 empty] | 11 | Nov | [22 empty] | 11 | Nov
12 |  | Turnover rate track record | [7 empty] | 12 | Dec | [22 empty] | 12 | Dec
13 |  | Plant/equipment downtime track record
14 |  | Number of technical queries raised
15 |  | Number of technical queries closed
16 |  | Average time to complete shop drawing reviews | 32
17 |  | Number of shop drawing review conducted | 13670
18 |  | Number of Shop Drawings Rejected | 947
19 |  | Number of material / product substitution requests | 7
20 |  | Average time to approve product sample & materials | 10
21 |  | Product & Material Approval Rate | 985
22 |  | Number of As-built drawing review conducted
23 |  | Average time to approve As-built rejections / iterations
24 |  | As-Built Drawing Approval Rate
25 |  | Average time to complete MIRs and close out approvals
26 |  | Average time to complete WIRs and close out approvals
27 |  | NCR Closed Rate | 0.86
28 |  | NCR Closed-Out Average Cycle Time | 14
29 |  | Number of NCRs open for between 30 and 60 days
30 |  | Number of NCRs open for more than 60 days
31 |  | Leadership engagement
32 |  | Total number of ITPs requested | 38
33 |  | Total number of ITPs attended | 33
34 |  | Total number of ITPs approved | 5
35 |  | Total number of ITPs completed | 38
36 |  | Total number Quality Reports required
37 |  | Total number Quality Reports completed
38 |  | Completeness of Quality Management Plan | Needs Improvement
39 |  | Required number of ITPs signed off throughout construction
40 |  | Total number of raised closed-out defects & NCRs | 86
41 |  | Forecasted Procurement Budget | 41445041101
42 |  | Actual Procurement Budget | 14555145496
43 |  | Vendor Database
44 |  | Vendor Shortlist
45 |  | Vendor Awarded
46 |  | Vendor KPIs
47 |  | Vendor Performance Database
48 |  | Tender return date: Planned / Actual
49 |  | Tender Review & award time: Planned / actual
50 |  | Pre-Tender Cost Estimate
51 |  | Tender Performance Index
52 |  | Contract clauses
53 |  | Contract negotiation
54 |  | Scope / design maturity
55 |  | Compliance with local content regulations / policies
56 |  | Dispute rate
57 |  | Claims processing cycle time
58 |  | No. of related CRs being requested during or after tendering phase due to identified scope gap
59 |  | Procurement cycle time
60 |  | Tender pack quality
61 |  | Total packages
62 |  | Planned Packages | 86
63 |  | Awarded Packages | 18
64 |  | Trade Most at Risk
65 |  | Highest Risk Work Site
66 |  | Number of planned audits | 4
67 |  | Number of conducted audits | 3
68 |  | Total Safe Manhours | 59143494
69 |  | Total number of closed Corrective actions | 193
70 |  | Inspection Pass Rate | 0.9504
71 |  | No. of recurring incidents / safety observations outside control
72 |  | Total Site Manhours | 9579384
73 |  | Welfare of labor camps
74 |  | Welfare of site facilities
75 |  | Labor accommodation inspection rate | 0.836
76 |  | Regulation Compliance
Go to Main Page
Refresh

## DevCoAssessmentInput(CE&O)
PIF Project Lighthouse
DevCoAssessmentInput(CE&O)
Assessment Criteria | Data Point | Input Value | Data Source | Assessor Remarks | Assessment Time Stamp | Reviewer Remarks | Review Time Stamp | Formula
Budget Variance | PIF Approved Capex budget (Initial Business Plan) | 204358702695.671 | DR-003-01 | This is the reported BoD budget in the cost report in Q3 2023. This is not the budget at the time of the DevCo inception. |  | In collaboration with PIF, we determined that further historical analysis was unnecessary. The current budget variance provides a clear indication of trends and highlights the critical need for enhanced budget planning and controls. This presents an excellent opportunity to define processes and achieve greater financial accuracy moving forward. |  | [Forecast Budget - PIF Approved Capex budget (Initial Business Plan)]/ PIF Approved Capex budget (Initial Business Plan)
| Forecast budget (EAC) | 349203458382.3173 | DR-003-01 | Value taken from the cost report provided by Diriyah. (Estimate to Complete from Cost report and also the Reference Forecast from commercial report) |  | The significant budget increase over a short period highlights the need to review the original budget and address any challenges in budget control.
% of projects having Budget Variance | Number of Projects with Budget Variance | 102 | DR-065 | The value taken from the cost template provided by Diriyah. |  | About 43% of the projects have variance, requiring the need for deeper analysis as to which Masterplan and projects are most affected. Enhanced mechanism and controls in developing project scope may help reducing this percentage and better improve budgeting and financial planning. |  | Number of Projects with Budget Variance / Total number of Projects
| Total number of projects | 239 | DR-003-01 | - The total number of projects has been taken from the Cost Report. - This number of split in 4 portfolios and 39 Districts. - There are 9 projects on hold, 4 projects cancelled and 2 projects not initiated. |  | The extensive number of projects highlights the complexities of managing numerous initiatives through large PMC teams and multiple contractors. Considering the procurement of additional superpackages could be beneficial. Comparing the performance of current superpackages with individual projects may provide valuable insights. Reviewing the procurement strategy could help optimize delivery, contractor management, and associated costs, thereby minimizing risks and exposure.
% of projects with contingency utilization rate > 1 | Number of projects with contingency utilization > 1 | 28 |  | The value is assessed from the commercial report, in the contingency utilization which analysis is challenging due to the reported information and terminology considered. |  | This matter has been discussed with DevCo, and they are expected to provide clarity on this requirement. The contingency percentage allowance may need to be revisited, and a deeper analysis of the specific projects required to understand the full - if not more - utilization of the contingency budget. |  | (Number of projects with contingency utilization > 1) / (Total number of projects)
% of projects with Approved Change Requests (design/construction) having a cost impact greater than 2% | No. of projects with approved change request having a cost impact greater than 2% | 0 |  | A number of projects have been affected by variations. However, the report is not specifically highlighting those which cost impact are over 2% of the budget. |  | Reporting this information and conducting a deeper analysis would provide valuable insights into the reasons for the cost impact. This would enable the development of measures to prevent significant cost impacts from variations. |  | (No. of projects with approved change request having a cost impact greater than 2%) / (Total number of projects)
% of projects with Approved Claims | No. of projects with approved claims | 0 |  | Data not provided. On top 10 project listed |  | As above |  | (No. of projects with approved claims) / (Total number of projects)
% of provisional sums of the latest PIF Approved Capex budget | Total provisional sums | 0 |  | No indication of utilisation of provisional sums |  | Although the information is not currently reported, DevCo has confirmed that it is available at the project level. Consolidating this information at the Masterplan and DevCo levels would be helpful to ensure that sufficient provisional sums have been accounted for, given the total amount consumed. Enhanced budget planning measures are recommended to improve visibility of provisional sums and their utilization. |  | Total Provisional Sums/Latest Approved Budget
| Latest Approved budget | 204358702695.671 |  | latest provisionnal sums approved budget is not available |  | As above
% of variance of Allocated Provisional sums against the awarded amount | Actual Utilized Provisional Sums | 0 |  | No indication of utilisation of provisional sums and its utilisation |  | As above |  | (Total Provisional Sums−Actual Utilized Provisional Sums)/Total Provisional Sums
Go to Main Page
Refresh
Go to Document
Go to Analysis

## DevCoAssessmentAnalysis(CE&O)
PIF Project Lighthouse
DevCoAssessmentAnalysis(CE&O)
Assessment Criteria | Data Point | Value | Rating | Score | Assessment Criteria Weightage | Assessment Guideline/Formula | Good | Satisfactory | Needs Improvement | Remarks 1 | Performance Signal | Performance Signal Score | Performance Signals Weightage | Remarks 2 | Key Topic | Key Topic Score | Remarks 3
Budget Variance | PIF Approved Capex budget (Initial Business Plan) | 70.88% | Needs Improvement | 1 | 80% | [Forecast Budget - PIF Approved Capex budget (Initial Business Plan)]/ PIF Approved Capex budget (Initial Business Plan) | <10% | 10-20% | >20% |  | Budget Variance | 1 | 60% |  | Overall Budget | 1.04
Forecast budget (EAC)
% of projects having Budget Variance | Number of Projects with Budget Variance | 42.68% | Needs Improvement | 1 | 20% | Number of Projects with Budget Variance / Total number of Projects | <10% | 10-30% | >30%
Total number of projects
% of projects with contingency utilization rate > 1 | Number of projects with contingency utilization > 1 | 11.72% | Satisfactory | 2 | 20% | (Number of projects with contingency utilization > 1) / (Total number of projects) | <10% | 10-30% | >30% |  | Budget Trend | 1.2 | 20%
% of projects with Approved Change Requests (design/construction) having a cost impact greater than 2% | No. of projects with approved change request having a cost impact greater than 2% | 0% | Needs Improvement | 1 | 40% | (No. of projects with approved change request having a cost impact greater than 2%) / (Total number of projects) | <5% | 5-15% | >15%
% of projects with Approved Claims | No. of projects with approved claims | 0% | Needs Improvement | 1 | 40% | (No. of projects with approved claims) / (Total number of projects) | <2% | 2-5% | >5%
% of provisional sums of the latest PIF Approved Capex budget | Total provisional sums | 0% | Needs Improvement | 1 | 40% | Total Provisional Sums/Latest Approved Budget | <5% | 5-15% | >15% |  | Provisional Sum Utilization | 1 | 20%
Latest Approved budget
% of variance of Allocated Provisional sums against the awarded amount | Actual Utilized Provisional Sums | Data Not Available | Needs Improvement | 1 | 60% | (Total Provisional Sums−Actual Utilized Provisional Sums)/Total Provisional Sums | <10% | 10-20% | >20%
Go to Main Page
Refresh
Go to Document
Go to Input

## InterviewQuestion(CE&O)
PIF Project Lighthouse
InterviewQuestion(CE&O)
SN | Question | Date of Interview | Response | Internal Comment | Follow Up Question
1 | What corrective actions were taken when a project exceeds its budget? | 2025-05-09 16:05
2 | What had been the three key factors contributing to budget overruns? | 2025-05-09 16:05
3 | Based on the revisions to the budget did the DevCo perform any trend analysis to understand the root cause factors contributing to such revisions and was the same recorded in the lessons learnt repository? | 2025-05-09 16:05
4 | Which project categories or project stages requested for more budget than planned? | 2025-05-09 16:05
5 | Was the scope of work identified for Provisional sums defined at concept stage? | 2025-05-09 16:05
6 | Was the amount estimated based on historical benchmarking rates? If yes, please provide a sample. | 2025-05-09 16:05
Go to Main Page
Refresh

## AddDataPoint(CE&O)
PIF Project Lighthouse
AddDataPoint(CE&O) |  |  |  |  | Budget Performance
SN | Data Source | Additional Data Point | Value | Scorecard Visualization | Year | Budget Value (Baseline) in M SAR | Budget Value (Revised) in M SAR | Budget Value (Forecast) in M SAR
1 |  | Estimate to Completion Declared by DevCo | 316068041489.5395
2 |  | Total Expenditure to Date | 33213178137.7779
3 |  | Contingency budgeted at DevCo level | 27772826385
4 |  | Contingency utilized at DevCo level | 1183022352
5 |  | Contingency Utilization Rate | 4.26%
6 |  | Value of Changes in Design Stage
7 |  | Value of Changes in Construction Stage
8 |  | Number of Changes (Concept MP)
9 |  | Number of Changes (Detailed MP)
10 |  | Number of Changes (Concept Design)
11 |  | Number of Changes (Detailed Design)
12 |  | Number of Changes (Construction)
13 |  | Total Awarded Cost | 83140439457.2953
14 |  | Approved Variations and Claims
15 |  | Uncommitted Cost | 266140780170.0221
16 |  | Pending Variations
17 |  | Anticipated Variations
Go to Main Page
Refresh

## DevCoAssessmentInput(I&T)
PIF Project Lighthouse
DevCoAssessmentInput(I&T)
Assessment Criteria | Data Point | Input Value | Data Source | Assessor Remarks | Assessment Time Stamp | Reviewer Remarks | Review Time Stamp | Formula
Is there an innovation Strategy or document that lists the key focus areas and initiatives across design, construction and operation and aligned with DevCo strategic plan? | Availability of an innovation strategy | No | [5 empty] | Innovation Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10%
| Alignment of innovation strategy with DevCo Strategic Plan | No
| List of focus areas of innovation and technology | No
| List of innovative initiatives throughout project lifecycle (design, construction and operation) | No
| Availability of innovation cost-benefit analysis | No
| Implementation Success Rate for Innovation Strategy | No
| Process for innovation | No
| Budget of implementation | No
Is there a smart city Strategy or document that lists the key focus areas of smart city aligned with DevCo strategic plan? | Availability of a smart city strategy | Yes | [5 empty] | Smart City Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10%
| Alignment of smart city strategy with DevCo Strategic Plan | Yes
| List of Smart City focus areas | Yes
| List of smart city initiatives within each key focus area | Yes
| Availability of smart city goals and set of KPIs | Yes
| Availability of smart city cost-benefit analysis | Yes
| Implementation Roadmap for selected smart city initiatives | Yes
| Budget of implementation | Yes
Is there an impact assessment report or identified process/ guidelines to evaluate the impact of the innovation / smart city technologies adoption on DevCo performance? | Availability of approach / process and guidelines to evaluate the impact of implementing innovations and technologies | Yes | [5 empty] | Adoption on DevCo performance? Robust assessment process and guidelines - 30%; Availability of sample of impact assessment report - 30%; Availability of action plan - 10%; Use of innovative tools/platforms/dashboards - 30%
| Availability of sample of impact assessment report | No
| Availability of action plan | Yes
| Use of innovative tools/platforms/dashboards | No
Is there evidence for innovation / smart city technologies successful implementation (in final design report, master plan or other)? | Evidence for adoption of innovation/smart city considerations within the master plan | Yes | [5 empty] | Evidence for innovation/smart city technologies successful implementation
| Evidence for adoption of innovation/smart city considerations within the project detailed design | Yes
Are there Pilot or R&D projects conducted? | Availability of innovation/smart city piloting or R&D procedures | Yes | [5 empty] | Pilot or R&D projects conducted? Availability - 20%; Adequate list of focus areas - 35%; Procedure - 15%; Outcome assessment robustness - 30%
| List of focus areas | Yes
| Procedure | Yes
| Robustness of assessment of pilot and R&D outcomes | No
% of pilot / R&D Projects Transitioned into Full-Scale | Number of pilot projects | 2 | [5 empty] | [(Number of pilots that are scaled successfully + Number of R&D projects that are successfully piloted or fully-scaled) / (Number of pilot projects + Number of R&D projects)]
| Number of R&D projects | 0
| Number of pilot projects that are scaled successfully | 2
| Number of R&D projects that are successfully piloted or fully-scaled | 0
Availability of Innovation unit / department with structured team | Availability of Innovation unit/department | No | [5 empty] | Availability of Innovation: Availability - 20%; Adequate Key positions planned in the org. structure - 30%; Unit/department position within the company hierarchy - 20%; Qualifications of the innovation team - 30%
| Key positions planned in the innovation unit/department | No
| Innovation unit/department within the company hierachy | No
| Qualifications of the innovation team | No
% of pilot / R&D Projects Transitioned into Full-Scale | Innovation Unit Strategy / Process & Framework | No | [5 empty] | [(Number of pilots that are scaled successfully + Number of R&D projects that are successfully piloted or fully-scaled) / (Number of pilot projects + Number of R&D projects)]
| Implementation of innovation department process / framework | No
Go to Main Page
Refresh
Go to Document
Go to Analysis

## DevCoAssessmentAnalysis(I&T)
PIF Project Lighthouse
DevCoAssessmentAnalysis(I&T)
Assessment Criteria | Data Point | Value | Rating | Score | Assessment Criteria Weightage | Assessment Guideline/Formula | Good | Satisfactory | Needs Improvement | Remarks 1 | Performance Signal | Performance Signal Score | Performance Signals Weightage | Remarks 2 | Key Topic | Key Topic Score | Remarks 3
Is there an innovation Strategy or document that lists the key focus areas and initiatives across design, construction and operation and aligned with DevCo strategic plan? | Availability of an innovation strategy | 0% | Needs Improvement | 1 | 30% | Innovation Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10% | >75% | 60-75% | <60% |  | Innovation & Technology Deployment | 1.8 | 40% | Robust smart city framework with procedures, guidelines and checklists | Innovation and Technology Adoption | 1.32 |  | #REF! | #REF! | 0 | 0 | 0.3 | 0
| Alignment of innovation strategy with DevCo Strategic Plan | [16 empty] | #REF! | #REF! | 0 | 0 | 0.3 | 0.15
| List of focus areas of innovation and technology | [17 empty] | #REF! | 0 | 0 | 0 | 0.1
| List of innovative initiatives throughout project lifecycle (design, construction and operation) | [17 empty] | #REF! | 0 | 0 | 0.3 | 0.1
| Availability of innovation cost-benefit analysis | [19 empty] | 0 |  | 0.15
| Process for innovation | [19 empty] | 0 |  | 0.15
| Budget of implementation | [19 empty] | 0 |  | 0.1
Is there a smart city Strategy or document that lists the key focus areas of smart city aligned with DevCo strategic plan? | Availability of a smart city strategy | 85% | Good | 3 | 30% | Smart City Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10% | >75% | 60-75% | <60% | [11 empty] | 0 |  | 0.1
Alignment of smart city strategy with DevCo Strategic Plan
List of Smart City focus areas
List of smart city initiatives within each key focus area
Availability of smart city goals and set of KPIs
Availability of smart city cost-benefit analysis
Implementation Roadmap for selected smart city initiatives
Budget of implementation
Is there an impact assessment report or identified process/ guidelines to evaluate the impact of the innovation / smart city technologies adoption on DevCo performance? | Availability of approach / process and guidelines to evaluate the impact of implementing innovations and technologies | 90% | Good | 3 | 10% | Adoption on DevCo performance? Robust assessment process and guidelines - 30%; Availability of sample of impact assessment report - 30%; Availability of action plan - 10%; Use of innovative tools/platforms/dashboards - 30% | >75% | 60-75% | <60%
Availability of sample of impact assessment report
Availability of action plan
Use of innovative tools/platforms/dashboards
Is there evidence for innovation / smart city technologies successful implementation (in final design report, master plan or other)? | Innovation Adoption Effectiveness Index (strategy & leadership alignment) | Data Not Available | Needs Improvement | 1 | 30% | Effectiveness index in the mentioned areas is an evaluation of successful implementation (Up to 8.3% for each element of the innovation adoption effective index) (Up to 10% for each element of the smart city adoption effective index) | >75% | 60-75% | <60%
Smart City Adoption Effectiveness Index (realized benefits & performance)
Are there Pilot or R&D projects conducted? | Availability of innovation/smart city piloting or R&D procedures | 0% | Needs Improvement | 1 | 50% | Pilot or R&D projects conducted? Availability - 20%; Adequate list of focus areas - 35%; Procedure - 15%; Outcome assessment robustness - 30% | >75% | 60-75% | <60% |  | Pilot and R&D Transition Rate | 1 | 30% | Digital Twin and Smart City Platform started as pilots and are now being implemented and scaled.
List of focus areas
Procedure
Robustness of assessment of pilot and R&D outcomes
% of pilot / R&D Projects Transitioned into Full-Scale | Number of pilot projects | Data Not Available | Needs Improvement | 1 | 50% | [(Number of pilots that are scaled successfully + Number of R&D projects that are successfully piloted or fully-scaled) / (Number of pilot projects + Number of R&D projects)] | >40% | 20-40% | <20%
Number of R&D projects
Number of pilot projects that are scaled successfully
Number of R&D projects that are successfully piloted or fully-scaled
Availability of Innovation unit / department with structured team | Availability of Innovation unit/department | Data Not Available | Needs Improvement | 1 | 50% | Availability of Innovation: Availability - 20%; Adequate Key positions planned in the org. structure - 30%; Unit/department position within the company hierarchy - 20%; Qualifications of the innovation team - 30% | >60% | 40-60% | <40% |  | Organization Maturity Towards Innovation Adoption | 1 | 30% | No DevCo-level innovation strategy and centralized innovation team
Key positions planned in the innovation unit/department
Innovation unit/department within the company hierachy
Qualifications of the innovation team
Availability of Innovation and Technology Strategy / Process & Framework | Innovation Unit Strategy / Process & Framework | Data Not Available | Needs Improvement | 1 | 50% | Availability - 50% Implementation of the unit/department framework/ process - 50% | >50% | 50% | <50%
Implementation of innovation department process / framework
Go to Main Page
Refresh
Go to Document
Go to Input

## InterviewQuestion(I&T)
PIF Project Lighthouse
InterviewQuestion(I&T)
SN | Question | Date of Interview | Response | Internal Comment | Follow Up Question
1 | If there is no innovation or smart city strategy, is there a document that lists the areas and initiatives for innovation and smart city technology applied during the design, construction, and operations stages? | 2025-05-09 16:05
2 | Are there guidelines for assessing the impact of innovation and smart city technologies on DevCo performance? | 2025-05-09 16:05
3 | If there is no pilot or R&D register, did you conduct any pilot or R&D projects? what is the number of conducted pilot/ R&D projects? Please provide a sample. | 2025-05-09 16:05
4 | What is the number of pilots / R&D projects that are scaled successfully? | 2025-05-09 16:05
5 | Is there an Innovation unit / department setup? How does the hierarchy look like? | 2025-05-09 16:05
6 | Is there an Innovation Unit strategy/ Process and Framework? If yes, please share a document relating to this. | 2025-05-09 16:05
Go to Main Page
Refresh

## AddDataPoint(I&T)
PIF Project Lighthouse
AddDataPoint(I&T)
SN | Data Source | Additional Data Point | Value | Scorecard Visualization
1 |  | Implementation Success Rate for Innovation Strategy | 0 | 0
2 |  | Innovation Adoption Effectiveness Index (strategy & leadership alignment) | 3 | 3
3 |  | Innovation Adoption Effectiveness Index (skilled human resources) | 2 | 2
4 |  | Innovation Adoption Effectiveness Index (planning & governance) | 2 | 2
5 |  | Innovation Adoption Effectiveness Index (process management) | 2 | 2
6 |  | Innovation Adoption Effectiveness Index (partnerships and collaboration) | 2 | 2
7 |  | Innovation Adoption Effectiveness Index (resource management) | 3 | 3
8 |  | Implementation Success Rate for Smart City Strategy
9 |  | Number of Smart City Use Cases | 50 | 50
10 |  | Smart City Adoption Effectiveness Index (strategy & leadership alignment) | 3 | 3
11 |  | Smart City Adoption Effectiveness Index (infrastructure readiness) | 3 | 3
12 |  | Smart City Adoption Effectiveness Index (planning & governance) | 3 | 3
13 |  | Smart City Adoption Effectiveness Index (stakeholder alignment) | 2 | 2
14 |  | Smart City Adoption Effectiveness Index (realized benefits & performance) | 1 | 1
Go to Main Page
Refresh

## DevCoAssessmentInput(S&O)
PIF Project Lighthouse
DevCoAssessmentInput(S&O)
Assessment Criteria | Data Point | Input Value | Data Source | Assessor Remarks | Assessment Time Stamp | Reviewer Remarks | Review Time Stamp | Formula
Availability of Technical Function Strategy | Availability of strategy | Yes | DR-074 |  |  |  |  | Give 'satisfactory' score if there is a technical function strategy, but it is very general and does not provide specific details of the strategy
Alignment of Technical Strategy with Organizational Strategy | Alignment of technical functions' strategy and initiatives with the overarching organizational strategy | Some Gaps | [5 empty] | Assess if elements of technical strategy is aligned with organizational strategy. "Average" score if key elements of organizational strategy is not addressed in technical strategy
Severity of Key Challenges Faced in Strategy Execution Technically | Key challenges in strategy execution | Moderate | [5 empty] | "Severe" score if challenges faced can impact strategy execution significantly (in terms of time, cost and/or quality)
Availability of Technical KPIs | Availability of KPIs | Yes, but very brief | [5 empty] | Give 'satisfactory' score if there are technical KPIs, but they are very generic
Progress of Achievement of KPIs for Technical Team | Total Number of KPIs set for the preceding year | [6 empty] | Number of KPIs achieved / Total Number of KPIs set for the same period
Number of KPIs achieved in the preceding year
Appropriateness of KPIs for Technical Team |  | Some gaps with industry benchmarks | [5 empty] | Expected elements from industry benchmarks: 1. Schedule adherence 2. Budget adherence 3. Employee attrition 4. HSE and Welfare 5. ESG
Criticality of Vacant/Missing Positions in Organization | Key positions which are missing, if any | Moderate | [5 empty] | "Severe" if more than 25% of technical department head (N-2 or 3) and above are vacant Technical department head: person leading a technical function (depends on organization size) "Moderate" if 2 position for technical department head are vacant
Appropriateness of Qualifications in Recruitment of Vacant Technical Department Head Positions | Qualifications of job descriptions for vacant technical department head positions - are they appropriate? | [6 empty] | "Critical" score if there is little to no relevance in the requested qualifications to the role
Robustness of Policy/Guideline/Procedure Communication | List of policies/procedures communicated to all employees | Moderate | [5 empty] | Strong if these are done: 1. Regular update and review of policies (3 mths) 2. All relevant policies/guidelines captured 3. Easy access (one repository with easy to find link) 4. Multi-channels to inform updates to documents e.g. email, intranet
Robustness of Policy/Guideline/Procedure Compliance Monitoring Framework | Monitoring of policies and procedures compliance | Moderate | [5 empty] | Strong if these are done: 1. Regular internal audits of processes (ongoing and rotation of topics/departments) 2. Independent internal audit department reporting directly to CEO or Board 3. Whistleblowing policy 4. Regular training for all staff (annual)
Robustness of Board Reporting Framework | Frequency of reporting to Board and PIF | Moderate | [5 empty] | Strong if all of these following points are done: 1. Board reporting policy covering frequency/trigger for updates 2. Register of Board Papers/Presentations 3. Register of Board meetings and meeting minutes
Availability of Technical Function Strategy and KPIs
Availability of Technical Function Strategy and KPIs
Availability of Technical Function Strategy and KPIs
Robustness of Board Reporting Framework Frequency of reporting to Board and PIF
Robustness of Board Reporting Framework Frequency of reporting to Board and PIF
Robustness of Board Reporting Framework Frequency of reporting to Board and PIF
Go to Main Page
Refresh
Go to Document
Go to Analysis

## DevCoAssessmentAnalysis(S&O)
PIF Project Lighthouse
DevCoAssessmentAnalysis(S&O)
Assessment Criteria | Data Point | Value | Rating | Score | Assessment Criteria Weightage | Assessment Guideline/Formula | Good | Satisfactory | Needs Improvement | Remarks 1 | Performance Signal | Performance Signal Score | Performance Signals Weightage | Remarks 2 | Key Topic | Key Topic Score | Remarks 3
Availability of Technical Function Strategy | Availability of strategy | Yes | Good | 3 | 30% | Give 'satisfactory' score if there is a technical function strategy, but it is very general and does not provide specific details of the strategy | Yes | Yes, but very brief | No |  | Technical Strategy Achievement | 2.3 | 20% |  | Technical Strategy and Enablers | 1.9
Alignment of Technical Strategy with Organizational Strategy | Alignment of technical functions' strategy and initiatives with the overarching organizational strategy | Some Gaps | Satisfactory | 2 | 30% | Assess if elements of technical strategy is aligned with organizational strategy. "Average" score if key elements of organizational strategy is not addressed in technical strategy | Well-aligned | Some gaps | Misaligned
Severity of Key Challenges Faced in Strategy Execution Technically | Key challenges in strategy execution | Moderate | Satisfactory | 2 | 40% | "Severe" score if challenges faced can impact strategy execution significantly (in terms of time, cost and/or quality) | Minor | Moderate | Severe
Availability of Technical KPIs | Availability of KPIs | Yes, but very brief | Satisfactory | 2 | 40% | Give 'satisfactory' score if there are technical KPIs, but they are very generic | Yes | Yes, but very brief | No |  | Technical KPI Achievement | 1.8 | 20%
Progress of Achievement of KPIs for Technical Team | Total Number of KPIs set for the preceding year | Data Not Available | Needs Improvement | 1 | 20% | Number of KPIs achieved / Total Number of KPIs set for the same period | >75% | 50-75% | <50%
Number of KPIs achieved in the preceding year
Appropriateness of KPIs for Technical Team |  | Some gaps with industry benchmarks | Satisfactory | 2 | 40% | Expected elements from industry benchmarks: 1. Schedule adherence 2. Budget adherence 3. Employee attrition 4. HSE and Welfare 5. ESG | Aligned with industry benchmarks | Some gaps with industry benchmarks | Significant deviation from industry benchmarks
Criticality of Vacant/Missing Positions in Organization | Key positions which are missing, if any | Moderate | Satisfactory | 2 | 60% | "Severe" if more than 25% of technical department head (N-2 or 3) and above are vacant Technical department head: person leading a technical function (depends on organization size) "Moderate" if 2 position for technical department head are vacant | Minor | Moderate | Severe |  | Technical Organization | 1.6 | 30%
Appropriateness of Qualifications in Recruitment of Vacant Technical Department Head Positions | Qualifications of job descriptions for vacant technical department head positions - are they appropriate? | 0% | Needs Improvement | 1 | 40% | "Critical" score if there is little to no relevance in the requested qualifications to the role | Well-aligned | Some gaps | Misaligned
Robustness of Policy/Guideline/Procedure Communication | List of policies/procedures communicated to all employees | Moderate | Satisfactory | 2 | 30% | Strong if these are done: 1. Regular update and review of policies (3 mths) 2. All relevant policies/guidelines captured 3. Easy access (one repository with easy to find link) 4. Multi-channels to inform updates to documents e.g. email, intranet | Strong | Moderate | Poor |  | Technical Control Environment | 2 | 30%
Robustness of Policy/Guideline/Procedure Compliance Monitoring Framework | Monitoring of policies and procedures compliance | Moderate | Satisfactory | 2 | 40% | Strong if these are done: 1. Regular internal audits of processes (ongoing and rotation of topics/departments) 2. Independent internal audit department reporting directly to CEO or Board 3. Whistleblowing policy 4. Regular training for all staff (annual) | Strong | Moderate | Poor
Robustness of Board Reporting Framework | Frequency of reporting to Board and PIF | Moderate | Satisfactory | 2 | 30% | Strong if all of these following points are done: 1. Board reporting policy covering frequency/trigger for updates 2. Register of Board Papers/Presentations 3. Register of Board meetings and meeting minutes | Strong | Moderate | Poor
Go to Main Page
Refresh
Go to Document
Go to Input

## InterviewQuestion(S&O)
PIF Project Lighthouse
InterviewQuestion(S&O)
SN | Question | Date of Interview | Response | Internal Comment | Follow Up Question
1 | How do the technical functions’ strategy and initiatives align with the overarching organizational strategy? | 2025-05-02 17:10
2 | Share any key challenges faced in executing the strategy from a technical perspective | 2025-05-02 17:10
3 | Are there any vacant/missing roles which are critical and impeding optimal execution of projects? | 2025-05-02
4 | Are there any gaps in experience/qualifications/skill sets of the existing team in delivery of the DevCo’s mandate? | 2025-05-02
5 | How are policies/procedures communicated to all employees? | 2025-05-02
6 | How is compliance with policies and procedures monitored & ensured? | 2025-05-02
7 | What is the framework for reporting to the Board? | 2025-05-02
Go to Main Page
Refresh

## AddDataPoint(S&O)
PIF Project Lighthouse
AddDataPoint(S&O) |  |  |  |  | Unfulfilled Positions |  |  |  | Critical Position Currently Unstaffed/Missing |  | Critical Position Currently Unstaffed |  | Critical Policies Missing |  |  | Critical Technical Platforms Missing |  |  | Top KPI
SN | Data Source | Additional Data Point | Value | Scorecard Visualization | Department | Total Positions | No of Positions Unfullfiled | % of Position Unfullfilled | Position Vacant | Position Missing | Name of the Department | No of Position Missing | Name of the Policy | Criticality Policies (Y/N) | Availability Policies (Y/N) | Name of the Technical Platform | Criticality Technical (Y/N) | Availability Technical (Y/N) | Name of the KPI | Weightage
1 |  | Top 5 KPIs |  |  | Project controls | 6 | 1 | 16.66% | Centralised Innovation Team | N | Project controls | 1
2 |  | Key positions |  |  | Procurment and Contracts Management | 17 | 5 | 29.41% |  |  | Procurment and Contracts Management | 5
3 |  | Unstaffed positions | 230 | 230 | Innovation | 0 | 0 | 0 |  |  | Design Management | 20
4 |  | % Unfilled positions in Construction Management | 21.59% | 0.2159 | Design Management | 202 | 20 | 9.9% |  |  | Cost Management | 28
5 |  | % Unfilled positions in Design Management | 9.9% | 0.099 | Cost Management | 189 | 28 | 14.81% |  |  | Construction Management | 38
6 |  | % Unfilled positions in Cost Management | 14.81% | 0.1481 | Construction Management | 176 | 38 | 21.59%
7 |  | % Unfilled positions in Innovation | 0% | 0
8 |  | % Unfilled positions in Project Controls | 16.66% | 0.1666
9 |  | % Unfilled positions in Procurement and Contracts Management | 29.41% | 0.2941
10 |  | Unstaffed positions which are critical and impeding execution of projects | 150 | 150
11 |  | List of missing key technical platforms
12 |  | List of critical policies missing, if any
Go to Main Page
Refresh

## AssessmentSummary
PIF Project Lighthouse
AssessmentSummary | Q1 2025
Section | Performance Signal | Performance Signal Score | Key Topic | Key Topic Score | Section Score | Remarks
Go to Main Page
Refresh

## Log
PIF Project Lighthouse
Log
SN | Stakeholder | Identity | Assessor / Reviewer | Stamp | Cell | Section | Data Point | Event
1 | MEINHARDT | Administrator | Admin | 2025-06-06 12:10 | $K$10 | DevCoAssessmentAnalysis(P&M) | NA | DevCoAssessmentAnalysis(P&M) Cell $K$10 changed to [ ]
Go to Main Page
Refresh

## User
PIF Project Lighthouse
User
No. | User Name | Password | Identity | Stakeholder Group | Main | Instructions | Glossary&Definitions | DocumentList | Log | InterviewQuestion(P&M) | AddDataPoint(P&M) | DevCoAssessmentInput(P&M) | DevCoAssessmentAnalysis(P&M) | InterviewQuestion(D&T) | AddDataPoint(D&T) | DevCoAssessmentInput(D&T) | DevCoAssessmentAnalysis(D&T) | InterviewQuestion(D&C) | AddDataPoint(D&C) | DevCoAssessmentInput(D&C) | DevCoAssessmentAnalysis(D&C) | InterviewQuestion(CE&O) | AddDataPoint(CE&O) | DevCoAssessmentInput(CE&O) | DevCoAssessmentAnalysis(CE&O) | InterviewQuestion(I&T) | AddDataPoint(I&T) | DevCoAssessmentInput(I&T) | DevCoAssessmentAnalysis(I&T) | InterviewQuestion(S&O) | AddDataPoint(S&O) | DevCoAssessmentInput(S&O) | DevCoAssessmentAnalysis(S&O) | AssessmentSummary | User | Setting | Login
1 | Admin | A_PLH_Data | Administrator | MEINHARDT | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a
2 | AssessorP&M | PLH_P&M | Assessor (P&M) | MEINHARDT | a | a | a | a | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a
3 | AssessorD&T | PLH_D&T | Assessor (D&T) | MEINHARDT | a | a | a | a | a | x | x | x | x | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a
4 | AssessorD&C | PLH_D&C | Assessor (D&C) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a
5 | AssessorCE&O | PLH_CE&O | Assessor (CE&O) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | a
6 | AssessorI&T | PLH_I&T | Assessor (I&T) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a | a | a | a | x | x | x | x | x | x | x | a
7 | AssessorS&O | PLH_S&M | Assessor (S&O) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a | a | a | a | x | x | x | a
8 | ReviewerP&M | PLH_P&M | Reviewer (P&M) | MEINHARDT | a | a | a | a | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a
9 | ReviewerD&T | PLH_D&T | Reviewer (D&T) | MEINHARDT | a | a | a | a | a | x | x | x | x | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a
10 | ReviewerD&C | PLH_D&C | Reviewer (D&C) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a
11 | ReviewerCE&O | PLH_CE&O | Reviewer (CE&O) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | a
12 | ReviewerI&T | PLH_I&T | Reviewer (I&T) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a | a | a | a | x | x | x | x | x | x | x | a
13 | ReviewerS&O | PLH_S&M | Reviewer (S&O) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a | a | a | a | x | x | x | a
Go to Main Page
Refresh

## Setting
PIF Project Lighthouse
Setting | 9 | 3 | 3 | 1 | 1 | 15 | 7 | 80 | 80 | 120 |  |  |  |  | 80 | 80 | 120
No. | DDLPnM | DDLDnT | DDLDnC | DDLCEnO | DDLInT | DDLSnO | Section | DocID | Document | Formula | 3 | 2 | 1 | Section | DocID | Document | Formula | 3 | 2 | 1 | Section | P&M |  |  |  | D&T |  |  |  | D&C |  |  |  | CE&O |  |  |  | I&T |  |  |  | S&O |  |  |  | NEW FORMULA | 3 | 2 | 1 | SEC | OLD FORMULA | 3 | 2 | 1 | SEC | [12 empty] | ID | NEW DOC | ID | OLD DOC
1 | Data Not Available | Data Not Available | Data Not Available | Data Not Available | Data Not Available | Aligned with industry benchmarks | General | Cost Data | Cost Data Template | Earned Value (EV) / Planned Value (PV) | >1 | 0.85-1 | <0.85 | P&M | Cost Data | Cost Data Template | Earned Value (EV) / Planned Value (PV) | >1 | 0.85-1 | <0.85 | P&M | Earned Value (EV) / Planned Value (PV) | >1 | 0.85-1 | <0.85 | (Percentage similarity between Approved CGI and Latest CGI at same angle and scale) + (Percentage similarity between Approved Animation and Latest Animation at same camera angle) / 2 | >70% | 50-70% | <50% | Environmental mitigation measures included in CESMP / Environmental mitigation measures recommended in ESIA | >80% | 60-80% | <60% | [Forecast Budget - PIF Approved Capex budget (Initial Business Plan)]/ PIF Approved Capex budget (Initial Business Plan) | <10% | 10-20% | >20% | Innovation Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10% | >75% | 60-75% | <60% | Give 'satisfactory' score if there is a technical function strategy, but it is very general and does not provide specific details of the strategy | Yes | Yes, but very brief | No | Earned Value (EV) / Planned Value (PV) | >1 | 0.85-1 | <0.85 | P&M | Earned Value (EV) / Planned Value (PV) | >1 | 0.85-1 | <0.85 | P&M | 1 | Baseline and Updated Master schedule (including cost linked Milestone summary for earned value, planned value analysis, Monthly Progress Report and Schedule Updates) | 11 | Original Approved and Latest version of CGI & Animation (Material Palette & Finish Schedule) at DevCo Level | 28 | Construction Environmental and Social Management Plan (including Environmental Permit Register) | 3 | Latest approved progress report (including latest PIF approved capex budget, revised and forecast budget) | 67 | Innovation Strategy (DevCo level) | 72 | Technical functions' strategy and initiatives | 1 | Baseline and Updated Master schedule (including cost linked Milestone summary for earned value, planned value analysis, Monthly Progress Report and Schedule Updates) | Cost Data | Cost Data Template
2 | No | No | No |  |  | Data Not Available | Planning & Monitoring | 1 | Baseline and Updated Master schedule (including cost linked Milestone summary for earned value, planned value analysis, Monthly Progress Report and Schedule Updates) | No. of milestones achieved on time/ No. of planned milestones | >70% | 50-70% | <50% | P&M | 1 | Baseline and Updated Master schedule (including cost linked Milestone summary for earned value, planned value analysis, Monthly Progress Report and Schedule Updates) | No. of milestones achieved on time/ No. of planned milestones | >70% | 50-70% | <50% | P&M | No. of milestones achieved on time/ No. of planned milestones | >70% | 50-70% | <50% | Material Palette & Finish Schedule matched Approved CGI | >70% | 50-70% | <50% | Update of construction execution plan | Yes |  | No | Number of Projects with Budget Variance / Total number of Projects | <10% | 10-30% | >30% | Smart City Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10% | >75% | 60-75% | <60% | Assess if elements of technical strategy is aligned with organizational strategy. "Average" score if key elements of organizational strategy is not addressed in technical strategy | Well-aligned | Some gaps | Misaligned | No. of milestones achieved on time/ No. of planned milestones | >70% | 50-70% | <50% | P&M | No. of milestones achieved on time/ No. of planned milestones | >70% | 50-70% | <50% | P&M | 2 | Program Management Plan | 12 | Original Approved and Latest version of the Drawings | 29 | Construction Execution Plan | 65 | Quarterly/annual progress reports for preceding three years (including approved budget, contingency utilization and change requests / claims) | 68 | Smart City Strategy (DevCo level) | 73 | Latest report which includes the progress of technical strategy initiatives​ | 2 | Program Management Plan | 1 | Baseline and Updated Master schedule (including cost linked Milestone summary for earned value, planned value analysis, Monthly Progress Report and Schedule Updates)
3 | Yes | Yes | Yes |  |  | Minor | Design & Technical | 2 | Program Management Plan | Number of projects with approved change requests in design phase since inception with time impact of more than 1 month / Total number of projects in design phase | <30% | 30-70% | >70% | P&M | 2 | Program Management Plan | Number of projects with approved change requests in design phase since inception with time impact of more than 1 month / Total number of projects in design phase | <30% | 30-70% | >70% | P&M | Schedule Predictability Index = Duration planned for the project or phase as per the approved schedule/Duration taken to complete the project or phase | >1.1 | 0.75-1.1 | <0.75 | The Design and Technical Guidelines exist | Yes |  | No | Review and approval of construction sequence and method statement | Yes |  | No | (Number of projects with contingency utilization > 1) / (Total number of projects) | <10% | 10-30% | >30% | Adoption on DevCo performance? Robust assessment process and guidelines - 30%; Availability of sample of impact assessment report - 30%; Availability of action plan - 10%; Use of innovative tools/platforms/dashboards - 30% | >75% | 60-75% | <60% | "Severe" score if challenges faced can impact strategy execution significantly (in terms of time, cost and/or quality) | Minor | Moderate | Severe | Schedule Predictability Index = Duration planned for the project or phase as per the approved schedule/Duration taken to complete the project or phase | >1.1 | 0.75-1.1 | <0.75 | P&M | Number of projects with approved change requests in design phase since inception with time impact of more than 1 month / Total number of projects in design phase | <30% | 30-70% | >70% | P&M | 3 | Latest Approved Monthly Progress Report | 13 | DevCo Design & Technical Guidelines (including Look & Feel Design Guidelines) | 30 | Site and Logistics Plan (including traffic simulations) | 9 | Updated Cost Report (including approved budget, contingency utilization and change requests, variations, claims) | 69 | Innovation/ smart city impact assessment Report (DevCo level) | 74 | List of technical functions’ KPIs (including baseline and targets) | 3 | Latest Approved Monthly Progress Report | 2 | Program Management Plan
4 | Yes, but inadequate |  |  |  |  | Misaligned | Development & Construction | 3 | Latest Approved Monthly Progress Report | Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months / Total number of projects in construction phase | <30% | 30-70% | >70% | P&M | 3 | Latest Approved Monthly Progress Report | Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months / Total number of projects in construction phase | <30% | 30-70% | >70% | P&M | Number of projects with approved change requests in design phase since inception with time impact of more than 1 month / Total number of projects in design phase | <30% | 30-70% | >70% | Material Palette & Finish Schedule aligns with Look & Feel Guideline | >70% | 50-70% | <50% | Sufficient land acquired | Yes |  | No | (No. of projects with approved change request having a cost impact greater than 2%) / (Total number of projects) | <5% | 5-15% | >15% | Effectiveness index in the mentioned areas is an evaluation of successful implementation (Up to 8.3% for each element of the innovation adoption effective index) (Up to 10% for each element of the smart city adoption effective index) | >75% | 60-75% | <60% | Give 'satisfactory' score if there are technical KPIs, but they are very generic | Yes | Yes, but very brief | No | Number of projects with approved change requests in design phase since inception with time impact of more than 1 month / Total number of projects in design phase | <30% | 30-70% | >70% | P&M | Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months / Total number of projects in construction phase | <30% | 30-70% | >70% | P&M | 4 | Change request register (covering latest approved schedule extension requests) | 14 | Return Brief Report (including approved and latest Asset Area Schedule & Population) | 18 | Project Execution Plan (including packaging and phasing strategy) | 3 | Latest approved monthly progress report (including committed / uncommitted costs, etc.) | 70 | Sample(s) of project-level final master plan showing innovation/ Smart city considerations | 75 | Latest report which includes the progress of achievement of technical functions’ KPIs | 4 | Change request register (covering latest approved schedule extension requests) | 3 | Latest Approved Monthly Progress Report
5 | Yes, but less than 1% |  |  |  |  | Moderate | Cost Estimation & Optimization | 4 | Change request register (covering latest approved schedule extension requests) | (Number of Projects with Approved Schedule Extension)/Total Number of Projects) | <20% | 20-40% | >40% | P&M | 4 | Change request register (covering latest approved schedule extension requests) | (Number of Projects with Approved Schedule Extension)/Total Number of Projects) | <20% | 20-40% | >40% | P&M | Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months / Total number of projects in construction phase | <30% | 30-70% | >70% | (Latest BUA - Approved BUA) / Approved BUA | <15% | 15-30% | >30% | Completion of traffic simulations | Yes |  | No | (No. of projects with approved claims) / (Total number of projects) | <2% | 2-5% | >5% | Pilot or R&D projects conducted? Availability - 20%; Adequate list of focus areas - 35%; Procedure - 15%; Outcome assessment robustness - 30% | >75% | 60-75% | <60% | Number of KPIs achieved / Total Number of KPIs set for the same period | >75% | 50-75% | <50% | Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months / Total number of projects in construction phase | <30% | 30-70% | >70% | P&M | (Number of Projects with Approved Schedule Extension)/Total Number of Projects) | <20% | 20-40% | >40% | P&M | 1 | Baseline and Updated Master Schedule (same as above) | 15 | Latest Stage Gate Cost Plan (Project level) | 31 | Interface Management Plan (including Stakeholder Management Plan*, Communication Plan & Contractor Staging Plan and Handover & Close-out Plan) | 66 | Provisional Sums Status | 71 | Register of Innovation & Technology pilots and R&D projects along with progress tracker | 76 | Approved and as-is org structure, including staffed/unstaffed positions, roles & responsibilities | 5 | Latest approved risk mapping / risk register (including mitigation plans) documented at DevCo level and the list of Stakeholders | 4 | Change request register (covering latest approved schedule extension requests)
6 | Yes, but less than 5% |  |  |  |  | No | Innovation & Technology | 5 | Latest approved risk mapping / risk register (including mitigation plans) documented at DevCo level and the list of Stakeholders | Number of projects with forecast completion date beyond the latest approved schedule / [No. of projects with schedule extension (design stage) + No. of projects with schedule extension (construction stage)] | <20% | 20-40% | >40% | P&M | 5 | Latest approved risk mapping / risk register (including mitigation plans) documented at DevCo level and the list of Stakeholders | Number of projects with forecast completion date beyond the latest approved schedule / [No. of projects with schedule extension (design stage) + No. of projects with schedule extension (construction stage)] | <20% | 20-40% | >40% | P&M | (Number of Projects with Approved Schedule Extension)/Total Number of Projects) | <20% | 20-40% | >40% | (Latest Land Area - Approved Land Area) / Approved Land Area | <15% | 15-30% | >30% | Date of latest approved Procurement Plan less than 12 months from Current Date | Yes |  | No | Total Provisional Sums/Latest Approved Budget | <5% | 5-15% | >15% | [(Number of pilots that are scaled successfully + Number of R&D projects that are successfully piloted or fully-scaled) / (Number of pilot projects + Number of R&D projects)] | >40% | 20-40% | <20% | Expected elements from industry benchmarks: 1. Schedule adherence 2. Budget adherence 3. Employee attrition 4. HSE and Welfare 5. ESG | Aligned with industry benchmarks | Some gaps with industry benchmarks | Significant deviation from industry benchmarks | (Number of Projects with Approved Schedule Extension)/Total Number of Projects) | <20% | 20-40% | >40% | P&M | Number of projects with forecast completion date beyond the latest approved schedule / [No. of projects with schedule extension (design stage) + No. of projects with schedule extension (construction stage)] | <20% | 20-40% | >40% | P&M | 5 | Latest approved risk mapping / risk register (including mitigation plans) documented at DevCo level and the list of Stakeholders | 16 | Report including constructability feasibility and construction packaging including enabeling work and methodology | 32 | Workforce Planning Strategy |  |  | 76 | Company Organization chart (that shows the availability of innovation unit/ department) (listed in Strategy & Operations) | 77 | Strategic DevCo technical workforce planning report, including capacity and competency planning | 6 | Lookahead Schedules / Short-term execution plans (e.g., 4-week or 6-week lookahead) | 5 | Latest approved risk mapping / risk register (including mitigation plans) documented at DevCo level and the list of Stakeholders
7 | Yes, but less than 0.5% |  |  |  |  | Poor | Strategy & Operations | 6 | Lookahead Schedules / Short-term execution plans (e.g., 4-week or 6-week lookahead) | "Satisfactory Score" if key project stakeholders (engineering, procurement, construction, client teams) were formally briefed, discussed on the forecast date includ any foreseen risks but no formal sign off doc on the forecast finish date is available | Yes | Yes, but inadequate | No | P&M | 6 | Lookahead Schedules / Short-term execution plans (e.g., 4-week or 6-week lookahead) | "Satisfactory Score" if key project stakeholders (engineering, procurement, construction, client teams) were formally briefed, discussed on the forecast date includ any foreseen risks but no formal sign off doc on the forecast finish date is available | Yes | Yes, but inadequate | No | P&M | Number of projects with forecast completion date beyond the latest approved schedule / [No. of projects with schedule extension (design stage) + No. of projects with schedule extension (construction stage)] | <20% | 20-40% | >40% | (Latest Population - Approved Population) / Approved Population | <30% | 30-40% | >40% | Number of Stakeholder MOU or Land Use Permits not executed on time/ Total number of Stakeholder MOU or Land Use Permits required | <20% | 20-60% | >60% | (Total Provisional Sums−Actual Utilized Provisional Sums)/Total Provisional Sums | <10% | 10-20% | >20% | Availability of Innovation: Availability - 20%; Adequate Key positions planned in the org. structure - 30%; Unit/department position within the company hierarchy - 20%; Qualifications of the innovation team - 30% | >60% | 40-60% | <40% | "Severe" if more than 25% of technical department head (N-2 or 3) and above are vacant Technical department head: person leading a technical function (depends on organization size) "Moderate" if 2 position for technical department head are vacant | Minor | Moderate | Severe | Number of projects with forecast completion date beyond the latest approved schedule / [No. of projects with schedule extension (design stage) + No. of projects with schedule extension (construction stage)] | <20% | 20-40% | >40% | P&M | "Satisfactory Score" if key project stakeholders (engineering, procurement, construction, client teams) were formally briefed, discussed on the forecast date includ any foreseen risks but no formal sign off doc on the forecast finish date is available | Yes | Yes, but inadequate | No | P&M | 4 | Change request register (same as above) | 17 | Digital Information Management Plan | 33 | Construction Progress Report (including workforce numbers) |  |  |  |  | 78 | Register of Approved technical-related policies and procedures | 7 | Sample of project level approved risk register | 6 | Lookahead Schedules / Short-term execution plans (e.g., 4-week or 6-week lookahead)
8 | Yes, but less than 1 month |  |  |  |  | Severe |  | 7 | Sample of project level approved risk register | "Satisfactory" if new activities as per the risks identified and discussions with stakeholders are added in the revised programme but do not have logical relationships and there is no comparison of the critical path analysis before and after date change | Yes | Yes, but inadequate | No | P&M | 7 | Sample of project level approved risk register | "Satisfactory" if new activities as per the risks identified and discussions with stakeholders are added in the revised programme but do not have logical relationships and there is no comparison of the critical path analysis before and after date change | Yes | Yes, but inadequate | No | P&M | "Satisfactory Score" if key project stakeholders (engineering, procurement, construction, client teams) were formally briefed, discussed on the forecast date includ any foreseen risks but no formal sign off doc on the forecast finish date is available | Yes | Yes, but inadequate | No | Modularized Construction Cost / Total Construction Cost | >40% | 20-40% | <20% | Actual workforce employed / forecast workforce requirements | >90% | 70-90% | <70% |  |  |  |  | Availability - 50% Implementation of the unit/department framework/ process - 50% | >50% | 0.5 | <50% | "Critical" score if there is little to no relevance in the requested qualifications to the role | Well-aligned | Some gaps | Misaligned | "Satisfactory Score" if key project stakeholders (engineering, procurement, construction, client teams) were formally briefed, discussed on the forecast date includ any foreseen risks but no formal sign off doc on the forecast finish date is available | Yes | Yes, but inadequate | No | P&M | "Satisfactory" if new activities as per the risks identified and discussions with stakeholders are added in the revised programme but do not have logical relationships and there is no comparison of the critical path analysis before and after date change | Yes | Yes, but inadequate | No | P&M | 6 | Lookahead Schedules / Short-term execution plans (e.g., 4-week or 6-week lookahead) | 18 | Latest Project Execution Plan (including Design Strategy, Packaging Strategy and Phasing Strategy) | 34 | Register of Technical Queries |  |  |  |  | 79 | Register of technical platforms | 8 | Risk Management Plan | 7 | Sample of project level approved risk register
9 | Yes, but less than 2 weeks |  |  |  |  | Significant deviation from industry benchmarks |  | 8 | Risk Management Plan | Satisfactory Score if - Contingency allocated but not aligning with the risk severity as per the heat map | Yes | Yes, but inadequate | No | P&M | 8 | Risk Management Plan | Satisfactory Score if - Contingency allocated but not aligning with the risk severity as per the heat map | Yes | Yes, but inadequate | No | P&M | "Satisfactory" if new activities as per the risks identified and discussions with stakeholders are added in the revised programme but do not have logical relationships and there is no comparison of the critical path analysis before and after date change | Yes | Yes, but inadequate | No | Constructability Report exists | Yes |  | No | Actual number of labor camps / Forecast number of labor camps | >90% | 70-90% | <70% | [8 empty] | Strong if these are done: 1. Regular update and review of policies (3 mths) 2. All relevant policies/guidelines captured 3. Easy access (one repository with easy to find link) 4. Multi-channels to inform updates to documents e.g. email, intranet | Strong | Moderate | Poor | "Satisfactory" if new activities as per the risks identified and discussions with stakeholders are added in the revised programme but do not have logical relationships and there is no comparison of the critical path analysis before and after date change | Yes | Yes, but inadequate | No | P&M | Satisfactory Score if - Contingency allocated but not aligning with the risk severity as per the heat map | Yes | Yes, but inadequate | No | P&M | 5 | Latest approved risk mapping / risk register documented at DevCo level (same as above) | 19 | Design Master Schedule | 35 | Register of Shop Drawing Reviews | [6 empty] | 9 | Updated Cost report | 8 | Risk Management Plan
10 | [5 empty] | Some gaps |  | 9 | Updated Cost report | Satisfactory Score if - the deferment was less than 1 month | No | Yes, but less than 1 month | Yes | P&M | 9 | Updated Cost report | Satisfactory Score if - the deferment was less than 1 month | No | Yes, but less than 1 month | Yes | P&M | Satisfactory Score if - Contingency allocated but not aligning with the risk severity as per the heat map | Yes | Yes, but inadequate | No | Consideration of design for enabling work package | Yes |  | No | Actual number of batching plants / forecast number of batching plants | >80% | 40-80% | <40% | [8 empty] | Strong if these are done: 1. Regular internal audits of processes (ongoing and rotation of topics/departments) 2. Independent internal audit department reporting directly to CEO or Board 3. Whistleblowing policy 4. Regular training for all staff (annual) | Strong | Moderate | Poor | Satisfactory Score if - Contingency allocated but not aligning with the risk severity as per the heat map | Yes | Yes, but inadequate | No | P&M | Satisfactory Score if - the deferment was less than 1 month | No | Yes, but less than 1 month | Yes | P&M | 7 | Sample of project level approved risk register | 20 | Procedures and Governance for design approvals and change management | 36 | Register of Material & Product Approval / Change Requests | [6 empty] | 10 | Program Tracker | 9 | Updated Cost report
11 | [5 empty] | Some gaps with industry benchmarks |  | 10 | Program Tracker | Satisfactory Score if - the cost overrun was less than 5% | No | Yes, but less than 5% | Yes | P&M | 10 | Program Tracker | Satisfactory Score if - the cost overrun was less than 5% | No | Yes, but less than 5% | Yes | P&M | Satisfactory Score if - the deferment was less than 1 month | No | Yes, but less than 1 month | Yes | LOD Documented matches LOD Required | Yes |  | No | Adherence to Technical Submittals Review Cycle Time | Yes |  | No | [8 empty] | Strong if all of these following points are done: 1. Board reporting policy covering frequency/trigger for updates 2. Register of Board Papers/Presentations 3. Register of Board meetings and meeting minutes | Strong | Moderate | Poor | Satisfactory Score if - the deferment was less than 1 month | No | Yes, but less than 1 month | Yes | P&M | Satisfactory Score if - the cost overrun was less than 5% | No | Yes, but less than 5% | Yes | P&M | 8 | Risk Management Plan | 21 | Design Basis Report and Stage Gate Design Report (including Design Management Report, Design Reviews & Verifications Register) | 37 | Register of As-Built Drawings | [6 empty] | 11 | Original Approved and Latest version of CGI & Animation (Material Palette & Finish Schedule) at DevCo Level | 10 | Program Tracker
12 | [5 empty] | Strong |  | 11 | Original Approved and Latest version of CGI & Animation (Material Palette & Finish Schedule) at DevCo Level | Satisfactory Score if - the cost overrun was less than 1% | No | Yes, but less than 1% | Yes | P&M | 11 | Original Approved and Latest version of CGI & Animation (Material Palette & Finish Schedule) at DevCo Level | Satisfactory Score if - the cost overrun was less than 1% | No | Yes, but less than 1% | Yes | P&M | Satisfactory Score if - the cost overrun was less than 5% | No | Yes, but less than 5% | Yes | BIM Documentation exists | Yes |  | No | Total number of shop drawing reviews approved / Total number of shop drawing review requests | >90% | 60-90% | <60% | [12 empty] | Satisfactory Score if - the cost overrun was less than 5% | No | Yes, but less than 5% | Yes | P&M | Satisfactory Score if - the cost overrun was less than 1% | No | Yes, but less than 1% | Yes | P&M | 5 | Latest approved risk mapping / risk register documented at DevCo level (same as above) | 22 | Infrastructure and Engineering report (including Water, Energy, Waste, Infrastructure & Mobility Plans) | 38 | Register of Material Inspection Requests | [6 empty] | 12 | Original Approved and Latest version of the Drawings | 11 | Original Approved and Latest version of CGI & Animation (Material Palette & Finish Schedule) at DevCo Level
13 | [5 empty] | Well-aligned |  | 12 | Original Approved and Latest version of the Drawings | Number of Controlled Risks / Total number of identified risks | >70% | 40-70% | <40% | P&M | 12 | Original Approved and Latest version of the Drawings | Number of Controlled Risks / Total number of identified risks | >70% | 40-70% | <40% | P&M | Satisfactory Score if - the cost overrun was less than 1% | No | Yes, but less than 1% | Yes | Review Latest Approved Design Strategy and compare with the Stage Gate Design Report | Yes |  | No | Total number of product sample & materials approved / Total number of product sample & material approvals requested | >90% | 60-90% | <60% | [12 empty] | Satisfactory Score if - the cost overrun was less than 1% | No | Yes, but less than 1% | Yes | P&M | Number of Controlled Risks / Total number of identified risks | >70% | 40-70% | <40% | P&M | 8 | Risk Management Plan (same as above) | 23 | Environmental and Social Impact Assessment | 39 | Register of Work Inspection Requests | [6 empty] | 13 | DevCo Design & Technical Guidelines (including Look & Feel Design Guidelines) | 12 | Original Approved and Latest version of the Drawings
14 | [5 empty] | Yes |  | 13 | DevCo Design & Technical Guidelines (including Look & Feel Design Guidelines) | Satisfactory Score if - the risks were identified, mitigations planned but not communicated to all the relevant stakeholders. And the risk register is updated | Yes | Yes, but inadequate | No | P&M | 13 | DevCo Design & Technical Guidelines (including Look & Feel Design Guidelines) | Satisfactory Score if - the risks were identified, mitigations planned but not communicated to all the relevant stakeholders. And the risk register is updated | Yes | Yes, but inadequate | No | P&M | Number of Controlled Risks / Total number of identified risks | >70% | 40-70% | <40% | Check the Design Review & Verification Register, assess if correct number of Design Reviews have occurred in accordance with the Design Management Report | >70% | 50-70% | <50% | Number of As-built reviews / approvals / Number of As-Built review requests | >80% | 60-80% | <60% | [12 empty] | Number of Controlled Risks / Total number of identified risks | >70% | 40-70% | <40% | P&M | Satisfactory Score if - the risks were identified, mitigations planned but not communicated to all the relevant stakeholders. And the risk register is updated | Yes | Yes, but inadequate | No | P&M | 9 | Updated Cost report | 24 | Environmental Compliance Report | 40 | Quality Management Manual (QMP) | [6 empty] | 14 | Return Brief Report (including approved and latest Asset Area Schedule & Population) | 13 | DevCo Design & Technical Guidelines (including Look & Feel Design Guidelines)
15 | [5 empty] | Yes, but very brief |  | 14 | Return Brief Report (including approved and latest Asset Area Schedule & Population) | Satisfactory Score if - the time impact is less than 2 weeks for Design phase completion and less than 1 month of Construction Phase Completion | No | Yes, but less than 2 weeks | Yes | P&M | 14 | Return Brief Report (including approved and latest Asset Area Schedule & Population) | Satisfactory Score if - the time impact is less than 2 weeks for Design phase completion and less than 1 month of Construction Phase Completion | No | Yes, but less than 2 weeks | Yes | P&M | Satisfactory Score if - the risks were identified, mitigations planned but not communicated to all the relevant stakeholders. And the risk register is updated | Yes | Yes, but inadequate | No | Closed Corrective Actions / Total Corrective Actions | >70% | 40-70% | <40% | Number of MIR Inspected / Total number of MIRs requested | >80% | 60-80% | <60% | [12 empty] | Satisfactory Score if - the risks were identified, mitigations planned but not communicated to all the relevant stakeholders. And the risk register is updated | Yes | Yes, but inadequate | No | P&M | Satisfactory Score if - the time impact is less than 2 weeks for Design phase completion and less than 1 month of Construction Phase Completion | No | Yes, but less than 2 weeks | Yes | P&M | 10 | Program Tracker | 15 | Design Basis Report and Stage Gate Design Report (including Design Management Report, Design Reviews & Verifications Register) | 41 | Latest Monthly Quality Report, including defects and NCR data | [6 empty] | 15 | Latest Stage Gate Cost Plan (Project level) | 14 | Return Brief Report (including approved and latest Asset Area Schedule & Population)
16 | [7 empty] | 15 | Latest Stage Gate Cost Plan (Project level) | Satisfactory Score if - the cost impact is less than 0.5% of the identified risk costing | No | Yes, but less than 0.5% | Yes | P&M | 15 | Latest Stage Gate Cost Plan (Project level) | Satisfactory Score if - the cost impact is less than 0.5% of the identified risk costing | No | Yes, but less than 0.5% | Yes | P&M | Satisfactory Score if - the time impact is less than 2 weeks for Design phase completion and less than 1 month of Construction Phase Completion | No | Yes, but less than 2 weeks | Yes | Average number of days between Date Corrective Action is recorded in the Corrective Action Register and the Date Corrective Action is Closed | <14days | 14-30days | >30days | Number of Approved MIR / Total number of MIRs requested | >80% | 60-80% | <60% | [12 empty] | Satisfactory Score if - the time impact is less than 2 weeks for Design phase completion and less than 1 month of Construction Phase Completion | No | Yes, but less than 2 weeks | Yes | P&M | Satisfactory Score if - the cost impact is less than 0.5% of the identified risk costing | No | Yes, but less than 0.5% | Yes | P&M |  |  | 25 | Register of Authority Engagement, Approvals and Waivers | 42 | Inspection Test Plan (ITP) | [6 empty] | 16 | Report including constructability feasibility and construction packaging including enabeling work and methodology | 15 | Latest Stage Gate Cost Plan (Project level)
17 | [7 empty] | 16 | Report including constructability feasibility and construction packaging including enabeling work and methodology | (Percentage similarity between Approved CGI and Latest CGI at same angle and scale) + (Percentage similarity between Approved Animation and Latest Animation at same camera angle) / 2 | >70% | 50-70% | <50% | D&T | 16 | Report including constructability feasibility and construction packaging including enabeling work and methodology | (Percentage similarity between Approved CGI and Latest CGI at same angle and scale) + (Percentage similarity between Approved Animation and Latest Animation at same camera angle) / 2 | >70% | 50-70% | <50% | D&T | Satisfactory Score if - the cost impact is less than 0.5% of the identified risk costing | No | Yes, but less than 0.5% | Yes | Average number of days between Design Review Submittals and Completion of the Design Reviews compared to the number of days required to complete the Design Reviews in accordance with the Design Management Report | Yes |  | No | Number of WIR Inspected / Total number of WIRs requested | >80% | 60-80% | <60% | [12 empty] | Satisfactory Score if - the cost impact is less than 0.5% of the identified risk costing | No | Yes, but less than 0.5% | Yes | P&M | (Percentage similarity between Approved CGI and Latest CGI at same angle and scale) + (Percentage similarity between Approved Animation and Latest Animation at same camera angle) / 2 | >70% | 50-70% | <50% | D&T |  |  | 26 | Stakeholder Management Plan (including Stakeholder Engagement Plan and Stakeholder Management Tracker) | 43 | Sample of project specific Project Quality Plan (PQP) | [6 empty] | 17 | Digital Information Management Plan | 16 | Report including constructability feasibility and construction packaging including enabeling work and methodology
18 | [7 empty] | 17 | Digital Information Management Plan | Material Palette & Finish Schedule matched Approved CGI | >70% | 50-70% | <50% | D&T | 17 | Digital Information Management Plan | Material Palette & Finish Schedule matched Approved CGI | >70% | 50-70% | <50% | D&T |  |  |  |  | Independent Certification exists | Yes |  | No | Number of Approved WIR / Total number of WIRs requested | >80% | 60-80% | <60% | [12 empty] | (Percentage similarity between Approved CGI and Latest CGI at same angle and scale) + (Percentage similarity between Approved Animation and Latest Animation at same camera angle) / 2 | >70% | 50-70% | <50% | D&T | Material Palette & Finish Schedule matched Approved CGI | >70% | 50-70% | <50% | D&T |  |  | 27 | Baseline ESG Strategy and Latest Annual ESG Report | 44 | Latest Quality Audit Report | [6 empty] | 18 | Latest Project Execution Plan (including Design Strategy, Packaging Strategy and Phasing Strategy) | 17 | Digital Information Management Plan
19 | [7 empty] | 18 | Latest Project Execution Plan (including Design Strategy, Packaging Strategy and Phasing Strategy) | The Design and Technical Guidelines exist | Yes |  | No | D&T | 18 | Latest Project Execution Plan (including Design Strategy, Packaging Strategy and Phasing Strategy) | The Design and Technical Guidelines exist | Yes |  | No | D&T |  |  |  |  | The Infrastructure and Engineering Report references the Regional Infrastructure & Mobility Plans and demonstrates adoption of Regional Strategies | Yes |  | No | Alignment of audit frequency | Yes |  | No | [12 empty] | Material Palette & Finish Schedule matched Approved CGI | >70% | 50-70% | <50% | D&T | The Design and Technical Guidelines exist | Yes |  | No | D&T |  |  |  |  | 45 | Procurement Management Plan (including annual procurement lookahead and pre-qualified vendor database) | [6 empty] | 19 | Design Master Schedule | 18 | Latest Project Execution Plan (including Design Strategy, Packaging Strategy and Phasing Strategy)
20 | [7 empty] | 19 | Design Master Schedule | Material Palette & Finish Schedule aligns with Look & Feel Guideline | >70% | 50-70% | <50% | D&T | 19 | Design Master Schedule | Material Palette & Finish Schedule aligns with Look & Feel Guideline | >70% | 50-70% | <50% | D&T |  |  |  |  | Key Environmental Risks and Site Environmental Factors are covered in the Environmental Compliance Report | Yes |  | No | Number of Non-Conformance Reports Closed / Total Number of Non-Conformance Reports | >80% | 60-80% | <60% | [12 empty] | The Design and Technical Guidelines exist | Yes |  | No | D&T | Material Palette & Finish Schedule aligns with Look & Feel Guideline | >70% | 50-70% | <50% | D&T |  |  |  |  | 46 | Sample of Tender Award Report | [6 empty] | 20 | Procedures and Governance for design approvals and change management | 19 | Design Master Schedule
21 | [7 empty] | 20 | Procedures and Governance for design approvals and change management | (Latest BUA - Approved BUA) / Approved BUA | <15% | 15-30% | >30% | D&T | 20 | Procedures and Governance for design approvals and change management | (Latest BUA - Approved BUA) / Approved BUA | <15% | 15-30% | >30% | D&T |  |  |  |  | Total Number of Code Compliance Violations taken from the Code Compliance Assessment Report | <10% | 10-30% | >30% | Sum (NCR Closeout cycle time)/Total number of Non-Conformance Reports | <10 days | 10-21 days | >21 days | [12 empty] | Material Palette & Finish Schedule aligns with Look & Feel Guideline | >70% | 50-70% | <50% | D&T | (Latest BUA - Approved BUA) / Approved BUA | <15% | 15-30% | >30% | D&T |  |  |  |  | 47 | Procurement and Contracting Risk Register | [6 empty] | 21 | Design Basis Report and Stage Gate Design Report (including Design Management Report, Design Reviews & Verifications Register) | 20 | Procedures and Governance for design approvals and change management
22 | [7 empty] | 21 | Design Basis Report and Stage Gate Design Report (including Design Management Report, Design Reviews & Verifications Register) | (Latest Land Area - Approved Land Area) / Approved Land Area | <15% | 15-30% | >30% | D&T | 21 | Design Basis Report and Stage Gate Design Report (including Design Management Report, Design Reviews & Verifications Register) | (Latest Land Area - Approved Land Area) / Approved Land Area | <15% | 15-30% | >30% | D&T |  |  |  |  | Total Waivers Approved / Total Waiver Applications Submitted | >70% | 50-70% | <50% | Number of Procurement Packages Delivered on Time / Number of Planned Procurement Packages | >80% | 70-80% | 40-70% | [12 empty] | (Latest BUA - Approved BUA) / Approved BUA | <15% | 15-30% | >30% | D&T | (Latest Land Area - Approved Land Area) / Approved Land Area | <15% | 15-30% | >30% | D&T |  |  |  |  | 48 | List of Appointed Vendors (including due-diligence checks) | [6 empty] | 22 | Infrastructure and Engineering report (including Water, Energy, Waste, Infrastructure & Mobility Plans) | 21 | Design Basis Report and Stage Gate Design Report (including Design Management Report, Design Reviews & Verifications Register)
23 | [7 empty] | 22 | Infrastructure and Engineering report (including Water, Energy, Waste, Infrastructure & Mobility Plans) | (Latest Population - Approved Population) / Approved Population | <30% | 30-40% | >40% | D&T | 22 | Infrastructure and Engineering report (including Water, Energy, Waste, Infrastructure & Mobility Plans) | (Latest Population - Approved Population) / Approved Population | <30% | 30-40% | >40% | D&T |  |  |  |  | Stakeholder Submittal Dates are in accordance with the Stakeholder Management Plan to ensure approvals can be achieved in line with Stage Gate completion requirements | Yes |  | No | Total number of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures / Total number of claims and variations | >70% | 50-70% | <50% | [12 empty] | (Latest Land Area - Approved Land Area) / Approved Land Area | <15% | 15-30% | >30% | D&T | (Latest Population - Approved Population) / Approved Population | <30% | 30-40% | >40% | D&T |  |  |  |  | 49 | Supply Chain Risk Assessment | [6 empty] | 23 | Environmental and Social Impact Assessment | 22 | Infrastructure and Engineering report (including Water, Energy, Waste, Infrastructure & Mobility Plans)
24 | [7 empty] | 23 | Environmental and Social Impact Assessment | Modularized Construction Cost / Total Construction Cost | >40% | 20-40% | <20% | D&T | 23 | Environmental and Social Impact Assessment | Modularized Construction Cost / Total Construction Cost | >40% | 20-40% | <20% | D&T |  |  |  |  | Number of Stakeholder approvals pending / Total number of stakeholder approvals required | <20% | 20-30% | >30% | Total number of packages procured with 100% complete, compliant and well-structured documentation / Total number of packages | >70% | 50-70% | <50% | [12 empty] | (Latest Population - Approved Population) / Approved Population | <30% | 30-40% | >40% | D&T | Modularized Construction Cost / Total Construction Cost | >40% | 20-40% | <20% | D&T |  |  |  |  | 50 | Current Procurement Schedule | [6 empty] | 24 | Environmental Compliance Report | 23 | Environmental and Social Impact Assessment
25 | [7 empty] | 24 | Environmental Compliance Report | Constructability Report exists | Yes |  | No | D&T | 24 | Environmental Compliance Report | Constructability Report exists | Yes |  | No | D&T |  |  |  |  | Proactive communication in Stakeholder Engagement Plan | Yes |  | No | No. of awarded contracts where vendors appointed passed full due-diligence checks / Total number of awarded contracts | >90% | 90-85% | <85% | [12 empty] | Modularized Construction Cost / Total Construction Cost | >40% | 20-40% | <20% | D&T | Constructability Report exists | Yes |  | No | D&T |  |  |  |  | 51 | Sample of Signed Agreement / Awarded Contract | [6 empty] | 25 | Register of Authority Engagement, Approvals and Waivers | 24 | Environmental Compliance Report
26 | [7 empty] | 25 | Register of Authority Engagement, Approvals and Waivers | Consideration of design for enabling work package | Yes |  | No | D&T | 25 | Register of Authority Engagement, Approvals and Waivers | Consideration of design for enabling work package | Yes |  | No | D&T |  |  |  |  | Stakeholder Comments Closed / Total Stakeholder Comments | >70% | 50-70% | <50% | Completion of supply chain risk-market intelligence assessment | Yes |  | No | [12 empty] | Constructability Report exists | Yes |  | No | D&T | Consideration of design for enabling work package | Yes |  | No | D&T |  |  |  |  | 52 | Sample of Supplier and Contractor Performance Report | [6 empty] | 26 | Stakeholder Management Plan (including Stakeholder Engagement Plan and Stakeholder Management Tracker) | 25 | Register of Authority Engagement, Approvals and Waivers
27 | [7 empty] | 26 | Stakeholder Management Plan (including Stakeholder Engagement Plan and Stakeholder Management Tracker) | LOD Documented matches LOD Required | Yes |  | No | D&T | 26 | Stakeholder Management Plan (including Stakeholder Engagement Plan and Stakeholder Management Tracker) | LOD Documented matches LOD Required | Yes |  | No | D&T |  |  |  |  | Actual ESG Target / Planned ESG Target | >70% | 50-70% | <50% | Number of procurement activities executed as planned / Total number of procurement activities | >60% | 20-60% | <20% | [12 empty] | Consideration of design for enabling work package | Yes |  | No | D&T | LOD Documented matches LOD Required | Yes |  | No | D&T |  |  |  |  | 53 | Contract Execution Register (including Letter of Award and Letter of Commencement) | [6 empty] | 27 | Baseline ESG Strategy and Latest Annual ESG Report | 26 | Stakeholder Management Plan (including Stakeholder Engagement Plan and Stakeholder Management Tracker)
28 | [7 empty] | 27 | Baseline ESG Strategy and Latest Annual ESG Report | BIM Documentation exists | Yes |  | No | D&T | 27 | Baseline ESG Strategy and Latest Annual ESG Report | BIM Documentation exists | Yes |  | No | D&T |  |  |  |  | Alignment with globally recognized Best Practice Targets | Yes |  | No | (Value of Contract Awarded - Tender Cost Estimate) / Value of Award Contract | <20% | 20-60% | >60% | [12 empty] | LOD Documented matches LOD Required | Yes |  | No | D&T | BIM Documentation exists | Yes |  | No | D&T |  |  |  |  | 54 | Claims Register | [6 empty] | 28 | Construction Environmental and Social Management Plan (including Environmental Permit Register) | 27 | Baseline ESG Strategy and Latest Annual ESG Report
29 | [7 empty] | 28 | Construction Environmental and Social Management Plan (including Environmental Permit Register) | Review Latest Approved Design Strategy and compare with the Stage Gate Design Report | Yes |  | No | D&T | 28 | Construction Environmental and Social Management Plan (including Environmental Permit Register) | Review Latest Approved Design Strategy and compare with the Stage Gate Design Report | Yes |  | No | D&T | [8 empty] | Number of contracts with filed claims / Total number of awarded contracts | <20% | 20-60% | >60% | [12 empty] | BIM Documentation exists | Yes |  | No | D&T | Review Latest Approved Design Strategy and compare with the Stage Gate Design Report | Yes |  | No | D&T |  |  |  |  | 4 | Change Request Register | [6 empty] | 29 | Construction Execution Plan | 28 | Construction Environmental and Social Management Plan (including Environmental Permit Register)
30 | [7 empty] | 29 | Construction Execution Plan | Check the Design Review & Verification Register, assess if correct number of Design Reviews have occurred in accordance with the Design Management Report | >70% | 50-70% | <50% | D&T | 29 | Construction Execution Plan | Check the Design Review & Verification Register, assess if correct number of Design Reviews have occurred in accordance with the Design Management Report | >70% | 50-70% | <50% | D&T | [8 empty] | Processing of payment certificates and payments | Yes |  | No | [12 empty] | Review Latest Approved Design Strategy and compare with the Stage Gate Design Report | Yes |  | No | D&T | Check the Design Review & Verification Register, assess if correct number of Design Reviews have occurred in accordance with the Design Management Report | >70% | 50-70% | <50% | D&T |  |  |  |  | 55 | Post Tender Clarification (PTC) Register | [6 empty] | 30 | Site and Logistics Plan (including traffic simulations) | 29 | Construction Execution Plan
31 | [7 empty] | 30 | Site and Logistics Plan (including traffic simulations) | Closed Corrective Actions / Total Corrective Actions | >70% | 40-70% | <40% | D&T | 30 | Site and Logistics Plan (including traffic simulations) | Closed Corrective Actions / Total Corrective Actions | >70% | 40-70% | <40% | D&T | [8 empty] | Vendor performance assessment | Yes |  | No | [12 empty] | Check the Design Review & Verification Register, assess if correct number of Design Reviews have occurred in accordance with the Design Management Report | >70% | 50-70% | <50% | D&T | Closed Corrective Actions / Total Corrective Actions | >70% | 40-70% | <40% | D&T |  |  |  |  | 56 | Payment Register | [6 empty] | 31 | Interface Management Plan (including Stakeholder Management Plan*, Communication Plan & Contractor Staging Plan and Handover & Close-out Plan) | 30 | Site and Logistics Plan (including traffic simulations)
32 | [7 empty] | 31 | Interface Management Plan (including Stakeholder Management Plan*, Communication Plan & Contractor Staging Plan and Handover & Close-out Plan) | Average number of days between Date Corrective Action is recorded in the Corrective Action Register and the Date Corrective Action is Closed | <14days | 14-30days | >30days | D&T | 31 | Interface Management Plan (including Stakeholder Management Plan*, Communication Plan & Contractor Staging Plan and Handover & Close-out Plan) | Average number of days between Date Corrective Action is recorded in the Corrective Action Register and the Date Corrective Action is Closed | <14days | 14-30days | >30days | D&T | [8 empty] | Provision for identification and escalation of high risk activities | Yes |  | No | [12 empty] | Closed Corrective Actions / Total Corrective Actions | >70% | 40-70% | <40% | D&T | Average number of days between Date Corrective Action is recorded in the Corrective Action Register and the Date Corrective Action is Closed | <14days | 14-30days | >30days | D&T |  |  |  |  | 57 | HSE Management Manual | [6 empty] | 32 | Workforce Planning Strategy | 31 | Interface Management Plan (including Stakeholder Management Plan*, Communication Plan & Contractor Staging Plan and Handover & Close-out Plan)
33 | [7 empty] | 32 | Workforce Planning Strategy | Average number of days between Design Review Submittals and Completion of the Design Reviews compared to the number of days required to complete the Design Reviews in accordance with the Design Management Report | Yes |  | No | D&T | 32 | Workforce Planning Strategy | Average number of days between Design Review Submittals and Completion of the Design Reviews compared to the number of days required to complete the Design Reviews in accordance with the Design Management Report | Yes |  | No | D&T | [8 empty] | Review rate of safety risk register | Yes |  | No | [12 empty] | Average number of days between Date Corrective Action is recorded in the Corrective Action Register and the Date Corrective Action is Closed | <14days | 14-30days | >30days | D&T | Average number of days between Design Review Submittals and Completion of the Design Reviews compared to the number of days required to complete the Design Reviews in accordance with the Design Management Report | Yes |  | No | D&T |  |  |  |  | 58 | HIRAC Methodology & Safety Risk Register | [6 empty] | 33 | Construction Progress Report (including workforce numbers) | 32 | Workforce Planning Strategy
34 | [7 empty] | 33 | Construction Progress Report (including workforce numbers) | Independent Certification exists | Yes |  | No | D&T | 33 | Construction Progress Report (including workforce numbers) | Independent Certification exists | Yes |  | No | D&T | [8 empty] | Total number of closed Safety Risk items / Total number of safety risk items | >80% | 60-80% | <60% | [12 empty] | Average number of days between Design Review Submittals and Completion of the Design Reviews compared to the number of days required to complete the Design Reviews in accordance with the Design Management Report | Yes |  | No | D&T | Independent Certification exists | Yes |  | No | D&T |  |  |  |  | 59 | Sample of Emergency Evacuation & Preparedness Plan (Project level) | [6 empty] | 34 | Register of Technical Queries | 33 | Construction Progress Report (including workforce numbers)
35 | [7 empty] | 34 | Register of Technical Queries | The Infrastructure and Engineering Report references the Regional Infrastructure & Mobility Plans and demonstrates adoption of Regional Strategies | Yes |  | No | D&T | 34 | Register of Technical Queries | The Infrastructure and Engineering Report references the Regional Infrastructure & Mobility Plans and demonstrates adoption of Regional Strategies | Yes |  | No | D&T | [8 empty] | To input final number Sum (Cycle time to close safety risk items) / Total number of closed safety risk items | <7 days | 7-14 days | >14 days | [12 empty] | Independent Certification exists | Yes |  | No | D&T | The Infrastructure and Engineering Report references the Regional Infrastructure & Mobility Plans and demonstrates adoption of Regional Strategies | Yes |  | No | D&T |  |  |  |  | 60 | Latest Monthly HSE Report | [6 empty] | 35 | Register of Shop Drawing Reviews | 34 | Register of Technical Queries
36 | [7 empty] | 35 | Register of Shop Drawing Reviews | Key Environmental Risks and Site Environmental Factors are covered in the Environmental Compliance Report | Yes |  | No | D&T | 35 | Register of Shop Drawing Reviews | Key Environmental Risks and Site Environmental Factors are covered in the Environmental Compliance Report | Yes |  | No | D&T | [8 empty] | To input final number. Sum (Cycle time to close safety incident) / Total number of closed safety incidents | <7 days | 7-14 days | >14 days | [12 empty] | The Infrastructure and Engineering Report references the Regional Infrastructure & Mobility Plans and demonstrates adoption of Regional Strategies | Yes |  | No | D&T | Key Environmental Risks and Site Environmental Factors are covered in the Environmental Compliance Report | Yes |  | No | D&T |  |  |  |  | 61 | Latest HSE Audit Report | [6 empty] | 36 | Register of Material & Product Approval / Change Requests | 35 | Register of Shop Drawing Reviews
37 | [7 empty] | 36 | Register of Material & Product Approval / Change Requests | Total Number of Code Compliance Violations taken from the Code Compliance Assessment Report | <10% | 10-30% | >30% | D&T | 36 | Register of Material & Product Approval / Change Requests | Total Number of Code Compliance Violations taken from the Code Compliance Assessment Report | <10% | 10-30% | >30% | D&T | [8 empty] | Compliance of emergency drill rate | Yes |  | No | [12 empty] | Key Environmental Risks and Site Environmental Factors are covered in the Environmental Compliance Report | Yes |  | No | D&T | Total Number of Code Compliance Violations taken from the Code Compliance Assessment Report | <10% | 10-30% | >30% | D&T |  |  |  |  | 62 | Latest Monthly Welfare Monitoring Report | [6 empty] | 37 | Register of As-Built Drawings | 36 | Register of Material & Product Approval / Change Requests
38 | [7 empty] | 37 | Register of As-Built Drawings | Total Waivers Approved / Total Waiver Applications Submitted | >70% | 50-70% | <50% | D&T | 37 | Register of As-Built Drawings | Total Waivers Approved / Total Waiver Applications Submitted | >70% | 50-70% | <50% | D&T | [8 empty] | No. of incidents resulting in fatality or severe impairment per 200,000 work hours | 0 | 0.001-0.0199 | >0.02 | [12 empty] | Total Number of Code Compliance Violations taken from the Code Compliance Assessment Report | <10% | 10-30% | >30% | D&T | Total Waivers Approved / Total Waiver Applications Submitted | >70% | 50-70% | <50% | D&T |  |  |  |  | 63 | Welfare Management Manual (including Vendor Management & Monitoring Program) | [6 empty] | 38 | Register of Material Inspection Requests | 37 | Register of As-Built Drawings
39 | [7 empty] | 38 | Register of Material Inspection Requests | Stakeholder Submittal Dates are in accordance with the Stakeholder Management Plan to ensure approvals can be achieved in line with Stage Gate completion requirements | Yes |  | No | D&T | 38 | Register of Material Inspection Requests | Stakeholder Submittal Dates are in accordance with the Stakeholder Management Plan to ensure approvals can be achieved in line with Stage Gate completion requirements | Yes |  | No | D&T | [8 empty] | No. of incidents resulting in lost time per 200,000 work hours | <0.1 | 0.1-1.5 | >1.5 | [12 empty] | Total Waivers Approved / Total Waiver Applications Submitted | >70% | 50-70% | <50% | D&T | Stakeholder Submittal Dates are in accordance with the Stakeholder Management Plan to ensure approvals can be achieved in line with Stage Gate completion requirements | Yes |  | No | D&T |  |  |  |  | 64 | Latest Welfare Audit Report | [6 empty] | 39 | Register of Work Inspection Requests | 38 | Register of Material Inspection Requests
40 | [7 empty] | 39 | Register of Work Inspection Requests | Number of Stakeholder approvals pending / Total number of stakeholder approvals required | <20% | 20-30% | >30% | D&T | 39 | Register of Work Inspection Requests | Number of Stakeholder approvals pending / Total number of stakeholder approvals required | <20% | 20-30% | >30% | D&T | [8 empty] | No. of recordable incidents per 200,000 work hours | <0.5 | 0.5-5 | >5 | [12 empty] | Stakeholder Submittal Dates are in accordance with the Stakeholder Management Plan to ensure approvals can be achieved in line with Stage Gate completion requirements | Yes |  | No | D&T | Number of Stakeholder approvals pending / Total number of stakeholder approvals required | <20% | 20-30% | >30% | D&T | [12 empty] | 40 | Quality Management Manual (QMP) | 39 | Register of Work Inspection Requests
41 | [7 empty] | 40 | Quality Management Manual (QMP) | Proactive communication in Stakeholder Engagement Plan | Yes |  | No | D&T | 40 | Quality Management Manual (QMP) | Proactive communication in Stakeholder Engagement Plan | Yes |  | No | D&T | [8 empty] | No. of near misses recorded per 200,000 work hours | >30 | 0.1-30 | 0 | [12 empty] | Number of Stakeholder approvals pending / Total number of stakeholder approvals required | <20% | 20-30% | >30% | D&T | Proactive communication in Stakeholder Engagement Plan | Yes |  | No | D&T | [12 empty] | 41 | Latest Monthly Quality Report, including defects and NCR data | 40 | Quality Management Manual (QMP)
42 | [7 empty] | 41 | Latest Monthly Quality Report, including defects and NCR data | Stakeholder Comments Closed / Total Stakeholder Comments | >70% | 50-70% | <50% | D&T | 41 | Latest Monthly Quality Report, including defects and NCR data | Stakeholder Comments Closed / Total Stakeholder Comments | >70% | 50-70% | <50% | D&T | [8 empty] | No. of safety observation recorded per 200,000 work hours | >200 | 10-200 | <10 | [12 empty] | Proactive communication in Stakeholder Engagement Plan | Yes |  | No | D&T | Stakeholder Comments Closed / Total Stakeholder Comments | >70% | 50-70% | <50% | D&T | [12 empty] | 42 | Inspection Test Plan (ITP) | 41 | Latest Monthly Quality Report, including defects and NCR data
43 | [7 empty] | 42 | Inspection Test Plan (ITP) | Actual ESG Target / Planned ESG Target | >70% | 50-70% | <50% | D&T | 42 | Inspection Test Plan (ITP) | Actual ESG Target / Planned ESG Target | >70% | 50-70% | <50% | D&T | [8 empty] | Total number of Safety Walks with Leadership / Total number of Safety Walks | >70% | 50-70% | <50% | [12 empty] | Stakeholder Comments Closed / Total Stakeholder Comments | >70% | 50-70% | <50% | D&T | Actual ESG Target / Planned ESG Target | >70% | 50-70% | <50% | D&T | [12 empty] | 43 | Sample of project specific Project Quality Plan (PQP) | 42 | Inspection Test Plan (ITP)
44 | [7 empty] | 43 | Sample of project specific Project Quality Plan (PQP) | Alignment with globally recognized Best Practice Targets | Yes |  | No | D&T | 43 | Sample of project specific Project Quality Plan (PQP) | Alignment with globally recognized Best Practice Targets | Yes |  | No | D&T | [8 empty] | Number of grievances closed / Total number of grievances | >80% | 60-80% | <60% | [12 empty] | Actual ESG Target / Planned ESG Target | >70% | 50-70% | <50% | D&T | Alignment with globally recognized Best Practice Targets | Yes |  | No | D&T | [12 empty] | 44 | Latest Quality Audit Report | 43 | Sample of project specific Project Quality Plan (PQP)
45 | [7 empty] | 44 | Latest Quality Audit Report | Environmental mitigation measures included in CESMP / Environmental mitigation measures recommended in ESIA | >80% | 60-80% | <60% | D&C | 44 | Latest Quality Audit Report | Environmental mitigation measures included in CESMP / Environmental mitigation measures recommended in ESIA | >80% | 60-80% | <60% | D&C | [8 empty] | Sum (Cycle time to close grievances) / Total number of grievances | <14 days | 14-28 days | >28 days | [12 empty] | Alignment with globally recognized Best Practice Targets | Yes |  | No | D&T | Environmental mitigation measures included in CESMP / Environmental mitigation measures recommended in ESIA | >80% | 60-80% | <60% | D&C | [12 empty] | 45 | Procurement Management Plan (including annual procurement lookahead and pre-qualified vendor database) | 44 | Latest Quality Audit Report
46 | [7 empty] | 45 | Procurement Management Plan (including annual procurement lookahead and pre-qualified vendor database) | Update of construction execution plan | Yes |  | No | D&C | 45 | Procurement Management Plan (including annual procurement lookahead and pre-qualified vendor database) | Update of construction execution plan | Yes |  | No | D&C | [8 empty] | Number of Welfare Staff / Total Number of Staff | >2% | 1-2% | <1% | [12 empty] | Environmental mitigation measures included in CESMP / Environmental mitigation measures recommended in ESIA | >80% | 60-80% | <60% | D&C | Update of construction execution plan | Yes |  | No | D&C | [12 empty] | 46 | Sample of Tender Award Report | 45 | Procurement Management Plan (including annual procurement lookahead and pre-qualified vendor database)
47 | [7 empty] | 46 | Sample of Tender Award Report | Review and approval of construction sequence and method statement | Yes |  | No | D&C | 46 | Sample of Tender Award Report | Review and approval of construction sequence and method statement | Yes |  | No | D&C | [8 empty] | Number of Welfare Observations Closed / Total number of Welfare Observations | >60% | 40-60% | <40% ; no observations recorded | [12 empty] | Update of construction execution plan | Yes |  | No | D&C | Review and approval of construction sequence and method statement | Yes |  | No | D&C | [12 empty] | 47 | Procurement and Contracting Risk Register | 46 | Sample of Tender Award Report
48 | [7 empty] | 47 | Procurement and Contracting Risk Register | Sufficient land acquired | Yes |  | No | D&C | 47 | Procurement and Contracting Risk Register | Sufficient land acquired | Yes |  | No | D&C | [8 empty] | Total Closed Welfare Non-compliances / Total Welfare Non-compliances | >80% | 60-80% | <60% | [12 empty] | Review and approval of construction sequence and method statement | Yes |  | No | D&C | Sufficient land acquired | Yes |  | No | D&C | [12 empty] | 48 | List of Appointed Vendors (including due-diligence checks) | 47 | Procurement and Contracting Risk Register
49 | [7 empty] | 48 | List of Appointed Vendors (including due-diligence checks) | Completion of traffic simulations | Yes |  | No | D&C | 48 | List of Appointed Vendors (including due-diligence checks) | Completion of traffic simulations | Yes |  | No | D&C | [8 empty] | Sum (Cycle time to close Welfare Non-compliances) / Total number of Welfare Non-compliances | <14 days | 14-28 days | >28 days | [12 empty] | Sufficient land acquired | Yes |  | No | D&C | Completion of traffic simulations | Yes |  | No | D&C | [12 empty] | 49 | Supply Chain Risk Assessment | 48 | List of Appointed Vendors (including due-diligence checks)
50 | [7 empty] | 49 | Supply Chain Risk Assessment | Date of latest approved Procurement Plan less than 12 months from Current Date | Yes |  | No | D&C | 49 | Supply Chain Risk Assessment | Date of latest approved Procurement Plan less than 12 months from Current Date | Yes |  | No | D&C | [24 empty] | Completion of traffic simulations | Yes |  | No | D&C | Date of latest approved Procurement Plan less than 12 months from Current Date | Yes |  | No | D&C | [12 empty] | 50 | Current Procurement Schedule | 49 | Supply Chain Risk Assessment
51 | [7 empty] | 50 | Current Procurement Schedule | Number of Stakeholder MOU or Land Use Permits not executed on time/ Total number of Stakeholder MOU or Land Use Permits required | <20% | 20-60% | >60% | D&C | 50 | Current Procurement Schedule | Number of Stakeholder MOU or Land Use Permits not executed on time/ Total number of Stakeholder MOU or Land Use Permits required | <20% | 20-60% | >60% | D&C | [24 empty] | Date of latest approved Procurement Plan less than 12 months from Current Date | Yes |  | No | D&C | Number of Stakeholder MOU or Land Use Permits not executed on time/ Total number of Stakeholder MOU or Land Use Permits required | <20% | 20-60% | >60% | D&C | [12 empty] | 51 | Sample of Signed Agreement / Awarded Contract | 50 | Current Procurement Schedule
52 | [7 empty] | 51 | Sample of Signed Agreement / Awarded Contract | Actual workforce employed / forecast workforce requirements | >90% | 70-90% | <70% | D&C | 51 | Sample of Signed Agreement / Awarded Contract | Actual workforce employed / forecast workforce requirements | >90% | 70-90% | <70% | D&C | [24 empty] | Number of Stakeholder MOU or Land Use Permits not executed on time/ Total number of Stakeholder MOU or Land Use Permits required | <20% | 20-60% | >60% | D&C | Actual workforce employed / forecast workforce requirements | >90% | 70-90% | <70% | D&C | [12 empty] | 52 | Sample of Supplier and Contractor Performance Report | 51 | Sample of Signed Agreement / Awarded Contract
53 | [7 empty] | 52 | Sample of Supplier and Contractor Performance Report | Actual number of labor camps / Forecast number of labor camps | >90% | 70-90% | <70% | D&C | 52 | Sample of Supplier and Contractor Performance Report | Actual number of labor camps / Forecast number of labor camps | >90% | 70-90% | <70% | D&C | [24 empty] | Actual workforce employed / forecast workforce requirements | >90% | 70-90% | <70% | D&C | Actual number of labor camps / Forecast number of labor camps | >90% | 70-90% | <70% | D&C | [12 empty] | 53 | Contract Execution Register (including Letter of Award and Letter of Commencement) | 52 | Sample of Supplier and Contractor Performance Report
54 | [7 empty] | 53 | Contract Execution Register (including Letter of Award and Letter of Commencement) | Actual number of batching plants / forecast number of batching plants | >80% | 40-80% | <40% | D&C | 53 | Contract Execution Register (including Letter of Award and Letter of Commencement) | Actual number of batching plants / forecast number of batching plants | >80% | 40-80% | <40% | D&C | [24 empty] | Actual number of labor camps / Forecast number of labor camps | >90% | 70-90% | <70% | D&C | Actual number of batching plants / forecast number of batching plants | >80% | 40-80% | <40% | D&C | [12 empty] | 54 | Claims Register | 53 | Contract Execution Register (including Letter of Award and Letter of Commencement)
55 | [7 empty] | 54 | Claims Register | Adherence to Technical Submittals Review Cycle Time | Yes |  | No | D&C | 54 | Claims Register | Adherence to Technical Submittals Review Cycle Time | Yes |  | No | D&C | [24 empty] | Actual number of batching plants / forecast number of batching plants | >80% | 40-80% | <40% | D&C | Adherence to Technical Submittals Review Cycle Time | Yes |  | No | D&C | [12 empty] | 55 | Post Tender Clarification (PTC) Register | 54 | Claims Register
56 | [7 empty] | 55 | Post Tender Clarification (PTC) Register | Total number of shop drawing reviews approved / Total number of shop drawing review requests | >90% | 60-90% | <60% | D&C | 55 | Post Tender Clarification (PTC) Register | Total number of shop drawing reviews approved / Total number of shop drawing review requests | >90% | 60-90% | <60% | D&C | [24 empty] | Adherence to Technical Submittals Review Cycle Time | Yes |  | No | D&C | Total number of shop drawing reviews approved / Total number of shop drawing review requests | >90% | 60-90% | <60% | D&C | [12 empty] | 56 | Payment Register | 55 | Post Tender Clarification (PTC) Register
57 | [7 empty] | 56 | Payment Register | Total number of product sample & materials approved / Total number of product sample & material approvals requested | >90% | 60-90% | <60% | D&C | 56 | Payment Register | Total number of product sample & materials approved / Total number of product sample & material approvals requested | >90% | 60-90% | <60% | D&C | [24 empty] | Total number of shop drawing reviews approved / Total number of shop drawing review requests | >90% | 60-90% | <60% | D&C | Total number of product sample & materials approved / Total number of product sample & material approvals requested | >90% | 60-90% | <60% | D&C | [12 empty] | 57 | HSE Management Manual | 56 | Payment Register
58 | [7 empty] | 57 | HSE Management Manual | Number of As-built reviews / approvals / Number of As-Built review requests | >80% | 60-80% | <60% | D&C | 57 | HSE Management Manual | Number of As-built reviews / approvals / Number of As-Built review requests | >80% | 60-80% | <60% | D&C | [24 empty] | Total number of product sample & materials approved / Total number of product sample & material approvals requested | >90% | 60-90% | <60% | D&C | Number of As-built reviews / approvals / Number of As-Built review requests | >80% | 60-80% | <60% | D&C | [12 empty] | 58 | HIRAC Methodology & Safety Risk Register | 57 | HSE Management Manual
59 | [7 empty] | 58 | HIRAC Methodology & Safety Risk Register | Number of MIR Inspected / Total number of MIRs requested | >80% | 60-80% | <60% | D&C | 58 | HIRAC Methodology & Safety Risk Register | Number of MIR Inspected / Total number of MIRs requested | >80% | 60-80% | <60% | D&C | [24 empty] | Number of As-built reviews / approvals / Number of As-Built review requests | >80% | 60-80% | <60% | D&C | Number of MIR Inspected / Total number of MIRs requested | >80% | 60-80% | <60% | D&C | [12 empty] | 59 | Sample of Emergency Evacuation & Preparedness Plan (Project level) | 58 | HIRAC Methodology & Safety Risk Register
60 | [7 empty] | 59 | Sample of Emergency Evacuation & Preparedness Plan (Project level) | Number of Approved MIR / Total number of MIRs requested | >80% | 60-80% | <60% | D&C | 59 | Sample of Emergency Evacuation & Preparedness Plan (Project level) | Number of Approved MIR / Total number of MIRs requested | >80% | 60-80% | <60% | D&C | [24 empty] | Number of MIR Inspected / Total number of MIRs requested | >80% | 60-80% | <60% | D&C | Number of Approved MIR / Total number of MIRs requested | >80% | 60-80% | <60% | D&C | [12 empty] | 60 | Latest Monthly HSE Report | 59 | Sample of Emergency Evacuation & Preparedness Plan (Project level)
61 | [7 empty] | 60 | Latest Monthly HSE Report | Number of WIR Inspected / Total number of WIRs requested | >80% | 60-80% | <60% | D&C | 60 | Latest Monthly HSE Report | Number of WIR Inspected / Total number of WIRs requested | >80% | 60-80% | <60% | D&C | [24 empty] | Number of Approved MIR / Total number of MIRs requested | >80% | 60-80% | <60% | D&C | Number of WIR Inspected / Total number of WIRs requested | >80% | 60-80% | <60% | D&C | [12 empty] | 61 | Latest HSE Audit Report | 60 | Latest Monthly HSE Report
62 | [7 empty] | 61 | Latest HSE Audit Report | Number of Approved WIR / Total number of WIRs requested | >80% | 60-80% | <60% | D&C | 61 | Latest HSE Audit Report | Number of Approved WIR / Total number of WIRs requested | >80% | 60-80% | <60% | D&C | [24 empty] | Number of WIR Inspected / Total number of WIRs requested | >80% | 60-80% | <60% | D&C | Number of Approved WIR / Total number of WIRs requested | >80% | 60-80% | <60% | D&C | [12 empty] | 62 | Latest Monthly Welfare Monitoring Report | 61 | Latest HSE Audit Report
63 | [7 empty] | 62 | Latest Monthly Welfare Monitoring Report | Alignment of audit frequency | Yes |  | No | D&C | 62 | Latest Monthly Welfare Monitoring Report | Alignment of audit frequency | Yes |  | No | D&C | [24 empty] | Number of Approved WIR / Total number of WIRs requested | >80% | 60-80% | <60% | D&C | Alignment of audit frequency | Yes |  | No | D&C | [12 empty] | 63 | Welfare Management Manual (including Vendor Management & Monitoring Program) | 62 | Latest Monthly Welfare Monitoring Report
64 | [7 empty] | 63 | Welfare Management Manual (including Vendor Management & Monitoring Program) | Number of Non-Conformance Reports Closed / Total Number of Non-Conformance Reports | >80% | 60-80% | <60% | D&C | 63 | Welfare Management Manual (including Vendor Management & Monitoring Program) | Number of Non-Conformance Reports Closed / Total Number of Non-Conformance Reports | >80% | 60-80% | <60% | D&C | [24 empty] | Alignment of audit frequency | Yes |  | No | D&C | Number of Non-Conformance Reports Closed / Total Number of Non-Conformance Reports | >80% | 60-80% | <60% | D&C | [12 empty] | 64 | Latest Welfare Audit Report | 63 | Welfare Management Manual (including Vendor Management & Monitoring Program)
65 | [7 empty] | 64 | Latest Welfare Audit Report | Sum (NCR Closeout cycle time)/Total number of Non-Conformance Reports | <10 days | 10-21 days | >21 days | D&C | 64 | Latest Welfare Audit Report | Sum (NCR Closeout cycle time)/Total number of Non-Conformance Reports | <10 days | 10-21 days | >21 days | D&C | [24 empty] | Number of Non-Conformance Reports Closed / Total Number of Non-Conformance Reports | >80% | 60-80% | <60% | D&C | Sum (NCR Closeout cycle time)/Total number of Non-Conformance Reports | <10 days | 10-21 days | >21 days | D&C | [12 empty] | 65 | Quarterly/annual progress reports for preceding three years (including approved budget, contingency utilization and change requests / claims) | 64 | Latest Welfare Audit Report
66 | [7 empty] | 65 | Quarterly/annual progress reports for preceding three years (including approved budget, contingency utilization and change requests / claims) | Number of Procurement Packages Delivered on Time / Number of Planned Procurement Packages | >80% | 70-80% | 40-70% | D&C | 65 | Quarterly/annual progress reports for preceding three years (including approved budget, contingency utilization and change requests / claims) | Number of Procurement Packages Delivered on Time / Number of Planned Procurement Packages | >80% | 70-80% | 40-70% | D&C | [24 empty] | Sum (NCR Closeout cycle time)/Total number of Non-Conformance Reports | <10 days | 10-21 days | >21 days | D&C | Number of Procurement Packages Delivered on Time / Number of Planned Procurement Packages | >80% | 70-80% | 40-70% | D&C | [12 empty] | 66 | Provisional Sums Status | 65 | Quarterly/annual progress reports for preceding three years (including approved budget, contingency utilization and change requests / claims)
67 | [7 empty] | 66 | Provisional Sums Status | Total number of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures / Total number of claims and variations | >70% | 50-70% | <50% | D&C | 66 | Provisional Sums Status | Total number of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures / Total number of claims and variations | >70% | 50-70% | <50% | D&C | [24 empty] | Number of Procurement Packages Delivered on Time / Number of Planned Procurement Packages | >80% | 70-80% | 40-70% | D&C | Total number of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures / Total number of claims and variations | >70% | 50-70% | <50% | D&C | [12 empty] | 67 | Innovation Strategy (DevCo level) | 66 | Provisional Sums Status
68 | [7 empty] | 67 | Innovation Strategy (DevCo level) | Total number of packages procured with 100% complete, compliant and well-structured documentation / Total number of packages | >70% | 50-70% | <50% | D&C | 67 | Innovation Strategy (DevCo level) | Total number of packages procured with 100% complete, compliant and well-structured documentation / Total number of packages | >70% | 50-70% | <50% | D&C | [24 empty] | Total number of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures / Total number of claims and variations | >70% | 50-70% | <50% | D&C | Total number of packages procured with 100% complete, compliant and well-structured documentation / Total number of packages | >70% | 50-70% | <50% | D&C | [12 empty] | 68 | Smart City Strategy (DevCo level) | 67 | Innovation Strategy (DevCo level)
69 | [7 empty] | 68 | Smart City Strategy (DevCo level) | No. of awarded contracts where vendors appointed passed full due-diligence checks / Total number of awarded contracts | >90% | 90-85% | <85% | D&C | 68 | Smart City Strategy (DevCo level) | No. of awarded contracts where vendors appointed passed full due-diligence checks / Total number of awarded contracts | >90% | 90-85% | <85% | D&C | [24 empty] | Total number of packages procured with 100% complete, compliant and well-structured documentation / Total number of packages | >70% | 50-70% | <50% | D&C | No. of awarded contracts where vendors appointed passed full due-diligence checks / Total number of awarded contracts | >90% | 90-85% | <85% | D&C | [12 empty] | 69 | Innovation/ smart city impact assessment Report (DevCo level) | 68 | Smart City Strategy (DevCo level)
70 | [7 empty] | 69 | Innovation/ smart city impact assessment Report (DevCo level) | Completion of supply chain risk-market intelligence assessment | Yes |  | No | D&C | 69 | Innovation/ smart city impact assessment Report (DevCo level) | Completion of supply chain risk-market intelligence assessment | Yes |  | No | D&C | [24 empty] | No. of awarded contracts where vendors appointed passed full due-diligence checks / Total number of awarded contracts | >90% | 90-85% | <85% | D&C | Completion of supply chain risk-market intelligence assessment | Yes |  | No | D&C | [12 empty] | 70 | Sample(s) of project-level final master plan showing innovation/ Smart city considerations | 69 | Innovation/ smart city impact assessment Report (DevCo level)
71 | [7 empty] | 70 | Sample(s) of project-level final master plan showing innovation/ Smart city considerations | Number of procurement activities executed as planned / Total number of procurement activities | >60% | 20-60% | <20% | D&C | 70 | Sample(s) of project-level final master plan showing innovation/ Smart city considerations | Number of procurement activities executed as planned / Total number of procurement activities | >60% | 20-60% | <20% | D&C | [24 empty] | Completion of supply chain risk-market intelligence assessment | Yes |  | No | D&C | Number of procurement activities executed as planned / Total number of procurement activities | >60% | 20-60% | <20% | D&C | [12 empty] | 71 | Register of Innovation & Technology pilots and R&D projects along with progress tracker | 70 | Sample(s) of project-level final master plan showing innovation/ Smart city considerations
72 | [7 empty] | 71 | Register of Innovation & Technology pilots and R&D projects along with progress tracker | (Value of Contract Awarded - Tender Cost Estimate) / Value of Award Contract | <20% | 20-60% | >60% | D&C | 71 | Register of Innovation & Technology pilots and R&D projects along with progress tracker | (Value of Contract Awarded - Tender Cost Estimate) / Value of Award Contract | <20% | 20-60% | >60% | D&C | [24 empty] | Number of procurement activities executed as planned / Total number of procurement activities | >60% | 20-60% | <20% | D&C | (Value of Contract Awarded - Tender Cost Estimate) / Value of Award Contract | <20% | 20-60% | >60% | D&C | [12 empty] | 76 | Company Organization chart (that shows the availability of innovation unit/ department) (listed in Strategy & Operations) | 71 | Register of Innovation & Technology pilots and R&D projects along with progress tracker
73 | [7 empty] | 72 | Technical functions' strategy and initiatives | Number of contracts with filed claims / Total number of awarded contracts | <20% | 20-60% | >60% | D&C | 72 | Technical functions' strategy and initiatives | Number of contracts with filed claims / Total number of awarded contracts | <20% | 20-60% | >60% | D&C | [24 empty] | (Value of Contract Awarded - Tender Cost Estimate) / Value of Award Contract | <20% | 20-60% | >60% | D&C | Number of contracts with filed claims / Total number of awarded contracts | <20% | 20-60% | >60% | D&C | [12 empty] | 72 | Technical functions' strategy and initiatives | 72 | Technical functions' strategy and initiatives
74 | [7 empty] | 73 | Latest report which includes the progress of technical strategy initiatives​ | Processing of payment certificates and payments | Yes |  | No | D&C | 73 | Latest report which includes the progress of technical strategy initiatives​ | Processing of payment certificates and payments | Yes |  | No | D&C | [24 empty] | Number of contracts with filed claims / Total number of awarded contracts | <20% | 20-60% | >60% | D&C | Processing of payment certificates and payments | Yes |  | No | D&C | [12 empty] | 73 | Latest report which includes the progress of technical strategy initiatives​ | 73 | Latest report which includes the progress of technical strategy initiatives​
75 | [7 empty] | 74 | List of technical functions’ KPIs (including baseline and targets) | Vendor performance assessment | Yes |  | No | D&C | 74 | List of technical functions’ KPIs (including baseline and targets) | Vendor performance assessment | Yes |  | No | D&C | [24 empty] | Processing of payment certificates and payments | Yes |  | No | D&C | Vendor performance assessment | Yes |  | No | D&C | [12 empty] | 74 | List of technical functions’ KPIs (including baseline and targets) | 74 | List of technical functions’ KPIs (including baseline and targets)
76 | [7 empty] | 75 | Latest report which includes the progress of achievement of technical functions’ KPIs | Provision for identification and escalation of high risk activities | Yes |  | No | D&C | 75 | Latest report which includes the progress of achievement of technical functions’ KPIs | Provision for identification and escalation of high risk activities | Yes |  | No | D&C | [24 empty] | Vendor performance assessment | Yes |  | No | D&C | Provision for identification and escalation of high risk activities | Yes |  | No | D&C | [12 empty] | 75 | Latest report which includes the progress of achievement of technical functions’ KPIs | 75 | Latest report which includes the progress of achievement of technical functions’ KPIs
77 | [7 empty] | 76 | Company Organization chart (that shows the availability of innovation unit/ department) (listed in Strategy & Operations) | Review rate of safety risk register | Yes |  | No | D&C | 76 | Company Organization chart (that shows the availability of innovation unit/ department) (listed in Strategy & Operations) | Review rate of safety risk register | Yes |  | No | D&C | [24 empty] | Provision for identification and escalation of high risk activities | Yes |  | No | D&C | Review rate of safety risk register | Yes |  | No | D&C | [12 empty] | 77 | Strategic DevCo technical workforce planning report, including capacity and competency planning | 76 | Company Organization chart (that shows the availability of innovation unit/ department) (listed in Strategy & Operations)
78 | [7 empty] | 77 | Strategic DevCo technical workforce planning report, including capacity and competency planning | Total number of closed Safety Risk items / Total number of safety risk items | >80% | 60-80% | <60% | D&C | 77 | Strategic DevCo technical workforce planning report, including capacity and competency planning | Total number of closed Safety Risk items / Total number of safety risk items | >80% | 60-80% | <60% | D&C | [24 empty] | Review rate of safety risk register | Yes |  | No | D&C | Total number of closed Safety Risk items / Total number of safety risk items | >80% | 60-80% | <60% | D&C | [12 empty] | 78 | Register of Approved technical-related policies and procedures | 77 | Strategic DevCo technical workforce planning report, including capacity and competency planning
79 | [7 empty] | 78 | Register of Approved technical-related policies and procedures | To input final number Sum (Cycle time to close safety risk items) / Total number of closed safety risk items | <7 days | 7-14 days | >14 days | D&C | 78 | Register of Approved technical-related policies and procedures | To input final number Sum (Cycle time to close safety risk items) / Total number of closed safety risk items | <7 days | 7-14 days | >14 days | D&C | [24 empty] | Total number of closed Safety Risk items / Total number of safety risk items | >80% | 60-80% | <60% | D&C | To input final number Sum (Cycle time to close safety risk items) / Total number of closed safety risk items | <7 days | 7-14 days | >14 days | D&C | [12 empty] | 79 | Register of technical platforms | 78 | Register of Approved technical-related policies and procedures
80 | [7 empty] | 79 | Register of technical platforms | To input final number. Sum (Cycle time to close safety incident) / Total number of closed safety incidents | <7 days | 7-14 days | >14 days | D&C | 79 | Register of technical platforms | To input final number. Sum (Cycle time to close safety incident) / Total number of closed safety incidents | <7 days | 7-14 days | >14 days | D&C | [24 empty] | To input final number Sum (Cycle time to close safety risk items) / Total number of closed safety risk items | <7 days | 7-14 days | >14 days | D&C | To input final number. Sum (Cycle time to close safety incident) / Total number of closed safety incidents | <7 days | 7-14 days | >14 days | D&C | [14 empty] | 79 | Register of technical platforms
81 | [9 empty] | Compliance of emergency drill rate | Yes |  | No | D&C |  |  | Compliance of emergency drill rate | Yes |  | No | D&C | [24 empty] | To input final number. Sum (Cycle time to close safety incident) / Total number of closed safety incidents | <7 days | 7-14 days | >14 days | D&C | Compliance of emergency drill rate | Yes |  | No | D&C
82 | [9 empty] | No. of incidents resulting in fatality or severe impairment per 200,000 work hours | 0 | 0.001-0.0199 | >0.02 | D&C |  |  | No. of incidents resulting in fatality or severe impairment per 200,000 work hours | 0 | 0.001-0.0199 | >0.02 | D&C | [24 empty] | Compliance of emergency drill rate | Yes |  | No | D&C | No. of incidents resulting in fatality or severe impairment per 200,000 work hours | 0 | 0.001-0.0199 | >0.02 | D&C
83 | [9 empty] | No. of incidents resulting in lost time per 200,000 work hours | <0.1 | 0.1-1.5 | >1.5 | D&C |  |  | No. of incidents resulting in lost time per 200,000 work hours | <0.1 | 0.1-1.5 | >1.5 | D&C | [24 empty] | No. of incidents resulting in fatality or severe impairment per 200,000 work hours | 0 | 0.001-0.0199 | >0.02 | D&C | No. of incidents resulting in lost time per 200,000 work hours | <0.1 | 0.1-1.5 | >1.5 | D&C
84 | [9 empty] | No. of recordable incidents per 200,000 work hours | <0.5 | 0.5-5 | >5 | D&C |  |  | No. of recordable incidents per 200,000 work hours | <0.5 | 0.5-5 | >5 | D&C | [24 empty] | No. of incidents resulting in lost time per 200,000 work hours | <0.1 | 0.1-1.5 | >1.5 | D&C | No. of recordable incidents per 200,000 work hours | <0.5 | 0.5-5 | >5 | D&C
85 | [9 empty] | No. of near misses recorded per 200,000 work hours | >30 | 0.1-30 | 0 | D&C |  |  | No. of near misses recorded per 200,000 work hours | >30 | 0.1-30 | 0 | D&C | [24 empty] | No. of recordable incidents per 200,000 work hours | <0.5 | 0.5-5 | >5 | D&C | No. of near misses recorded per 200,000 work hours | >30 | 0.1-30 | 0 | D&C
86 | [9 empty] | No. of safety observation recorded per 200,000 work hours | >200 | 10-200 | <10 | D&C |  |  | No. of safety observation recorded per 200,000 work hours | >200 | 10-200 | <10 | D&C | [24 empty] | No. of near misses recorded per 200,000 work hours | >30 | 0.1-30 | 0 | D&C | No. of safety observation recorded per 200,000 work hours | >200 | 10-200 | <10 | D&C
87 | [9 empty] | Total number of Safety Walks with Leadership / Total number of Safety Walks | >70% | 50-70% | <50% | D&C |  |  | Total number of Safety Walks with Leadership / Total number of Safety Walks | >70% | 50-70% | <50% | D&C | [24 empty] | No. of safety observation recorded per 200,000 work hours | >200 | 10-200 | <10 | D&C | Total number of Safety Walks with Leadership / Total number of Safety Walks | >70% | 50-70% | <50% | D&C
88 | [9 empty] | Number of grievances closed / Total number of grievances | >80% | 60-80% | <60% | D&C |  |  | Number of grievances closed / Total number of grievances | >80% | 60-80% | <60% | D&C | [24 empty] | Total number of Safety Walks with Leadership / Total number of Safety Walks | >70% | 50-70% | <50% | D&C | Number of grievances closed / Total number of grievances | >80% | 60-80% | <60% | D&C
89 | [9 empty] | Sum (Cycle time to close grievances) / Total number of grievances | <14 days | 14-28 days | >28 days | D&C |  |  | Sum (Cycle time to close grievances) / Total number of grievances | <14 days | 14-28 days | >28 days | D&C | [24 empty] | Number of grievances closed / Total number of grievances | >80% | 60-80% | <60% | D&C | Sum (Cycle time to close grievances) / Total number of grievances | <14 days | 14-28 days | >28 days | D&C
90 | [9 empty] | Number of Welfare Staff / Total Number of Staff | >2% | 1-2% | <1% | D&C |  |  | Number of Welfare Staff / Total Number of Staff | >2% | 1-2% | <1% | D&C | [24 empty] | Sum (Cycle time to close grievances) / Total number of grievances | <14 days | 14-28 days | >28 days | D&C | Number of Welfare Staff / Total Number of Staff | >2% | 1-2% | <1% | D&C
91 | [9 empty] | Number of Welfare Observations Closed / Total number of Welfare Observations | >60% | 40-60% | <40% ; no observations recorded | D&C |  |  | Number of Welfare Observations Closed / Total number of Welfare Observations | >60% | 40-60% | <40% ; no observations recorded | D&C | [24 empty] | Number of Welfare Staff / Total Number of Staff | >2% | 1-2% | <1% | D&C | Number of Welfare Observations Closed / Total number of Welfare Observations | >60% | 40-60% | <40% ; no observations recorded | D&C
92 | [9 empty] | Total Closed Welfare Non-compliances / Total Welfare Non-compliances | >80% | 60-80% | <60% | D&C |  |  | Total Closed Welfare Non-compliances / Total Welfare Non-compliances | >80% | 60-80% | <60% | D&C | [24 empty] | Number of Welfare Observations Closed / Total number of Welfare Observations | >60% | 40-60% | <40% ; no observations recorded | D&C | Total Closed Welfare Non-compliances / Total Welfare Non-compliances | >80% | 60-80% | <60% | D&C
93 | [9 empty] | Sum (Cycle time to close Welfare Non-compliances) / Total number of Welfare Non-compliances | <14 days | 14-28 days | >28 days | D&C |  |  | Sum (Cycle time to close Welfare Non-compliances) / Total number of Welfare Non-compliances | <14 days | 14-28 days | >28 days | D&C | [24 empty] | Total Closed Welfare Non-compliances / Total Welfare Non-compliances | >80% | 60-80% | <60% | D&C | Sum (Cycle time to close Welfare Non-compliances) / Total number of Welfare Non-compliances | <14 days | 14-28 days | >28 days | D&C
94 | [9 empty] | Labor accommodation inspection frequency | Yes |  | No | D&C |  |  | Labor accommodation inspection frequency | Yes |  | No | D&C | [24 empty] | Sum (Cycle time to close Welfare Non-compliances) / Total number of Welfare Non-compliances | <14 days | 14-28 days | >28 days | D&C | Labor accommodation inspection frequency | Yes |  | No | D&C
95 | [9 empty] | [Forecast Budget - PIF Approved Capex budget (Initial Business Plan)]/ PIF Approved Capex budget (Initial Business Plan) | <10% | 10-20% | >20% | CE&O |  |  | [Forecast Budget - PIF Approved Capex budget (Initial Business Plan)]/ PIF Approved Capex budget (Initial Business Plan) | <10% | 10-20% | >20% | CE&O | [24 empty] | [Forecast Budget - PIF Approved Capex budget (Initial Business Plan)]/ PIF Approved Capex budget (Initial Business Plan) | <10% | 10-20% | >20% | CE&O | [Forecast Budget - PIF Approved Capex budget (Initial Business Plan)]/ PIF Approved Capex budget (Initial Business Plan) | <10% | 10-20% | >20% | CE&O
96 | [9 empty] | Number of Projects with Budget Variance / Total number of Projects | <10% | 10-30% | >30% | CE&O |  |  | Number of Projects with Budget Variance / Total number of Projects | <10% | 10-30% | >30% | CE&O | [24 empty] | Number of Projects with Budget Variance / Total number of Projects | <10% | 10-30% | >30% | CE&O | Number of Projects with Budget Variance / Total number of Projects | <10% | 10-30% | >30% | CE&O
97 | [9 empty] | (Number of projects with contingency utilization > 1) / (Total number of projects) | <10% | 10-30% | >30% | CE&O |  |  | (Number of projects with contingency utilization > 1) / (Total number of projects) | <10% | 10-30% | >30% | CE&O | [24 empty] | (Number of projects with contingency utilization > 1) / (Total number of projects) | <10% | 10-30% | >30% | CE&O | (Number of projects with contingency utilization > 1) / (Total number of projects) | <10% | 10-30% | >30% | CE&O
98 | [9 empty] | (No. of projects with approved change request having a cost impact greater than 2%) / (Total number of projects) | <5% | 5-15% | >15% | CE&O |  |  | (No. of projects with approved change request having a cost impact greater than 2%) / (Total number of projects) | <5% | 5-15% | >15% | CE&O | [24 empty] | (No. of projects with approved change request having a cost impact greater than 2%) / (Total number of projects) | <5% | 5-15% | >15% | CE&O | (No. of projects with approved change request having a cost impact greater than 2%) / (Total number of projects) | <5% | 5-15% | >15% | CE&O
99 | [9 empty] | (No. of projects with approved claims) / (Total number of projects) | <2% | 2-5% | >5% | CE&O |  |  | (No. of projects with approved claims) / (Total number of projects) | <2% | 2-5% | >5% | CE&O | [24 empty] | (No. of projects with approved claims) / (Total number of projects) | <2% | 2-5% | >5% | CE&O | (No. of projects with approved claims) / (Total number of projects) | <2% | 2-5% | >5% | CE&O
100 | [9 empty] | Total Provisional Sums/Latest Approved Budget | <5% | 5-15% | >15% | CE&O |  |  | Total Provisional Sums/Latest Approved Budget | <5% | 5-15% | >15% | CE&O | [24 empty] | Total Provisional Sums/Latest Approved Budget | <5% | 5-15% | >15% | CE&O | Total Provisional Sums/Latest Approved Budget | <5% | 5-15% | >15% | CE&O
101 | [9 empty] | (Total Provisional Sums−Actual Utilized Provisional Sums)/Total Provisional Sums | <10% | 10-20% | >20% | CE&O |  |  | (Total Provisional Sums−Actual Utilized Provisional Sums)/Total Provisional Sums | <10% | 10-20% | >20% | CE&O | [24 empty] | (Total Provisional Sums−Actual Utilized Provisional Sums)/Total Provisional Sums | <10% | 10-20% | >20% | CE&O | (Total Provisional Sums−Actual Utilized Provisional Sums)/Total Provisional Sums | <10% | 10-20% | >20% | CE&O
102 | [9 empty] | Innovation Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10% | >75% | 60-75% | <60% | I&T |  |  | Innovation Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10% | >75% | 60-75% | <60% | I&T | [24 empty] | Innovation Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10% | >75% | 60-75% | <60% | I&T | Innovation Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10% | >75% | 60-75% | <60% | I&T
103 | [9 empty] | Smart City Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10% | >75% | 60-75% | <60% | I&T |  |  | Smart City Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10% | >75% | 60-75% | <60% | I&T | [24 empty] | Smart City Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10% | >75% | 60-75% | <60% | I&T | Smart City Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10% | >75% | 60-75% | <60% | I&T
104 | [9 empty] | Adoption on DevCo performance? Robust assessment process and guidelines - 30%; Availability of sample of impact assessment report - 30%; Availability of action plan - 10%; Use of innovative tools/platforms/dashboards - 30% | >75% | 60-75% | <60% | I&T |  |  | Adoption on DevCo performance? Robust assessment process and guidelines - 30%; Availability of sample of impact assessment report - 30%; Availability of action plan - 10%; Use of innovative tools/platforms/dashboards - 30% | >75% | 60-75% | <60% | I&T | [24 empty] | Adoption on DevCo performance? Robust assessment process and guidelines - 30%; Availability of sample of impact assessment report - 30%; Availability of action plan - 10%; Use of innovative tools/platforms/dashboards - 30% | >75% | 60-75% | <60% | I&T | Adoption on DevCo performance? Robust assessment process and guidelines - 30%; Availability of sample of impact assessment report - 30%; Availability of action plan - 10%; Use of innovative tools/platforms/dashboards - 30% | >75% | 60-75% | <60% | I&T
105 | [9 empty] | Effectiveness index in the mentioned areas is an evaluation of successful implementation (Up to 8.3% for each element of the innovation adoption effective index) (Up to 10% for each element of the smart city adoption effective index) | >75% | 60-75% | <60% | I&T |  |  | Effectiveness index in the mentioned areas is an evaluation of successful implementation (Up to 8.3% for each element of the innovation adoption effective index) (Up to 10% for each element of the smart city adoption effective index) | >75% | 60-75% | <60% | I&T | [24 empty] | Effectiveness index in the mentioned areas is an evaluation of successful implementation (Up to 8.3% for each element of the innovation adoption effective index) (Up to 10% for each element of the smart city adoption effective index) | >75% | 60-75% | <60% | I&T | Effectiveness index in the mentioned areas is an evaluation of successful implementation (Up to 8.3% for each element of the innovation adoption effective index) (Up to 10% for each element of the smart city adoption effective index) | >75% | 60-75% | <60% | I&T
106 | [9 empty] | Pilot or R&D projects conducted? Availability - 20%; Adequate list of focus areas - 35%; Procedure - 15%; Outcome assessment robustness - 30% | >75% | 60-75% | <60% | I&T |  |  | Pilot or R&D projects conducted? Availability - 20%; Adequate list of focus areas - 35%; Procedure - 15%; Outcome assessment robustness - 30% | >75% | 60-75% | <60% | I&T | [24 empty] | Pilot or R&D projects conducted? Availability - 20%; Adequate list of focus areas - 35%; Procedure - 15%; Outcome assessment robustness - 30% | >75% | 60-75% | <60% | I&T | Pilot or R&D projects conducted? Availability - 20%; Adequate list of focus areas - 35%; Procedure - 15%; Outcome assessment robustness - 30% | >75% | 60-75% | <60% | I&T
107 | [9 empty] | [(Number of pilots that are scaled successfully + Number of R&D projects that are successfully piloted or fully-scaled) / (Number of pilot projects + Number of R&D projects)] | >40% | 20-40% | <20% | I&T |  |  | [(Number of pilots that are scaled successfully + Number of R&D projects that are successfully piloted or fully-scaled) / (Number of pilot projects + Number of R&D projects)] | >40% | 20-40% | <20% | I&T | [24 empty] | [(Number of pilots that are scaled successfully + Number of R&D projects that are successfully piloted or fully-scaled) / (Number of pilot projects + Number of R&D projects)] | >40% | 20-40% | <20% | I&T | [(Number of pilots that are scaled successfully + Number of R&D projects that are successfully piloted or fully-scaled) / (Number of pilot projects + Number of R&D projects)] | >40% | 20-40% | <20% | I&T
108 | [9 empty] | Availability of Innovation: Availability - 20%; Adequate Key positions planned in the org. structure - 30%; Unit/department position within the company hierarchy - 20%; Qualifications of the innovation team - 30% | >60% | 40-60% | <40% | I&T |  |  | Availability of Innovation: Availability - 20%; Adequate Key positions planned in the org. structure - 30%; Unit/department position within the company hierarchy - 20%; Qualifications of the innovation team - 30% | >60% | 40-60% | <40% | I&T | [24 empty] | Availability of Innovation: Availability - 20%; Adequate Key positions planned in the org. structure - 30%; Unit/department position within the company hierarchy - 20%; Qualifications of the innovation team - 30% | >60% | 40-60% | <40% | I&T | Availability of Innovation: Availability - 20%; Adequate Key positions planned in the org. structure - 30%; Unit/department position within the company hierarchy - 20%; Qualifications of the innovation team - 30% | >60% | 40-60% | <40% | I&T
109 | [9 empty] | Availability - 50% Implementation of the unit/department framework/ process - 50% | >50% | 0.5 | <50% | I&T |  |  | Availability - 50% Implementation of the unit/department framework/ process - 50% | >50% | 0.5 | <50% | I&T | [24 empty] | Availability - 50% Implementation of the unit/department framework/ process - 50% | >50% | 0.5 | <50% | I&T | Availability - 50% Implementation of the unit/department framework/ process - 50% | >50% | 0.5 | <50% | I&T
110 | [9 empty] | Give 'satisfactory' score if there is a technical function strategy, but it is very general and does not provide specific details of the strategy | Yes | Yes, but very brief | No | S&O |  |  | Give 'satisfactory' score if there is a technical function strategy, but it is very general and does not provide specific details of the strategy | Yes | Yes, but very brief | No | S&O | [24 empty] | Give 'satisfactory' score if there is a technical function strategy, but it is very general and does not provide specific details of the strategy | Yes | Yes, but very brief | No | S&O | Give 'satisfactory' score if there is a technical function strategy, but it is very general and does not provide specific details of the strategy | Yes | Yes, but very brief | No | S&O
111 | [9 empty] | Assess if elements of technical strategy is aligned with organizational strategy. "Average" score if key elements of organizational strategy is not addressed in technical strategy | Well-aligned | Some gaps | Misaligned | S&O |  |  | Assess if elements of technical strategy is aligned with organizational strategy. "Average" score if key elements of organizational strategy is not addressed in technical strategy | Well-aligned | Some gaps | Misaligned | S&O | [24 empty] | Assess if elements of technical strategy is aligned with organizational strategy. "Average" score if key elements of organizational strategy is not addressed in technical strategy | Well-aligned | Some gaps | Misaligned | S&O | Assess if elements of technical strategy is aligned with organizational strategy. "Average" score if key elements of organizational strategy is not addressed in technical strategy | Well-aligned | Some gaps | Misaligned | S&O
112 | [9 empty] | "Severe" score if challenges faced can impact strategy execution significantly (in terms of time, cost and/or quality) | Minor | Moderate | Severe | S&O |  |  | "Severe" score if challenges faced can impact strategy execution significantly (in terms of time, cost and/or quality) | Minor | Moderate | Severe | S&O | [24 empty] | "Severe" score if challenges faced can impact strategy execution significantly (in terms of time, cost and/or quality) | Minor | Moderate | Severe | S&O | "Severe" score if challenges faced can impact strategy execution significantly (in terms of time, cost and/or quality) | Minor | Moderate | Severe | S&O
113 | [9 empty] | Give 'satisfactory' score if there are technical KPIs, but they are very generic | Yes | Yes, but very brief | No | S&O |  |  | Give 'satisfactory' score if there are technical KPIs, but they are very generic | Yes | Yes, but very brief | No | S&O | [24 empty] | Give 'satisfactory' score if there are technical KPIs, but they are very generic | Yes | Yes, but very brief | No | S&O | Give 'satisfactory' score if there are technical KPIs, but they are very generic | Yes | Yes, but very brief | No | S&O
114 | [9 empty] | Number of KPIs achieved / Total Number of KPIs set for the same period | >75% | 50-75% | <50% | S&O |  |  | Number of KPIs achieved / Total Number of KPIs set for the same period | >75% | 50-75% | <50% | S&O | [24 empty] | Number of KPIs achieved / Total Number of KPIs set for the same period | >75% | 50-75% | <50% | S&O | Number of KPIs achieved / Total Number of KPIs set for the same period | >75% | 50-75% | <50% | S&O
115 | [9 empty] | Expected elements from industry benchmarks: 1. Schedule adherence 2. Budget adherence 3. Employee attrition 4. HSE and Welfare 5. ESG | Aligned with industry benchmarks | Some gaps with industry benchmarks | Significant deviation from industry benchmarks | S&O |  |  | Expected elements from industry benchmarks: 1. Schedule adherence 2. Budget adherence 3. Employee attrition 4. HSE and Welfare 5. ESG | Aligned with industry benchmarks | Some gaps with industry benchmarks | Significant deviation from industry benchmarks | S&O | [24 empty] | Expected elements from industry benchmarks: 1. Schedule adherence 2. Budget adherence 3. Employee attrition 4. HSE and Welfare 5. ESG | Aligned with industry benchmarks | Some gaps with industry benchmarks | Significant deviation from industry benchmarks | S&O | Expected elements from industry benchmarks: 1. Schedule adherence 2. Budget adherence 3. Employee attrition 4. HSE and Welfare 5. ESG | Aligned with industry benchmarks | Some gaps with industry benchmarks | Significant deviation from industry benchmarks | S&O
116 | [9 empty] | "Severe" if more than 25% of technical department head (N-2 or 3) and above are vacant Technical department head: person leading a technical function (depends on organization size) "Moderate" if 2 position for technical department head are vacant | Minor | Moderate | Severe | S&O |  |  | "Severe" if more than 25% of technical department head (N-2 or 3) and above are vacant Technical department head: person leading a technical function (depends on organization size) "Moderate" if 2 position for technical department head are vacant | Minor | Moderate | Severe | S&O | [24 empty] | "Severe" if more than 25% of technical department head (N-2 or 3) and above are vacant Technical department head: person leading a technical function (depends on organization size) "Moderate" if 2 position for technical department head are vacant | Minor | Moderate | Severe | S&O | "Severe" if more than 25% of technical department head (N-2 or 3) and above are vacant Technical department head: person leading a technical function (depends on organization size) "Moderate" if 2 position for technical department head are vacant | Minor | Moderate | Severe | S&O
117 | [9 empty] | "Critical" score if there is little to no relevance in the requested qualifications to the role | Well-aligned | Some gaps | Misaligned | S&O |  |  | "Critical" score if there is little to no relevance in the requested qualifications to the role | Well-aligned | Some gaps | Misaligned | S&O | [24 empty] | "Critical" score if there is little to no relevance in the requested qualifications to the role | Well-aligned | Some gaps | Misaligned | S&O | "Critical" score if there is little to no relevance in the requested qualifications to the role | Well-aligned | Some gaps | Misaligned | S&O
118 | [9 empty] | Strong if these are done: 1. Regular update and review of policies (3 mths) 2. All relevant policies/guidelines captured 3. Easy access (one repository with easy to find link) 4. Multi-channels to inform updates to documents e.g. email, intranet | Strong | Moderate | Poor | S&O |  |  | Strong if these are done: 1. Regular update and review of policies (3 mths) 2. All relevant policies/guidelines captured 3. Easy access (one repository with easy to find link) 4. Multi-channels to inform updates to documents e.g. email, intranet | Strong | Moderate | Poor | S&O | [24 empty] | Strong if these are done: 1. Regular update and review of policies (3 mths) 2. All relevant policies/guidelines captured 3. Easy access (one repository with easy to find link) 4. Multi-channels to inform updates to documents e.g. email, intranet | Strong | Moderate | Poor | S&O | Strong if these are done: 1. Regular update and review of policies (3 mths) 2. All relevant policies/guidelines captured 3. Easy access (one repository with easy to find link) 4. Multi-channels to inform updates to documents e.g. email, intranet | Strong | Moderate | Poor | S&O
119 | [9 empty] | Strong if these are done: 1. Regular internal audits of processes (ongoing and rotation of topics/departments) 2. Independent internal audit department reporting directly to CEO or Board 3. Whistleblowing policy 4. Regular training for all staff (annual) | Strong | Moderate | Poor | S&O |  |  | Strong if these are done: 1. Regular internal audits of processes (ongoing and rotation of topics/departments) 2. Independent internal audit department reporting directly to CEO or Board 3. Whistleblowing policy 4. Regular training for all staff (annual) | Strong | Moderate | Poor | S&O | [24 empty] | Strong if these are done: 1. Regular internal audits of processes (ongoing and rotation of topics/departments) 2. Independent internal audit department reporting directly to CEO or Board 3. Whistleblowing policy 4. Regular training for all staff (annual) | Strong | Moderate | Poor | S&O | Strong if these are done: 1. Regular internal audits of processes (ongoing and rotation of topics/departments) 2. Independent internal audit department reporting directly to CEO or Board 3. Whistleblowing policy 4. Regular training for all staff (annual) | Strong | Moderate | Poor | S&O
120 | [9 empty] | Strong if all of these following points are done: 1. Board reporting policy covering frequency/trigger for updates 2. Register of Board Papers/Presentations 3. Register of Board meetings and meeting minutes | Strong | Moderate | Poor | S&O |  |  | Strong if all of these following points are done: 1. Board reporting policy covering frequency/trigger for updates 2. Register of Board Papers/Presentations 3. Register of Board meetings and meeting minutes | Strong | Moderate | Poor | S&O | [24 empty] | Strong if all of these following points are done: 1. Board reporting policy covering frequency/trigger for updates 2. Register of Board Papers/Presentations 3. Register of Board meetings and meeting minutes | Strong | Moderate | Poor | S&O | Strong if all of these following points are done: 1. Board reporting policy covering frequency/trigger for updates 2. Register of Board Papers/Presentations 3. Register of Board meetings and meeting minutes | Strong | Moderate | Poor | S&O
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
Consolidate D&F
Go to Main Page
Refresh
Compare D&F