## Sheet1
DevCo | Additional Data Point | Value | Year | Value Completed (Baseline) in M SAR | Value Completed (Actual) in M SAR | Value Completed (Forecast) in M SAR | Risk Category | Number of Risk Items | Risk | Source | Potential Impact | Risk Rating | Risk Status | Current Measures | Assessment Criteria | Value | Rating | Additional Data Point | Value | Year | Budget Value (Baseline) in M SAR | Budget Value (Revised) in M SAR | Budget Value (Forecast) in M SAR | Assessment Criteria | Value | Rating | Data Point | Input Value | Number of Quality Audits | Month | Additional Data Point | Value | Baseline | Actual | Forecast | Incident Category | Number of Incidents (To-Date) | Number of Investigations in Progress | Number of Investigations Completed | Number of Investigations Pending Approval | Audits/Inspections | In Progress_audits | Completed_audits | Remaining Planned | Actions | In Progress_actions | Completed_actions | Pending Approval | Year | Value_training | Assessment Criteria | Value | Performance Signal | Performance Signal Score | Assessment Criteria | Data Point | Input Value | Additional Data Point | Value | Assessment Criteria | Value | Rating | Performance Signal Score | Performance Signal | SourceFile
diriyah | Latest Approved Completion Date​ | Q2-28 | 2025 | 0 |  |  |  |  | Risk 1 | Contractor | Cost | High | Open | Measure 02 | DevCo Schedule Performance Index (SPI) | 0.9 | Satisfactory | Estimate to Completion Declared by DevCo | 519000000 | 2023 | 400 | 400 | 400 | Budget Variance | -0.05 | Good | PIF Approved Capex budget (Initial Business Plan) | 500000000 | 2 | Jan | No. of Site Access Required | 180 | 186 | 129 | 50 | Fatalities | 0 | 0 | 0 | 0 | HSE Audit | 3 | 5 | 4 | HSE | 6 | 22 | 12 | Jan | 30 | % of CESMP mitigation measures which align with ESIA* | 0.5 | Construction Planning Maturity | 2.1 | % of CESMP mitigation measures which align with ESIA* | Environmental mitigation measures included in CESMP | 0.1 | Implementation Success Rate for Innovation Strategy | 3 | Is there an innovation Strategy or document that lists the key focus areas and initiatives across design, construction and operation and aligned with DevCo strategic plan? | 0.4 | Needs Improvement | 1.7 | Innovation & Technology Deployment | assessment_guide_diriyah.xlsx
diriyah | Forecast Completion Date​ | Q1-29 | 2026 | 1250 | 1250 |  |  |  | Risk 2 | Source A | Impact O | Med | Ongoing | Measure 01 |  |  |  | Total Expenditure to Date | 100000000 | 2024 | 420 | 420 | 420 |  |  |  | Forecast budget (EAC) | 525000000 | 5 | Feb | No. of Site Access Provided | 120 | 16100 | 9600 | 6800 | Severe Impairment | 1 | 0 | 1 | 0 | Welfare Inspection | 2 | 4 | 4 | Welfare | 25 | 10 | 7 | Feb | 40 | [5 empty] | Environmental mitigation measures recommended in ESIA | 0.2 | Innovation Adoption Effectiveness Index (strategy & leadership alignment) | 1 | [5 empty] | assessment_guide_diriyah.xlsx
diriyah | Approved baseline completion date | Q3-27 | 2027 | 2000 | 1550 | 1550 | Risk 1 | 19 | Risk 3 | Source B | Impact P | High | Open | Measure 04 | % milestone achievement in accordance with the approved business plan | 0.7 | Satisfactory | Contingency budgeted at DevCo level | 2000000 | 2025 | 440 | 455 | 455 | % of projects having Budget Variance | 0.75 | Needs Improvement | Number of Projects with Budget Variance | 15 | 3 | Mar | Packaging & Phasing Strategy |  |  |  |  | Lost Time Incidents | 3 | 0 | 1 | 2 | [8 empty] | Mar | 38 | Has the Construction Execution Plan been updated to reflect the latest stage of construction? | Yes |  |  | Has the Construction Execution Plan been updated to reflect the latest stage of construction? | Update of construction execution plan | Yes | Innovation Adoption Effectiveness Index (skilled human resources) | 3 | [5 empty] | assessment_guide_diriyah.xlsx
diriyah | No. of schedule iterations | 8 | 2028 | 3100 |  | 2200 | Risk 2 | 16 | Risk 4 | Source F | Impact T | Med | Closed | Measure 05 |  |  |  | Contingency utilized at DevCo level | 1500000 | 2026 | 460 | 480 | 500 |  |  |  | Total number of projects | 20 | 1 | Apr | Execution & Site Logistics |  |  |  |  | Recordable Incidents | 14 | 3 | 11 | 0 | [8 empty] | Apr | 35 | Has the construction sequence and method statement been reviewed and approved? | No |  |  | Has the construction sequence and method statement been reviewed and approved? | Review and approval of Construction sequence & method statement | No | Innovation Adoption Effectiveness Index (planning & governance) | 2 | [5 empty] | assessment_guide_diriyah.xlsx
diriyah | Planned duration up to a specific phase as per approved Baseline programme | 120 | 2029 |  |  | 3100 | Risk 3 | 12 | Risk 5 | PMC | Reputation | Low | Ongoing | Measure 06 | % of projects with approved change requests in design phase since inception with time impact of more than 1 month | 0.22222 | Good | Contingency Utilization Rate | 200000 | 2027 | 480 | 500 | 510 | % of projects with contingency utilization rate > 1 | 0.25 | Satisfactory | Number of projects with contingency utilization > 1 | 5 | 0 | May | Procurement Strategy |  |  |  |  | Nears Misses | 26 | 2 | 21 | 3 | [8 empty] | May | 0 | Is total land acquisition sufficient to achieve the area required for construction site logistics? | No |  |  | Is total land acquisition sufficient to achieve the area required for construction site logistics? | Planned Area provision for site offices, amenities, laydown areas, storage facilities, workforce accommodations | Average | Innovation Adoption Effectiveness Index (process management) | 4 | [5 empty] | assessment_guide_diriyah.xlsx
diriyah | Duration taken to complete works up to the specific phase | 145 |  |  |  |  | Risk 4 | 7 | Risk 6 | Source C | Impact Q | Med | Open | Measure 07 |  |  |  | Value of Changes in Design Stage | 5000000 | 2028 | 500 | 510 | 525 | % of projects with Approved Change Requests (design/construction) having a cost impact greater than 2% | 0.6 | Needs Improvement | No. of projects with approved change request having a cost impact greater than 2% | 12 | 0 | Jun | Required area for land acquisition | [17 empty] | Jun | 0 | [5 empty] | Actual Area provision for site offices, amenities, laydown areas, storage facilities, workforce accommodations | No | Innovation Adoption Effectiveness Index (partnerships and collaboration) | 2 | [5 empty] | assessment_guide_diriyah.xlsx
diriyah | Recovery Plan | Needs Improvement |  |  |  |  | Risk 5 | 5 | Risk 7 | Source D | Impact R | Low | Closed | Measure 08 | % of projects with approved change requests in construction phase since inception with time impact of more than 4 months | 0.54545 | Satisfactory | Value of Changes in Construction Stage | 1 |  |  |  |  | % of projects with Approved Claims | 0.5 | Needs Improvement | No. of projects with approved claims | 10 | 0 | Jul | Mitigation of Project Execution Plan implementation challenges | [17 empty] | Jul | 0 | Have Traffic Simulations been completed in preparing the Site & Logistics Plan? | Yes |  |  | Have Traffic Simulations been completed in preparing the Site & Logistics Plan? | Completion of Traffic Simulations | Yes | Innovation Adoption Effectiveness Index (resource management) | 0.6 | [5 empty] | assessment_guide_diriyah.xlsx
diriyah | Extent of all EOT (design stage) | 3 | [6 empty] | Risk 8 | Supplier | Time | High | Closed | Measure 09 |  |  |  | Number of Changes (Concept MP) | 0 |  |  |  |  | % of provisional sums of the latest PIF Approved Capex budget | 0.0039216 | Good | Total provisional sums | 2000000 | 0 | Aug | Occurred delays due to stakeholder objections | [17 empty] | Aug | 0 | Has the Project Execution Plan been updated and approved in the last 12 months? | No |  |  | Has the Project Execution Plan been updated and approved in the last 12 months? | Date of latest approved Procurement Plan | No | Implementation Success Rate for Smart City Strategy | 3 | [5 empty] | assessment_guide_diriyah.xlsx
diriyah | Extent of all EOT (const. stage) | 6 | [6 empty] | Risk 9 | CAA | Impact M | High | Closed | Measure 10 | % of projects with approved schedule extension | 0.65 | Needs Improvement | Number of Changes (Detailed MP) | 3 | [7 empty] | Latest Approved budget | 510000000 | 0 | Sep | Workforce Availability | [17 empty] | Sep | 0 | % of Stakeholder MOU** / LUPs*** not executed in accordance with critical lead time | 1.3 |  |  | % of Stakeholder MOU** / LUPs*** not executed in accordance with critical lead time | Number of Stakeholder MOU or Land Use Permits not executed on time | 0.13 | Number of Smart City Use Cases | 10 | Is there a smart city Strategy or document that lists the key focus areas of smart city aligned with DevCo strategic plan? | 0.4 | Needs Improvement |  |  | assessment_guide_diriyah.xlsx
diriyah | No. of unresolved issues | 7 | [6 empty] | Risk 10 | Source E | Impact S | Med | Ongoing | Measure 11 |  |  |  | Number of Changes (Concept Design) | 2 |  |  |  |  | % of variance of Allocated Provisional sums against the awarded amount | 2.5 | Needs Improvement | Actual Utilized Provisional Sums | 800000 | 0 | Oct | Resource Availability | [17 empty] | Oct | 0 | [5 empty] | Total Stakeholder MOU or Land Use Permits required | 0.1 | Smart City Adoption Effectiveness Index (strategy & leadership alignment) | 2 | [5 empty] | assessment_guide_diriyah.xlsx
diriyah | No. of (Open) Inherent Risks | 15 | [15 empty] | Number of Changes (Detailed Design) | 6 | [9 empty] | 0 | Nov | Workforce retention track record | [17 empty] | Nov | 0 | % of Workforce Hired against Workforce Estimates | 1 | Workforce Resource Availability | 3 | % of Workforce Hired against Workforce Estimates | Forecast workforce requirements | 0.4 | Smart City Adoption Effectiveness Index (infrastructure readiness) | 2 | [5 empty] | assessment_guide_diriyah.xlsx
diriyah | No. of (Closed) Residual Risks | 35 | [12 empty] | % of projects with Forecast completion date beyond the latest approved schedule | 0.23077 | Satisfactory | Number of Changes (Construction) | 8 | [9 empty] | 0 | Dec | Turnover rate track record | [17 empty] | Dec | 0 | [5 empty] | Actual workforce employed | 0.4 | Smart City Adoption Effectiveness Index (planning & governance) | 3 | [5 empty] | assessment_guide_diriyah.xlsx
diriyah | Project-level risks (including low, medium, and high severity) | 65 | [12 empty] | Is the Forecast Finish Date at a given data date based on the alignment and buy-in from project teams and other listed stakeholders? | Yes | Good | Total Awarded Cost | 15000000 | [11 empty] | Plant/equipment downtime track record | [19 empty] | % of Labor Camp Capacity against Workforce Estimates | 1.125 |  |  | % of Labor Camp Capacity against Workforce Estimates | Forecast number of labor camps | 0.8 | Smart City Adoption Effectiveness Index (stakeholder alignment) | 1 | [5 empty] | assessment_guide_diriyah.xlsx
diriyah | Procedures for risk management | Satisfactory | [12 empty] | Based on the risks identified and approved change requests, has the DevCo conducted a sensitivity assessment on the forecast completion at a given data date? | Yes, but inadequate | Satisfactory | Approved Variations and Claims | 30 | [11 empty] | Number of technical queries raised | [24 empty] | Actual number of labor camps | 0.9 | Smart City Adoption Effectiveness Index (realized benefits & performance) | 0.5 | [5 empty] | assessment_guide_diriyah.xlsx
diriyah | Risks identified and corresponding impact on schedule | NIL | [12 empty] | Has DevCo allocated risk contingency for the identified risks? | Yes | Good | Uncommitted Cost | 300000000 | [11 empty] | Number of technical queries closed | [19 empty] | % of Material Supply Capacity against Material Demand Estimates | 1.4 |  |  | % of Material Supply Capacity against Material Demand Estimates | Forecast number of batching / crushing plants/ precast yards, etc. | 0.5 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | Extra Cost due to Unresolved Issues | 1700000 | [12 empty] | Was there any deferment in the project completion date due to unidentified risks? | Yes, but less than 1 month | Satisfactory | Pending Variations | 0 | [11 empty] | Average time to complete shop drawing reviews | [24 empty] | Actual number of batching / crushing plants/ precast yards, etc. | 0.7 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [14 empty] | Was there any Cost Overrun because of identified risk? | No | Good | Anticipated Variations | 1 | [11 empty] | Number of shop drawing review conducted | 480 | [18 empty] | Did DevCo adhere to Technical Submittals Review Cycle Time (RCT)? | Yes | Adherence to Design | 3 | Did DevCo adhere to Technical Submittals Review Cycle Time (RCT)? | Time taken for closure of technical queries | Yes |  |  | Is there an impact assessment report or identified process/ guidelines to evaluate the impact of the innovation / smart city technologies adoption on DevCo performance? | 0.6 | Satisfactory |  |  | assessment_guide_diriyah.xlsx
diriyah | [14 empty] | Was there any Cost Overrun because of unidentified risk? | Yes, but less than 1% | Satisfactory | [13 empty] | Number of material / product substitution requests | [24 empty] | Technical Submittal Review Cycle Time (RCT) | Yes | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [14 empty] | Risk Control Rate of the identified risks at DevCo Level | 0.8125 | Good | [13 empty] | Average time to approve product sample & materials | [19 empty] | % of approved shop drawing reviews vs planned | 0.99167 |  |  | % of approved shop drawing reviews vs planned | Total number of shop drawing review requests | 480 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Product & Material Approval Rate | [24 empty] | Total number of shop drawing reviews approved | 476 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [14 empty] | Is the DevCo fully compliant with Risk Management Plan requirements? | No | Needs Improvement | [13 empty] | Number of as-built drawing review conducted | 485 | [18 empty] | % of approved product waivers vs product specified | 2 |  |  | % of approved product waivers vs product specified | Total number of product sample & material approvals requested | 0.3 |  |  | Is there evidence for innovation / smart city technologies successful implementation (in final design report, master plan or other)? | Yes | Good |  |  | assessment_guide_diriyah.xlsx
diriyah | [14 empty] | Is there a difference in the time impact forecast before and after the risk event has triggered? | Yes, but less than 2 weeks | Satisfactory | [13 empty] | Average time to approve As-built rejections / iterations | [24 empty] | Total number of product sample & materials approved | 0.6 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [14 empty] | Is there a difference in the Cost impact forecast before and after the risk event has triggered? | Yes, but less than 0.5% | Satisfactory | [13 empty] | As-Built Drawing Approval Rate | [19 empty] | % of Certified As-Built Drawing Packages vs Planned | 0.95 |  |  | % of Certified As-Built Drawing Packages vs Planned | Number of As-Built review requests | 500 |  |  | Are there Pilot or R&D projects conducted? | 0.55 | Needs Improvement | 1 | Pilot and R&D Transition Rate | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Average time to complete MIRs and close out approvals | [24 empty] | Number of As-built reviews / approvals | 475 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Average time to complete WIRs and close out approvals | [19 empty] | MIR Inspection Rate | 0.98333 |  |  | MIR Inspection Rate | Total number of MIRs requested | 120 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Number of NCRs open for between 30 and 60 days | 23 | [23 empty] | Total number of MIRs inspected | 118 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Number of NCRs open for more than 60 days | 5 | [18 empty] | MIR Acceptance and Approval Rate | 0.91667 |  |  | MIR Acceptance and Approval Rate | Total number of MIRs approved | 110 |  |  | % of pilot / R&D Projects Transitioned into Full-Scale | 0.13043 | Needs Improvement |  |  | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Leadership engagement | Satisfactory | [18 empty] | WIR Inspection Rate | 0.97143 |  |  | WIR Inspection Rate | Total number of WIRs requested | 350 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Total number of ITPs requested | 100 | [23 empty] | Total number of WIRs inspected | 340 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Total number of ITPs attended | 98 | [18 empty] | WIR Acceptance and Approval Rate | 0.95714 |  |  | WIR Acceptance and Approval Rate | Total number of WIRs approved | 335 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Total number of ITPs approved | 87 | [18 empty] | Does the frequency of Audits align with the QMP? | Yes | Quality Assurance / Quality Control (QA/QC) | 2.6 | Does the frequency of Audits align with the QMP? | Required Audit frequency | Yes |  |  | Availability of Innovation unit / department with structured team | 0 | Needs Improvement | 1.5 | Organization Maturity Towards Innovation Adoption | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Total number of ITPs completed | 85 | [18 empty] | % closure of Non-Conformance Reports (NCR) | 0.96667 |  |  | % closure of Non-Conformance Reports (NCR) | Total number of defects & NCRs | 150 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Total number Quality Reports required | [24 empty] | Total number of closed defects & NCRs | 145 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Total number Quality Reports completed | [19 empty] | Average NCRs closeout Cycle Time | 5 Weeks |  |  | Average NCRs closeout Cycle Time | Average time to close NCRs | 5 Weeks | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Completeness of Quality Management Plan | Needs Improvement | [18 empty] | % of procurement packages delivered within the planned lead times defined in the PMP | 2 | Procurement & Contracting Compliance | 2.8 | % of procurement packages delivered within the planned lead times defined in the PMP | Planned Procurement Package Lead Time | 5 |  |  | Availability of Innovation and Technology Strategy / Process & Framework | 0.5 | Satisfactory |  |  | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Required number of ITPs signed off throughout construction | [24 empty] | Actual Procurement Package Delivery Time | 10 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Total number of raised closed-out defects & NCRs | [19 empty] | % of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures | 0.875 |  |  | % of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures | Total number of claims and variations | 800 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Forecasted Procurement Budget | [24 empty] | Total number of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures | 700 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Actual Procurement Budget | [19 empty] | % of packages procured with 100% complete, compliant and well-structured documentation | 0.6 |  |  | % of packages procured with 100% complete, compliant and well-structured documentation | Total number of packages | 0.5 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Vendor Database | [24 empty] | Total number of packages procured with 100% complete, compliant and well-structured documentation | 0.3 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Vendor Shortlist | [19 empty] | % of awarded contracts where vendors appointed passed full due diligence checks | 1.2857 |  |  | % of awarded contracts where vendors appointed passed full due diligence checks | No. of awarded contracts where vendors appointed passed full due-diligence checks | 0.9 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Vendor Awarded | [24 empty] | Total number of awarded contracts | 0.7 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Vendor KPIs | [19 empty] | Did the DevCo complete a Supply Chain Risk-Market Intelligence Assessment in the last quarter? | Yes |  |  | Did the DevCo complete a Supply Chain Risk-Market Intelligence Assessment in the last quarter? | Supply Chain Risk-Market Intelligence Assessment | Yes | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Vendor Performance Database | [19 empty] | % of procurement activities executed as planned in the Annual Procurement Plan | 0.66667 | Procurement & Contracting Execution Performance |  | % of procurement activities executed as planned in the Annual Procurement Plan | Total number of procurement activities | 129 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Tender return date: Planned / Actual | [24 empty] | Number of procurement activities executed as planned | 86 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Tender Review & award time: Planned / actual | [19 empty] | % of deviations in total awarded contract value with tender cost estimates | 0.4 |  |  | % of deviations in total awarded contract value with tender cost estimates | Value of Awarded Contract | 0.1 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Pre-Tender Cost Estimate | [24 empty] | Tender Cost Estimate | 0.06 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Tender Performance Index | [19 empty] | % of contracts with filed claims | 0.3 |  |  | % of contracts with filed claims | Number of contracts with filed claims | 0.3 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Contract clauses | Satisfactory | [18 empty] | Are Payment Certificates and payments being processed in accordance with the Contract terms and conditions? | 80 |  |  | Are Payment Certificates and payments being processed in accordance with the Contract terms and conditions? | Processing of payment certificates and payments | 80 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Procurement Management Plan | Good | [18 empty] | Are Vendor performance assessment occurring which capture financial instability, delays, repeated quality issues in real-time? | No |  |  | Are Vendor performance assessment occurring which capture financial instability, delays, repeated quality issues in real-time? | Alignment of sourcing strategies with project schedules and requirements | No | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Scope / design maturity | Satisfactory | [18 empty] | Does the HSE Management Manual have adequate provision for identification and escalation of high risk activities? | Yes | HSE Compliance | 1.87 | Does the HSE Management Manual have adequate provision for identification and escalation of high risk activities? | Escalation criteria for high risk activities | Yes | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Compliance with local content regulations / policies | [19 empty] | Is the rate of review of the Safety Risk Register in accordance with the HSE Management Manual? | Yes |  |  | Is the rate of review of the Safety Risk Register in accordance with the HSE Management Manual? | HSE Risk Register Review Rate | Yes | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Dispute rate | [19 empty] | % of closed Safety Risk items | 0.83333 |  |  | % of closed Safety Risk items | Total number of Safety Risk items | 0.9 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Claims processing cycle time | [24 empty] | Total number of closed Safety Risk items | 0.75 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | No. of related CRs being requested during or after tendering phase due to identified scope gap | [19 empty] | Average cycle time to close Safety Risk items | 14 Days |  |  | Average cycle time to close Safety Risk items | Cycle time to close Safety Risk items | 14 Days | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Vendor Performance Assessment | Good | [18 empty] | Average cycle time to close Safety Incident | 0.65 |  |  | Average cycle time to close Safety Incident | Cycle time to close Safety Incident | 20 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Tender pack quality | Satisfactory | [23 empty] | Total number of closed safety incidents | 13 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Total packages | [19 empty] | Is the emergency drill rate compliant with EEPP? | No |  |  | Is the emergency drill rate compliant with EEPP? | Planned number of Emergency Drills | 35 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Planned Packages | [24 empty] | Actual number of Emergency Drills | 20 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Awarded Packages | [24 empty] | Recommended time to complete Emergency drills | 5 Days | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Trade Most at Risk | [24 empty] | Actual Time to complete Emergency drills | 10 Days | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Highest Risk Work Site | [19 empty] | Fatality Rate (FR) | 5 |  |  | Fatality Rate (FR) | No. of incidents resulting in fatality or severe impairment per 200,000 work hours | 5 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Number of planned audits | [19 empty] | Lost Time Injury Frequency Rate (LTIFR) | 10 |  |  | Lost Time Injury Frequency Rate (LTIFR) | No. of incidents resulting in lost time per 200,000 work hours | 10 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Number of conducted audits | [19 empty] | Total Recordable Incident Rate (TRIR) | 30 |  |  | Total Recordable Incident Rate (TRIR) | No. of recordable incidents per 200,000 work hours | 30 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Number of Notifiable Incidents | 6 | [18 empty] | Near Miss Rate | 60 |  |  | Near Miss Rate | No. of near misses recorded per 200,000 work hours | 60 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Number of Infringement Notices | 2 | [18 empty] | Safety Observation Rate | 80 |  |  | Safety Observation Rate | No. of safety observation recorded per 200,000 work hours | 80 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Total Safe Manhours | 2 | [18 empty] | Leadership Safety Walk Rate | 0.6 |  |  | Leadership Safety Walk Rate | Total number of Safety Walks | 50 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Total number of closed Corrective actions | 1 | [23 empty] | Total number of Safety Walks with Leadership | 30 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Inspection Pass Rate | [19 empty] | % of Grievances Closed | 1 | Welfare Compliance | 2.4 | % of Grievances Closed | Number of grievances closed | 5 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | No. of recurring incidents / safety observations outside control | [24 empty] | Total number of grievances | 5 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Total Site Manhours | 180000000 | [18 empty] | Average Cycle Time to Close Grievances | Good |  |  | Average Cycle Time to Close Grievances | Cycle time to close grievances | Good | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Welfare of labor camps | [19 empty] | % of Welfare Staff vs Total workforce | Good |  |  | % of Welfare Staff vs Total workforce | Percentage of Welfare Staff against total staff | Good | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Welfare of site facilities | [19 empty] | % closed welfare observations or red flag if 0 observations | 0.75 |  |  | % closed welfare observations or red flag if 0 observations | Total number of Welfare Observations | 20 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Labor accommodation inspection rate | [24 empty] | Total number of Closed Welfare Observations | 15 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [30 empty] | Regulation Compliance | [19 empty] | % of Welfare Non-compliances closed | 0.58 |  |  | % of Welfare Non-compliances closed | Total Welfare Non-compliances | 100 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [55 empty] | Total Closed Welfare Non-compliances | 58 | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [50 empty] | Average Cycle Time to Close Welfare Non-compliances | 10 Days |  |  | Average Cycle Time to Close Welfare Non-compliances | Cycle time to close Welfare Non-Compliances | 10 Days | [7 empty] | assessment_guide_diriyah.xlsx
diriyah | [50 empty] | Is frequency of Labor Accommodation Inspection occurring in accordance with VMMP? | Yes |  |  | Is frequency of Labor Accommodation Inspection occurring in accordance with VMMP? | Mitigation measures in the event of welfare audit observations & recommendations | Yes | [7 empty] | assessment_guide_diriyah.xlsx
qiddiyah | Latest Approved Completion Date​ | Q1-29 | 2025 | 0 |  |  |  |  | Risk 1 | Contractor | Cost | Low | Open | Measure 02 | DevCo Schedule Performance Index (SPI) | 0.96 | Satisfactory | Estimate to Completion Declared by DevCo | 519000000 | 2023 | 400 | 420 | 400 | Budget Variance | -0.11111 | Good | PIF Approved Capex budget (Initial Business Plan) | 450000000 | 2 | Jan | No. of Site Access Required | 180 | 186 | 129 | 50 | Fatalities | 0 | 0 | 0 | 0 | HSE Audit | 3 | 5 | 4 | HSE | 6 | 22 | 12 | Jan | 30 | % of CESMP mitigation measures which align with ESIA* | 0.5 | Construction Planning Maturity | 2.1 | % of CESMP mitigation measures which align with ESIA* | Environmental mitigation measures included in CESMP | 0.1 | Implementation Success Rate for Innovation Strategy | 3 | Is there an innovation Strategy or document that lists the key focus areas and initiatives across design, construction and operation and aligned with DevCo strategic plan? | 0.4 | Needs Improvement | 1.7 | Innovation & Technology Deployment | assessment_guide_qiddiyah.xlsm
qiddiyah | Forecast Completion Date​ | Q3-29 | 2026 | 1350 | 1350 |  |  |  | Risk 2 | Source A | Impact O | Med | Ongoing | Measure 01 |  |  |  | Total Expenditure to Date | 100000000 | 2024 | 420 | 440 | 420 |  |  |  | Forecast budget (EAC) | 500000000 | 5 | Feb | No. of Site Access Provided | 120 | 16100 | 9600 | 6800 | Severe Impairment | 1 | 0 | 1 | 0 | Welfare Inspection | 2 | 4 | 4 | Welfare | 25 | 10 | 7 | Feb | 40 | [5 empty] | Environmental mitigation measures recommended in ESIA | 0.2 | Innovation Adoption Effectiveness Index (strategy & leadership alignment) | 1 | [5 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | Approved baseline completion date | Q2-27 | 2027 | 3200 | 1600 | 1600 | Risk 1 | 20 | Risk 3 | Source B | Impact P | High | Open | Measure 04 | % milestone achievement in accordance with the approved business plan | 0.9 | Good | Contingency budgeted at DevCo level | 2000000 | 2025 | 440 | 460 | 455 | % of projects having Budget Variance | 1 | Needs Improvement | Number of Projects with Budget Variance | 15 | 3 | Mar | Packaging & Phasing Strategy | Good |  |  |  | Lost Time Incidents | 3 | 0 | 1 | 2 | [8 empty] | Mar | 38 | Has the Construction Execution Plan been updated to reflect the latest stage of construction? | Yes |  |  | Has the Construction Execution Plan been updated to reflect the latest stage of construction? | Update of construction execution plan | Yes | Innovation Adoption Effectiveness Index (skilled human resources) | 3 | [5 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | No. of schedule iterations | 8 | 2028 | 4000 |  | 2300 | Risk 2 | 18 | Risk 4 | Source F | Impact T | High | Closed | Measure 05 |  |  |  | Contingency utilized at DevCo level | 2500000 | 2026 | 460 | 480 | 500 |  |  |  | Total number of projects | 15 | 1 | Apr | Execution & Site Logistics | Satisfactory |  |  |  | Recordable Incidents | 14 | 3 | 11 | 0 | [8 empty] | Apr | 35 | Has the construction sequence and method statement been reviewed and approved? | No |  |  | Has the construction sequence and method statement been reviewed and approved? | Review and approval of Construction sequence & method statement | No | Innovation Adoption Effectiveness Index (planning & governance) | 2 | [5 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | Planned duration up to a specific phase as per approved Baseline programme | 145 | 2029 |  |  | 4000 | Risk 3 | 15 | Risk 5 | PMC | Reputation | Low | Ongoing | Measure 06 | % of projects with approved change requests in design phase since inception with time impact of more than 1 month | 0.16667 | Good | Contingency Utilization Rate | 200000 | 2027 | 480 | 500 | 520 | % of projects with contingency utilization rate > 1 | 0.8 | Needs Improvement | Number of projects with contingency utilization > 1 | 12 | 0 | May | Procurement Strategy | Good |  |  |  | Nears Misses | 26 | 2 | 21 | 3 | [8 empty] | May | 0 | Is total land acquisition sufficient to achieve the area required for construction site logistics? | No |  |  | Is total land acquisition sufficient to achieve the area required for construction site logistics? | Planned Area provision for site offices, amenities, laydown areas, storage facilities, workforce accommodations | Average | Innovation Adoption Effectiveness Index (process management) | 4 | [5 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | Duration taken to complete works up to the specific phase | 160 |  |  |  |  | Risk 4 | 4 | Risk 6 | Source C | Impact Q | Med | Open | Measure 07 |  |  |  | Value of Changes in Design Stage | 6000000 | 2028 | 500 | 520 | 535 | % of projects with Approved Change Requests (design/construction) having a cost impact greater than 2% | 0.8 | Needs Improvement | No. of projects with approved change request having a cost impact greater than 2% | 12 | 0 | Jun | Required area for land acquisition | [17 empty] | Jun | 0 | [5 empty] | Actual Area provision for site offices, amenities, laydown areas, storage facilities, workforce accommodations | No | Innovation Adoption Effectiveness Index (partnerships and collaboration) | 2 | [5 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | Recovery Plan | Satisfactory |  |  |  |  | Risk 5 | 7 | Risk 7 | Source D | Impact R | Low | Closed | Measure 08 | % of projects with approved change requests in construction phase since inception with time impact of more than 4 months | 0.33333 | Satisfactory | Value of Changes in Construction Stage | 3000000 |  |  |  |  | % of projects with Approved Claims | 0.66667 | Needs Improvement | No. of projects with approved claims | 10 | 0 | Jul | Mitigation of Project Execution Plan implementation challenges | [17 empty] | Jul | 0 | Have Traffic Simulations been completed in preparing the Site & Logistics Plan? | Yes |  |  | Have Traffic Simulations been completed in preparing the Site & Logistics Plan? | Completion of Traffic Simulations | Yes | Innovation Adoption Effectiveness Index (resource management) | 0.6 | [5 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | Extent of all EOT (design stage) | 4 | [6 empty] | Risk 8 | Supplier | Time | High | Closed | Measure 09 |  |  |  | Number of Changes (Concept MP) | 0 |  |  |  |  | % of provisional sums of the latest PIF Approved Capex budget | 0.0032787 | Good | Total provisional sums | 2000000 | 0 | Aug | Occurred delays due to stakeholder objections | [17 empty] | Aug | 0 | Has the Project Execution Plan been updated and approved in the last 12 months? | No |  |  | Has the Project Execution Plan been updated and approved in the last 12 months? | Date of latest approved Procurement Plan | No | Implementation Success Rate for Smart City Strategy | 3 | [5 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | Extent of all EOT (const. stage) | 8 | [6 empty] | Risk 9 | CAA | Impact M | Low | Closed | Measure 10 | % of projects with approved schedule extension | 0.43333 | Needs Improvement | Number of Changes (Detailed MP) | 6 | [7 empty] | Latest Approved budget | 610000000 | 0 | Sep | Workforce Availability | Needs Improvement | [16 empty] | Sep | 0 | % of Stakeholder MOU** / LUPs*** not executed in accordance with critical lead time | 0.05 |  |  | % of Stakeholder MOU** / LUPs*** not executed in accordance with critical lead time | Number of Stakeholder MOU or Land Use Permits not executed on time | 5 | Number of Smart City Use Cases | 10 | Is there a smart city Strategy or document that lists the key focus areas of smart city aligned with DevCo strategic plan? | 0.4 | Needs Improvement |  |  | assessment_guide_qiddiyah.xlsm
qiddiyah | No. of unresolved issues | 10 | [6 empty] | Risk 10 | Source E | Impact S | Med | Ongoing | Measure 11 |  |  |  | Number of Changes (Concept Design) | 3 |  |  |  |  | % of variance of Allocated Provisional sums against the awarded amount | 1.6667 | Needs Improvement | Actual Utilized Provisional Sums | 1200000 | 0 | Oct | Resource Availability | Good | [16 empty] | Oct | 0 | [5 empty] | Total Stakeholder MOU or Land Use Permits required | 100 | Smart City Adoption Effectiveness Index (strategy & leadership alignment) | 2 | [5 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | No. of (Open) Inherent Risks | 20 | [15 empty] | Number of Changes (Detailed Design) | 4 | [9 empty] | 0 | Nov | Workforce retention track record | [17 empty] | Nov | 0 | % of Workforce Hired against Workforce Estimates | 1 | Workforce Resource Availability | 3 | % of Workforce Hired against Workforce Estimates | Forecast workforce requirements | 0.4 | Smart City Adoption Effectiveness Index (infrastructure readiness) | 2 | [5 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | No. of (Closed) Residual Risks | 45 | [12 empty] | % of projects with Forecast completion date beyond the latest approved schedule | 0.46154 | Needs Improvement | Number of Changes (Construction) | 10 | [9 empty] | 0 | Dec | Turnover rate track record | [17 empty] | Dec | 0 | [5 empty] | Actual workforce employed | 0.4 | Smart City Adoption Effectiveness Index (planning & governance) | 3 | [5 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | Project-level risks (including low, medium, and high severity) | 80 | [12 empty] | Is the Forecast Finish Date at a given data date based on the alignment and buy-in from project teams and other listed stakeholders? | Yes | Good | Total Awarded Cost | 15000000 | [11 empty] | Plant/equipment downtime track record | [19 empty] | % of Labor Camp Capacity against Workforce Estimates | 1.125 |  |  | % of Labor Camp Capacity against Workforce Estimates | Forecast number of labor camps | 0.8 | Smart City Adoption Effectiveness Index (stakeholder alignment) | 1 | [5 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | Procedures for risk management | Satisfactory | [12 empty] | Based on the risks identified and approved change requests, has the DevCo conducted a sensitivity assessment on the forecast completion at a given data date? | Yes, but inadequate | Satisfactory | Approved Variations and Claims | 10000000 | [11 empty] | Number of technical queries raised | [24 empty] | Actual number of labor camps | 0.9 | Smart City Adoption Effectiveness Index (realized benefits & performance) | 0.5 | [5 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | Risks identified and corresponding impact on schedule | NIL | [12 empty] | Has DevCo allocated risk contingency for the identified risks? | Yes | Good | Uncommitted Cost | 250000000 | [11 empty] | Number of technical queries closed | [19 empty] | % of Material Supply Capacity against Material Demand Estimates | 1.4 |  |  | % of Material Supply Capacity against Material Demand Estimates | Forecast number of batching / crushing plants/ precast yards, etc. | 0.5 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | Extra Cost due to Unresolved Issues | 2000000 | [12 empty] | Was there any deferment in the project completion date due to unidentified risks? | Yes, but less than 1 month | Satisfactory | Pending Variations | 0 | [11 empty] | Average time to complete shop drawing reviews | [24 empty] | Actual number of batching / crushing plants/ precast yards, etc. | 0.7 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [14 empty] | Was there any Cost Overrun because of identified risk? | No | Good | Anticipated Variations | 1 | [11 empty] | Number of shop drawing review conducted | 480 | [18 empty] | Did DevCo adhere to Technical Submittals Review Cycle Time (RCT)? | Yes | Adherence to Design | 3 | Did DevCo adhere to Technical Submittals Review Cycle Time (RCT)? | Time taken for closure of technical queries | Yes |  |  | Is there an impact assessment report or identified process/ guidelines to evaluate the impact of the innovation / smart city technologies adoption on DevCo performance? | 0.6 | Satisfactory |  |  | assessment_guide_qiddiyah.xlsm
qiddiyah | [14 empty] | Was there any Cost Overrun because of unidentified risk? | Yes, but less than 1% | Satisfactory | [13 empty] | Number of material / product substitution requests | [24 empty] | Technical Submittal Review Cycle Time (RCT) | Yes | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [14 empty] | Risk Control Rate of the identified risks at DevCo Level | 0.6 | Satisfactory | [13 empty] | Average time to approve product sample & materials | [19 empty] | % of approved shop drawing reviews vs planned | 0.99167 |  |  | % of approved shop drawing reviews vs planned | Total number of shop drawing review requests | 480 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Product & Material Approval Rate | [24 empty] | Total number of shop drawing reviews approved | 476 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [14 empty] | Is the DevCo fully compliant with Risk Management Plan requirements? | No | Needs Improvement | [13 empty] | Number of as-built drawing review conducted | 485 | [18 empty] | % of approved product waivers vs product specified | 2 |  |  | % of approved product waivers vs product specified | Total number of product sample & material approvals requested | 0.3 |  |  | Is there evidence for innovation / smart city technologies successful implementation (in final design report, master plan or other)? | Yes | Good |  |  | assessment_guide_qiddiyah.xlsm
qiddiyah | [14 empty] | Is there a difference in the time impact forecast before and after the risk event has triggered? | Yes, but less than 2 weeks | Satisfactory | [13 empty] | Average time to approve As-built rejections / iterations | [24 empty] | Total number of product sample & materials approved | 0.6 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [14 empty] | Is there a difference in the Cost impact forecast before and after the risk event has triggered? | Yes, but less than 0.5% | Satisfactory | [13 empty] | As-Built Drawing Approval Rate | [19 empty] | % of Certified As-Built Drawing Packages vs Planned | 0.95 |  |  | % of Certified As-Built Drawing Packages vs Planned | Number of As-Built review requests | 500 |  |  | Are there Pilot or R&D projects conducted? | 0.55 | Needs Improvement | 1 | Pilot and R&D Transition Rate | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Average time to complete MIRs and close out approvals | [24 empty] | Number of As-built reviews / approvals | 475 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Average time to complete WIRs and close out approvals | [19 empty] | MIR Inspection Rate | 0.98333 |  |  | MIR Inspection Rate | Total number of MIRs requested | 120 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Number of NCRs open for between 30 and 60 days | 23 | [23 empty] | Total number of MIRs inspected | 118 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Number of NCRs open for more than 60 days | 5 | [18 empty] | MIR Acceptance and Approval Rate | 0.91667 |  |  | MIR Acceptance and Approval Rate | Total number of MIRs approved | 110 |  |  | % of pilot / R&D Projects Transitioned into Full-Scale | 0.13043 | Needs Improvement |  |  | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Leadership engagement | Satisfactory | [18 empty] | WIR Inspection Rate | 0.97143 |  |  | WIR Inspection Rate | Total number of WIRs requested | 350 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Total number of ITPs requested | 100 | [23 empty] | Total number of WIRs inspected | 340 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Total number of ITPs attended | 98 | [18 empty] | WIR Acceptance and Approval Rate | 0.95714 |  |  | WIR Acceptance and Approval Rate | Total number of WIRs approved | 335 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Total number of ITPs approved | 87 | [18 empty] | Does the frequency of Audits align with the QMP? | Yes | Quality Assurance / Quality Control (QA/QC) | 2.6 | Does the frequency of Audits align with the QMP? | Required Audit frequency | Yes |  |  | Availability of Innovation unit / department with structured team | 0 | Needs Improvement | 1.5 | Organization Maturity Towards Innovation Adoption | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Total number of ITPs completed | 85 | [18 empty] | % closure of Non-Conformance Reports (NCR) | 0.96667 |  |  | % closure of Non-Conformance Reports (NCR) | Total number of defects & NCRs | 150 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Total number Quality Reports required | [24 empty] | Total number of closed defects & NCRs | 145 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Total number Quality Reports completed | [19 empty] | Average NCRs closeout Cycle Time | 5 Weeks |  |  | Average NCRs closeout Cycle Time | Average time to close NCRs | 5 Weeks | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Completeness of Quality Management Plan | Needs Improvement | [18 empty] | % of procurement packages delivered within the planned lead times defined in the PMP | 2 | Procurement & Contracting Compliance | 2.8 | % of procurement packages delivered within the planned lead times defined in the PMP | Planned Procurement Package Lead Time | 5 |  |  | Availability of Innovation and Technology Strategy / Process & Framework | 0.5 | Satisfactory |  |  | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Required number of ITPs signed off throughout construction | [24 empty] | Actual Procurement Package Delivery Time | 10 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Total number of raised closed-out defects & NCRs | [19 empty] | % of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures | 0.875 |  |  | % of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures | Total number of claims and variations | 800 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Forecasted Procurement Budget | [24 empty] | Total number of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures | 700 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Actual Procurement Budget | [19 empty] | % of packages procured with 100% complete, compliant and well-structured documentation | 0.6 |  |  | % of packages procured with 100% complete, compliant and well-structured documentation | Total number of packages | 0.5 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Vendor Database | [24 empty] | Total number of packages procured with 100% complete, compliant and well-structured documentation | 0.3 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Vendor Shortlist | [19 empty] | % of awarded contracts where vendors appointed passed full due diligence checks | 1.2857 |  |  | % of awarded contracts where vendors appointed passed full due diligence checks | No. of awarded contracts where vendors appointed passed full due-diligence checks | 0.9 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Vendor Awarded | [24 empty] | Total number of awarded contracts | 0.7 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Vendor KPIs | [19 empty] | Did the DevCo complete a Supply Chain Risk-Market Intelligence Assessment in the last quarter? | Yes |  |  | Did the DevCo complete a Supply Chain Risk-Market Intelligence Assessment in the last quarter? | Supply Chain Risk-Market Intelligence Assessment | Yes | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Vendor Performance Database | [19 empty] | % of procurement activities executed as planned in the Annual Procurement Plan | 0.66667 | Procurement & Contracting Execution Performance |  | % of procurement activities executed as planned in the Annual Procurement Plan | Total number of procurement activities | 129 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Tender return date: Planned / Actual | [24 empty] | Number of procurement activities executed as planned | 86 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Tender Review & award time: Planned / actual | [19 empty] | % of deviations in total awarded contract value with tender cost estimates | 0.4 |  |  | % of deviations in total awarded contract value with tender cost estimates | Value of Awarded Contract | 0.1 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Pre-Tender Cost Estimate | [24 empty] | Tender Cost Estimate | 0.06 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Tender Performance Index | [19 empty] | % of contracts with filed claims | 0.3 |  |  | % of contracts with filed claims | Number of contracts with filed claims | 0.3 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Contract clauses | Satisfactory | [18 empty] | Are Payment Certificates and payments being processed in accordance with the Contract terms and conditions? | 80 |  |  | Are Payment Certificates and payments being processed in accordance with the Contract terms and conditions? | Processing of payment certificates and payments | 80 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Procurement Management Plan | Good | [18 empty] | Are Vendor performance assessment occurring which capture financial instability, delays, repeated quality issues in real-time? | No |  |  | Are Vendor performance assessment occurring which capture financial instability, delays, repeated quality issues in real-time? | Alignment of sourcing strategies with project schedules and requirements | No | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Scope / design maturity | Satisfactory | [18 empty] | Does the HSE Management Manual have adequate provision for identification and escalation of high risk activities? | Yes | HSE Compliance | 1.87 | Does the HSE Management Manual have adequate provision for identification and escalation of high risk activities? | Escalation criteria for high risk activities | Yes | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Compliance with local content regulations / policies | [19 empty] | Is the rate of review of the Safety Risk Register in accordance with the HSE Management Manual? | Yes |  |  | Is the rate of review of the Safety Risk Register in accordance with the HSE Management Manual? | HSE Risk Register Review Rate | Yes | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Dispute rate | [19 empty] | % of closed Safety Risk items | 0.83333 |  |  | % of closed Safety Risk items | Total number of Safety Risk items | 0.9 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Claims processing cycle time | [24 empty] | Total number of closed Safety Risk items | 0.75 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | No. of related CRs being requested during or after tendering phase due to identified scope gap | [19 empty] | Average cycle time to close Safety Risk items | 14 Days |  |  | Average cycle time to close Safety Risk items | Cycle time to close Safety Risk items | 14 Days | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Vendor Performance Assessment | Good | [18 empty] | Average cycle time to close Safety Incident | 0.65 |  |  | Average cycle time to close Safety Incident | Cycle time to close Safety Incident | 20 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Tender pack quality | Satisfactory | [23 empty] | Total number of closed safety incidents | 13 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Total packages | [19 empty] | Is the emergency drill rate compliant with EEPP? | No |  |  | Is the emergency drill rate compliant with EEPP? | Planned number of Emergency Drills | 35 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Planned Packages | [24 empty] | Actual number of Emergency Drills | 20 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Awarded Packages | [24 empty] | Recommended time to complete Emergency drills | 5 Days | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Trade Most at Risk | [24 empty] | Actual Time to complete Emergency drills | 10 Days | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Highest Risk Work Site | [19 empty] | Fatality Rate (FR) | 5 |  |  | Fatality Rate (FR) | No. of incidents resulting in fatality or severe impairment per 200,000 work hours | 5 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Number of planned audits | [19 empty] | Lost Time Injury Frequency Rate (LTIFR) | 10 |  |  | Lost Time Injury Frequency Rate (LTIFR) | No. of incidents resulting in lost time per 200,000 work hours | 10 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Number of conducted audits | [19 empty] | Total Recordable Incident Rate (TRIR) | 30 |  |  | Total Recordable Incident Rate (TRIR) | No. of recordable incidents per 200,000 work hours | 30 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Number of Notifiable Incidents | 6 | [18 empty] | Near Miss Rate | 60 |  |  | Near Miss Rate | No. of near misses recorded per 200,000 work hours | 60 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Number of Infringement Notices | 2 | [18 empty] | Safety Observation Rate | 80 |  |  | Safety Observation Rate | No. of safety observation recorded per 200,000 work hours | 80 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Total Safe Manhours | 2 | [18 empty] | Leadership Safety Walk Rate | 0.6 |  |  | Leadership Safety Walk Rate | Total number of Safety Walks | 50 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Total number of closed Corrective actions | 1 | [23 empty] | Total number of Safety Walks with Leadership | 30 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Inspection Pass Rate | [19 empty] | % of Grievances Closed | 1 | Welfare Compliance | 2.4 | % of Grievances Closed | Number of grievances closed | 5 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | No. of recurring incidents / safety observations outside control | [24 empty] | Total number of grievances | 5 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Total Site Manhours | 180000000 | [18 empty] | Average Cycle Time to Close Grievances | Good |  |  | Average Cycle Time to Close Grievances | Cycle time to close grievances | Good | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Welfare of labor camps | [19 empty] | % of Welfare Staff vs Total workforce | Good |  |  | % of Welfare Staff vs Total workforce | Percentage of Welfare Staff against total staff | Good | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Welfare of site facilities | [19 empty] | % closed welfare observations or red flag if 0 observations | 0.75 |  |  | % closed welfare observations or red flag if 0 observations | Total number of Welfare Observations | 20 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Labor accommodation inspection rate | [24 empty] | Total number of Closed Welfare Observations | 15 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [30 empty] | Regulation Compliance | [19 empty] | % of Welfare Non-compliances closed | 0.58 |  |  | % of Welfare Non-compliances closed | Total Welfare Non-compliances | 100 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [55 empty] | Total Closed Welfare Non-compliances | 58 | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [50 empty] | Average Cycle Time to Close Welfare Non-compliances | 10 Days |  |  | Average Cycle Time to Close Welfare Non-compliances | Cycle time to close Welfare Non-Compliances | 10 Days | [7 empty] | assessment_guide_qiddiyah.xlsm
qiddiyah | [50 empty] | Is frequency of Labor Accommodation Inspection occurring in accordance with VMMP? | Yes |  |  | Is frequency of Labor Accommodation Inspection occurring in accordance with VMMP? | Mitigation measures in the event of welfare audit observations & recommendations | Yes | [7 empty] | assessment_guide_qiddiyah.xlsm