## Main
0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | MEINHARDT | Administrator: | Admin
0.8
PLH
PROJECT LIGHTHOUSE
ASSESSMENT GUIDE
DIRIYAH
LOGIN
STRICTLY CONFIDENTIAL
þ Assessment In Progress
þ To Be Assessed
þ To Be Reviewed
þ In Review
þ Assessment Completed
Design
& Technical
(D&T)
Development
& Construction
(D&C)
Cost Estimation & Optimization
(CE&O)
Innovation
& Technology
(I&T)
Strategy
& Operations
(S&O)
þ Assessment In Progress
þ To Be Assessed
þ To Be Reviewed
þ In Review
þ Assessment Completed
þ Assessment In Progress
þ To Be Assessed
þ To Be Reviewed
þ In Review
þ Assessment Completed
þ Assessment In Progress
þ To Be Assessed
þ To Be Reviewed
þ In Review
þ Assessment Completed
þ Assessment In Progress
þ To Be Assessed
þ To Be Reviewed
þ In Review
þ Assessment Completed
þ Assessment In Progress
þ To Be Assessed
þ To Be Reviewed
þ In Review
þ Assessment Completed
Planning
& Monitoring
(P&M)
UPDATE
DevCo Assessment Input (P&M)
DevCo Assessment Analysis (P&M)
DevCo Assessment Input (D&T)
DevCo Assessment Analysis (D&T)
DevCo Assessment Input (D&C)
DevCo Assessment Analysis (D&C)
DevCo Assessment Input (CE&O)
DevCo Assessment Analysis (CE&O)
DevCo Assessment Input (I&T)
DevCo Assessment Analysis (I&T)
DevCo Assessment Input (S&O)
DevCo Assessment Analysis (S&O)
Interview Question (P&M)
Interview Question (D&T)
Interview Question (D&C)
Interview Question (CE&O)
Interview Question (I&T)
Interview Question (S&O)
Additional Data Points (P&M)
Additional Data Points (D&T)
Additional Data Points (D&C)
Additional Data Points (CE&O)
Additional Data Points (I&T)
Additional Data Points (S&O)
Log
Instructions
Glossary & Definitions
Document List
User
Setting
Get Section Data
Assessment Summary
Q1 2025
Period of Assessment

## Instructions
PIF Project Lighthouse
Instructions
SN | Page | Role | Instructions
1 | Document List |  | This page lists all the documents submitted by the DevCo, which consist the location of the documents and the file names.
2 | DevCo Assessment Input |  | This page is used for the input of data points required for the assessment criteria
3 | DevCo Assessment Input | Assessor | Enter the assessment value for each data point in " INPUT VALUE" column. Note: 1) For non-quantitative AC, use the drop-down box to select the right option 2) The drop down box would have options across all the Assessment critera (AC) and hence you may see drop down values, which are not relevant to the specific AC. Please toggle to the Assessment Analysis page to identify the relevant options to input.
4 | DevCo Assessment Input | Assessor | Input the Document Request Number (for e.g., DR-017) under the "DATA SOURCE" column. Please refer to the Document List for the Document Request (DR) number
5 | DevCo Assessment Input | Assessor | Please note down any remarks in the Assessor Remarks column
6 | DevCo Assessment Input | Reviewer | Please review the findings with the Data Analyst/Assessor and update the "INPUT VALUE" column (if required). For any changes to the "INPUT VALUE" input or to make any additional remarks, please update the "REVIEWER REMARKS" column
7 | DevCo Assessment Analysis | All | A score of 'Good', 'Satisfactory', and 'Critical' will be automatically generated based on each Assessment Criteria's value
8 | DevCo Assessment Analysis | All | Please note down remarks, if any
9 | Interview Questions (IQs) |  | This page is used for the discussions with DevCos
10 | Interview Question | All | Predefined interview questions will be populated here and additional questions can be added as needed.
11 | Interview Question | All | Please note down the conversation/interview date in the "DATE OF INTERVIEW" column
12 | Interview Question | All | Please note down DevCo answers to the interview questions in " RESPONSE" Column
13 | Interview Question | All | Please note down any further queries in "FOLLOW UP QUESTIONS " for easy tracking
14 | Additional Data Points (ADPs) |  | This page is used for the input of additional data points which are not required for the assessment criteria but are needed for the dashboard
15 | Additional Data Points | Data Analyst / Assessor | Please populate the "VALUE" column for each Additional Data Points
Go to Main Page
Refresh

## Glossary&Definitions
PIF Project Lighthouse
Glossary&Definitions
SN | Section | Term | Description
1 | Cost Estimation & Optimization | Actual Cost (AC) | Actual Cost is the total cost incurred for work completed on a project at a given point in time. It includes all direct and indirect costs spent on labor, materials, equipment, and other expenses.
2 | Cost Estimation & Optimization | Aggregated Budget Variance | Cumulative difference between total budgeted figures and actual results across multiple categories or projects, highlighting overall financial performance deviations within a specific period
3 | Planning & Monitoring | Aggregated SPI | Indication of overall schedule performance at DevCo level
4 | Development & Construction | Annual Procurement Plan / Strategy | The Procurement Plan is required to be reviewed and updated by the DevCo as a minimum annually and submitted to PIF for approval in accordance with the requirements of the Project Execution Plan.
5 | General | Authority | Each development stage requires approval. The Authority is the relevant party responsible for the approval at the relevant stage (e.g. CEO, Founding Board etc.)
6 | Design & Technical | BUA | Built Up Area (BUA) is the total area being developed or constructed. It is the Gross Floor Area (GFA) plus Parking plus any Service Area.
7 | Cost Estimation & Optimization | Budget Variance (BV) | Extent of variance in budget
8 | Cost Estimation & Optimization | Budget At Completion (BAC) | The Budget at Completion (BAC) represents the total budgeted cost for all the work planned for a project
9 | Cost Estimation & Optimization | Estimate To Complete (ETC) | The estimated cost required to complete the remaining work of a project
10 | Cost Estimation & Optimization | Estimate At Completion (EAC) | Total forecasted cost of the project based on the ongoing
11 | General | Business Plan | Documentation developed by PIF informing the Vision and key objectives of the project
12 | General | Change Management Log | A document summarising the status of all proposed and approved Variations
13 | General | Change Management Procedure | Procedural document stipulating the requirements to be met when administering any amendment to a Contract or Project.
14 | Cost Estimate & Optimization | Contingency Utilization Rate (CUR) | Percentage of a project’s allocated contingency fund that has been used to address unforeseen costs or risks, reflecting the efficiency of contingency planning and management.
15 | Development & Construction | Contract Management Policy | A policy outlining award and management of contracts between DevCo and Vendors.
16 | Cost Estimate & Optimization | Cost Estimate and Optimization (CE&O) | Technical function which covers cost benchmarks for development of budgets, and cost optimization levers
17 | Cost Estimate & Optimization | Cost Report | A document provided on an interim basis to inform of the current financial status of a Project
18 | Design & Technical | Design and Technical (D&T) | Technical Function which covers all design-related topics of a project including architecture, engineering, masterplanning, infrastructure and environment & sustainability
19 | Development & Construction | Development and Construction (D&C) | Technical function which covers construction project execution plans, contract management and procurement, and construction quality and Health, Safety and Environment (HSE) topics
20 | Planning & Monitoring | Earned Value (EV) | Value of the work that is completed at a given time, measured against the budgeted cost.
21 | Planning & Monitoring | Extension of Time (EOT) | Extension of Time is a contractual provision in construction allowing the project completion date to be extended due to unforeseen delays beyond the contractor’s control, ensuring fairness and mitigating penalties.
22 | Design & Technical | Gross Floor Area (GFA) | Gross Floor Area (GFA) is the total floor area of a building including any underground saleable or leasable area but excluding parking and underground technical/service areas. The GFA is calculated based on the distance from external wall to external wall.
23 | Innovation & Technology | Innovation and Technology (I&T) | Technical function which covers incorporation of high-impact advanced technologies and methodologies across the entire project life cycle, and implementation of smart city use cases.
24 | Development & Construction | Inspection Test Plan (ITP) | A document which specifies the manatory Inspection, Witness and Hold Points throughout construction that must be verified by a suitably qualified person before works are authorised to proceed.
25 | General | Key Performance Indicator (KPI) | Key quantifiable indicators of progress toward an intended result
26 | Development & Construction | Non-Conformance Report (NCR) | Non-Conformance Report is a quality management document that identifies, tracks, and records deviations from specified standards, facilitating process improvement and quality control.
27 | Cost Estimate & Optimization | Planned Budget (PB) | It represents how much is expected to be spent at a given point in time from the Approved Over All Budget (BAC)
28 | Planning & Monitoring | Planned Value (PV) | The amount of work that was planned to be completed at a given time as per the approved Schedule.
29 | Planning & Monitoring | Planning and Monitoring (P&M) | Technical Function which covers schedule development and monitoring, and risk management
30 | Development & Construction | Procurement Strategy | Methodical approach for determining the contractural relationship and agreements between DevCo and Vendors
31 | Development & Construction | Procurement Procedures Manual | A manual which details every aspect of the tendering and overall procurement activities.
32 | Development & Construction | Project Execution Plan (PEP) | Project Execution Plan prepared initially by PIF as part of the Business Plan Stage, which is then passed to the DevCo to lead, review and update from Masterplan Stage onwards
33 | Development & Construction | Request For Information (RFI) | A formal communication tool for requesing information
34 | Development & Construction | Rework Cost | Indication of the rework done due to quality, design etc issues
35 | Planning & Monitoring | Schedule Performance Index (SPI) | Indication of project schedule performance
36 | Cost Estimate & Optimization | Soft Cost | Soft costs are indirect, non-physical expenses in a construction project that are not directly tied to labor, materials, or physical construction work.
37 | General | Stage | The description of the Project Stage as per Development Company and PIF terminology.
38 | Strategy & Operations | Strategy & Organization | Technical Function which covers topics around strategy development and execution, people and tools.
39 | Design & Technical | Value Engineering | Process to derive greater value within a Project seeking improvement in time and/ or cost outcomes
40 | Development & Construction | Vendor Database | A database of Vendors, including pre-qualified Vendors, Vendor appraisal and performance assessment and a list of blacklisted Vendors.
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
Go to Main Page
Refresh

## DocumentList
PIF Project Lighthouse
DocumentList
SN | Document Request ID (Sharepoint) | Document Request | DevCo or Project Level | Document Number | File Name | Date Received | Remarks
1 | Cost Data | Cost Data Template | DevCo
2 | DR-001 | Baseline and Updated Master schedule (including cost linked Milestone summary for earned value, planned value analysis, and Schedule Updates) | DevCo
3 | DR-002 | Program Management Plan | DevCo | DR-002-01 | 15th April - Updated DGCL DoA 7 | 2025-05-07 21:29
4 |  |  |  | DR-002-02 | Completion, Handover & Opening (Policy and Process Manual) | 2025-05-07 21:29
5 |  |  |  | DR-002-03 | Development Managment Policy Process Manual_ | 2025-05-07 21:29
6 |  |  |  | DR-002-04 | GCEO Signed Sub-DOA V2 7 | 2025-05-07 21:29
7 |  |  |  | DR-002-05 | 2025.03.20 Periodic Schedule Update - Two Step Approach | 2025-05-07 21:29
8 |  |  |  | DR-002-06 | SW-SWD-550-0000-MAC-GDL-PC-000042 - Integrated Master Schedule Update | 2025-05-07 21:29
9 |  |  |  | DR-002-07 | SW-SWD-550-0000-MAC-PLN-PC-000003 - Schedule Management Plan | 2025-05-07 21:29
10 |  |  |  | DR-002-08 | SW-SWD-550-0000-MAC-PRO-PC-000025 - Integrated Master Schedule Update | 2025-05-07 21:29
11 | DR-003 | Latest Approved Monthly Progress Report | DevCo | DR-003-01 | DevCo President Commercial Update - Dec -2024 | 2025-05-07 21:29
12 |  |  |  | DR-003-02 | 241226-DC-PMO-GCEO Programme Update - DI DII HD&WH WS | 2025-05-07 21:29
13 |  |  |  | DR-003-03 | 241226-DC-PMO-GCEO Report DI DII HD&WH WS - Dec-24 | 2025-05-07 21:29
14 |  |  |  | DR-003-04 | DevCo President Commercial Update - Dec -2024 | 2025-05-07 21:29
15 | DR-004 | Change request register (covering latest approved schedule extension requests) | DevCo
16 | DR-005 | Latest approved risk mapping / risk register (including mitigation plans) documented at DevCo level and the list of Stakeholders | DevCo | DR-005-01 | 00-000-000-0000-MAC-REG-RK-000002(17) DC Portfolio Risk Register_Mar25 (1) | 2025-05-07 21:29
17 |  |  |  | DR-005-02 | 00-000-000-0000-MAC-REG-RK-000003(16) DC Portfolio Issue Register_Mar25 | 2025-05-07 21:29
18 |  |  |  | DR-005-03 | Risk Management Dashboard_New | 2025-05-07 21:29
19 |  |  |  | DR-005-04 | SW-SWD-550-0000-MAC-PRE-RK-000002(11) Principal Risk and Issue Mtg Presentation_Feb25_Final (1) | 2025-05-07 21:29
20 |  |  |  | DR-005-05 | SW-SWD-550-0000-MAC-ROM-RK-000002(08) DC Principal Risk Meeting Minutes_Feb25 | 2025-05-07 21:29
21 | DR-006 | Lookahead Schedules / Short-term execution plans (e.g., 4-week or 6-week lookahead) | DevCo | DR-006-01 | DC - DevCo Risk Management Procedure (Rev 00) signed | 2025-05-07 21:29
22 | DR-007 | Sample of project level approved risk register | Project
23 | DR-008 | Risk Management Plan | DevCo
24 | DR-009 | Latest Updated Cost report | DevCo
25 | DR-010 | Program Tracker | DevCo
26 | DR-011 | Original Approved and Latest version of CGI & Animation (Material Palette & Finish Schedule) | Project
27 | DR-012 | Original Approved and Latest version of the Drawings | DevCo
28 | DR-013 | DevCo Design & Technical Guidelines (including, but not limited to, Look & Feel Design Guidelines) | DevCo | DR-013-01 | 123DG_GUIDELINES_Part III_RWK.PDF | 2025-05-07 21:29
29 |  |  |  | DR-013-02 | 240117 [1] DII Residential Design Guidelines.PDF | 2025-05-07 21:29
30 |  |  |  | DR-013-03 | FLS Guidelines | 2025-05-07 21:29
31 |  |  |  | DR-013-04 | MEP Guidelines | 2025-05-07 21:29
32 |  |  |  | DR-013-05 | Structural Guidelines | 2025-05-07 21:29
33 | DR-014 | Design Report / Return Brief Report (including approved and latest Asset Area Schedule & Population) | Project
34 | DR-015 | Latest Stage Gate Cost Plan | Project
35 | DR-016 | Report including constructability feasibility and construction methodology | Project
36 | DR-017 | Digital Information Management Plan | DevCo | DR-017-01 | 20231022 Spatial Data GIS Requirements | 2025-05-07 21:29
37 |  |  |  | DR-017-02 | SW-SWD-550-0000-DGD-STD-BM-000001 Employer Information Requirements. | 2025-05-07 21:29
38 |  |  |  | DR-017-03 | SW-SWD-550-0000-DGD-STD-BM-000002 Appendix 01 - Asset Information Requirements | 2025-05-07 21:29
39 |  |  |  | DR-017-04 | SW-SWD-550-0000-DGD-STD-BM-000003 Appendix 01.1-Asset Information Data Structure & Classification. | 2025-05-07 21:29
40 |  |  |  | DR-017-05 | SW-SWD-550-0000-DGD-STD-BM-000004 Appendix 01.2 -Asset Classification&Information Mapping | 2025-05-07 21:29
41 | DR-018 | Latest Project Execution Plan (including Design Strategy, Packaging Strategy and Phasing Strategy) | DevCo | DR-018-01 | DG2 High Level Delivery Strategy_Final r15MAR25_FK | 2025-05-07 21:29
42 | DR-019 | Design Master Schedule | DevCo
43 | DR-020 | Procedures and Governance for design approvals and change management | DevCo | DR-020-01 | Change Approval Map | 2025-05-07 21:29
44 | DR-021 | Design Basis Report and Stage Gate Design Report (including Design Management Report, Design Reviews & Verifications Register) | Project
45 | DR-022 | Infrastructure and Engineering report (including Water, Energy, Waste, Infrastructure & Mobility Plans) | DevCo
46 | DR-023 | Environmental and Social Impact Assessment | DevCo | DR-023-01 | 1. Enviromental Permit GAMEP - DGI - Arabic | 2025-05-07 21:29
47 |  |  |  | DR-023-02 | 2. Environmental permit GAMEP- DGI - Translation | 2025-05-07 21:29
48 |  |  |  | DR-023-03 | 3. Extension letter - Translation | 2025-05-07 21:29
49 |  |  |  | DR-023-04 | 140920-Enviromental Permit GAMEP | 2025-05-07 21:29
50 |  |  |  | DR-023-05 | OG_GN_NCEC_44-8902_بشأن عدم الحاجة لتجديد التصاريح البيئية | 2025-05-07 21:29
51 |  |  |  | DR-023-06 | Diriyah Gate EIA report - 20feb20 | 2025-05-07 21:29
52 |  |  |  | DR-023-07 | Appendix A | 2025-05-07 21:29
53 |  |  |  | DR-023-08 | Appendix B | 2025-05-07 21:29
54 |  |  |  | DR-023-09 | Appendix C | 2025-05-07 21:29
55 |  |  |  | DR-023-10 | Appendix D | 2025-05-07 21:29
56 |  |  |  | DR-023-11 | DG002-KEO-CM-TCR-0000049_OACEMP_rev06 | 2025-05-07 21:29
57 |  |  |  | DR-023-12 | appendix_a_diriyah_gate_development_bujairi_samhan_wh_epc | 2025-05-07 21:29
58 |  |  |  | DR-023-13 | appendix_a_diriyah_gate_development_epc | 2025-05-07 21:29
59 |  |  |  | DR-023-14 | appendix_B_current_contracts_information_08122024 | 2025-05-07 21:29
60 |  |  |  | DR-023-15 | Appendix_C_unpaved_road_chemical_treatment_08122024 | 2025-05-07 21:29
61 |  |  |  | DR-023-16 | Appendix_D_waste_signage_08032024 | 2025-05-07 21:29
62 |  |  |  | DR-023-17 | appendix_E_soil_sampling_and_analysis_procedure_08122024 | 2025-05-07 21:29
63 |  |  |  | DR-023-18 | incident_reporting_forms_investigation_08122024 | 2025-05-07 21:29
64 |  |  |  | DR-023-19 | incident_reporting_forms_notification_24-hr_08122024 | 2025-05-07 21:29
65 |  |  |  | DR-023-20 | mwan_approved_waste_licensed_parties | 2025-05-07 21:29
66 |  |  |  | DR-023-21 | ncec_approved_waste_licensed_parties | 2025-05-07 21:29
67 |  |  |  | DR-023-22 | appendix_H_legal_register_08122024 | 2025-05-07 21:29
68 |  |  |  | DR-023-23 | Appendix_I_waste_management_manifest_arabic | 2025-05-07 21:29
69 |  |  |  | DR-023-24 | Appendix_I_waste_management_manifest_english | 2025-05-07 21:29
70 |  |  |  | DR-023-25 | appendix_J_contractor's_cemp_specific_structure_08122024 | 2025-05-07 21:29
71 |  |  |  | DR-023-26 | appendix_K_CEMP_Compliance_checklist 08122024 | 2025-05-07 21:29
72 |  |  |  | DR-023-27 | appendix_L_demobilization_audit_checklist_08122024 | 2025-05-07 21:29
73 |  |  |  | DR-023-28 | appendix_M_non_conformance_report | 2025-05-07 21:29
74 |  |  |  | DR-023-29 | appendix_N_Pre_Construction-mobilization_audit_checklist_08122024 | 2025-05-07 21:29
75 |  |  |  | DR-023-30 | appendix_O_Air_Quality_Management_checklist_08032024 | 2025-05-07 21:29
76 |  |  |  | DR-023-32 | DG220-JCB-DE-TCR-000081-EIA-Rev03 | 2025-05-07 21:29
77 |  |  |  | DR-023-33 | DG220-JCB-DE-TCR-000063-02-Hydrology Study | 2025-05-07 21:29
78 |  |  |  | DR-023-34 | DG220-JCB-DE-TCR-000064-03 EPEP | 2025-05-07 21:29
79 |  |  |  | DR-023-35 | DG220-JCB-DE-TCR-000095-01_Traffic Noise Modelling Assessment | 2025-05-07 21:29
80 |  |  |  | DR-023-36 | DG220-JCB-DE-TCR-000085-03 Baseline Report | 2025-05-07 21:29
81 |  |  |  | DR-023-37 | DG220-JCB-DE-TCR-000096-02_Traffic ADM | 2025-05-07 21:29
82 |  |  |  | DR-023-38 | Visual Directory | 2025-05-07 21:29
83 |  |  |  | DR-023-39 | DG220-JCB-DE-TCR-000091-02_OCEMP | 2025-05-07 21:29
84 |  |  |  | DR-023-40 | DGII SW-MPL-008-0000-KEO-PLN-EN-000001 | 2025-05-07 21:29
85 |  |  |  | DR-023-41 | DG220-JCB-DE-TCR-000091-02_OCEMP | 2025-05-07 21:29
86 |  |  |  | DR-023-42 | 1. Environmental Permit NCEC - Wadi Safar - Arabic | 2025-05-07 21:29
87 |  |  |  | DR-023-43 | 2. Environmental Permit NCEC - Wadi Safar - Translation | 2025-05-07 21:29
88 |  |  |  | DR-023-44 | 3. Extension letter - Translated | 2025-05-07 21:29
89 |  |  |  | DR-023-45 | Volume 1 | 2025-05-07 21:29
90 |  |  |  | DR-023-46 | Volume 2 | 2025-05-07 21:29
91 |  |  |  | DR-023-47 | Appendix A - GAMEP License | 2025-05-07 21:29
92 |  |  |  | DR-023-48 | Appendix B - Legal and Statutory Requirements from General Authority of Meteorology and Environmental Protection (GAMEP) | 2025-05-07 21:29
93 |  |  |  | DR-023-49 | Appendix C - Ambient Air Quality and Noise Monitoring Report, LEAF Global, January 2020 | 2025-05-07 21:29
94 |  |  |  | DR-023-50 | Appendix D - Geotechnical Investigation Report (Extract), SAFCO, April 2020 | 2025-05-07 21:29
95 |  |  |  | DR-023-51 | Appendix E – Flood Study Report, Jacobs, August 2020 | 2025-05-07 21:29
96 |  |  |  | DR-023-52 | Appendix F – Preliminary Slope Assessment, BuroHappold, January 2020 | 2025-05-07 21:29
97 |  |  |  | DR-023-53 | Appendix G – Outline Environmental Construction Management Plan (O-CEMP) | 2025-05-07 21:29
98 |  |  |  | DR-023-54 | WS-000-000-0000-KEO-PLN-EN-000001OCEMP - Rev01 | 2025-05-07 21:29
99 |  |  |  | DR-023-55 | OG_GN_NCEC_44-8902_بشأن عدم الحاجة لتجديد التصاريح البيئية | 2025-05-07 21:29
100 |  |  |  | DR-023-56 | WS Env. Permit_200007170458 | 2025-05-07 21:29
101 |  |  |  | DR-023-57 | SW-SWD-551-0000-SET-GDL-EV-000004-Ver 01 - NTM Facility Bulletin-Revised_AK_KK_HJ (1) | 2025-05-07 21:29
102 |  |  |  | DR-023-58 | تعميم بشأن معالجة مخالفات رمي مخلفات البناء والحفريات في مدينة الرياض | 2025-05-07 21:29
103 |  |  |  | DR-023-59 | appendix_c_current_contracts_information_20230921 | 2025-05-07 21:29
104 |  |  |  | DR-023-60 | Appendix_d_unpaved_road_chemical_treatment_20230921 | 2025-05-07 21:29
105 |  |  |  | DR-023-61 | Appendix_e_waste_signage_20240330 | 2025-05-07 21:29
106 |  |  |  | DR-023-62 | appendix_f_soil_sampling_and_analysis_procedure_20230921 | 2025-05-07 21:29
107 |  |  |  | DR-023-63 | incident_reporting_forms_investigation_20230921 | 2025-05-07 21:29
108 |  |  |  | DR-023-64 | incident_reporting_forms_notification_24-hr_20230921 | 2025-05-07 21:29
109 |  |  |  | DR-023-65 | mwan_approved_waste_licensed_parties | 2025-05-07 21:29
110 |  |  |  | DR-023-66 | ncec_approved_waste_licensed_parties | 2025-05-07 21:29
111 |  |  |  | DR-023-67 | appendix_i_legal_register_20230921 | 2025-05-07 21:29
112 |  |  |  | DR-023-68 | DC Waste Manifest_Arabic | 2025-05-07 21:29
113 |  |  |  | DR-023-69 | DC Waste Manifest_English | 2025-05-07 21:29
114 |  |  |  | DR-023-70 | appendix_k_contractor's_cemp_specific_structure_20230921 | 2025-05-07 21:29
115 |  |  |  | DR-023-71 | Weekly Environment Inspection Report_Rev02 | 2025-05-07 21:29
116 |  |  |  | DR-023-72 | Pre_Mobilization_Environmental_Checklist_Rev06 Aug 24 | 2025-05-07 21:29
117 |  |  |  | DR-023-73 | DC_TEBS - Methodology Guideline_July 2024 | 2025-05-07 21:29
118 |  |  |  | DR-023-74 | Appendix_o_demobilization_audit_checklist_20230921 | 2025-05-07 21:29
119 |  |  |  | DR-023-75 | NCR - Non-Conformance Report | 2025-05-07 21:29
120 |  |  |  | DR-023-76 | Air Quality Management Checklist | 2025-05-07 21:29
121 |  |  |  | DR-023-77 | Monthly Environmental Report Rev 02 | 2025-05-07 21:29
122 |  |  |  | DR-023-78 | Quarterly CEMP Compliance Review Checklist | 2025-05-07 21:29
123 |  |  |  | DR-023-79 | KPIs and Scoring Criteria | 2025-05-07 21:29
124 |  |  |  | DR-023-80 | 1. DC_Environment Requirements_Contractors_Nov. 2023 | 2025-05-07 21:29
125 |  |  |  | DR-023-81 | 2. DC_Environment Requirements_CSC_Nov. 2023 | 2025-05-07 21:29
126 |  |  |  | DR-023-82 | 3. DC_Environment Requirements_PMC_Nov. 2023 | 2025-05-07 21:29
127 |  |  |  | DR-023-83 | DG-DSQ-000-0000-SSA-SCH-PC-000001(03) | 2025-05-07 21:29
128 |  |  |  | DR-023-84 | Oberoi Hotel CEMP | 2025-05-07 21:29
129 |  |  |  | DR-023-85 | DG-BUJ-106-0000-NSM-PLN-EN-000002 Rev.02 | 2025-05-07 21:29
130 |  |  |  | DR-023-86 | appendix_a_diriyah_gate_development_bujairi_samhan_wh_epc | 2025-05-07 21:29
131 |  |  |  | DR-023-87 | Appendix_d_unpaved_road_chemical_treatment_20230921 | 2025-05-07 21:29
132 |  |  |  | DR-023-88 | Appendix_D_waste_signage_08032024 | 2025-05-07 21:29
133 |  |  |  | DR-023-89 | appendix_g_soil_sampling_and_analysis_procedure_20230921 | 2025-05-07 21:29
134 |  |  |  | DR-023-90 | incident_reporting_forms_investigation_20230921 | 2025-05-07 21:29
135 |  |  |  | DR-023-91 | incident_reporting_forms_notification_24-hr_20230921 | 2025-05-07 21:29
136 |  |  |  | DR-023-92 | ZAB SIGNED AGREEMENT | 2025-05-07 21:29
137 |  |  |  | DR-023-93 | appendix_t_legal_register_20230921 | 2025-05-07 21:29
138 |  |  |  | DR-023-94 | Appendix_j_waste_management_manifest_arabic | 2025-05-07 21:29
139 |  |  |  | DR-023-95 | Appendix_j_waste_management_manifest_english | 2025-05-07 21:29
140 |  |  |  | DR-023-96 | appendix_l_contractor's_cemp_specific_structure_20230921 | 2025-05-07 21:29
141 |  |  |  | DR-023-97 | CEMP COMPLIANCE CHECKLIST | 2025-05-07 21:29
142 |  |  |  | DR-023-98 | appendix_M_demobilization_audit_checklist_20230921 | 2025-05-07 21:29
143 |  |  |  | DR-023-99 | appendix_N_non_conformance_report_20230921 | 2025-05-07 21:29
144 |  |  |  | DR-023-100 | appendix_N_Pre_Construction-mobilization_audit_checklist_08122024 | 2025-05-07 21:29
145 |  |  |  | DR-023-101 | Air Quality Management Checklist for Earthwork Activities - Template | 2025-05-07 21:29
146 |  |  |  | DR-023-102 | 02A. Schedule Narrative- Zallal P3 | 2025-05-07 21:29
147 |  |  |  | DR-023-103 | 02B. Baseline Schedule Zallal Package-3, Rev-04 (6-june-24) | 2025-05-07 21:29
148 |  |  |  | DR-023-104 | Overall Logistic Plan | 2025-05-07 21:29
149 |  |  |  | DR-023-105 | APPENDIX P – ENVIRONMENTAL TRAINING MATRIX | 2025-05-07 21:29
150 |  |  |  | DR-023-106 | DG-BUJ-106-0000-NSM-MTS-CE-000016 Rev.03 | 2025-05-07 21:29
151 |  |  |  | DR-023-107 | DG-BUJ-106-0000-NSM-MTS-CE-000024 Rev.02 | 2025-05-07 21:29
152 |  |  |  | DR-023-108 | DG-BUJ-106-0000-NSM-MTS-CE-000025 Rev.02 | 2025-05-07 21:29
153 |  |  |  | DR-023-109 | DG-BUJ-106-0000-NSM-MTS-CE-000026 | 2025-05-07 21:29
154 |  |  |  | DR-023-110 | DG-BUJ-106-0000-NSM-MTS-CE-000027 Rev.01 | 2025-05-07 21:29
155 |  |  |  | DR-023-111 | DG-BUJ-106-0000-NSM-ORG-AD-000001 Rev.02 | 2025-05-07 21:29
156 |  |  |  | DR-023-112 | Daily Checklist | 2025-05-07 21:29
157 |  |  |  | DR-023-113 | 1. MAINTENANCE RECORD WORK SHOP SEPTEMBER 2024 | 2025-05-07 21:29
158 |  |  |  | DR-023-114 | Spill Kits Checklist | 2025-05-07 21:29
159 |  |  |  | DR-023-115 | LIST OF CHEMICAL REPORT 322823 | 2025-05-07 21:29
160 |  |  |  | DR-023-116 | Drinking Water Checklist | 2025-05-07 21:29
161 |  |  |  | DR-023-117 | Waste Management Checklist | 2025-05-07 21:29
162 | DR-024 | Environmental Compliance Report | DevCo
163 | DR-025 | Register of Authority Engagement, Approvals and Waivers | DevCo
164 | DR-026 | Stakeholder Management Plan (including Stakeholder Management Tracker) | DevCo
165 | DR-027 | Baseline ESG Strategy and Latest Annual ESG Report | DevCo
166 | DR-028 | Construction Environmental and Social Management Plan (including Environmental Permit Register) | Project
167 | DR-029 | Construction Execution Plan | Project
168 | DR-030 | Site and Logistics Plan (including traffic simulations) | Project
169 | DR-031 | Interface Management Plan (including Stakeholder Management Plan*, Communication Plan & Contractor Staging Plan and Commissioning, Handover & Close-out Plan) | DevCo
170 | DR-032 | Workforce Planning Strategy | DevCo | DR-032 | IMS_Report-Dec'24-R2 | 2025-05-07 21:29
171 | DR-033 | Construction Progress Report (including workforce numbers) | Project
172 | DR-034 | Register of Technical Queries | Project
173 | DR-035 | Register of Shop Drawing Reviews | Project
174 | DR-036 | Register of Material & Product Approval / Product Substitution or Change Requests | Project
175 | DR-037 | Register of As-Built Drawings | Project
176 | DR-038 | Register of Material Inspection Requests | Project
177 | DR-039 | Register of Work Inspection Requests | Project
178 | DR-040 | Quality Management Manual (QMP) | DevCo
179 | DR-041 | Latest Monthly Quality Report, including defects and NCR data | DevCo
180 | DR-042 | Inspection Test Plan (ITP) | Project
181 | DR-043 | Sample of project specific Project Quality Plan (PQP) | Project
182 | DR-044 | Latest Quality Audit Report | Project
183 | DR-045 | Procurement Management Plan (including annual procurement lookahead and pre-qualified vendor database) | DevCo | DR-045-01 | DR-045a Procurement Executive Dashboard | 2025-05-07 21:29
184 |  |  |  | DR-045-02 | DR-045b-PQQ & Shortlist Process Map | 2025-05-07 21:29
185 | DR-046 | Sample of Tender Award Report | Project
186 | DR-047 | Procurement and Contracting Risk Register | DevCo
187 | DR-048 | List of Appointed Vendors (including due-diligence checks) | DevCo | DR-048-01 | PSPR Extract Appendices | 2025-05-07 21:29
188 |  |  |  | DR-048-02 | PSPR Extract | 2025-05-07 21:29
189 | DR-049 | Supply Chain Risk Assessment | DevCo | DR-049 | Portfolio Risk and Issue Register Procurement-Extract | 2025-05-07 21:29
190 | DR-050 | Current Procurement Schedule | DevCo | DR-050 | DR-050 12 Month Forecast | 2025-05-07 21:29
191 | DR-051 | Sample of Signed Agreement / Awarded Contract | Project
192 | DR-052 | Sample of Supplier and Contractor Performance Report | DevCo | DR-052-01 | Jacobs Performance | 2025-05-07 21:29
193 |  |  |  | DR-052-02 | Salini Performance | 2025-05-07 21:29
194 | DR-053 | Contract Execution Register (including Letter of Award and Letter of Commencement) | DevCo | DR-053 | LOA_Contract_New_Tracker_Extract | 2025-05-07 21:29
195 | DR-054 | Claims Register | DevCo | DR-054 | Claims Register Extract Sample | 2025-05-07 21:29
196 | DR-055 | Post Tender Clarification (PTC) Register | DevCo | DR-055-01 | DR-055a Tender Report PTC excerpt - PTC log | 2025-05-07 21:29
197 |  |  |  | DR-055-02 | DR-055b Tender Report PTC excerpt log signed | 2025-05-07 21:29
198 | DR-056 | Payment Register | DevCo | DR-056 | Payments Tracker 31.12.2024 | 2025-05-07 21:29
199 | DR-057 | HSE Management Manual | DevCo | DR-057-01 | DD-SWD-SW-SWD-000-000-DGD-MAN-HS-000001 (05)_DGCL Construction Occupational Health and Safety Manual | 2025-05-07 21:29
200 |  |  |  | DR-057-02 | DG-DSQ-000-0000-SSA-PLN-HS-000001(04) (3) Approved SSA HSE Plan | 2025-05-07 21:29
201 |  |  |  | DR-057-03 | Oberoi Hotel - HSE Management Plan - WS-WSH-685-0000-USC-PLN-HS-000001 | 2025-05-07 21:29
202 |  |  |  | DR-057-04 | DG-BUJ-106-0000-NSM-PLN-HS-000015 Rev.01 | 2025-05-07 21:29
203 |  |  |  | DR-057-05 | DG-BUJ-106-0000-NSM-PLN-HS-000019 Rev.01 | 2025-05-07 21:29
204 | DR-058 | HIRAC Methodology & Safety Risk Register | DevCo | DR-058-01 | DG-BUJ-106-0000-NSM-RPT-HS-000045 - Zallal | 2025-05-07 21:29
205 |  |  |  | DR-058-02 | DG-DSQ-000-0000-SSA-PLN-HS-000001(04) (3) Approved SSA HSE Plan | 2025-05-07 21:29
206 | DR-059 | Emergency Evacuation & Preparedness Plan | Project
207 | DR-060 | Latest Monthly HSE Report | DevCo | DR-060-01 | DG-DSQ-000-0000-SSA-RPT-HS-000001(07) | 2025-05-07 21:29
208 |  |  |  | DR-060-02 | Zallal Monthly OH&S Trend Analysis Report January 2025 | 2025-05-07 21:29
209 |  |  |  | DR-060-03 | Zallal-OHS Monthly KPIs-Jan- 2025 | 2025-05-07 21:29
210 | DR-061 | Latest HSE Audit Report | DevCo | DR-061-01 | Monthly PCI - Oberoi Hotel - April 2025 | 2025-05-07 21:29
211 |  |  |  | DR-061-02 | PCI - AGA-P3-6-7 Apr 2025 Score (signed) - DSQ | 2025-05-07 21:29
212 |  |  |  | DR-061-03 | PCI -Jan 2025 | 2025-05-07 21:29
213 |  |  |  | DR-061-04 | PCI SCAR Report Jan 2025 | 2025-05-07 21:29
214 |  |  |  | DR-061-05 | Zallal-PCI Jan 2025-Signed | 2025-05-07 21:29
215 | DR-062 | Latest Monthly Welfare Monitoring Report | DevCo | DR-062-01 | DG-DSQ-316-0000-AEC-RPT-HS-001081 (00) | 2025-05-07 21:29
216 |  |  |  | DR-062-02 | Zallal Mixed Use- Monthly Welfare Facilities and Transportation Focus Inspection - 19-10-2024 | 2025-05-07 21:29
217 | DR-063 | Latest Monthly Welfare Monitoring Report | DevCo | DR-062-03 | Camp Inspection Report-Oberoi Hotel -April 2025 | 2025-05-07 21:29
218 | DR-064 | Latest Monthly Welfare Monitoring Report | DevCo | DR-062-04 | Focus Inspection Checklist - Drinking & Ablution Water-12022025 | 2025-05-07 21:29
219 | DR-065 | Latest Monthly Welfare Monitoring Report | DevCo | DR-062-05 | Welfare Focused Inspection - Oberoi Hotel - April 2025 | 2025-05-07 21:29
220 | DR-063 | Welfare Management Manual (including Vendor Management & Monitoring Program) | DevCo | DR-063-01 | 04- Contractors Workers’ Quality of Life and Accommodations Procedures- 2024 - DSQ | 2025-05-07 21:29
221 |  |  |  | DR-063-02 | DG-BUJ-106-0000-NSM-PLN-HS-000021 Rev.02 - Zallal | 2025-05-07 21:29
222 | DR-064 | Latest Welfare Audit Report | DevCo | DR-064-01 | Accommodation Camp Audit Inspection Report-14 Oct 2024 - Zallal | 2025-05-07 21:29
223 |  |  |  | DR-064-02 | Alpha - Accommodation Camp Audit Inspection Report April 2025 | 2025-05-07 21:29
224 |  |  |  | DR-064-03 | Azzam - Accommodation Camp Audit Inspection Report April 2025 | 2025-05-07 21:29
225 |  |  |  | DR-064-04 | Salboukh - Accommodation Camp Audit Inspection Report April 2025 | 2025-05-07 21:29
226 |  |  |  | DR-064-05 | Camp Inspection Report-Oberoi Hotel -April 2025 | 2025-05-07 21:29
227 |  |  |  | DR-064-06 | Focus Inspection Checklist - Drinking & Ablution Water-12022025 | 2025-05-07 21:29
228 | DR-065 | Quarterly/annual progress reports for preceding three years (including approved budget, contingency utilization and change requests / claims) | DevCo | DR-065 | Cost Data Template_Diriyah (Dec24) | 2025-05-07 21:29
229 | DR-066 | Provisional Sums Status | DevCo
230 | DR-067 | Innovation Strategy | DevCo | DR-067-01 | 250430_DevCo's innovation strategic approach_vs | 2025-05-07 21:29
231 | DR-068 | Smart City Strategy | DevCo | DR-068 | Smart Diriyah overarching strategy (Executive summary) v2 | 2025-05-07 21:29
232 | DR-069 | Innovation/ smart city impact assessment Report | DevCo
233 | DR-070 | Sample of final master plan showing innovation/ Smart city considerations | Project
234 | DR-071 | Register of Innovation & Technology pilots and R&D projects along with progress tracker | DevCo
235 | DR-072 | Technical functions' strategy and initiatives | DevCo | DR-072-01 | 20250318_Business plan BoD deck_vDevco.pdf | 2025-05-07 21:29
236 |  |  |  | DR-072-02 | 241027_DevCo_onboarding_v35 (without video) | 2025-05-07 21:29
237 |  |  |  | DR-072-03 | DevCo development capacity_v29 (for PIF) | 2025-05-07 21:29
238 | DR-073 | Latest report which includes the progress of technical strategy initiatives | DevCo | DR-073 | 250503_Portfolio wide projects | 2025-05-07 21:29
239 | DR-074 | List of technical functions’ KPIs (including baseline and targets) | DevCo | DR-074 | Performance Management Handbook v37.1 | 2025-05-07 21:29
240 | DR-075 | Latest report which includes the progress of achievement of technical functions’ KPIs | DevCo | DR-075 | E-Annual plan components and details v1 | 2025-05-07 21:29
241 | DR-076 | Approved and as-is org structure, including staffed/unstaffed positions, roles & responsibilities | DevCo | DR-076-01 | Busness Development | 2025-05-07 21:29
242 |  |  |  | DR-076-02 | Commercial Leasing | 2025-05-07 21:29
243 |  |  |  | DR-076-03 | Commercial | 2025-05-07 21:29
244 |  |  |  | DR-076-04 | Design | 2025-05-07 21:29
245 |  |  |  | DR-076-05 | DevCo Organization Chart | 2025-05-07 21:29
246 |  |  |  | DR-076-06 | Development DG1 | 2025-05-07 21:29
247 |  |  |  | DR-076-07 | Development DG2 | 2025-05-07 21:29
248 |  |  |  | DR-076-08 | Development WS | 2025-05-07 21:29
249 |  |  |  | DR-076-09 | Materplanning | 2025-05-07 21:29
250 |  |  |  | DR-076-10 | OHSS Str 29.4.25 | 2025-05-07 21:29
251 |  |  |  | DR-076-11 | Projects | 2025-05-07 21:29
252 |  |  |  | DR-076-12 | Retail Leasing | 2025-05-07 21:29
253 |  |  |  | DR-076-13 | Sales | 2025-05-07 21:29
254 | DR-077 | Strategic DevCo technical workforce planning report, including capacity and competency planning | DevCo | DR-077 | DevCo Workforce | 2025-05-07 21:29
255 | DR-078 | Register of Approved technical-related policies and procedures | DevCo
256 | DR-079 | Register of technical platforms | DevCo
Go to P&M
Go to D&T
Go to D&C
Go to CE&O
Go to I&T
Go to S&O
Go to Main Page
Refresh
Add Document
Delete Document

## DevCoAssessmentInput(P&M)
PIF Project Lighthouse
DevCoAssessmentInput(P&M)
Assessment Criteria | Data Point | Input Value | Data Source | Assessor Remarks | Assessment Time Stamp | Reviewer Remarks | Review Time Stamp | Formula
DevCo Schedule Performance Index (SPI) | Planned Value (PV) | 500000000 | [5 empty] | Earned Value (EV) / Planned Value (PV)
| Earned Value (EV) | 450000000
% milestone achievement in accordance with the approved business plan | No. of planned milestones | 20 | [5 empty] | No. of milestones achieved on time/ No. of planned milestones
| No. of milestones achieved on time | 14
% of projects with approved change requests in design phase since inception with time impact of more than 1 month | Total number of projects in design phase | 9 | [5 empty] | Number of projects with approved change requests in design phase since inception with time impact of more than 1 month / Total number of projects in design phase
| Number of projects with approved change requests in design phase since inception with time impact of more than 1 month | 2
% of projects with approved change requests in construction phase since inception with time impact of more than 4 months | Total number of projects in construction phase | 11 | [5 empty] | Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months / Total number of projects in construction phase
| Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months | 6
% of projects with approved schedule extension | No. of Approved EOTs | 25 | [5 empty] | (Number of Projects with Approved Schedule Extension)/Total Number of Projects)
| No. of projects with schedule extension (design stage) | 4
| No. of projects with schedule extension (construction stage) | 9
% of projects with Forecast completion date beyond the latest approved schedule | Number of projects with forecast completion date beyond the latest approved schedule | 3 | [5 empty] | Number of projects with forecast completion date beyond the latest approved schedule / [No. of projects with schedule extension (design stage) + No. of projects with schedule extension (construction stage)]
Is the Forecast Finish Date at a given data date based on the alignment and buy-in from project teams and other listed stakeholders? | Total list of stakeholders and their commitment to the forecast finish date | Yes | [5 empty] | "Satisfactory Score" if key project stakeholders (engineering, procurement, construction, client teams) were formally briefed, discussed on the forecast date includ any foreseen risks but no formal sign off doc on the forecast finish date is available
Based on the risks identified and approved change requests, has the DevCo conducted a sensitivity assessment on the forecast completion at a given data date? | Identified risks with probability and impact ratings and Historical Project Performance (SPI, past variances, Productivity Trends) | Yes, but inadequate | [5 empty] | "Satisfactory" if new activities as per the risks identified and discussions with stakeholders are added in the revised programme but do not have logical relationships and there is no comparison of the critical path analysis before and after date change
Has DevCo allocated risk contingency for the identified risks? | Risk severity and Risk mapping | Yes | [5 empty] | Satisfactory Score if - Contingency allocated but not aligning with the risk severity as per the heat map
Was there any deferment in the project completion date due to unidentified risks? | Source of the unidentified risk | Yes, but less than 1 month | [5 empty] | Satisfactory Score if - the deferment was less than 1 month
Was there any Cost Overrun because of identified risk? | % of cost overrun from the latest approved budget due to identified risk | No | [5 empty] | Satisfactory Score if - the cost overrun was less than 5%
Was there any Cost Overrun because of unidentified risk? | % of cost overrun from the latest approved budget due to unidentified risk | Yes, but less than 1% | [5 empty] | Satisfactory Score if - the cost overrun was less than 1%
Risk Control Rate of the identified risks at DevCo Level | Number of controlled risks | 65 | [5 empty] | Number of Controlled Risks / Total number of identified risks
| Total number of identified risks | 80
Is the DevCo fully compliant with Risk Management Plan requirements? | Risk Manager or Risk Committee overseeing risk governance | No | [5 empty] | Satisfactory Score if - the risks were identified, mitigations planned but not communicated to all the relevant stakeholders. And the risk register is updated
Is there a difference in the time impact forecast before and after the risk event has triggered? | Difference between anticipated and actual effects on time and cost, after the risk event triggered | Yes, but less than 2 weeks | [5 empty] | Satisfactory Score if - the time impact is less than 2 weeks for Design phase completion and less than 1 month of Construction Phase Completion
Is there a difference in the Cost impact forecast before and after the risk event has triggered? | Reasons on the difference between anticipated and actual effects on time and cost | Yes, but less than 0.5% | [5 empty] | Satisfactory Score if - the cost impact is less than 0.5% of the identified risk costing
Go to Main Page
Refresh
Go to Document
Go to Analysis

## DevCoAssessmentAnalysis(P&M)
PIF Project Lighthouse
DevCoAssessmentAnalysis(P&M)
Assessment Criteria | Data Point | Value | Rating | Score | Assessment Criteria Weightage | Assessment Guideline/Formula | Good | Satisfactory | Needs Improvement | Remarks 1 | Performance Signal | Performance Signal Score | Performance Signals Weightage | Remarks 2 | Key Topic | Key Topic Score | Remarks 3
DevCo Schedule Performance Index (SPI) | Planned Value (PV) | 0.9 | Satisfactory | 2 | 70% | Earned Value (EV) / Planned Value (PV) | >1 | 0.85-1 | <0.85 |  | Schedule Adherence | 2 | 50% |  | Overall Progress | 2.1 | Key milestones are on track, with some delivered ahead of schedule. There are delays expected of ongoing projects due to complexities related to infrastructure
Earned Value (EV)
% milestone achievement in accordance with the approved business plan | No. of planned milestones | 70% | Satisfactory | 2 | 30% | No. of milestones achieved on time/ No. of planned milestones | >70% | 50-70% | <50%
No. of milestones achieved on time
% of projects with approved change requests in design phase since inception with time impact of more than 1 month | Total number of projects in design phase | 22.22% | Good | 3 | 40% | Number of projects with approved change requests in design phase since inception with time impact of more than 1 month / Total number of projects in design phase | <30% | 30-70% | >70% |  | Schedule Extension | 2.2 | 30%
Number of projects with approved change requests in design phase since inception with time impact of more than 1 month
% of projects with approved change requests in construction phase since inception with time impact of more than 4 months | Total number of projects in construction phase | 54.55% | Satisfactory | 2 | 40% | Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months / Total number of projects in construction phase | <30% | 30-70% | >70%
Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months
% of projects with approved schedule extension | No. of Approved EOTs | 65% | Needs Improvement | 1 | 20% | (Number of Projects with Approved Schedule Extension)/Total Number of Projects) | <20% | 20-40% | >40%
No. of projects with schedule extension (design stage)
No. of projects with schedule extension (construction stage)
% of projects with Forecast completion date beyond the latest approved schedule | Number of projects with forecast completion date beyond the latest approved schedule | 23.08% | Satisfactory | 2 | 60% | Number of projects with forecast completion date beyond the latest approved schedule / [No. of projects with schedule extension (design stage) + No. of projects with schedule extension (construction stage)] | <20% | 20-40% | >40% |  | Schedule Achievability | 2.2 | 20%
Is the Forecast Finish Date at a given data date based on the alignment and buy-in from project teams and other listed stakeholders? | Total list of stakeholders and their commitment to the forecast finish date | Yes | Good | 3 | 20% | "Satisfactory Score" if key project stakeholders (engineering, procurement, construction, client teams) were formally briefed, discussed on the forecast date includ any foreseen risks but no formal sign off doc on the forecast finish date is available | Yes | Yes, but inadequate | No
Based on the risks identified and approved change requests, has the DevCo conducted a sensitivity assessment on the forecast completion at a given data date? | Identified risks with probability and impact ratings and Historical Project Performance (SPI, past variances, Productivity Trends) | Yes, but inadequate | Satisfactory | 2 | 20% | "Satisfactory" if new activities as per the risks identified and discussions with stakeholders are added in the revised programme but do not have logical relationships and there is no comparison of the critical path analysis before and after date change | Yes | Yes, but inadequate | No
Has DevCo allocated risk contingency for the identified risks? | Risk severity and Risk mapping | Yes | Good | 3 | 20% | Satisfactory Score if - Contingency allocated but not aligning with the risk severity as per the heat map | Yes | Yes, but inadequate | No |  | Risk Governance | 2.5 | 60% |  | Risk Performance | 2.38 | Key risks include a mix of internal and external risks. Key external risks relate to material supply and logistics. Proactive actions have been taken to mitigate these risks. However, there has been an impact on the project delivery.
Was there any deferment in the project completion date due to unidentified risks? | Source of the unidentified risk | Yes, but less than 1 month | Satisfactory | 2 | 30% | Satisfactory Score if - the deferment was less than 1 month | No | Yes, but less than 1 month | Yes
Was there any Cost Overrun because of identified risk? | % of cost overrun from the latest approved budget due to identified risk | No | Good | 3 | 30% | Satisfactory Score if - the cost overrun was less than 5% | No | Yes, but less than 5% | Yes
Was there any Cost Overrun because of unidentified risk? | % of cost overrun from the latest approved budget due to unidentified risk | Yes, but less than 1% | Satisfactory | 2 | 20% | Satisfactory Score if - the cost overrun was less than 1% | No | Yes, but less than 1% | Yes
Risk Control Rate of the identified risks at DevCo Level | Number of controlled risks | 81.25% | Good | 3 | 40% | Number of Controlled Risks / Total number of identified risks | >70% | 40-70% | <40% |  | Realized Risk Status | 2.2 | 40%
Total number of identified risks
Is the DevCo fully compliant with Risk Management Plan requirements? | Risk Manager or Risk Committee overseeing risk governance | No | Needs Improvement | 1 | 20% | Satisfactory Score if - the risks were identified, mitigations planned but not communicated to all the relevant stakeholders. And the risk register is updated | Yes | Yes, but inadequate | No
Is there a difference in the time impact forecast before and after the risk event has triggered? | Difference between anticipated and actual effects on time and cost, after the risk event triggered | Yes, but less than 2 weeks | Satisfactory | 2 | 20% | Satisfactory Score if - the time impact is less than 2 weeks for Design phase completion and less than 1 month of Construction Phase Completion | No | Yes, but less than 2 weeks | Yes
Is there a difference in the Cost impact forecast before and after the risk event has triggered? | Reasons on the difference between anticipated and actual effects on time and cost | Yes, but less than 0.5% | Satisfactory | 2 | 20% | Satisfactory Score if - the cost impact is less than 0.5% of the identified risk costing | No | Yes, but less than 0.5% | Yes
Go to Main Page
Refresh
Go to Document
Go to Input

## InterviewQuestion(P&M)
PIF Project Lighthouse
InterviewQuestion(P&M)
SN | Question | Date of Interview | Response | Internal Comment | Follow Up Question
1 | In case the project is behind schedule, is there a recovery program to address the delay? | 2025-05-09 16:05
2 | What factors led to approve the change(s) in the completion date (design/construction/stakeholder approvals)? | 2025-05-09 16:05
3 | Using a sample project, please show how an in-depth analysis was conducted to ensure how realistic the remaining duration of the project planned/ forecasted was, critical path defined, considering resource availability, project constraints, and risk factors in order to avoid likelihood of schedule slippages & cost overruns. | 2025-05-09 16:05
4 | Did the approved schedule consider the risks identified during the Risk Assessment stage? | 2025-05-09 18:10
5 | What percentage of projects have an approved risk register? | 2025-05-09 16:05
6 | What percentage of risk associated costs is a part of total budget? | 2025-05-09 16:05
7 | After the risk event triggered, was there a difference between the anticipated and actual effects on time and cost? If so, what were the reasons and what is the plan to reduce the further overrun. | 2025-05-09 16:05
Go to Main Page
Refresh

## AddDataPoint(P&M)
PIF Project Lighthouse
AddDataPoint(P&M) |  |  |  |  | Schedule Chart |  |  |  | Top 10 Risks | [5 empty] | Top 5 Risk Categories |  | Project Overview
SN | Criteria | Additional Data Point | Value | Scorecard Visualization | Year | Value Completed (Baseline) in M SAR | Value Completed (Actual) in M SAR | Value Completed (Forecast) in M SAR | Risk | Source | Potential Impact | Risk Rating | Risk Status | Current Measures | Risk Category | Number of Risk Items | ProjectID | ForecastCompletionYear | ProjectType | ProjectStage | Criticality | DelayInSchedule | CostOverrun | Priority | ProjectValue
1 |  | Latest Approved Completion Date​ | Q2-28 | Visualized with no score | 2025 | 0 |  |  | Risk 1 | Contractor | Cost | High | Open | Measure 02 | Risk 1 | 19 | Project A | Completed | Residential | Design | Priority | Yes | No | Yes | 1.5
2 |  | Forecast Completion Date​ | Q1-29 | Visualized with Score | 2026 | 1250 | 1250 |  | Risk 2 | Source A | Impact O | Med | Ongoing | Measure 01 | Risk 2 | 16 | Project B | 2027 | Commercial | Construction | Standard | No | Yes | No | 1
3 |  | Approved baseline completion date | Q3-27 | Visualized with no score | 2027 | 2000 | 1550 | 1550 | Risk 3 | Source B | Impact P | High | Open | Measure 04 | Risk 3 | 12 | Project C | Completed | Mixed Use | Initiation | Priority | No | No | No | 2
4 |  | No. of schedule iterations | 8 | Raw Data for Indicator | 2028 | 3100 |  | 2200 | Risk 4 | Source F | Impact T | Med | Closed | Measure 05 | Risk 4 | 7 | Project D | 2030 | Residential | Construction | Standard | Yes | Yes | Yes | 1.5
5 |  | Planned duration up to a specific phase as per approved Baseline programme | 120 | Raw Data for Indicator | 2029 |  |  | 3100 | Risk 5 | PMC | Reputation | Low | Ongoing | Measure 06 | Risk 5 | 5 | Project E | 2028 | Hospitality | Design | Priority | No | No | No | 3
6 |  | Duration taken to complete works up to the specific phase | 145 | Raw Data for Indicator |  |  |  |  | Risk 6 | Source C | Impact Q | Med | Open | Measure 07
7 |  | Recovery Plan | Needs Improvement | Visualized with Score |  |  |  |  | Risk 7 | Source D | Impact R | Low | Closed | Measure 08
8 |  | Extent of all EOT (design stage) | 3 | Visualized with Score |  |  |  |  | Risk 8 | Supplier | Time | High | Closed | Measure 09
9 |  | Extent of all EOT (const. stage) | 6 | Visualized with Score |  |  |  |  | Risk 9 | CAA | Impact M | High | Closed | Measure 10
10 |  | No. of unresolved issues | 7 | Visualized with Score |  |  |  |  | Risk 10 | Source E | Impact S | Med | Ongoing | Measure 11
11 |  | No. of (Open) Inherent Risks | 15 | Visualized with Score
12 |  | No. of (Closed) Residual Risks | 35 | Visualized with Score
13 |  | Project-level risks (including low, medium, and high severity) | 65 | Visualized with Score
14 |  | Procedures for risk management | Satisfactory | Visualized with Score
15 |  | Risks identified and corresponding impact on schedule | NIL | Visualized with No Score
16 |  | Extra Cost due to Unresolved Issues | 1700000 | Visualized with Score
Go to Main Page
Refresh

## DevCoAssessmentInput(D&T)
PIF Project Lighthouse
DevCoAssessmentInput(D&T)
Assessment Criteria | Data Point | Input Value | Data Source | Assessor Remarks | Assessment Time Stamp | Reviewer Remarks | Review Time Stamp | Formula
Similarity between Original/Approved and Latest CGI and Animation | Percentage similarity between Approved CGI and Latest CGI at same angle and scale | 0.2 | [5 empty] | (Percentage similarity between Approved CGI and Latest CGI at same angle and scale) + (Percentage similarity between Approved Animation and Latest Animation at same camera angle) / 2
| Percentage similarity between Approved Animation and Latest Animation at same camera angle | 0.6
Does the Latest Material Palette & Finish Schedule support the look of the Approved CGI? | Material Palette & Finish Schedule | Yes | [5 empty] | Material Palette & Finish Schedule matched Approved CGI
Does the DevCo have Design & Technical Guidelines (including Look & Feel Design Guidelines)? | Design and Technical Guidelines | Yes | [5 empty] | The Design and Technical Guidelines exist
Do DevCo projects comply with DDTG? | Look & Feel Guideline | No | [5 empty] | Material Palette & Finish Schedule aligns with Look & Feel Guideline
% variance from approved Built-Up Area (BUA) | Latest BUA | 16 | [5 empty] | (Latest BUA - Approved BUA) / Approved BUA
| Approved BUA | 14
% variance in land use permit area | Latest Land Area | 2.5 | [5 empty] | (Latest Land Area - Approved Land Area) / Approved Land Area
| Approved Land Area | 2.4
% variance from approved population | Latest Population | 1000 | [5 empty] | (Latest Population - Approved Population) / Approved Population
| Approved Population | 950
% value of modularization compared to the total construction value | Value of Modularized Construction Cost | 0.01 | [5 empty] | Modularized Construction Cost / Total Construction Cost
| Value of Total Construction Cost | 0.03
Have all projects completed a Constructability Report/Document? | Date and Revision of Constructability Report | Yes | [5 empty] | Constructability Report exists
Was design for Enabling Work Package considerd as part of the design process to ensure the readiness of the site for the main construction work? | Assessment of enabling works required | Yes | [5 empty] | Consideration of design for enabling work package
Are documentation packages meeting the LOD requirements of the latest Design Stage Gate? | LOD Required | Yes | [5 empty] | LOD Documented matches LOD Required
| LOD Documented (drawing sample from Design Report) | Yes
Have all projects adopted digital delivery using BIM and/or GIS? | % of projects adopting digital delivery using BIM/GIS | Yes | [5 empty] | BIM Documentation exists
Is project delivery occurring in accordance with the latest approved design strategy? | Date of Latest Approved Design Strategy | Yes | [5 empty] | Review Latest Approved Design Strategy and compare with the Stage Gate Design Report
% of projects with completed technical design/peer reviews and verifications/certifications as required for the latest Design Stage Gate | Number of projects with completed design reviews and verification register | 0.1 | [5 empty] | Check the Design Review & Verification Register, assess if correct number of Design Reviews have occurred in accordance with the Design Management Report
% of Corrective Actions closed | Total Corrective Actions | 40 | [5 empty] | Closed Corrective Actions / Total Corrective Actions
| Number of Closed Corrective Actions | 34
Average Cycle time to close corrective actions | Days taken to Close Corrective Actions | 14 | [5 empty] | Average number of days between Date Corrective Action is recorded in the Corrective Action Register and the Date Corrective Action is Closed
Is the average cycle time to complete reviews and certifications in accordance with the Design Management Report? | Days taken to complete Design Reviews | Yes | [5 empty] | Average number of days between Design Review Submittals and Completion of the Design Reviews compared to the number of days required to complete the Design Reviews in accordance with the Design Management Report
Has the DevCo engaged independent certification of major critical elements? | Level of review and verification required for Stage Gate | Yes | [5 empty] | Independent Certification exists
Are all project designs integrated with Regional Infrastructure & Mobility Plans? | Regional Strategies | No | [5 empty] | The Infrastructure and Engineering Report references the Regional Infrastructure & Mobility Plans and demonstrates adoption of Regional Strategies
Do all projects comply with environmental guidelines in accordance with ESIA? | Extent of compliance to environmental guidelines | Yes | [5 empty] | Key Environmental Risks and Site Environmental Factors are covered in the Environmental Compliance Report
% of projects with Code Compliance Violations | Total Number of Code Compliance Violations | 0.15 | [5 empty] | Total Number of Code Compliance Violations taken from the Code Compliance Assessment Report
% of approved deviation waivers against compliant codes & standards | Total Waiver Applications Submitted | 21 | [5 empty] | Total Waivers Approved / Total Waiver Applications Submitted
| Total Waivers Approved | 22
Have all required Stakeholder Submittals been issued? | Stakeholder Submittal Date | Yes | [5 empty] | Stakeholder Submittal Dates are in accordance with the Stakeholder Management Plan to ensure approvals can be achieved in line with Stage Gate completion requirements
% of time critical Stakeholder Approvals Pending impacting Design Stage Gate completion | Number of Stakeholder Approvals Pending | 0.2 | [5 empty] | Number of Stakeholder approvals pending / Total number of stakeholder approvals required
| Total number of stakeholder approvals required | 0.63
Does the Stakeholder Engagement Plan include proactive communication process to ensure timley coordination and approvals? | Scheduled Design Stage Gate Completion | Yes | [5 empty] | Proactive communication in Stakeholder Engagement Plan
% of Stakeholder Comments Closed | Total Stakeholder Comments | 21 | [5 empty] | Stakeholder Comments Closed / Total Stakeholder Comments
| Stakeholder Comments Closed | 4
% of projects achieving DevCo ESG Targets | Planned ESG Target | 1 | [5 empty] | Actual ESG Target / Planned ESG Target
| Actual ESG Target | 0
Does the DevCo ESG Target align with globally recognized Best Practice Targets? | Alignment with globally recognized Best Practice Targets | No | [5 empty] | Alignment with globally recognized Best Practice Targets
Go to Main Page
Refresh
Go to Document
Go to Analysis

## DevCoAssessmentAnalysis(D&T)
PIF Project Lighthouse
DevCoAssessmentAnalysis(D&T)
Assessment Criteria | Data Point | Value | Rating | Score | Assessment Criteria Weightage | Assessment Guideline /Formula | Good | Satisfactory | Needs Improvement | Remarks 1 | Performance Signal | Performance Signal Score | Performance Signals Weightage | Remarks 2 | Key Topic | Key Topic Score | Remarks 3
Similarity between Original/Approved and Latest CGI and Animation | Percentage similarity between Approved CGI and Latest CGI at same angle and scale | 40% | Needs Improvement | 1 | 30% | (Percentage similarity between Approved CGI and Latest CGI at same angle and scale) + (Percentage similarity between Approved Animation and Latest Animation at same camera angle) / 2 | >70% | 50-70% | <50% |  | CGI and Animation Compliance | 2.4 | 50% | Projects are generally aligned with vision and strategic goals | Vision Adherence | 2.7 | DevCo has maintained adherence to the Vision, with a few outstanding variance approvals pending. The DevCo has demonstrated poor consideration for construction methodology simplification during the design phase, however, is demonstrating effective use of BIM software for interdisciplinary coordination across most projects.
Percentage similarity between Approved Animation and Latest Animation at same camera angle
Does the Latest Material Palette & Finish Schedule support the look of the Approved CGI? | Material Palette & Finish Schedule | Yes | Good | 3 | 20% | Material Palette & Finish Schedule matched Approved CGI | >70% | 50-70% | <50%
Does the DevCo have Design & Technical Guidelines (including Look & Feel Design Guidelines)? | Design and Technical Guidelines | Yes | Good | 3 | 20% | The Design and Technical Guidelines exist | Yes |  | No
Do DevCo projects comply with DDTG? | Look & Feel Guideline | No | Good | 3 | 30% | Material Palette & Finish Schedule aligns with Look & Feel Guideline | >70% | 50-70% | <50%
% variance from approved Built-Up Area (BUA) | Latest BUA | 14.29% | Good | 3 | 30% | (Latest BUA - Approved BUA) / Approved BUA | <15% | 15-30% | >30% |  | Development Program Variance | 3 | 50% | Variance in development program are justified and acceptable
Approved BUA
% variance in land use permit area | Latest Land Area | 4.167% | Good | 3 | 30% | (Latest Land Area - Approved Land Area) / Approved Land Area | <15% | 15-30% | >30%
Approved Land Area
% variance from approved population | Latest Population | 5.263% | Good | 3 | 40% | (Latest Population - Approved Population) / Approved Population | <30% | 30-40% | >40%
Approved Population
% value of modularization compared to the total construction value | Value of Modularized Construction Cost | 33.33% | Satisfactory | 2 | 20% | Modularized Construction Cost / Total Construction Cost | >40% | 20-40% | <20% |  | Construction Design Maturity | 2.8 | 100% | Strong adherence to processes during design phases to ensure designs can be constructed feasibly. | Design for Constructability | 2.8
Value of Total Construction Cost
Have all projects completed a Constructability Report/Document? | Date and Revision of Constructability Report | Yes | Good | 3 | 20% | Constructability Report exists | Yes |  | No
Was design for Enabling Work Package considerd as part of the design process to ensure the readiness of the site for the main construction work? | Assessment of enabling works required | Yes | Good | 3 | 20% | Consideration of design for enabling work package | Yes |  | No
Are documentation packages meeting the LOD requirements of the latest Design Stage Gate? | LOD Required | Yes | Good | 3 | 20% | LOD Documented matches LOD Required | Yes |  | No
LOD Documented (drawing sample from Design Report)
Have all projects adopted digital delivery using BIM and/or GIS? | % of projects adopting digital delivery using BIM/GIS | Yes | Good | 3 | 20% | BIM Documentation exists | Yes |  | No
Is project delivery occurring in accordance with the latest approved design strategy? | Date of Latest Approved Design Strategy | Yes | Good | 3 | 10% | Review Latest Approved Design Strategy and compare with the Stage Gate Design Report | Yes |  | No |  | Design Management Maturity | 2.6 | 100% | Robust processes with peer reviews of design and prompt closure of corrective actions | Design Management | 2.6
% of projects with completed technical design/peer reviews and verifications/certifications as required for the latest Design Stage Gate | Number of projects with completed design reviews and verification register | 10% | Needs Improvement | 1 | 20% | Check the Design Review & Verification Register, assess if correct number of Design Reviews have occurred in accordance with the Design Management Report | >70% | 50-70% | <50%
% of Corrective Actions closed | Total Corrective Actions | 85% | Good | 3 | 20% | Closed Corrective Actions / Total Corrective Actions | >70% | 40-70% | <40%
Number of Closed Corrective Actions
Average Cycle time to close corrective actions | Days taken to Close Corrective Actions | 14 | Satisfactory | 2 |  | Average number of days between Date Corrective Action is recorded in the Corrective Action Register and the Date Corrective Action is Closed | <14days | 14-30days | >30days
Is the average cycle time to complete reviews and certifications in accordance with the Design Management Report? | Days taken to complete Design Reviews | Yes | Good | 3 | 20% | Average number of days between Design Review Submittals and Completion of the Design Reviews compared to the number of days required to complete the Design Reviews in accordance with the Design Management Report | Yes |  | No
Has the DevCo engaged independent certification of major critical elements? | Level of review and verification required for Stage Gate | Yes | Good | 3 | 30% | Independent Certification exists | Yes |  | No
Are all project designs integrated with Regional Infrastructure & Mobility Plans? | Regional Strategies | No | Needs Improvement | 1 | 50% | The Infrastructure and Engineering Report references the Regional Infrastructure & Mobility Plans and demonstrates adoption of Regional Strategies | Yes |  | No |  | Environmental Compliance Status | 2 | 40% |  | Regulatory Compliance | 2.12
Do all projects comply with environmental guidelines in accordance with ESIA? | Extent of compliance to environmental guidelines | Yes | Good | 3 | 50% | Key Environmental Risks and Site Environmental Factors are covered in the Environmental Compliance Report | Yes |  | No
% of projects with Code Compliance Violations | Total Number of Code Compliance Violations | 15% | Satisfactory | 2 | 20% | Total Number of Code Compliance Violations taken from the Code Compliance Assessment Report | <10% | 10-30% | >30% |  | Authority Compliance Status | 2.2 | 60%
% of approved deviation waivers against compliant codes & standards | Total Waiver Applications Submitted | 104.8% | Good | 3 | 20% | Total Waivers Approved / Total Waiver Applications Submitted | >70% | 50-70% | <50%
Total Waivers Approved
Have all required Stakeholder Submittals been issued? | Stakeholder Submittal Date | Yes | Good | 3 | 15% | Stakeholder Submittal Dates are in accordance with the Stakeholder Management Plan to ensure approvals can be achieved in line with Stage Gate completion requirements | Yes |  | No
% of time critical Stakeholder Approvals Pending impacting Design Stage Gate completion | Number of Stakeholder Approvals Pending | 31.75% | Needs Improvement | 1 | 15% | Number of Stakeholder approvals pending / Total number of stakeholder approvals required | <20% | 20-30% | >30%
Total number of stakeholder approvals required
Does the Stakeholder Engagement Plan include proactive communication process to ensure timley coordination and approvals? | Scheduled Design Stage Gate Completion | Yes | Good | 3 | 15% | Proactive communication in Stakeholder Engagement Plan | Yes |  | No
% of Stakeholder Comments Closed | Total Stakeholder Comments | 19.05% | Needs Improvement | 1 | 15% | Stakeholder Comments Closed / Total Stakeholder Comments | >70% | 50-70% | <50%
Stakeholder Comments Closed
% of projects achieving DevCo ESG Targets | Planned ESG Target | 0% | Needs Improvement | 1 | 100% | Actual ESG Target / Planned ESG Target | >70% | 50-70% | <50% |  | DevCo ESG Target Achievement | 1 | 80% | No DevCo-level ESG targets have been set | ESG Target Realization | 1
Actual ESG Target
Does the DevCo ESG Target align with globally recognized Best Practice Targets? | Alignment with globally recognized Best Practice Targets | No | Needs Improvement | 1 | 100% | Alignment with globally recognized Best Practice Targets | Yes |  | No |  | Global ESG Target Alignment | 1 | 20% | No DevCo-level ESG targets have been set
Go to Main Page
Refresh
Go to Document
Go to Input

## InterviewQuestion(D&T)
PIF Project Lighthouse
InterviewQuestion(D&T)
SN | Question | Date of Interview | Response | Internal Comment | Follow Up Question
1 | How was the supply chain assessment done for materials & finishes required to achieve the Vision at point of incorporation? | 2025-05-09 16:05
2 | What were the reasons for any changes from original approved designs to latest design, and at which stage were these changes approved? | 2025-05-09 16:05
3 | Have the project designs aligned with DevCo Design & Technical Guidelines? Have there been any challenges adhering to the Vision? Provide an example how this has been resolved. | 2025-05-09 16:05
4 | Has the variance to the Development Program been submitted for approval? | 2025-05-09 16:05
5 | What were the reasons for the variance between the current business plan and latest development program? Were these submitted for approval? | 2025-05-09 16:05
6 | What is the impact, if any, on the business plan with these changes? Are there mitigation measures in place? | 2025-05-09 16:05
7 | Are there any outstanding FB directions and resolutions relating to design and development program? If so, please provide. | 2025-05-09 16:05
8 | Was the Vision assessed for construction viability at point of incorporation? | 2025-05-09 16:05
9 | How was designing for constructability incorporated in the design process? | 2025-05-09 16:05
10 | Have enabling works been considered to ensure the site is ready for development? | 2025-05-09 16:05
11 | Do all projects adopt digital delivery using BIM/GIS? If not, how are they managing coordination? | 2025-05-09 16:05
12 | What challenges has the DevCo faced in achieving the Design Strategy, how have these been overcome and has the PEP been updated and approved to reflect the changes. Provide example | 2025-05-09 16:05
13 | Has the DevCo had any difficulty engaging independent/peer design reviews for critical design packages. What method is used for design verification & certification? | 2025-05-09 16:05
14 | How has the design accommodated the regional guidelines and requirements (e.g. infrastructure, mobility, environment)? | 2025-05-09 16:05
15 | What are the environmental risks identified and how have they been mitigated? | 2025-05-09 16:05
16 | Are there any deviations from KSA or local codes and guidelines, justified by international/industry best practices? | 2025-05-09 16:05
17 | Has engagement commenced with all required stakeholders and what is the rate of closure of conditions and requirements? | 2025-05-09 16:05
18 | What are the challenges in meeting the targets? | 2025-05-09 16:05
Go to Main Page
Refresh

## AddDataPoint(D&T)
PIF Project Lighthouse
AddDataPoint(D&T)
SN | Criteria | Additional Data Point | Value | Scorecard Visualization
1 |  | Date & Revision of Construction Management Plan | 31 July 2025 | Raw Data for Indicator
2 |  | Date & Revision of Notional Construction Sequencing Drawing | 27 May 2025 | Raw Data for Indicator
3 |  | Key Environmental Risks
4 |  | Site Environmental Factors
Go to Main Page
Refresh

## DevCoAssessmentInput(D&C)
PIF Project Lighthouse
DevCoAssessmentInput(D&C)
Assessment Criteria | Data Point | Input Value | Data Source | Assessor Remarks | Assessment Time Stamp | Reviewer Remarks | Review Time Stamp | Formula
% of CESMP mitigation measures which align with ESIA* | Environmental mitigation measures included in CESMP | 10 | [5 empty] | Environmental mitigation measures included in CESMP / Environmental mitigation measures recommended in ESIA
| Environmental mitigation measures recommended in ESIA | 20
Has the Construction Execution Plan been updated to reflect the latest stage of construction? | Update of construction execution plan | Yes | [5 empty] | Update of construction execution plan
Has the construction sequence and method statement been reviewed and approved? | Review and approval of Construction sequence & method statement | No |  | Unable to determine |  |  |  | Review and approval of construction sequence and method statement
Is total land acquisition sufficient to achieve the area required for construction site logistics? | Planned Area provision for site offices, amenities, laydown areas, storage facilities, workforce accommodations | Average | [5 empty] | Sufficient land acquired
| Actual Area provision for site offices, amenities, laydown areas, storage facilities, workforce accommodations | No
Have Traffic Simulations been completed in preparing the Site & Logistics Plan? | Completion of Traffic Simulations | Yes |  | Unable to determine |  |  |  | Completion of traffic simulations
Has the Project Execution Plan been updated and approved in the last 12 months? | Date of latest approved Procurement Plan | 2025-03-25 | DR-018-01 |  |  |  |  | Date of latest approved Procurement Plan less than 12 months from Current Date
% of Stakeholder MOU** / LUPs*** not executed in accordance with critical lead time | Number of Stakeholder MOU or Land Use Permits not executed on time | 5 | [5 empty] | Number of Stakeholder MOU or Land Use Permits not executed on time/ Total number of Stakeholder MOU or Land Use Permits required
| Total Stakeholder MOU or Land Use Permits required | 100
% of Workforce Hired against Workforce Estimates | Forecast workforce requirements | 10000 | [5 empty] | Actual workforce employed / forecast workforce requirements
| Actual workforce employed | 11000
% of Labor Camp Capacity against Workforce Estimates | Forecast number of labor camps | 6 | [5 empty] | Actual number of labor camps / Forecast number of labor camps
| Actual number of labor camps | 6
% of Material Supply Capacity against Material Demand Estimates | Forecast number of batching / crushing plants/ precast yards, etc. | 3 | DR-032 | Assessed against concrete batching plant requirements forcasted in the IMS report. Generally, based on the number of operating batching plants, conctete demand can be met. A projected shortfall for 2 months may occur based on the current peak demand projections. |  |  |  | Actual number of batching plants / forecast number of batching plants
| Actual number of batching / crushing plants/ precast yards, etc. | 4 | DR-023-32
Did DevCo adhere to Technical Submittals Review Cycle Time (RCT)? | Time taken for closure of technical queries | Yes | [5 empty] | Adherence to Technical Submittals Review Cycle Time
| Technical Submittal Review Cycle Time (RCT) | Yes
% of approved shop drawing reviews vs planned | Total number of shop drawing review requests | 14760 | [5 empty] | Total number of shop drawing reviews approved / Total number of shop drawing review requests
| Total number of shop drawing reviews approved | 13970
% of approved product waivers vs product specified | Total number of product sample & material approvals requested | 1000 | [5 empty] | Total number of product sample & materials approved / Total number of product sample & material approvals requested
| Total number of product sample & materials approved | 986
% of Certified As-Built Drawing Packages vs Planned | Number of As-Built Drawing review requests | 500 | [5 empty] | Number of As-built reviews / approvals / Number of As-Built review requests
| Number of As-Built Drawings reviews approved | 475
MIR Inspection Rate | Total number of MIRs requested | 120 | [5 empty] | Number of MIR Inspected / Total number of MIRs requested
| Total number of MIRs inspected | 118
MIR Acceptance and Approval Rate | Total number of MIRs approved | 110 | [5 empty] | Number of Approved MIR / Total number of MIRs requested
WIR Inspection Rate | Total number of WIRs requested | 350 | [5 empty] | Number of WIR Inspected / Total number of WIRs requested
| Total number of WIRs inspected | 340
WIR Acceptance and Approval Rate | Total number of WIRs approved | 335 | [5 empty] | Number of Approved WIR / Total number of WIRs requested
Does the frequency of Audits align with the QMP? | Required Audit frequency | Yes | [5 empty] | Alignment of audit frequency
% closure of Non-Conformance Reports (NCR) | Total number of defects & NCRs | 150 | [5 empty] | Number of Non-Conformance Reports Closed / Total Number of Non-Conformance Reports
| Total number of closed defects & NCRs | 145
Average NCRs closeout Cycle Time | Average time to close NCRs | 23 | [5 empty] | Sum (NCR Closeout cycle time)/Total number of Non-Conformance Reports
% of procurement packages delivered within the planned lead times defined in the PMP | Planned Procurement Package Lead Time | 100 | [5 empty] | Sum( Actual Procurement Package Delivery Time / Planned Procurement Package Delivery Time)
| Actual Procurement Package Delivery Time | 86
% of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures | Total number of claims and variations | 800 | [5 empty] | Total number of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures / Total number of claims and variations
| Total number of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures | 700
% of packages procured with 100% complete, compliant and well-structured documentation | Total number of packages | 0.5 | [5 empty] | Total number of packages procured with 100% complete, compliant and well-structured documentation / Total number of packages
| Total number of packages procured with 100% complete, compliant and well-structured documentation | 0.3
% of awarded contracts where vendors appointed passed full due diligence checks | No. of awarded contracts where vendors appointed passed full due-diligence checks | 0.9 | [5 empty] | No. of awarded contracts where vendors appointed passed full due-diligence checks / Total number of awarded contracts
| Total number of awarded contracts | 0.7
Did the DevCo complete a Supply Chain Risk-Market Intelligence Assessment in the last quarter? | Supply Chain Risk-Market Intelligence Assessment | Yes | DR-049 | Supply Chain Risk appears to be an ongoing item flagged in the risk register, factors noted include: Shipping delays due to regional conflicts Parallel giga projects competing for resources impacting cost of materials and causing delays |  |  |  | Completion of supply chain risk-market intelligence assessment
% of procurement activities executed as planned in the Annual Procurement Plan | Total number of procurement activities | 186 | [5 empty] | Number of procurement activities executed as planned / Total number of procurement activities
| Number of procurement activities executed as planned | 129
% of deviations in total awarded contract value with tender cost estimates | Value of Awarded Contract | 35.32 | [5 empty] | (Value of Contract Awarded - Tender Cost Estimate) / Value of Award Contract
| Tender Cost Estimate | 32.1
% of contracts with filed claims | Number of contracts with filed claims | 10 | [5 empty] | Number of contracts with filed claims / Total number of awarded contracts
Are Payment Certificates and payments being processed in accordance with the Contract terms and conditions? | Processing of payment certificates and payments | Yes | [5 empty] | Processing of payment certificates and payments
Are Vendor performance assessment occurring which capture financial instability, delays, repeated quality issues in real-time? | Alignment of sourcing strategies with project schedules and requirements | No | [5 empty] | Vendor performance assessment
Does the HSE Management Manual have adequate provision for identification and escalation of high risk activities? | Escalation criteria for high risk activities | Yes | [5 empty] | Provision for identification and escalation of high risk activities
Is the rate of review of the Safety Risk Register in accordance with the HSE Management Manual? | HSE Risk Register Review Rate | Yes | [5 empty] | Review rate of safety risk register
% of closed Safety Risk items | Total number of Safety Risk items | 0.9 | [5 empty] | Total number of closed Safety Risk items / Total number of safety risk items
| Total number of closed Safety Risk items | 0.75
Average cycle time to close Safety Risk items | Cycle time to close Safety Risk items | 14 Days | [5 empty] | Sum (Cycle time to close safety risk items) / Total number of closed safety risk items
Average cycle time to close Safety Incident | Cycle time to close Safety Incident | 20 | [5 empty] | Sum (Cycle time to close safety incident) / Total number of closed safety incidents
| Total number of closed safety incidents | 13
Is the emergency drill rate compliant with EEPP? | Planned number of Emergency Drills | 35 | [5 empty] | Compliance of emergency drill rate
| Actual number of Emergency Drills | 20
| Recommended time to complete Emergency drills | 5 Days
| Actual Time to complete Emergency drills | 10 Days
Fatality Rate (FR) | No. of incidents resulting in fatality or severe impairment per 200,000 work hours | 0 | DR-061-01 | DGCL Monthly OH&S Trend Analysis Report January 2025- Monthly KPI's Section 3.1- Zero recored fatalities. Salini Saudi Arabia Monthly HSE Report April 2025- Zero fatalaties recorded. |  |  |  | No. of incidents resulting in fatality or severe impairment per 200,000 work hours
Lost Time Injury Frequency Rate (LTIFR) | No. of incidents resulting in lost time per 200,000 work hours | 0 | DR-061-01 | DGCL Monthly OH&S Trend Analysis Report January 2025- Monthly KPI's Section 3.2- Zero recored LTIs. Salini Saudi Arabia Monthly HSE Report April 2025- Zero LTIs recorded. |  |  |  | No. of incidents resulting in lost time per 200,000 work hours
Total Recordable Incident Rate (TRIR) | No. of recordable incidents per 200,000 work hours | 0 | DR-061-01 | DGCL Monthly OH&S Trend Analysis Report January 2025- Monthly KPI's Section 3.1- Zero recorded Total Recordable Incident Rate (TRIR) Salini Saudi Arabia Monthly HSE Report April 2025- Zero Total Recordable Incident Rate (TRIR) recorded. |  |  |  | No. of recordable incidents per 200,000 work hours
Near Miss Rate | No. of near misses recorded per 200,000 work hours | 3 | [5 empty] | No. of near misses recorded per 200,000 work hours
Safety Observation Rate | No. of safety observation recorded per 200,000 work hours | 8 | [5 empty] | No. of safety observation recorded per 200,000 work hours
Leadership Safety Walk Rate | Total number of Safety Walks | 300 | [5 empty] | Total number of Safety Walks with Leadership / Total number of Safety Walks
| Total number of Safety Walks with Leadership | 219 | DR-060-02 | DGCL Monthly OH&S Trend Analysis Report January 2025- States in section 3- Monthly OH&S KPIs-Section 2.6- 219 OH&S Safety Leadership Site Walkthroughs were conducted for the month.
% of Grievances Closed | Number of grievances closed | 5 | [5 empty] | Number of grievances closed / Total number of grievances
| Total number of grievances | 5
Average Cycle Time to Close Grievances | Cycle time to close grievances | Good | [5 empty] | Sum (Cycle time to close grievances) / Total number of grievances
% of Welfare Staff vs Total workforce | Percentage of Welfare Staff against total staff | Good | [5 empty] | Number of Welfare Staff / Total Number of Staff
% closed welfare observations or red flag if 0 observations | Total number of Welfare Observations | 20 | [5 empty] | Number of Welfare Observations Closed / Total number of Welfare Observations
| Total number of Closed Welfare Observations | 15
% of Welfare Non-compliances closed | Total Welfare Non-compliances | 100 | [5 empty] | Total Closed Welfare Non-compliances / Total Welfare Non-compliances
| Total Closed Welfare Non-compliances | 58
Average Cycle Time to Close Welfare Non-compliances | Cycle time to close Welfare Non-Compliances | 10 Days | [5 empty] | Sum (Cycle time to close Welfare Non-compliances) / Total number of Welfare Non-compliances
Is frequency of Labor Accommodation Inspection occurring in accordance with VMMP? | Mitigation measures in the event of welfare audit observations & recommendations | Yes | [5 empty] | Labor accommodation inspection frequency
Go to Main Page
Refresh
Go to Document
Go to Analysis
Note on C13: dd-mm-yyyy

## DevCoAssessmentAnalysis(D&C)
PIF Project Lighthouse
DevCoAssessmentAnalysis(D&C)
Assessment Criteria | Data Point | Value | Rating | Score | Assessment Criteria Weightage | Assessment Guideline/Formula | Good | Satisfactory | Needs Improvement | Remarks 1 | Performance Signal | Performance Signal Score | Performance Signals Weightage | Remarks 2 | Key Topic | Key Topic Score | Remarks 3
% of CESMP mitigation measures which align with ESIA* | Environmental mitigation measures included in CESMP | 50% | Needs Improvement | 1 | 10% | Environmental mitigation measures included in CESMP / Environmental mitigation measures recommended in ESIA | >80% | 60-80% | <60% |  | Construction Planning Maturity | 2.3 | 70% |  | Construction | 2.51
Environmental mitigation measures recommended in ESIA
Has the Construction Execution Plan been updated to reflect the latest stage of construction? | Update of construction execution plan | Yes | Good | 3 | 15% | Update of construction execution plan | Yes |  | No
Has the construction sequence and method statement been reviewed and approved? | Review and approval of Construction sequence & method statement | No | Needs Improvement | 1 | 15% | Review and approval of construction sequence and method statement | Yes |  | No
Is total land acquisition sufficient to achieve the area required for construction site logistics? | Planned Area provision for site offices, amenities, laydown areas, storage facilities, workforce accommodations | No | Needs Improvement | 1 | 10% | Sufficient land acquired | Yes |  | No
Actual Area provision for site offices, amenities, laydown areas, storage facilities, workforce accommodations
Have Traffic Simulations been completed in preparing the Site & Logistics Plan? | Completion of Traffic Simulations | Yes | Good | 3 | 10% | Completion of traffic simulations | Yes |  | No
Has the Project Execution Plan been updated and approved in the last 12 months? | Date of latest approved Procurement Plan | Yes | Good | 3 | 10% | Date of latest approved Procurement Plan less than 12 months from Current Date | Yes |  | No
% of Stakeholder MOU** / LUPs*** not executed in accordance with critical lead time | Number of Stakeholder MOU or Land Use Permits not executed on time | 5% | Good | 3 | 30% | Number of Stakeholder MOU or Land Use Permits not executed on time/ Total number of Stakeholder MOU or Land Use Permits required | <20% | 20-60% | >60%
Total Stakeholder MOU or Land Use Permits required
% of Workforce Hired against Workforce Estimates | Forecast workforce requirements | 110% | Good | 3 | 30% | Actual workforce employed / forecast workforce requirements | >90% | 70-90% | <70% |  | Workforce Resource Availability | 3 | 30%
Actual workforce employed
% of Labor Camp Capacity against Workforce Estimates | Forecast number of labor camps | 100% | Good | 3 | 30% | Actual number of labor camps / Forecast number of labor camps | >90% | 70-90% | <70%
Actual number of labor camps
% of Material Supply Capacity against Material Demand Estimates | Forecast number of batching / crushing plants/ precast yards, etc. | 133.3% | Good | 3 | 40% | Actual number of batching plants / forecast number of batching plants | >80% | 40-80% | <40%
Actual number of batching / crushing plants/ precast yards, etc.
Did DevCo adhere to Technical Submittals Review Cycle Time (RCT)? | Time taken for closure of technical queries | Yes | Good | 3 | 10% | Adherence to Technical Submittals Review Cycle Time | Yes |  | No |  | Adherence to Design | 3 | 70% |  | Quality | 2.88
Technical Submittal Review Cycle Time (RCT)
% of approved shop drawing reviews vs planned | Total number of shop drawing review requests | 94.65% | Good | 3 | 15% | Total number of shop drawing reviews approved / Total number of shop drawing review requests | >90% | 60-90% | <60%
Total number of shop drawing reviews approved
% of approved product waivers vs product specified | Total number of product sample & material approvals requested | 98.6% | Good | 3 | 15% | Total number of product sample & materials approved / Total number of product sample & material approvals requested | >90% | 60-90% | <60%
Total number of product sample & materials approved
% of Certified As-Built Drawing Packages vs Planned | Number of As-Built review requests | 95% | Good | 3 | 20% | Number of As-built reviews / approvals / Number of As-Built review requests | >80% | 60-80% | <60%
Number of As-built reviews / approvals
MIR Inspection Rate | Total number of MIRs requested | 98.33% | Good | 3 | 10% | Number of MIR Inspected / Total number of MIRs requested | >80% | 60-80% | <60%
Total number of MIRs inspected
MIR Acceptance and Approval Rate | Total number of MIRs approved / rejected | 91.67% | Good | 3 | 10% | Number of Approved MIR / Total number of MIRs requested | >80% | 60-80% | <60%
WIR Inspection Rate | Total number of WIRs requested | 97.14% | Good | 3 | 10% | Number of WIR Inspected / Total number of WIRs requested | >80% | 60-80% | <60%
Total number of WIRs inspected
WIR Acceptance and Approval Rate | Total number of WIRs approved / rejected | 95.71% | Good | 3 | 10% | Number of Approved WIR / Total number of WIRs requested | >80% | 60-80% | <60%
Does the frequency of Audits align with the QMP? | Required Audit frequency | Yes | Good | 3 | 40% | Alignment of audit frequency | Yes |  | No |  | Quality Assurance / Quality Control (QA/QC) | 2.6 | 30%
% closure of Non-Conformance Reports (NCR) | Total number of defects & NCRs | 96.67% | Good | 3 | 40% | Number of Non-Conformance Reports Closed / Total Number of Non-Conformance Reports | >80% | 60-80% | <60%
Total number of closed defects & NCRs
Average NCRs closeout Cycle Time | Average time to close NCRs | 23 | Needs Improvement | 1 | 20% | Sum (NCR Closeout cycle time)/Total number of Non-Conformance Reports | <10 days | 10-21 days | >21 days
% of procurement packages delivered within the planned lead times defined in the PMP | Planned Procurement Package Lead Time | 86% | Good | 3 | 20% | Sum( Actual Procurement Package Delivery Time / Planned Procurement Package Delivery Time) | >80% | 70-80% | 40-70% |  | Procurement & Contracting Compliance | 2.8 | 30% |  | Procurement | 2.1
Actual Procurement Package Delivery Time
% of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures | Total number of claims and variations | 87.5% | Good | 3 | 20% | Total number of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures / Total number of claims and variations | >70% | 50-70% | <50%
Total number of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures
% of packages procured with 100% complete, compliant and well-structured documentation | Total number of packages | 60% | Satisfactory | 2 | 20% | Total number of packages procured with 100% complete, compliant and well-structured documentation / Total number of packages | >70% | 50-70% | <50%
Total number of packages procured with 100% complete, compliant and well-structured documentation
% of awarded contracts where vendors appointed passed full due diligence checks | No. of awarded contracts where vendors appointed passed full due-diligence checks | 128.6% | Good | 3 | 10% | No. of awarded contracts where vendors appointed passed full due-diligence checks / Total number of awarded contracts | >90% | 90-85% | <85%
Total number of awarded contracts
Did the DevCo complete a Supply Chain Risk-Market Intelligence Assessment in the last quarter? | Supply Chain Risk-Market Intelligence Assessment | Yes | Good | 3 | 30% | Completion of supply chain risk-market intelligence assessment | Yes |  | No
% of procurement activities executed as planned in the Annual Procurement Plan | Total number of procurement activities | 69.35% | Needs Improvement | 1 | 30% | Number of procurement activities executed as planned / Total number of procurement activities | <20% | 20-60% | >60% |  | Procurement & Contracting Execution Performance | 1.8 | 70%
Number of procurement activities executed as planned
% of deviations in total awarded contract value with tender cost estimates | Value of Awarded Contract | 9.117% | Good | 3 | 30% | (Value of Contract Awarded - Tender Cost Estimate) / Value of Award Contract | <20% | 20-60% | >60%
Tender Cost Estimate
% of contracts with filed claims | Number of contracts with filed claims | 1000% | Needs Improvement | 1 | 20% | Number of contracts with filed claims / Total number of awarded contracts | <20% | 20-60% | >60%
Are Payment Certificates and payments being processed in accordance with the Contract terms and conditions? | Processing of payment certificates and payments | Yes | Good | 3 | 10% | Processing of payment certificates and payments | Yes |  | No
Are Vendor performance assessment occurring which capture financial instability, delays, repeated quality issues in real-time? | Alignment of sourcing strategies with project schedules and requirements | No | Needs Improvement | 1 | 10% | Vendor performance assessment | Yes |  | No
Does the HSE Management Manual have adequate provision for identification and escalation of high risk activities? | Escalation criteria for high risk activities | Yes | Good | 3 | 5% | Provision for identification and escalation of high risk activities | Yes |  | No |  | HSE Compliance | 2.47 | 50% |  | HSE and Welfare | 2.435
Is the rate of review of the Safety Risk Register in accordance with the HSE Management Manual? | HSE Risk Register Review Rate | Yes | Good | 3 | 2% | Review rate of safety risk register | Yes |  | No
% of closed Safety Risk items | Total number of Safety Risk items | 83.33% | Good | 3 | 4% | Total number of closed Safety Risk items / Total number of safety risk items | >80% | 60-80% | <60%
Total number of closed Safety Risk items
Average cycle time to close Safety Risk items | Cycle time to close Safety Risk items | 14 Days | Needs Improvement | 1 | 4% | Sum (Cycle time to close safety risk items) / Total number of closed safety risk items | <7 days | 7-14 days | >14 days
Average cycle time to close Safety Incident | Cycle time to close Safety Incident | 0.65 | Good | 3 | 5% | Sum (Cycle time to close safety incident) / Total number of closed safety incidents | <7 days | 7-14 days | >14 days
Total number of closed safety incidents
Is the emergency drill rate compliant with EEPP? | Planned number of Emergency Drills | No | Needs Improvement | 1 | 5% | Compliance of emergency drill rate | Yes |  | No
Actual number of Emergency Drills
Recommended time to complete Emergency drills
Actual Time to complete Emergency drills
Fatality Rate (FR) | No. of incidents resulting in fatality or severe impairment per 200,000 work hours | 0 | Good | 3 | 15% | No. of incidents resulting in fatality or severe impairment per 200,000 work hours | 0% | 0.001-0.0199 | >0.02
Lost Time Injury Frequency Rate (LTIFR) | No. of incidents resulting in lost time per 200,000 work hours | 0 | Good | 3 | 10% | No. of incidents resulting in lost time per 200,000 work hours | <0.1 | 0.1-1.5 | >1.5
Total Recordable Incident Rate (TRIR) | No. of recordable incidents per 200,000 work hours | 0 | Good | 3 | 10% | No. of recordable incidents per 200,000 work hours | <0.5 | 0.5-5 | >5
Near Miss Rate | No. of near misses recorded per 200,000 work hours | 3 | Satisfactory | 2 | 15% | No. of near misses recorded per 200,000 work hours | >30 | 0.1-30 | 0%
Safety Observation Rate | No. of safety observation recorded per 200,000 work hours | 8 | Needs Improvement | 1 | 10% | No. of safety observation recorded per 200,000 work hours | >200 | 10-200 | <10
Leadership Safety Walk Rate | Total number of Safety Walks | 73% | Good | 3 | 15% | Total number of Safety Walks with Leadership / Total number of Safety Walks | >70% | 50-70% | <50%
Total number of Safety Walks with Leadership
% of Grievances Closed | Number of grievances closed | 100% | Good | 3 | 15% | Number of grievances closed / Total number of grievances | >80% | 60-80% | <60% |  | Welfare Compliance | 2.4 | 50%
Total number of grievances
Average Cycle Time to Close Grievances | Cycle time to close grievances | Good | Needs Improvement | 1 | 10% | Sum (Cycle time to close grievances) / Total number of grievances | <14 days | 14-28 days | >28 days
% of Welfare Staff vs Total workforce | Percentage of Welfare Staff against total staff | Good | Good | 3 | 20% | Number of Welfare Staff / Total Number of Staff | Good | Average | Poor
% closed welfare observations or red flag if 0 observations | Total number of Welfare Observations | 75% | Good | 3 | 0.1 | Number of Welfare Observations Closed / Total number of Welfare Observations | >60% | 40-60% | <40% ; no observations recorded
Total number of Closed Welfare Observations
% of Welfare Non-compliances closed | Total Welfare Non-compliances | 58% | Needs Improvement | 1 | 10% | Total Closed Welfare Non-compliances / Total Welfare Non-compliances | >80% | 60-80% | <60%
Total Closed Welfare Non-compliances
Average Cycle Time to Close Welfare Non-compliances | Cycle time to close Welfare Non-Compliances | 10 Days | Needs Improvement | 1 | 10% | Sum (Cycle time to close Welfare Non-compliances) / Total number of Welfare Non-compliances | <14 days | 14-28 days | >28 days
Is frequency of Labor Accommodation Inspection occurring in accordance with VMMP? | Mitigation measures in the event of welfare audit observations & recommendations | Yes | Good | 3 | 25% | Labor accommodation inspection frequency | Yes |  | No
Go to Main Page
Refresh
Go to Document
Go to Input

## InterviewQuestion(D&C)
PIF Project Lighthouse
InterviewQuestion(D&C)
SN | Question | Date of Interview | Response | Internal Comment | Follow Up Question
1 | What are the challenges in implementation of the Project Execution Plan and how are you managing those? | 2025-05-09 16:05
2 | Have there been any setbacks with the required land acquisition, if so, what are they and how do you plan to overcome the issues? | 2025-05-09 16:05
3 | Have any delays occurred due to stakeholder objections; how did you resolve the issue? | 2025-05-09 16:05
4 | Have there been any challenges with labor camp establishment, number, quality or provision of amenities in accordance with workforce estimates? | 2025-05-09 16:05
5 | Have there been any challenges in hiring the required skilled labor workforce, how do you plan to overcome this? | 2025-05-09 16:05
6 | How do you track and record workforce retention and turnover rate? | 2025-05-09 16:05
7 | How do you track and record plant/ equipment downtime? | 2025-05-09 16:05
8 | What are the reasons for any deviations from the approved design intent? | 2025-05-09 16:05
9 | Have there been delays in the approval's workflow, if so, what actions have been taken to resolve the delays? | 2025-05-09 16:05
10 | Have material or product availability and lead times led to substitution requests? | 2025-05-09 16:05
11 | Has the required number of ITPs been signed off throughout construction? | 2025-05-09 16:05
12 | Out of all the defects and NCRs raised, how many are closed out? | 2025-05-09 16:05
13 | What are the challenges preventing adherence to the planned number of audits, what measures have you undertaken to resolve the challenges? | 2025-05-09 16:05
14 | Have any Vendors failed to deliver the work under contact, what has been done to resolve the issue and to track Vendor performance? | 2025-05-09 16:05
15 | What strategies are in place to catch up on the procurement schedule, can you show evidence this is working? | 2025-05-09 16:05
16 | What level of market intelligence has been applied to the Supply Chain Risk Assessment, provide example. | 2025-05-09 16:05
17 | Is the DevCo aware of suppliers/contractors not fulfilling service delivery compliance requirement as per contract terms (contract KPI compliance). Are there any mitigation measures in place? Provide example. | 2025-05-09 16:05
18 | Are there any claims or disputes resulting in financial risk, project disruption or legal escalation? Are these resolved within contractually agreed timelines? What is the plan for resolution? | 2025-05-09 16:05
19 | Were there procurement bottlenecks due to approval delays, bid evaluation inefficiencies, or poor planning, negatively impacting project schedules, what is being done to resolve this? Provide example. | 2025-05-09 16:05
20 | Of the incidents / safety concerns raised, are there any that are difficult to resolve and why? | 2025-05-09 16:05
21 | What mitigation measures have been implemented as a result of incidents and safety observations raised? How many have had mitigation measures put in place? Provide an example. | 2025-05-09 16:05
22 | Are there any recurring incidents / safety observations outside of your control, if so, please provide detail? | 2025-05-09 16:05
23 | What are the challenges preventing leadership safety walks, what measures have you undertaken to resolve the challenges? | 2025-05-09 16:05
24 | Have there been challenges in sourcing qualified HSE&W leaders? If so, what have you done to resolve the shortfall, such as training? Do you maintain a training register? If so, please provide a sample. | 2025-05-09 16:05
25 | What mitigation measures have been implemented as a result of welfare audit observations & recommendations? | 2025-05-09 16:05
Go to Main Page
Refresh

## AddDataPoint(D&C)
PIF Project Lighthouse
AddDataPoint(D&C) |  |  |  |  | Land Acquisition Requirements |  |  |  |  | Quality Audits |  |  | Procurement Packages |  |  |  |  | Incident Management | [5 empty] | Compliance Management - Audits/Inspections |  |  |  |  | Compliance Management - Actions |  |  |  |  | Safety Trainings
SN | Criteria | Additional Data Point | Value | Scorecard Visualization | SN | Program | Acquired (Ha) | Under Negotiation (Ha) | Pending (Ha) | SN | Month | Number of Quality Audits | SN | Parameter | Baseline | Actual | Forecast | SN | Incident Category | Number of Incidents (To-Date) | Number of Investigations in Progress | Number of Investigations Completed | Number of Investigations Pending Approval | SN | Audits/Inspections | In Progress_audits | Completed_audits | Remaining Planned | SN | Actions | In Progress_actions | Completed_actions | Pending Approval | SN | Year | Value_training
1 |  | No. of Site Access Required | 180 | Raw Data for Indicator | 1 | Program 1 | 50 | 25 | 5 | 1 | Jan | 2 | 1 | Count | 186 | 129 | 50 | 1 | Fatalities | 0 | 0 | 0 | 0 | 1 | HSE Audit | 3 | 5 | 4 | 1 | HSE | 6 | 22 | 12 | 1 | Jan | 30
2 |  | No. of Site Access Provided | 120 | Raw Data for Indicator | 2 | Program 2 | 230 | 40 | 30 | 2 | Feb | 5 | 2 | Value | 16100 | 9600 | 6800 | 2 | Severe Impairment | 1 | 0 | 1 | 0 | 2 | Welfare Inspection | 2 | 4 | 4 | 2 | Welfare | 25 | 10 | 7 | 2 | Feb | 40
3 |  | Packaging & Phasing Strategy | Good | Visualized with No Score | 3 | Program 3 | 10 | 80 | 10 | 3 | Mar | 3 | [5 empty] | 3 | Lost Time Incidents | 3 | 0 | 1 | 2 | [10 empty] | 3 | Mar | 38
4 |  | Execution & Site Logistics | Satisfactory | Visualized with No Score | [5 empty] | 4 | Apr | 1 | [5 empty] | 4 | Recordable Incidents | 14 | 3 | 11 | 0 | [10 empty] | 4 | Apr | 35
5 |  | Procurement Strategy | Good | Visualized with No Score | [5 empty] | 5 | May | 0 | [5 empty] | 5 | Near Misses | 26 | 2 | 21 | 3 | [10 empty] | 5 | May | 0
6 |  | Required area for land acquisition |  | Visualized with Score | [5 empty] | 6 | Jun | 0 | [21 empty] | 6 | Jun | 0
7 |  | Mitigation of Project Execution Plan implementation challenges |  | Visualized with Score | [5 empty] | 7 | Jul | 0 | [21 empty] | 7 | Jul | 0
8 |  | Occurred delays due to stakeholder objections |  | Visualized with Score | [5 empty] | 8 | Aug | 0 | [21 empty] | 8 | Aug | 0
9 |  | Workforce Planning and Availability | Needs Improvement | Visualized with Score | [5 empty] | 9 | Sep | 0 | [21 empty] | 9 | Sep | 0
10 |  | Resource Planning and Availability | Good | Visualized with Score | [5 empty] | 10 | Oct | 0 | [21 empty] | 10 | Oct | 0
11 |  | Workforce retention track record |  | Raw Data for Indicator | [5 empty] | 11 | Nov | 0 | [21 empty] | 11 | Nov | 0
12 |  | Turnover rate track record |  | Raw Data for Indicator | [5 empty] | 12 | Dec | 0 | [21 empty] | 12 | Dec | 0
13 |  | Plant/equipment downtime track record |  | Raw Data for Indicator
14 |  | Number of technical queries raised |  | Raw Data for Indicator
15 |  | Number of technical queries closed |  | Raw Data for Indicator
16 |  | Average time to complete shop drawing reviews |  | Raw Data for Indicator
17 |  | Number of shop drawing review conducted | 14550 | Visualized with Score
18 |  | Number of material / product substitution requests |  | Raw Data for Indicator
19 |  | Average time to approve product sample & materials |  | Raw Data for Indicator
20 |  | Product & Material Approval Rate |  | Visualized with Score
21 |  | Number of as-built drawing review conducted | 485 | Raw Data for Indicator
22 |  | Average time to approve As-built rejections / iterations |  | Raw Data for Indicator
23 |  | As-Built Drawing Approval Rate |  | Visualized with Score
24 |  | Average time to complete MIRs and close out approvals |  | Raw Data for Indicator
25 |  | Average time to complete WIRs and close out approvals |  | Raw Data for Indicator
26 |  | Number of NCRs open for between 30 and 60 days | 23 | Visualized with Score
27 |  | Number of NCRs open for more than 60 days | 5 | Visualized with Score
28 |  | Leadership engagement | Satisfactory | Raw Data for Indicator
29 |  | Total number of ITPs requested | 100 | Raw Data for Indicator
30 |  | Total number of ITPs attended | 98 | Raw Data for Indicator
31 |  | Total number of ITPs approved | 87 | Raw Data for Indicator
32 |  | Total number of ITPs completed | 85 | Raw Data for Indicator
33 |  | Total number Quality Reports completed |  | Raw Data for Indicator
34 |  | Completeness of Quality Management Plan | Needs Improvement | Visualized with Score
35 |  | Required number of ITPs signed off throughout construction |  | Visualized with No Score
36 |  | Total number of raised closed-out defects & NCRs |  | Raw Data for Indicator
37 |  | Forecasted Procurement Budget |  | Visualized with Score
38 |  | Actual Procurement Budget |  | Visualized with Score
39 |  | Vendor Database |  | Raw Data for Indicator
40 |  | Vendor Shortlist |  | Raw Data for Indicator
41 |  | Vendor Awarded |  | Raw Data for Indicator
42 |  | Vendor KPIs |  | Raw Data for Indicator
43 |  | Vendor Performance Database |  | Visualized with Score
44 |  | Tender return date: Planned / Actual |  | Raw Data for Indicator
45 |  | Tender Review & award time: Planned / actual |  | Raw Data for Indicator
46 |  | Pre-Tender Cost Estimate |  | Raw Data for Indicator
47 |  | Tender Performance Index |  | Visualized with Score
48 |  | Contract clauses | Satisfactory | Visualized with No Score
49 |  | Procurement Management Plan | Good | Visualized with No Score
50 |  | Scope / design maturity | Satisfactory | Visualized with No Score
51 |  | Compliance with local content regulations / policies |  | Visualized with Score
52 |  | Dispute rate |  | Visualized with Score
53 |  | Claims processing cycle time |  | Visualized with Score
54 |  | No. of related CRs being requested during or after tendering phase due to identified scope gap
55 |  | Vendor Performance Assessment | Good | Visualized with Score
56 |  | Tender pack quality | Satisfactory | Visualized with No Score
57 |  | % payment paid within contractual terms | 80 | Visualized with Score
58 |  | Planned Packages |  | Visualized with Score
59 |  | Awarded Packages |  | Visualized with Score
60 |  | Trade Most at Risk |  | Visualized with No Score
61 |  | Highest Risk Work Site |  | Visualized with No Score
62 |  | Number of planned audits |  | Raw Data for Indicator
63 |  | Number of conducted audits |  | Raw Data for Indicator
64 |  | Number of Notifiable Incidents | 6 | Visualized with Score
65 |  | Number of Infringement Notices | 2 | Visualized with Score
66 |  | Total Safe Manhours |  | Visualized with Score
67 |  | Total number of closed Corrective actions |  | Raw Data for Indicator
68 |  | Inspection Pass Rate |  | Visualized with Score
69 |  | No. of recurring incidents / safety observations outside control |  | Visualized with Score
70 |  | Total Site Manhours | 180000000 | Visualized with Score
71 |  | Welfare of labor camps |  | Visualized with Score
74 |  | Welfare of site facilities |  | Visualized with Score
73 |  | Labor accommodation inspection rate
74 |  | Regulation Compliance
Go to Main Page
Refresh

## DevCoAssessmentInput(CE&O)
PIF Project Lighthouse
DevCoAssessmentInput(CE&O)
Assessment Criteria | Data Point | Input Value | Data Source | Assessor Remarks | Assessment Time Stamp | Reviewer Remarks | Review Time Stamp | Formula
Budget Variance | PIF Approved Capex budget (Initial Business Plan) | 2800000000 | [5 empty] | PIF Approved Capex budget (Initial Business Plan) – Estimate At Completion
| Forecast budget (EAC) | 3100000000
% of projects having Budget Variance | Number of Projects with Budget Variance | 15 | [5 empty] | Number of Projects with Budget Variance / Total number of Projects
| Total number of projects | 20
% of projects with contingency utilization rate > 1 | Number of projects with contingency utilization > 1 | 5 | [5 empty] | (Number of projects with contingency utilization > 1) / (Total number of projects)
% of projects with Approved Change Requests (design/construction) having a cost impact greater than 2% | No. of projects with approved change request having a cost impact greater than 2% | 12 | [5 empty] | (No. of projects with approved change request having a cost impact greater than 2%) / (Total number of projects)
% of projects with Approved Claims | No. of projects with approved claims | 10 | [5 empty] | (No. of projects with approved claims) / (Total number of projects)
% of provisional sums of the latest PIF Approved Capex budget | Total provisional sums | 2000000 | [5 empty] | Total Provisional Sums/Latest Approved Budget
| Latest Approved budget | 2900000000
% of variance of Allocated Provisional sums against the awarded amount | Actual Utilized Provisional Sums | 800000 | [5 empty] | (Total Provisional Sums−Actual Utilized Provisional Sums)/Total Provisional Sums
Go to Main Page
Refresh
Go to Document
Go to Analysis

## DevCoAssessmentAnalysis(CE&O)
PIF Project Lighthouse
DevCoAssessmentAnalysis(CE&O)
Assessment Criteria | Data Point | Value | Rating | Score | Assessment Criteria Weightage | Assessment Guideline/Formula | Good | Satisfactory | Needs Improvement | Remarks 1 | Performance Signal | Performance Signal Score | Performance Signals Weightage | Remarks 2 | Key Topic | Key Topic Score | Remarks 3
Budget Variance | PIF Approved Capex budget (Initial Business Plan) | 10.71% | Satisfactory | 2 | 80% | PIF Approved Capex budget (Initial Business Plan) – Estimate At Completion | <10% | 10-20% | >20% |  | Budget Variance | 1.8 | 60% |  | Overall Budget | 1.68 | Significant increase in budget due to inadequate contingency planning
Forecast budget (EAC)
% of projects having Budget Variance | Number of Projects with Budget Variance | 75% | Needs Improvement | 1 | 20% | Number of Projects with Budget Variance / Total number of Projects | <10% | 10-30% | >30%
Total number of projects
% of projects with contingency utilization rate > 1 | Number of projects with contingency utilization > 1 | 25% | Satisfactory | 2 | 20% | (Number of projects with contingency utilization > 1) / (Total number of projects) | <10% | 10-30% | >30% |  | Budget Trend | 1.2 | 20%
% of projects with Approved Change Requests (design/construction) having a cost impact greater than 2% | No. of projects with approved change request having a cost impact greater than 2% | 60% | Needs Improvement | 1 | 40% | (No. of projects with approved change request having a cost impact greater than 2%) / (Total number of projects) | <5% | 5-15% | >15%
% of projects with Approved Claims | No. of projects with approved claims | 50% | Needs Improvement | 1 | 40% | (No. of projects with approved claims) / (Total number of projects) | <2% | 2-5% | >5%
% of provisional sums of the latest PIF Approved Capex budget | Total provisional sums | 0.06897% | Good | 3 | 40% | Total Provisional Sums/Latest Approved Budget | <5% | 5-15% | >15% |  | Provisional Sum Utilization | 1.8 | 20%
Latest Approved budget
% of variance of Allocated Provisional sums against the awarded amount | Actual Utilized Provisional Sums | 250% | Needs Improvement | 1 | 60% | (Total Provisional Sums−Actual Utilized Provisional Sums)/Total Provisional Sums | <10% | 10-20% | >20%
Go to Main Page
Refresh
Go to Document
Go to Input

## InterviewQuestion(CE&O)
PIF Project Lighthouse
InterviewQuestion(CE&O)
SN | Question | Date of Interview | Response | Internal Comment | Follow Up Question
1 | What corrective actions were taken when a project exceeds its budget? | 2025-05-09 16:05
2 | What had been the three key factors contributing to budget overruns? | 2025-05-09 16:05
3 | Based on the revisions to the budget did the DevCo perform any trend analysis to understand the root cause factors contributing to such revisions and was the same recorded in the lessons learnt repository? | 2025-05-09 16:05
4 | Which project categories or project stages requested for more budget than planned? | 2025-05-09 16:05
5 | Was the scope of work identified for Provisional sums defined at concept stage? | 2025-05-09 16:05
6 | Was the amount estimated based on historical benchmarking rates? If yes, please provide a sample. | 2025-05-09 16:05
Go to Main Page
Refresh

## AddDataPoint(CE&O)
PIF Project Lighthouse
AddDataPoint(CE&O) |  |  |  |  | Budget Performance
SN | Criteria | Additional Data Point | Value | Scorecard Visualization | Year | Budget Value (Baseline) in M SAR | Budget Value (Revised) in M SAR | Budget Value (Forecast) in M SAR
1 |  | Estimate to Completion Declared by DevCo | 3200000000 | Visualized with No Score | 2023 | 400 | 400 | 400
2 |  | Total Expenditure to Date | 100000000 | Visualized with No Score | 2024 | 1000 | 1200 | 1200
3 |  | Contingency budgeted at DevCo level | 20000000 | Raw Data for Indicator | 2025 | 1500 | 1800 | 1800
4 |  | Contingency utilized at DevCo level | 7500000 | Raw Data for Indicator | 2026 | 2000 | 2200 | 2300
5 |  | Contingency Utilization Rate |  |  | 2027 | 2500 | 2750 | 2900
6 |  | Value of Changes in Design Stage | 200000 | Visualized with No Score | 2028 | 2800 | 3100 | 3200
7 |  | Value of Changes in Construction Stage | 5000000 | Visualized with No Score
8 |  | Number of Changes (Concept MP) | 0 | Visualized with Score
9 |  | Number of Changes (Detailed MP) | 3 | Visualized with Score
10 |  | Number of Changes (Concept Design) | 2 | Visualized with Score
11 |  | Number of Changes (Detailed Design) | 6 | Visualized with Score
12 |  | Number of Changes (Construction) | 8 | Visualized with Score
13 |  | Total Awarded Cost | 15000000 | Raw Data for Indicator
14 |  | Approved Variations and Claims | 5200000 | Visualized with No Score
15 |  | Uncommitted Cost | 300000000 | Visualized with No Score
16 |  | Pending Variations | 0 | Visualized with No Score
17 |  | Anticipated Variations | 1 | Visualized with No Score
Go to Main Page
Refresh

## DevCoAssessmentInput(I&T)
PIF Project Lighthouse
DevCoAssessmentInput(I&T)
Assessment Criteria | Data Point | Input Value | Data Source | Assessor Remarks | Assessment Time Stamp | Reviewer Remarks | Review Time Stamp | Formula
Is there an innovation Strategy or document that lists the key focus areas and initiatives across design, construction and operation and aligned with DevCo strategic plan? | Availability of an innovation strategy | Yes | [5 empty] | Innovation Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10%
| Alignment of innovation strategy with DevCo Strategic Plan | Yes
| List of focus areas of innovation and technology | Yes
| List of innovative initiatives throughout project lifecycle (design, construction and operation) | No
| Availability of innovation cost-benefit analysis | No
| Implementation Success Rate for Innovation Strategy | No
| Process for innovation | No
| Budget of implementation | No
Is there a smart city Strategy or document that lists the key focus areas of smart city aligned with DevCo strategic plan? | Availability of a smart city strategy | Yes | [5 empty] | Smart City Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10%
| Alignment of smart city strategy with DevCo Strategic Plan | Yes
| List of Smart City focus areas | Yes
| List of smart city initiatives within each key focus area | No
| Availability of smart city goals and set of KPIs | No
| Availability of smart city cost-benefit analysis | No
| Implementation Roadmap for selected smart city initiatives | No
| Budget of implementation | No
Is there an impact assessment report or identified process/ guidelines to evaluate the impact of the innovation / smart city technologies adoption on DevCo performance? | Availability of approach / process and guidelines to evaluate the impact of implementing innovations and technologies | Yes | [5 empty] | Adoption on DevCo performance? Robust assessment process and guidelines - 30%; Availability of sample of impact assessment report - 30%; Availability of action plan - 10%; Use of innovative tools/platforms/dashboards - 30%
| Availability of sample of impact assessment report | Yes
| Availability of action plan | No
| Use of innovative tools/platforms/dashboards | No
Is there evidence for innovation / smart city technologies successful implementation (in final design report, master plan or other)? | Evidence for adoption of innovation/smart city considerations within the master plan | Yes | [5 empty] | Evidence for innovation/smart city technologies successful implementation
| Evidence for adoption of innovation/smart city considerations within the project detailed design | Yes
Are there Pilot or R&D projects conducted? | Availability of innovation/smart city piloting or R&D procedures | Yes | [5 empty] | Pilot or R&D projects conducted? Availability - 20%; Adequate list of focus areas - 35%; Procedure - 15%; Outcome assessment robustness - 30%
| List of focus areas | Yes
| Procedure | No
| Robustness of assessment of pilot and R&D outcomes | No
% of pilot / R&D Projects Transitioned into Full-Scale | Number of pilot projects | 20 | [5 empty] | [(Number of pilots that are scaled successfully + Number of R&D projects that are successfully piloted or fully-scaled) / (Number of pilot projects + Number of R&D projects)]
| Number of R&D projects | 3
| Number of pilot projects that are scaled successfully | 2
| Number of R&D projects that are successfully piloted or fully-scaled | 1
Availability of Innovation unit / department with structured team | Availability of Innovation unit/department | No | [5 empty] | Availability of Innovation: Availability - 20%; Adequate Key positions planned in the org. structure - 30%; Unit/department position within the company hierarchy - 20%; Qualifications of the innovation team - 30%
| Key positions planned in the innovation unit/department | No
| Innovation unit/department within the company hierachy | No
| Qualifications of the innovation team | No
Availability of Innovation and Technology Strategy / Process & Framework | Innovation Unit Strategy / Process & Framework | Yes | [5 empty] | Availability - 50% Implementation of the unit/department framework/ process - 50%
| Implementation of innovation department process / framework | No
Go to Main Page
Refresh
Go to Document
Go to Analysis

## DevCoAssessmentAnalysis(I&T)
PIF Project Lighthouse
DevCoAssessmentAnalysis(I&T)
Assessment Criteria | Data Point | Value | Rating | Score | Assessment Criteria Weightage | Assessment Guideline/Formula | Good | Satisfactory | Needs Improvement | Remarks 1 | Performance Signal | Performance Signal Score | Performance Signals Weightage | Remarks 2 | Key Topic | Key Topic Score | Remarks 3
Is there an innovation Strategy or document that lists the key focus areas and initiatives across design, construction and operation and aligned with DevCo strategic plan? | Availability of an innovation strategy | 40% | Needs Improvement | 1 | 30% | Innovation Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10% | >75% | 60-75% | <60% |  | Innovation & Technology Deployment | 1.7 | 40% |  | Innovation and Technology Adoption | 1.43 |  | 0.5 | 0 | 0.2 | 0.15 | 0.3 | 0.15 | Yes
| Alignment of innovation strategy with DevCo Strategic Plan | [16 empty] | 0 | 0 | 0.35 | 0.15 | 0.3 | 0.15 | Yes
| List of focus areas of innovation and technology | [17 empty] | 0 | 0 | 0.1 | 0 | 0.1
| List of innovative initiatives throughout project lifecycle (design, construction and operation) | [17 empty] | 0 | 0 | 0 | 0 | 0
| Availability of innovation cost-benefit analysis | [17 empty] | 0 |  | 0 |  | 0
| Implementation Success Rate for Innovation Strategy | [19 empty] | 0 |  | 0
| Process for innovation | [19 empty] | 0 |  | 0
| Budget of implementation | [19 empty] | 0 |  | 0
Is there a smart city Strategy or document that lists the key focus areas of smart city aligned with DevCo strategic plan? | Availability of a smart city strategy | 40% | Needs Improvement | 1 | 30% | Smart City Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10% | >75% | 60-75% | <60%
Alignment of smart city strategy with DevCo Strategic Plan
List of Smart City focus areas
List of smart city initiatives within each key focus area
Availability of smart city goals and set of KPIs
Availability of smart city cost-benefit analysis
Implementation Roadmap for selected smart city initiatives
Budget of implementation
Is there an impact assessment report or identified process/ guidelines to evaluate the impact of the innovation / smart city technologies adoption on DevCo performance? | Availability of approach / process and guidelines to evaluate the impact of implementing innovations and technologies | 60% | Satisfactory | 2 | 10% | Adoption on DevCo performance? Robust assessment process and guidelines - 30%; Availability of sample of impact assessment report - 30%; Availability of action plan - 10%; Use of innovative tools/platforms/dashboards - 30% | >75% | 60-75% | <60%
Availability of sample of impact assessment report
Availability of action plan
Use of innovative tools/platforms/dashboards
Is there evidence for innovation / smart city technologies successful implementation (in final design report, master plan or other)? | Evidence for adoption of innovation/smart city considerations within the master plan | Yes | Good | 3 | 30% | Evidence for innovation/smart city technologies successful implementation | Yes |  | No
Evidence for adoption of innovation/smart city considerations within the project detailed design
Are there Pilot or R&D projects conducted? | Availability of innovation/smart city piloting or R&D procedures | 55% | Needs Improvement | 1 | 50% | Pilot or R&D projects conducted? Availability - 20%; Adequate list of focus areas - 35%; Procedure - 15%; Outcome assessment robustness - 30% | >75% | 60-75% | <60% |  | Pilot and R&D Transition Rate | 1 | 30%
List of focus areas
Procedure
Robustness of assessment of pilot and R&D outcomes
% of pilot / R&D Projects Transitioned into Full-Scale | Number of pilot projects | 13.04% | Needs Improvement | 1 | 50% | [(Number of pilots that are scaled successfully + Number of R&D projects that are successfully piloted or fully-scaled) / (Number of pilot projects + Number of R&D projects)] | >40% | 20-40% | <20%
Number of R&D projects
Number of pilot projects that are scaled successfully
Number of R&D projects that are successfully piloted or fully-scaled
Availability of Innovation unit / department with structured team | Availability of Innovation unit/department | 0% | Needs Improvement | 1 | 50% | Availability of Innovation: Availability - 20%; Adequate Key positions planned in the org. structure - 30%; Unit/department position within the company hierarchy - 20%; Qualifications of the innovation team - 30% | >60% | 40-60% | <40% |  | Organization Maturity Towards Innovation Adoption | 1.5 | 30%
Key positions planned in the innovation unit/department
Innovation unit/department within the company hierachy
Qualifications of the innovation team
Availability of Innovation and Technology Strategy / Process & Framework | Innovation Unit Strategy / Process & Framework | 50% | Satisfactory | 2 | 50% | Availability - 50% Implementation of the unit/department framework/ process - 50% | >50% | 50% | <50%
Implementation of innovation department process / framework
Go to Main Page
Refresh
Go to Document
Go to Input

## InterviewQuestion(I&T)
PIF Project Lighthouse
InterviewQuestion(I&T)
SN | Question | Date of Interview | Response | Internal Comment | Follow Up Question
1 | If there is no innovation or smart city strategy, is there a document that lists the areas and initiatives for innovation and smart city technology applied during the design, construction, and operations stages? | 2025-05-09 16:05
2 | Are there guidelines for assessing the impact of innovation and smart city technologies on DevCo performance? | 2025-05-09 16:05
3 | If there is no pilot or R&D register, did you conduct any pilot or R&D projects? what is the number of conducted pilot/ R&D projects? Please provide a sample. | 2025-05-09 16:05
4 | What is the number of pilots / R&D projects that are scaled successfully? | 2025-05-09 16:05
5 | Is there an Innovation unit / department setup? How does the hierarchy look like? | 2025-05-09 16:05
6 | Is there an Innovation Unit strategy/ Process and Framework? If yes, please share a document relating to this. | 2025-05-09 16:05
Go to Main Page
Refresh

## AddDataPoint(I&T)
PIF Project Lighthouse
AddDataPoint(I&T)
SN | Criteria | Additional Data Point | Value | Scorecard Visualization
1 |  | Implementation Success Rate for Innovation Strategy | 50 | Visualized with Score
2 |  | Innovation Adoption Effectiveness Index (strategy & leadership alignment) | 1 | Visualized with Score
3 |  | Innovation Adoption Effectiveness Index (skilled human resources) | 3 | Visualized with Score
4 |  | Innovation Adoption Effectiveness Index (planning & governance) | 2 | Visualized with Score
5 |  | Innovation Adoption Effectiveness Index (process management) | 4 | Visualized with Score
6 |  | Innovation Adoption Effectiveness Index (partnerships and collaboration) | 2 | Visualized with Score
7 |  | Innovation Adoption Effectiveness Index (resource management) | 0.6 | Visualized with Score
8 |  | Implementation Success Rate for Smart City Strategy | 70 | Visualized with Score
9 |  | Number of Smart City Use Cases | 10 | Visualized with No Score
10 |  | Smart City Adoption Effectiveness Index (strategy & leadership alignment) | 2 | Visualized with Score
11 |  | Smart City Adoption Effectiveness Index (infrastructure readiness) | 2 | Visualized with Score
12 |  | Smart City Adoption Effectiveness Index (planning & governance) | 3 | Visualized with Score
13 |  | Smart City Adoption Effectiveness Index (stakeholder alignment) | 1 | Visualized with Score
14 |  | Smart City Adoption Effectiveness Index (realized benefits & performance) | 0.5 | Visualized with Score
Go to Main Page
Refresh

## DevCoAssessmentInput(S&O)
PIF Project Lighthouse
DevCoAssessmentInput(S&O)
Assessment Criteria | Data Point | Input Value | Data Source | Assessor Remarks | Assessment Time Stamp | Reviewer Remarks | Review Time Stamp | Formula
Availability of Technical Function Strategy | Availability of strategy | Yes, but very brief | [5 empty] | Give 'satisfactory' score if there is a technical function strategy, but it is very general and does not provide specific details of the strategy
Alignment of Technical Strategy with Organizational Strategy | Alignment of technical functions' strategy and initiatives with the overarching organizational strategy | Well-aligned | [5 empty] | Assess if elements of technical strategy is aligned with organizational strategy. "Average" score if key elements of organizational strategy is not addressed in technical strategy
Severity of Key Challenges Faced in Strategy Execution Technically | Key challenges in strategy execution | Moderate | [5 empty] | "Severe" score if challenges faced can impact strategy execution significantly (in terms of time, cost and/or quality)
Availability of Technical KPIs | Availability of KPIs | Yes, but very brief | [5 empty] | Give 'satisfactory' score if there are technical KPIs, but they are very generic
Progress of Achievement of KPIs for Technical Team | Total Number of KPIs set for the preceding year | 20 | [5 empty] | Number of KPIs achieved / Total Number of KPIs set for the same period
| Number of KPIs achieved in the preceding year | 16
Appropriateness of KPIs for Technical Team |  | Aligned with industry benchmarks | [5 empty] | Expected elements from industry benchmarks: 1. Schedule adherence 2. Budget adherence 3. Employee attrition 4. HSE and Welfare 5. Internal audit performance
Criticality of Vacant/Missing Positions in Organization | Key positions which are missing, if any | Minor | [5 empty] | "Severe" if more than 25% of technical department head (N-2 or 3) and above are vacant Technical department head: person leading a technical function (depends on organization size) "Moderate" if 2 position for technical department head are vacant
Appropriateness of Qualifications in Recruitment of Vacant Technical Department Head Positions | Qualifications of job descriptions for vacant technical department head positions - are they appropriate? | Minor | [5 empty] | "Critical" score if there is little to no relevance in the requested qualifications to the role
Robustness of Policy/Guideline/Procedure Communication | List of policies/procedures communicated to all employees | Strong | [5 empty] | Strong if these are done: 1. Regular update and review of policies (3 mths) 2. All relevant policies/guidelines captured 3. Easy access (one repository with easy to find link) 4. Multi-channels to inform updates to documents e.g. email, intranet
Robustness of Policy/Guideline/Procedure Compliance Monitoring Framework | Monitoring of policies and procedures compliance | Moderate | [5 empty] | Strong if these are done: 1. Regular internal audits of processes (ongoing and rotation of topics/departments) 2. Independent internal audit department reporting directly to CEO or Board 3. Whistleblowing policy 4. Regular training for all staff (annual)
Robustness of Board Reporting Framework | Frequency of reporting to Board and PIF | Moderate | [5 empty] | Strong if all of these following points are done: 1. Board reporting policy covering frequency/trigger for updates 2. Register of Board Papers/Presentations 3. Register of Board meetings and meeting minutes
Availability of Technical Function Strategy and KPIs
Availability of Technical Function Strategy and KPIs
Availability of Technical Function Strategy and KPIs
Robustness of Board Reporting Framework Frequency of reporting to Board and PIF
Robustness of Board Reporting Framework Frequency of reporting to Board and PIF
Robustness of Board Reporting Framework Frequency of reporting to Board and PIF
Go to Main Page
Refresh
Go to Document
Go to Analysis

## DevCoAssessmentAnalysis(S&O)
PIF Project Lighthouse
DevCoAssessmentAnalysis(S&O)
Assessment Criteria | Data Point | Value | Rating | Score | Assessment Criteria Weightage | Assessment Guideline/Formula | Good | Satisfactory | Needs Improvement | Remarks 1 | Performance Signal | Performance Signal Score | Performance Signals Weightage | Remarks 2 | Key Topic | Key Topic Score | Remarks 3
Availability of Technical Function Strategy | Availability of strategy | Yes, but very brief | Satisfactory | 2 | 30% | Give 'satisfactory' score if there is a technical function strategy, but it is very general and does not provide specific details of the strategy | Yes | Yes, but very brief | No |  | Technical Strategy Achievement | 2.3 | 20% |  | Technical Strategy and Enablers | 2.57
Alignment of Technical Strategy with Organizational Strategy | Alignment of technical functions' strategy and initiatives with the overarching organizational strategy | Well-aligned | Good | 3 | 30% | Assess if elements of technical strategy is aligned with organizational strategy. "Average" score if key elements of organizational strategy is not addressed in technical strategy | Well-aligned | Some gaps | Misaligned
Severity of Key Challenges Faced in Strategy Execution Technically | Key challenges in strategy execution | Moderate | Satisfactory | 2 | 40% | "Severe" score if challenges faced can impact strategy execution significantly (in terms of time, cost and/or quality) | Minor | Moderate | Severe
Availability of Technical KPIs | Availability of KPIs | Yes, but very brief | Satisfactory | 2 | 40% | Give 'satisfactory' score if there are technical KPIs, but they are very generic | Yes | Yes, but very brief | No |  | Technical KPI Achievement | 2.6 | 20%
Progress of Achievement of KPIs for Technical Team | Total Number of KPIs set for the preceding year | 80% | Good | 3 | 20% | Number of KPIs achieved / Total Number of KPIs set for the same period | >75% | 50-75% | <50%
Number of KPIs achieved in the preceding year
Appropriateness of KPIs for Technical Team |  | Aligned with industry benchmarks | Good | 3 | 40% | Expected elements from industry benchmarks: 1. Schedule adherence 2. Budget adherence 3. Employee attrition 4. HSE and Welfare 5. Internal audit performance | Aligned with industry benchmarks | Some gaps with industry benchmarks | Significant deviation from industry benchmarks
Criticality of Vacant/Missing Positions in Organization | Key positions which are missing, if any | Minor | Good | 3 | 60% | "Severe" if more than 25% of technical department head (N-2 or 3) and above are vacant Technical department head: person leading a technical function (depends on organization size) "Moderate" if 2 position for technical department head are vacant | Minor | Moderate | Severe |  | Technical Organization | 3 | 30%
Appropriateness of Qualifications in Recruitment of Vacant Technical Department Head Positions | Qualifications of job descriptions for vacant technical department head positions - are they appropriate? | Minor | Good | 3 | 40% | "Critical" score if there is little to no relevance in the requested qualifications to the role | Well-aligned | Some gaps | Misaligned
Robustness of Policy/Guideline/Procedure Communication | List of policies/procedures communicated to all employees | Strong | Good | 3 | 30% | Strong if these are done: 1. Regular update and review of policies (3 mths) 2. All relevant policies/guidelines captured 3. Easy access (one repository with easy to find link) 4. Multi-channels to inform updates to documents e.g. email, intranet | Strong | Moderate | Poor |  | Technical Control Environment | 2.3 | 30%
Robustness of Policy/Guideline/Procedure Compliance Monitoring Framework | Monitoring of policies and procedures compliance | Moderate | Satisfactory | 2 | 40% | Strong if these are done: 1. Regular internal audits of processes (ongoing and rotation of topics/departments) 2. Independent internal audit department reporting directly to CEO or Board 3. Whistleblowing policy 4. Regular training for all staff (annual) | Strong | Moderate | Poor
Robustness of Board Reporting Framework | Frequency of reporting to Board and PIF | Moderate | Satisfactory | 2 | 30% | Strong if all of these following points are done: 1. Board reporting policy covering frequency/trigger for updates 2. Register of Board Papers/Presentations 3. Register of Board meetings and meeting minutes | Strong | Moderate | Poor
Go to Main Page
Refresh
Go to Document
Go to Input

## InterviewQuestion(S&O)
PIF Project Lighthouse
InterviewQuestion(S&O)
SN | Question | Date of Interview | Response | Internal Comment | Follow Up Question
1 | How do the technical functions’ strategy and initiatives align with the overarching organizational strategy? | 2025-05-02 17:10
2 | Share any key challenges faced in executing the strategy from a technical perspective | 2025-05-02 17:10
3 | Are there any vacant/missing roles which are critical and impeding optimal execution of projects? | 2025-05-02
4 | Are there any gaps in experience/qualifications/skill sets of the existing team in delivery of the DevCo’s mandate? | 2025-05-02
5 | How are policies/procedures communicated to all employees? | 2025-05-02
6 | How is compliance with policies and procedures monitored & ensured? | 2025-05-02
7 | What is the framework for reporting to the Board? | 2025-05-02
Go to Main Page
Refresh

## AddDataPoint(S&O)
PIF Project Lighthouse
AddDataPoint(S&O) |  |  |  |  | Critical Position Currently Unstaffed/Missing |  | Critical Policies Missing |  |  | Critical Technical Platforms Missing |  |  | Top KPI |  | Org Chart
SN | Criteria | Additional Data Point | Value | Scorecard Visualization | Position Vacant | Position Missing | Name of the Policy | Criticality Policies (Y/N) | Availability Policies (Y/N) | Name of the Technical Platform | Criticality Technical (Y/N) | Availability Technical (Y/N) | Name of the KPI | Weightage | EmployeeID | ManagerID | Label | Group | Sub-Label
1 |  | Strategy Planning and Review | 3 | Visualized with No Score | Chief Development, MP3 | Head of HSE | Design Stage Gate Approval Procedures | Y | N | Cost Management Platform | Y | N | KPI 1 | 20 | 1 |  | Chief Development Officer | Filled | CDO
2 |  | Explicit Mapping against Organization Strategy | 3 | Visualized with No Score | Project Lead, MP1 | Stakeholder Interface Lead | [6 empty] | KPI 2 | 20 | 2 | 1 | Head | Filled | Development
3 |  | Benchmarking and Industry Standards | 3 | Visualized with No Score | [8 empty] | KPI 3 | 15 | 3 | 1 | Head | Filled | Projects
4 |  | Performance Management | 3 | Visualized with No Score | [8 empty] | KPI 4 | 10 | 4 | 1 | Head | Filled | Masterplan
5 |  | Communication and Implementation | 2 | Visualized with No Score | [8 empty] | KPI 5 | 10 | 5 | 1 | HSE | Missing | HSE
6 |  | Clear and Documented Process | 2 | Visualized with No Score | [8 empty] | Others | 25 | 6 | 2 | Chief Devt | Filled | MP1
7 |  | Technology Utilization | 3 | Visualized with No Score | [10 empty] | 7 | 2 | Chief Devt | Filled | MP2
8 |  | Risk Management and Technical Planning Deficiencies | Yes | Visualized with No Score | [10 empty] | 8 | 2 | Chief Devt | Vacant | MP3
9 |  | Technology Integration and Adaptation Challenges | Yes | Visualized with No Score | [10 empty] | 9 | 3 | Project Lead | Vacant | MP1
10 |  | Data Management and Information Flow | Yes | Visualized with No Score | [10 empty] | 10 | 3 | Project Lead | Filled | MP2
11 |  | Supply Chain and Logistics | No | Visualized with No Score | [10 empty] | 11 | 3 | Project Lead | Filled | MP3
12 |  | Cross-Functional Coordination and Communication | Yes | Visualized with No Score | [10 empty] | 12 | 3 | Lead | Missing | Stakeholder Interface
13 |  | Adaptability to Market Conditions | Yes
14 |  | Alignment with Critical Success Factors | 3
15 |  | Inclusion of both Lagging and Leading Indicators | 3
16 |  | Stakeholder Engagement in KPI Development | 2
17 |  | Comprehensive Coverage of Key Performance Areas | 3
18 |  | Continuous Improvement and Review | 3
19 |  | Total Positions | 500
20 |  | Vacant Positions | 100
21 |  | Management Positions | 50
22 |  | Vacant Management Positions | 5
Go to Main Page
Refresh

## AssessmentSummary
PIF Project Lighthouse
AssessmentSummary | Q1 2025
Section | n | Performance Signal Score | Key Topic | Key Topic Score | Remarks
Planning & Monitoring (P&M) | Schedule Adherence | 2 | Overall Progress | 2.1 | DevCo performance is generally good. While overall progress is delayed by 12 months, these are largely due to unforeseen circumstances and DevCo has shown ability to recover some of the delays. The lack of a smart city strategy and DevCo-level ESG targets and irregular adherence to procurement control processes are key areas for improvement.
| Schedule Extension | 2.2
| Schedule Achievability | 2.2
| Risk Governance | 2.5 | Risk Performance | 2.38
| Realized Risk Status | 2.2
Design & Technical (D&T) | CGI and Animation Compliance | 2.4 | Vision Adherence | 2.7
| Development Program Variance | 3
| Construction Design Maturity | 2.8 | Design for Constructability | 2.8
| Design Management Maturity | 2.6 | Design Management | 2.6
| Environmental Compliance Status | 2 | Regulatory Compliance | 2.12
| Authority Compliance Status | 2.2
| DevCo ESG Target Achievement | 1 | ESG Target Realization | 1
| Global ESG Target Alignment | 1
Development & Construction (D&C) | Construction Planning Maturity | 2.3 | Construction | 2.51
| Workforce Resource Availability | 3
| Adherence to Design | 3 | Quality | 2.88
| Quality Assurance / Quality Control (QA/QC) | 2.6
| Procurement & Contracting Compliance | 2.8 | Procurement | 2.24
| Procurement & Contracting Execution Performance | 2
| HSE Compliance | 1.87 | HSE and Welfare | 2.135
| Welfare Compliance | 2.4
Cost Estimation & Optimization (CE&O) | Budget Variance | 1.8 | Overall Budget | 1.68
| Budget Trend | 1.2
| Provisional Sum Utilization | 1.8
Innovation & Technology (I&T) | Innovation & Technology Deployment | 1.7 | Innovation and Technology Adoption | 1.4
| Pilot and R&D Transition Rate | 1
| Organization Maturity Towards Innovation Adoption | 1.5
Strategy & Operations (S&O) | Technical Strategy Achievement | 2.3 | Technical Strategy and Enablers | 2.6
| Technical KPI Achievement | 2.6
| Technical Organization | 3
| Technical Control Environment | 2.3
Go to Main Page
Refresh

## Log
PIF Project Lighthouse
Log
SN | Stakeholder | Identity | Assessor / Reviewer | Stamp | Cell | Section | Data Point | Event
1 | MEINHARDT | Administrator | Admin | 2025-05-07 18:15 | $E$6 | DevCoAssessmentInput(P&M) | Planned Value (PV) | DevCoAssessmentInput(P&M) Cell $E$6 changed to [ a ]
2 | MEINHARDT | Administrator | Admin | 2025-05-07 18:15 | $E$7 | DevCoAssessmentInput(P&M) | Earned Value (EV) | DevCoAssessmentInput(P&M) Cell $E$7 changed to [ b ]
3 | MEINHARDT | Administrator | Admin | 2025-05-07 18:15 | $E$8 | DevCoAssessmentInput(P&M) | No. of planned milestones | DevCoAssessmentInput(P&M) Cell $E$8 changed to [ c ]
4 | MEINHARDT | Administrator | Admin | 2025-05-07 18:15 | $G$6 | DevCoAssessmentInput(P&M) | Planned Value (PV) | DevCoAssessmentInput(P&M) Cell $G$6 changed to [ 1 ]
5 | MEINHARDT | Administrator | Admin | 2025-05-07 18:15 | $G$7 | DevCoAssessmentInput(P&M) | Earned Value (EV) | DevCoAssessmentInput(P&M) Cell $G$7 changed to [ 2 ]
6 | MEINHARDT | Administrator | Admin | 2025-05-07 18:15 | $G$8 | DevCoAssessmentInput(P&M) | No. of planned milestones | DevCoAssessmentInput(P&M) Cell $G$8 changed to [ 3 ]
7 | MEINHARDT | Administrator | Admin | 2025-05-21 18:08 | $E$10 | DevCoAssessmentInput(P&M) | Total number of projects in design phase | DevCoAssessmentInput(P&M) Cell $E$10 changed to [ ]
8 | MEINHARDT | Administrator | Admin | 2025-05-21 18:14 | $E$7 | DevCoAssessmentInput(D&T) | Percentage similarity between Approved Animation and Latest Animation at same camera angle | DevCoAssessmentInput(D&T) Cell $E$7 changed to [ ]
9 | MEINHARDT | Administrator | Admin | 2025-05-22 11:09 | $E$9 | DevCoAssessmentInput(P&M) | No. of milestones achieved on time | DevCoAssessmentInput(P&M) Cell $E$9 changed to [ ]
10 | MEINHARDT | Administrator | Admin | 2025-05-22 17:26 | $L$6 | DevCoAssessmentAnalysis(D&T) | NA | DevCoAssessmentAnalysis(D&T) Cell $L$6 changed to [ CGI and Animation Compliance ]
11 | MEINHARDT | Administrator | Admin | 2025-05-22 17:30 | $N$6 | DevCoAssessmentAnalysis(D&T) | NA | DevCoAssessmentAnalysis(D&T) Cell $N$6 changed to [ 0.5 ]
12 | MEINHARDT | Administrator | Admin | 2025-05-22 17:30 | $P$6 | DevCoAssessmentAnalysis(D&T) | NA | DevCoAssessmentAnalysis(D&T) Cell $P$6 changed to [ Vision Adherence ]
13 | MEINHARDT | Administrator | Admin | 2025-05-23 11:27 | $C$6 | DevCoAssessmentInput(D&C) | Environmental mitigation measures included in CESMP | DevCoAssessmentInput(D&C) Cell $C$6 changed to [ 10 ]
14 | MEINHARDT | Administrator | Admin | 2025-05-23 11:27 | $C$7 | DevCoAssessmentInput(D&C) | Environmental mitigation measures recommended in ESIA | DevCoAssessmentInput(D&C) Cell $C$7 changed to [ 20 ]
15 | MEINHARDT | Administrator | Admin | 2025-05-23 11:28 | $C$16 | DevCoAssessmentInput(D&C) | Forecast workforce requirements | DevCoAssessmentInput(D&C) Cell $C$16 changed to [ 10000 ]
16 | MEINHARDT | Administrator | Admin | 2025-05-23 11:28 | $C$17 | DevCoAssessmentInput(D&C) | Actual workforce employed | DevCoAssessmentInput(D&C) Cell $C$17 changed to [ 8900 ]
17 | MEINHARDT | Administrator | Admin | 2025-05-23 11:28 | $C$17 | DevCoAssessmentInput(D&C) | Actual workforce employed | DevCoAssessmentInput(D&C) Cell $C$17 changed to [ 11000 ]
18 | MEINHARDT | Administrator | Admin | 2025-05-23 11:28 | $C$18 | DevCoAssessmentInput(D&C) | Forecast number of labor camps | DevCoAssessmentInput(D&C) Cell $C$18 changed to [ 6 ]
19 | MEINHARDT | Administrator | Admin | 2025-05-23 11:28 | $C$19 | DevCoAssessmentInput(D&C) | Actual number of labor camps | DevCoAssessmentInput(D&C) Cell $C$19 changed to [ 6 ]
20 | MEINHARDT | Administrator | Admin | 2025-05-23 11:29 | $C$20 | DevCoAssessmentInput(D&C) | Forecast number of batching / crushing plants/ precast yards, etc. | DevCoAssessmentInput(D&C) Cell $C$20 changed to [ 3 ]
21 | MEINHARDT | Administrator | Admin | 2025-05-23 11:29 | $C$21 | DevCoAssessmentInput(D&C) | Actual number of batching / crushing plants/ precast yards, etc. | DevCoAssessmentInput(D&C) Cell $C$21 changed to [ 4 ]
22 | MEINHARDT | Administrator | Admin | 2025-05-23 11:29 | $C$26 | DevCoAssessmentInput(D&C) | Total number of product sample & material approvals requested | DevCoAssessmentInput(D&C) Cell $C$26 changed to [ 1000 ]
23 | MEINHARDT | Administrator | Admin | 2025-05-23 11:29 | $C$27 | DevCoAssessmentInput(D&C) | Total number of product sample & materials approved | DevCoAssessmentInput(D&C) Cell $C$27 changed to [ 986 ]
24 | MEINHARDT | Administrator | Admin | 2025-05-23 11:30 | $C$53 | DevCoAssessmentInput(D&C) | Number of contracts with filed claims | DevCoAssessmentInput(D&C) Cell $C$53 changed to [ 10 ]
25 | MEINHARDT | Administrator | Admin | 2025-05-23 11:31 | $C$70 | DevCoAssessmentInput(D&C) | No. of near misses recorded per 200,000 work hours | DevCoAssessmentInput(D&C) Cell $C$70 changed to [ 6 ]
26 | MEINHARDT | Administrator | Admin | 2025-05-23 11:31 | $C$71 | DevCoAssessmentInput(D&C) | No. of safety observation recorded per 200,000 work hours | DevCoAssessmentInput(D&C) Cell $C$71 changed to [ 8 ]
27 | MEINHARDT | Administrator | Admin | 2025-05-23 11:31 | $C$70 | DevCoAssessmentInput(D&C) | No. of near misses recorded per 200,000 work hours | DevCoAssessmentInput(D&C) Cell $C$70 changed to [ 5 ]
28 | MEINHARDT | Administrator | Admin | 2025-05-23 11:31 | $C$70 | DevCoAssessmentInput(D&C) | No. of near misses recorded per 200,000 work hours | DevCoAssessmentInput(D&C) Cell $C$70 changed to [ 3 ]
29 | MEINHARDT | Administrator | Admin | 2025-05-23 11:31 | $C$72 | DevCoAssessmentInput(D&C) | Total number of Safety Walks | DevCoAssessmentInput(D&C) Cell $C$72 changed to [ 300 ]
30 | MEINHARDT | Administrator | Admin | 2025-05-23 12:13 | $C$40 | DevCoAssessmentInput(D&C) | Planned Procurement Package Lead Time | DevCoAssessmentInput(D&C) Cell $C$40 changed to [ 10 ]
31 | MEINHARDT | Administrator | Admin | 2025-05-23 12:13 | $C$41 | DevCoAssessmentInput(D&C) | Actual Procurement Package Delivery Time | DevCoAssessmentInput(D&C) Cell $C$41 changed to [ 8 ]
32 | MEINHARDT | Administrator | Admin | 2025-05-23 12:13 | $C$40 | DevCoAssessmentInput(D&C) | Planned Procurement Package Lead Time | DevCoAssessmentInput(D&C) Cell $C$40 changed to [ 100 ]
33 | MEINHARDT | Administrator | Admin | 2025-05-23 12:13 | $C$41 | DevCoAssessmentInput(D&C) | Actual Procurement Package Delivery Time | DevCoAssessmentInput(D&C) Cell $C$41 changed to [ 86 ]
34 | MEINHARDT | Administrator | Admin | 2025-05-23 17:51 | $R$20 | DevCoAssessmentAnalysis(P&M) | NA | DevCoAssessmentAnalysis(P&M) Cell $R$20 changed to [ Key risks include a mix of internal and external risks. Key external risks relate to material supply and logistics. Proactive actions have been taken to mitigate these risks. However, there has been an impact on the project delivery. ]
Go to Main Page
Refresh

## User
PIF Project Lighthouse
User
No. | User Name | Password | Identity | Stakeholder Group | Main | Instructions | Glossary&Definitions | DocumentList | Log | InterviewQuestion(P&M) | AddDataPoint(P&M) | DevCoAssessmentInput(P&M) | DevCoAssessmentAnalysis(P&M) | InterviewQuestion(D&T) | AddDataPoint(D&T) | DevCoAssessmentInput(D&T) | DevCoAssessmentAnalysis(D&T) | InterviewQuestion(D&C) | AddDataPoint(D&C) | DevCoAssessmentInput(D&C) | DevCoAssessmentAnalysis(D&C) | InterviewQuestion(CE&O) | AddDataPoint(CE&O) | DevCoAssessmentInput(CE&O) | DevCoAssessmentAnalysis(CE&O) | InterviewQuestion(I&T) | AddDataPoint(I&T) | DevCoAssessmentInput(I&T) | DevCoAssessmentAnalysis(I&T) | InterviewQuestion(S&O) | AddDataPoint(S&O) | DevCoAssessmentInput(S&O) | DevCoAssessmentAnalysis(S&O) | User | Setting | Login
1 | Admin | A_PLH_Data | Administrator | MEINHARDT | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a
2 | AssessorP&M | PLH_P&M | Assessor (P&M) | MEINHARDT | a | a | a | a | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a
3 | AssessorD&T | PLH_D&T | Assessor (D&T) | MEINHARDT | a | a | a | a | a | x | x | x | x | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a
4 | AssessorD&C | PLH_D&C | Assessor (D&C) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a
5 | AssessorCE&O | PLH_CE&O | Assessor (CE&O) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | a | a | a | a | x | x | x | x | x | x | x | x | x | x | a
6 | AssessorI&T | PLH_I&T | Assessor (I&T) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a | a | a | a | x | x | x | x | x | x | a
7 | AssessorS&O | PLH_S&M | Assessor (S&O) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a | a | a | a | x | x | a
8 | ReviewerP&M | PLH_P&M | Reviewer (P&M) | MEINHARDT | a | a | a | a | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a
9 | ReviewerD&T | PLH_D&T | Reviewer (D&T) | MEINHARDT | a | a | a | a | a | x | x | x | x | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a
10 | ReviewerD&C | PLH_D&C | Reviewer (D&C) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a
11 | ReviewerCE&O | PLH_CE&O | Reviewer (CE&O) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | a | a | a | a | x | x | x | x | x | x | x | x | x | x | a
12 | ReviewerI&T | PLH_I&T | Reviewer (I&T) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a | a | a | a | x | x | x | x | x | x | a
13 | ReviewerS&O | PLH_S&M | Reviewer (S&O) | MEINHARDT | a | a | a | a | a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | a | a | a | a | x | x | a
Go to Main Page
Refresh

## Setting
PIF Project Lighthouse
Setting | 8 | 2 | 5 | 0 | 2 | 14 | 7 | 80 | 80 | 120
No. | DDLPnM | DDLDnT | DDLDnC | DDLCEnO | DDLInT | DDLSnO | Section | DocID | Document | Formula | 3 | 2 | 1 | Section
1 | No | No | Average |  | No | Aligned with industry benchmarks | General | Cost Data | Cost Data Template | Earned Value (EV) / Planned Value (PV) | >1 | 0.85-1 | <0.85 | P&M
2 | Yes | Yes | Good |  | Yes | Minor | Planning & Monitoring | DR-001 | Baseline and Updated Master schedule (including cost linked Milestone summary for earned value, planned value analysis, and Schedule Updates) | No. of milestones achieved on time/ No. of planned milestones | >70% | 50-70% | <50% | P&M
3 | Yes, but inadequate |  | No |  |  | Misaligned | Design & Technical | DR-002 | Program Management Plan | Number of projects with approved change requests in design phase since inception with time impact of more than 1 month / Total number of projects in design phase | <30% | 30-70% | >70% | P&M
4 | Yes, but less than 1% |  | Poor |  |  | Moderate | Development & Construction | DR-003 | Latest Approved Monthly Progress Report | Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months / Total number of projects in construction phase | <30% | 30-70% | >70% | P&M
5 | Yes, but less than 5% |  | Yes |  |  | No | Cost Estimation & Optimization | DR-004 | Change request register (covering latest approved schedule extension requests) | (Number of Projects with Approved Schedule Extension)/Total Number of Projects) | <20% | 20-40% | >40% | P&M
6 | Yes, but less than 0.5% |  |  |  |  | Poor | Innovation & Technology | DR-005 | Latest approved risk mapping / risk register (including mitigation plans) documented at DevCo level and the list of Stakeholders | Number of projects with forecast completion date beyond the latest approved schedule / [No. of projects with schedule extension (design stage) + No. of projects with schedule extension (construction stage)] | <20% | 20-40% | >40% | P&M
7 | Yes, but less than 1 month |  |  |  |  | Severe | Strategy & Operations | DR-006 | Lookahead Schedules / Short-term execution plans (e.g., 4-week or 6-week lookahead) | "Satisfactory Score" if key project stakeholders (engineering, procurement, construction, client teams) were formally briefed, discussed on the forecast date includ any foreseen risks but no formal sign off doc on the forecast finish date is available | Yes | Yes, but inadequate | No | P&M
8 | Yes, but less than 2 weeks |  |  |  |  | Significant deviation from industry benchmarks |  | DR-007 | Sample of project level approved risk register | "Satisfactory" if new activities as per the risks identified and discussions with stakeholders are added in the revised programme but do not have logical relationships and there is no comparison of the critical path analysis before and after date change | Yes | Yes, but inadequate | No | P&M
9 | [5 empty] | Some gaps |  | DR-008 | Risk Management Plan | Satisfactory Score if - Contingency allocated but not aligning with the risk severity as per the heat map | Yes | Yes, but inadequate | No | P&M
10 | [5 empty] | Some gaps with industry benchmarks |  | DR-009 | Latest Updated Cost report | Satisfactory Score if - the deferment was less than 1 month | No | Yes, but less than 1 month | Yes | P&M
11 | [5 empty] | Strong |  | DR-010 | Program Tracker | Satisfactory Score if - the cost overrun was less than 5% | No | Yes, but less than 5% | Yes | P&M
12 | [5 empty] | Well-aligned |  | DR-011 | Original Approved and Latest version of CGI & Animation (Material Palette & Finish Schedule) | Satisfactory Score if - the cost overrun was less than 1% | No | Yes, but less than 1% | Yes | P&M
13 | [5 empty] | Yes |  | DR-012 | Original Approved and Latest version of the Drawings | Number of Controlled Risks / Total number of identified risks | >70% | 40-70% | <40% | P&M
14 | [5 empty] | Yes, but very brief |  | DR-013 | DevCo Design & Technical Guidelines (including, but not limited to, Look & Feel Design Guidelines) | Satisfactory Score if - the risks were identified, mitigations planned but not communicated to all the relevant stakeholders. And the risk register is updated | Yes | Yes, but inadequate | No | P&M
15 | [7 empty] | DR-014 | Design Report / Return Brief Report (including approved and latest Asset Area Schedule & Population) | Satisfactory Score if - the time impact is less than 2 weeks for Design phase completion and less than 1 month of Construction Phase Completion | No | Yes, but less than 2 weeks | Yes | P&M
16 | [7 empty] | DR-015 | Latest Stage Gate Cost Plan | Satisfactory Score if - the cost impact is less than 0.5% of the identified risk costing | No | Yes, but less than 0.5% | Yes | P&M
17 | [7 empty] | DR-016 | Report including constructability feasibility and construction methodology | (Percentage similarity between Approved CGI and Latest CGI at same angle and scale) + (Percentage similarity between Approved Animation and Latest Animation at same camera angle) / 2 | >70% | 50-70% | <50% | D&T
18 | [7 empty] | DR-017 | Digital Information Management Plan | Material Palette & Finish Schedule matched Approved CGI | >70% | 50-70% | <50% | D&T
19 | [7 empty] | DR-018 | Latest Project Execution Plan (including Design Strategy, Packaging Strategy and Phasing Strategy) | The Design and Technical Guidelines exist | Yes |  | No | D&T
20 | [7 empty] | DR-019 | Design Master Schedule | Material Palette & Finish Schedule aligns with Look & Feel Guideline | >70% | 50-70% | <50% | D&T
21 | [7 empty] | DR-020 | Procedures and Governance for design approvals and change management | (Latest BUA - Approved BUA) / Approved BUA | <15% | 15-30% | >30% | D&T
22 | [7 empty] | DR-021 | Design Basis Report and Stage Gate Design Report (including Design Management Report, Design Reviews & Verifications Register) | (Latest Land Area - Approved Land Area) / Approved Land Area | <15% | 15-30% | >30% | D&T
23 | [7 empty] | DR-022 | Infrastructure and Engineering report (including Water, Energy, Waste, Infrastructure & Mobility Plans) | (Latest Population - Approved Population) / Approved Population | <30% | 30-40% | >40% | D&T
24 | [7 empty] | DR-023 | Environmental and Social Impact Assessment | Modularized Construction Cost / Total Construction Cost | >40% | 20-40% | <20% | D&T
25 | [7 empty] | DR-024 | Environmental Compliance Report | Constructability Report exists | Yes |  | No | D&T
26 | [7 empty] | DR-025 | Register of Authority Engagement, Approvals and Waivers | Consideration of design for enabling work package | Yes |  | No | D&T
27 | [7 empty] | DR-026 | Stakeholder Management Plan (including Stakeholder Management Tracker) | LOD Documented matches LOD Required | Yes |  | No | D&T
28 | [7 empty] | DR-027 | Baseline ESG Strategy and Latest Annual ESG Report | BIM Documentation exists | Yes |  | No | D&T
29 | [7 empty] | DR-028 | Construction Environmental and Social Management Plan (including Environmental Permit Register) | Review Latest Approved Design Strategy and compare with the Stage Gate Design Report | Yes |  | No | D&T
30 | [7 empty] | DR-029 | Construction Execution Plan | Check the Design Review & Verification Register, assess if correct number of Design Reviews have occurred in accordance with the Design Management Report | >70% | 50-70% | <50% | D&T
31 | [7 empty] | DR-030 | Site and Logistics Plan (including traffic simulations) | Closed Corrective Actions / Total Corrective Actions | >70% | 40-70% | <40% | D&T
32 | [7 empty] | DR-031 | Interface Management Plan (including Stakeholder Management Plan*, Communication Plan & Contractor Staging Plan and Commissioning, Handover & Close-out Plan) | Average number of days between Date Corrective Action is recorded in the Corrective Action Register and the Date Corrective Action is Closed | <14days | 14-30days | >30days | D&T
33 | [7 empty] | DR-032 | Workforce Planning Strategy | Average number of days between Design Review Submittals and Completion of the Design Reviews compared to the number of days required to complete the Design Reviews in accordance with the Design Management Report | Yes |  | No | D&T
34 | [7 empty] | DR-033 | Construction Progress Report (including workforce numbers) | Independent Certification exists | Yes |  | No | D&T
35 | [7 empty] | DR-034 | Register of Technical Queries | The Infrastructure and Engineering Report references the Regional Infrastructure & Mobility Plans and demonstrates adoption of Regional Strategies | Yes |  | No | D&T
36 | [7 empty] | DR-035 | Register of Shop Drawing Reviews | Key Environmental Risks and Site Environmental Factors are covered in the Environmental Compliance Report | Yes |  | No | D&T
37 | [7 empty] | DR-036 | Register of Material & Product Approval / Product Substitution or Change Requests | Total Number of Code Compliance Violations taken from the Code Compliance Assessment Report | <10% | 10-30% | >30% | D&T
38 | [7 empty] | DR-037 | Register of As-Built Drawings | Total Waivers Approved / Total Waiver Applications Submitted | >70% | 50-70% | <50% | D&T
39 | [7 empty] | DR-038 | Register of Material Inspection Requests | Stakeholder Submittal Dates are in accordance with the Stakeholder Management Plan to ensure approvals can be achieved in line with Stage Gate completion requirements | Yes |  | No | D&T
40 | [7 empty] | DR-039 | Register of Work Inspection Requests | Number of Stakeholder approvals pending / Total number of stakeholder approvals required | <20% | 20-30% | >30% | D&T
41 | [7 empty] | DR-040 | Quality Management Manual (QMP) | Proactive communication in Stakeholder Engagement Plan | Yes |  | No | D&T
42 | [7 empty] | DR-041 | Latest Monthly Quality Report, including defects and NCR data | Stakeholder Comments Closed / Total Stakeholder Comments | >70% | 50-70% | <50% | D&T
43 | [7 empty] | DR-042 | Inspection Test Plan (ITP) | Actual ESG Target / Planned ESG Target | >70% | 50-70% | <50% | D&T
44 | [7 empty] | DR-043 | Sample of project specific Project Quality Plan (PQP) | Alignment with globally recognized Best Practice Targets | Yes |  | No | D&T
45 | [7 empty] | DR-044 | Latest Quality Audit Report | Environmental mitigation measures included in CESMP / Environmental mitigation measures recommended in ESIA | >80% | 60-80% | <60% | D&C
46 | [7 empty] | DR-045 | Procurement Management Plan (including annual procurement lookahead and pre-qualified vendor database) | Update of construction execution plan | Yes |  | No | D&C
47 | [7 empty] | DR-046 | Sample of Tender Award Report | Review and approval of construction sequence and method statement | Yes |  | No | D&C
48 | [7 empty] | DR-047 | Procurement and Contracting Risk Register | Sufficient land acquired | Yes |  | No | D&C
49 | [7 empty] | DR-048 | List of Appointed Vendors (including due-diligence checks) | Completion of traffic simulations | Yes |  | No | D&C
50 | [7 empty] | DR-049 | Supply Chain Risk Assessment | Date of latest approved Procurement Plan less than 12 months from Current Date | Yes |  | No | D&C
51 | [7 empty] | DR-050 | Current Procurement Schedule | Number of Stakeholder MOU or Land Use Permits not executed on time/ Total number of Stakeholder MOU or Land Use Permits required | <20% | 20-60% | >60% | D&C
52 | [7 empty] | DR-051 | Sample of Signed Agreement / Awarded Contract | Actual workforce employed / forecast workforce requirements | >90% | 70-90% | <70% | D&C
53 | [7 empty] | DR-052 | Sample of Supplier and Contractor Performance Report | Actual number of labor camps / Forecast number of labor camps | >90% | 70-90% | <70% | D&C
54 | [7 empty] | DR-053 | Contract Execution Register (including Letter of Award and Letter of Commencement) | Actual number of batching plants / forecast number of batching plants | >80% | 40-80% | <40% | D&C
55 | [7 empty] | DR-054 | Claims Register | Adherence to Technical Submittals Review Cycle Time | Yes |  | No | D&C
56 | [7 empty] | DR-055 | Post Tender Clarification (PTC) Register | Total number of shop drawing reviews approved / Total number of shop drawing review requests | >90% | 60-90% | <60% | D&C
57 | [7 empty] | DR-056 | Payment Register | Total number of product sample & materials approved / Total number of product sample & material approvals requested | >90% | 60-90% | <60% | D&C
58 | [7 empty] | DR-057 | HSE Management Manual | Number of As-built reviews / approvals / Number of As-Built review requests | >80% | 60-80% | <60% | D&C
59 | [7 empty] | DR-058 | HIRAC Methodology & Safety Risk Register | Number of MIR Inspected / Total number of MIRs requested | >80% | 60-80% | <60% | D&C
60 | [7 empty] | DR-059 | Emergency Evacuation & Preparedness Plan | Number of Approved MIR / Total number of MIRs requested | >80% | 60-80% | <60% | D&C
61 | [7 empty] | DR-060 | Latest Monthly HSE Report | Number of WIR Inspected / Total number of WIRs requested | >80% | 60-80% | <60% | D&C
62 | [7 empty] | DR-061 | Latest HSE Audit Report | Number of Approved WIR / Total number of WIRs requested | >80% | 60-80% | <60% | D&C
63 | [7 empty] | DR-062 | Latest Monthly Welfare Monitoring Report | Alignment of audit frequency | Yes |  | No | D&C
64 | [7 empty] | DR-063 | Welfare Management Manual (including Vendor Management & Monitoring Program) | Number of Non-Conformance Reports Closed / Total Number of Non-Conformance Reports | >80% | 60-80% | <60% | D&C
65 | [7 empty] | DR-064 | Latest Welfare Audit Report | Sum (NCR Closeout cycle time)/Total number of Non-Conformance Reports | <10 days | 10-21 days | >21 days | D&C
66 | [7 empty] | DR-065 | Quarterly/annual progress reports for preceding three years (including approved budget, contingency utilization and change requests / claims) | Sum( Actual Procurement Package Delivery Time / Planned Procurement Package Delivery Time) | >80% | 70-80% | 40-70% | D&C
67 | [7 empty] | DR-066 | Provisional Sums Status | Total number of claims and variations processed within contractual conditions & timeframes and with alignment of internal procedures / Total number of claims and variations | >70% | 50-70% | <50% | D&C
68 | [7 empty] | DR-067 | Innovation Strategy | Total number of packages procured with 100% complete, compliant and well-structured documentation / Total number of packages | >70% | 50-70% | <50% | D&C
69 | [7 empty] | DR-068 | Smart City Strategy | No. of awarded contracts where vendors appointed passed full due-diligence checks / Total number of awarded contracts | >90% | 90-85% | <85% | D&C
70 | [7 empty] | DR-069 | Innovation/ smart city impact assessment Report | Completion of supply chain risk-market intelligence assessment | Yes |  | No | D&C
71 | [7 empty] | DR-070 | Sample of final master plan showing innovation/ Smart city considerations | Number of procurement activities executed as planned / Total number of procurement activities | <20% | 20-60% | >60% | D&C
72 | [7 empty] | DR-071 | Register of Innovation & Technology pilots and R&D projects along with progress tracker | (Value of Contract Awarded - Tender Cost Estimate) / Value of Award Contract | <20% | 20-60% | >60% | D&C
73 | [7 empty] | DR-072 | Technical functions' strategy and initiatives | Number of contracts with filed claims / Total number of awarded contracts | <20% | 20-60% | >60% | D&C
74 | [7 empty] | DR-073 | Latest report which includes the progress of technical strategy initiatives | Processing of payment certificates and payments | Yes |  | No | D&C
75 | [7 empty] | DR-074 | List of technical functions’ KPIs (including baseline and targets) | Vendor performance assessment | Yes |  | No | D&C
76 | [7 empty] | DR-075 | Latest report which includes the progress of achievement of technical functions’ KPIs | Provision for identification and escalation of high risk activities | Yes |  | No | D&C
77 | [7 empty] | DR-076 | Approved and as-is org structure, including staffed/unstaffed positions, roles & responsibilities | Review rate of safety risk register | Yes |  | No | D&C
78 | [7 empty] | DR-077 | Strategic DevCo technical workforce planning report, including capacity and competency planning | Total number of closed Safety Risk items / Total number of safety risk items | >80% | 60-80% | <60% | D&C
79 | [7 empty] | DR-078 | Register of Approved technical-related policies and procedures | Sum (Cycle time to close safety risk items) / Total number of closed safety risk items | <7 days | 7-14 days | >14 days | D&C
80 | [7 empty] | DR-079 | Register of technical platforms | Sum (Cycle time to close safety incident) / Total number of closed safety incidents | <7 days | 7-14 days | >14 days | D&C
81 | [9 empty] | Compliance of emergency drill rate | Yes |  | No | D&C
82 | [9 empty] | No. of incidents resulting in fatality or severe impairment per 200,000 work hours | 0 | 0.001-0.0199 | >0.02 | D&C
83 | [9 empty] | No. of incidents resulting in lost time per 200,000 work hours | <0.1 | 0.1-1.5 | >1.5 | D&C
84 | [9 empty] | No. of recordable incidents per 200,000 work hours | <0.5 | 0.5-5 | >5 | D&C
85 | [9 empty] | No. of near misses recorded per 200,000 work hours | >30 | 0.1-30 | 0 | D&C
86 | [9 empty] | No. of safety observation recorded per 200,000 work hours | >200 | 10-200 | <10 | D&C
87 | [9 empty] | Total number of Safety Walks with Leadership / Total number of Safety Walks | >70% | 50-70% | <50% | D&C
88 | [9 empty] | Number of grievances closed / Total number of grievances | >80% | 60-80% | <60% | D&C
89 | [9 empty] | Sum (Cycle time to close grievances) / Total number of grievances | <14 days | 14-28 days | >28 days | D&C
90 | [9 empty] | Number of Welfare Staff / Total Number of Staff | Good | Average | Poor | D&C
91 | [9 empty] | Number of Welfare Observations Closed / Total number of Welfare Observations | >60% | 40-60% | <40% ; no observations recorded | D&C
92 | [9 empty] | Total Closed Welfare Non-compliances / Total Welfare Non-compliances | >80% | 60-80% | <60% | D&C
93 | [9 empty] | Sum (Cycle time to close Welfare Non-compliances) / Total number of Welfare Non-compliances | <14 days | 14-28 days | >28 days | D&C
94 | [9 empty] | Labor accommodation inspection frequency | Yes |  | No | D&C
95 | [9 empty] | PIF Approved Capex budget (Initial Business Plan) – Estimate At Completion | <10% | 10-20% | >20% | CE&O
96 | [9 empty] | Number of Projects with Budget Variance / Total number of Projects | <10% | 10-30% | >30% | CE&O
97 | [9 empty] | (Number of projects with contingency utilization > 1) / (Total number of projects) | <10% | 10-30% | >30% | CE&O
98 | [9 empty] | (No. of projects with approved change request having a cost impact greater than 2%) / (Total number of projects) | <5% | 5-15% | >15% | CE&O
99 | [9 empty] | (No. of projects with approved claims) / (Total number of projects) | <2% | 2-5% | >5% | CE&O
100 | [9 empty] | Total Provisional Sums/Latest Approved Budget | <5% | 5-15% | >15% | CE&O
101 | [9 empty] | (Total Provisional Sums−Actual Utilized Provisional Sums)/Total Provisional Sums | <10% | 10-20% | >20% | CE&O
102 | [9 empty] | Innovation Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10% | >75% | 60-75% | <60% | I&T
103 | [9 empty] | Smart City Strategy: Availability - 15%; Strategic Alignment - 15%; Adequate list of key focus areas - 10%; Adequate list of detailed initiatives - 10%; CBA - 15%; Implementation Roadmap - 15%; Process formulated - 10%; Budget of implementation - 10% | >75% | 60-75% | <60% | I&T
104 | [9 empty] | Adoption on DevCo performance? Robust assessment process and guidelines - 30%; Availability of sample of impact assessment report - 30%; Availability of action plan - 10%; Use of innovative tools/platforms/dashboards - 30% | >75% | 60-75% | <60% | I&T
105 | [9 empty] | Evidence for innovation/smart city technologies successful implementation | Yes |  | No | I&T
106 | [9 empty] | Pilot or R&D projects conducted? Availability - 20%; Adequate list of focus areas - 35%; Procedure - 15%; Outcome assessment robustness - 30% | >75% | 60-75% | <60% | I&T
107 | [9 empty] | [(Number of pilots that are scaled successfully + Number of R&D projects that are successfully piloted or fully-scaled) / (Number of pilot projects + Number of R&D projects)] | >40% | 20-40% | <20% | I&T
108 | [9 empty] | Availability of Innovation: Availability - 20%; Adequate Key positions planned in the org. structure - 30%; Unit/department position within the company hierarchy - 20%; Qualifications of the innovation team - 30% | >60% | 40-60% | <40% | I&T
109 | [9 empty] | Availability - 50% Implementation of the unit/department framework/ process - 50% | >50% | 0.5 | <50% | I&T
110 | [9 empty] | Give 'satisfactory' score if there is a technical function strategy, but it is very general and does not provide specific details of the strategy | Yes | Yes, but very brief | No | S&O
111 | [9 empty] | Assess if elements of technical strategy is aligned with organizational strategy. "Average" score if key elements of organizational strategy is not addressed in technical strategy | Well-aligned | Some gaps | Misaligned | S&O
112 | [9 empty] | "Severe" score if challenges faced can impact strategy execution significantly (in terms of time, cost and/or quality) | Minor | Moderate | Severe | S&O
113 | [9 empty] | Give 'satisfactory' score if there are technical KPIs, but they are very generic | Yes | Yes, but very brief | No | S&O
114 | [9 empty] | Number of KPIs achieved / Total Number of KPIs set for the same period | >75% | 50-75% | <50% | S&O
115 | [9 empty] | Expected elements from industry benchmarks: 1. Schedule adherence 2. Budget adherence 3. Employee attrition 4. HSE and Welfare 5. Internal audit performance | Aligned with industry benchmarks | Some gaps with industry benchmarks | Significant deviation from industry benchmarks | S&O
116 | [9 empty] | "Severe" if more than 25% of technical department head (N-2 or 3) and above are vacant Technical department head: person leading a technical function (depends on organization size) "Moderate" if 2 position for technical department head are vacant | Minor | Moderate | Severe | S&O
117 | [9 empty] | "Critical" score if there is little to no relevance in the requested qualifications to the role | Well-aligned | Some gaps | Misaligned | S&O
118 | [9 empty] | Strong if these are done: 1. Regular update and review of policies (3 mths) 2. All relevant policies/guidelines captured 3. Easy access (one repository with easy to find link) 4. Multi-channels to inform updates to documents e.g. email, intranet | Strong | Moderate | Poor | S&O
119 | [9 empty] | Strong if these are done: 1. Regular internal audits of processes (ongoing and rotation of topics/departments) 2. Independent internal audit department reporting directly to CEO or Board 3. Whistleblowing policy 4. Regular training for all staff (annual) | Strong | Moderate | Poor | S&O
120 | [9 empty] | Strong if all of these following points are done: 1. Board reporting policy covering frequency/trigger for updates 2. Register of Board Papers/Presentations 3. Register of Board meetings and meeting minutes | Strong | Moderate | Poor | S&O
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
Update D&F
Go to Main Page
Refresh